## iWork,IBP & Framework_SOW Items
Area | Feature | Functionality | Module | Phase | Status | Remarks | Need Design Approval | ETA | Resource | Date Added
FRAMEWORK: Frontend | Project setup | Basic project / Development environment setup | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | UI Approach Design System | Building Design System | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Core Infrastructure | Core Infra | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Build UI components | This includes all the UI componnets to compose the application and module definitions: Form, Toast, Filter, Cards, Visualisation, Grid, Menu, Header, Footer, Maps Integration | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | UI Approach Style Establishment | UI Style Establishment | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Service Workers Implementation |  | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Core System |  | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | ACL & RBAC Control Framework |  | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Micro Frontend Setup |  | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Landing Page |  | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Services - Basic Modules | Access Control Management |  | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Services - Larger Modules | Auth Module (Simple Auth) |  | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Services - Larger Modules | Micro Service Framework Setup |  | Framework | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Employee Mgmt |  | iWork | Milestone 1 | Delivered | User deletion need to be handled |  | 2026-06-12 |  | 2026-06-19
iWORK: Common Components | Common - Audit Trail Mgmt - Becomes critical in this phase iteself |  | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Add/View/Edit Opportunity | Add Medium size form with 1->N list of Claims; Multiple drop downs Large View with several widgets, Simple Edit | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Manage TPA/Insurer | Basic Add, View with edit of basic data, with lists of policies/companies | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Core Infra | Infrastructure | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Add/View/Edit Company | Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. Simple edit like Add; View is multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Insurer/TPA Hub | List with Filter/Search | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Add/View/Edit Contact | Simple edit like Add Contacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Company (Prospect) Hub | Top 10/Latest companies, with search/filter, Table of basic attributes with GPS etc. | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Contact Hub | Top 10/Latest Contacts, with search/filter, list with basic attributes | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Opportunity Hub | Top Opportunities with search/filter, List of opportunities with high level summaries | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Contact /Company/Insurer/TPA Mgmt |  | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Task Mgmt |  | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Meeting Mgmt |  | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | RBAC and ACL setup for Iwork Module |  | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Opportunity Mgmt |  | iWork | Milestone 1 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Master Data Management |  | Framework | Milestone 2 | Delivered |  |  | 2026-05-27 |  | 2026-06-19
FRAMEWORK: Frontend | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion |  | 2026-06-12 |  | 2026-06-19
FRAMEWORK: Services - Basic Modules | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion |  | 2026-06-12 |  | 2026-06-19
FRAMEWORK: Services - Larger Modules | Data Security Considerations |  | Framework | Milestone 2 | Delivered | Duplicate of Covers in DPDP items |  | 2026-06-30 |  | 2026-06-19
FRAMEWORK: Frontend | Visualization framework | Charts and KPIs | Framework | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Document Management | Create, Upload, Seach, Download | Framework | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Frontend | Caching of API Data |  | Framework | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Services - Basic Modules | Audit Data Capturing |  | Framework | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Services - Larger Modules | CMS |  | Framework | Milestone 2 | Delivered | Used in IBP |  |  |  | 2026-06-19
FRAMEWORK: Services - Basic Modules | Notification and Communication Management | 23-May: In-App, Emails, SMS, both or all. Template vs Channel Renewal reminders - ASAP | Framework | Milestone 2 | Delivered - Deficit | Pending: Configuration UI |  | 2026-07-10 |  | 2026-07-06
FRAMEWORK: Services - Basic Modules | Usage Tracking System (Reports) | 23-May: Handle as a part of Reports | Framework | Milestone 2 | Delivered | Pending: IBP usage |  | 2026-07-02 |  | 2026-06-19
iWORK: Frontend | Common Data Mapping Component | Map input fields to output fields & Order | iWork | Milestone 2 | Delivered | Pending: Additional/Dynamic columns |  | 2026-06-09 |  | 2026-06-19
iWORK: AI Components | AI - (Non-OCR) Digital Document Processing for Content recognition (Company/Opportunity/Contact Creation from Previous Policy Document, Bizcard document) |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: AI Components | AI - OCR for Content Collection |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: AI Components | AI - Company Information by AI Search |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Common Components | Common, Contexual Upload Component |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Common Components | Common, Contexual Read and Spread Component (Utility) |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Manage Stage Planning/Performance/Approval | Add iWork Stages (table) - Dates with each iWork Stage and who are the team members assigned to each Stage; Once all iWork stages are complete, ISG Team activities must be planned ISG Team can approve/reject each iWork Stage. Approving RFP Stage approves all iWork stages Completion of each iWork Stage (Activity) & ISG Stage - Comments, Attach Document, Date recorded, submit | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Smart Add Component | Allow Upload of Document/Image, select what to create (Company/Contact/Opportunity) | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Dashboard - Drilldowns | Drill down from the Tables (Targets vs. Actuals, Pending Activities, Followups, AR Report, Schedule) | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Sales Team Hierarchy | Hierarchy / Org chart tied to Platform Users | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | View Policy | Long View, multiple widgets/entities, endorsements (each month), Claims, etc. | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Dashboard | Multiple KPI Cards: Business Performance, Svc Performance, Table of targets vs. actuals vs. lost, Sales Funnel, Renewal Funnel, Servce Funnel, AR from Insurers, Pending Activities(iWork Stages) Widget, Followups widget, Meetings widget Filters available (Geo, Branch, Team/Team Member, Dates), Approvals, iWork Stages, Tasks, Meetings | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Dashboard - Pending tasks, approvals | Pending tasks/approvals, | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Reports - Biz Done | Report View, Download, List of earlier snaps of the report, Search and Filter | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Core Infrastructure | Core Infra | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Organisation, Branch, Employee, & Hierarchy Mgmt |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Dashboard (Place Holder) |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Planning, Perform and Approval Mgmt |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Policy Mgmt |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Master Data Mgmt {Common, Contexual Master Data Mgmt} |  | iWork | Milestone 2 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Cut Off Mgmt |  | iWork | Milestone 2 | Yet to start | Need inputs related to the implementation |  | 2026-07-03 |  | 2026-06-19
FRAMEWORK: Services - Larger Modules | Document Generation |  | Framework | Milestone 3 | Delivered |  |  |  |  | 2026-06-19
|  | Risk Watch: Showing policy feature documents at each policy | IBP | Milestone 3 | Delivered |  |  | 2026-06-19 | Ravi | 2026-06-19
iWORK: Services - Basic Modules | Cover Mgmt |  | iWork | Milestone 3 | Delivered |  |  | 2026-06-10 | Karan | 2026-06-19
iWORK: Frontend | Manage Policy (Endorsements) | Add Endorsement - basic form with uploads of excel/document Validations of endorsement format - Map customer fields to internal fields Map internal fields to TPA fields (occasional per TPA) View/Update Endorsement, List View, Endorsement Performance | iWork | Milestone 3 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Stage Mgmt (Activity/Transaction/Quote) |  | iWork | Milestone 3 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Asset/Member Data Mgmt |  | iWork | Milestone 3 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Endorsement Mgmt |  | iWork | Milestone 3 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | iWork | Milestone 3 | Yet to start |  |  | 2026-07-10 | Pushyami | 2026-06-19
iWORK: Services - Basic Modules | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | iWork | Milestone 3 | Yet to start |  |  | 2026-07-10 | Pushyami | 2026-06-19
FRAMEWORK: Frontend | Accessibility |  | Framework | Milestone 4 | Yet to start |  |  | 2026-07-15 |  | 2026-06-19
FRAMEWORK: Frontend | Notifications Management |  | Framework | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Services - Basic Modules | Configuration Management |  | Framework | Milestone 4 | Delivered | Considered Policy Config |  |  |  | 2026-06-19
FRAMEWORK: Services - Basic Modules | Feature Flag Control Management |  | Framework | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Services - Larger Modules | Localistation Management |  | Framework | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
FRAMEWORK: Services - Larger Modules | Caching Implementation |  | Framework | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
Framework | NFR_Security | DPDP NFR | IBP | Milestone 4 | Yet to start |  |  | 2026-07-15 | Tharun | 2026-06-19
Framework | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | IBP/iWork | Milestone 4 | Delivered - Deficit | Pending: Provide the document on how do we store and view it |  | 2026-06-10 |  | 2026-06-19
iWORK: Services - Basic Modules | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | IBP/iWork | Milestone 4 | Yet to start |  |  | 2026-07-15 | Tharun | 2026-06-19
iWork: Services - Basic Modules | Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | iWork | Milestone 4 | Yet to start |  |  | 2026-07-07 | Karan | 2026-06-19
IBP: Services - Larger Modules | IBP - User Management | IBP: HR Portal - Company-Scoped Employee Access for Client HR (Ex. TeamLease's Customer) | IBP | Milestone 4 | Delivered |  |  | 2026-05-26 |  | 2026-06-19
IBP: Services - Larger Modules | IBP - Portal Setup | Post policy creation, create default IBP Portal Config for all the company-policy(ies) | IBP | Milestone 4 | Delivered |  |  | 2026-06-19 | Manjusha | 2026-06-19
IBP: SERVICES - Basic Modules | Personal Profile Mgmt | Profile settings | IBP | Milestone 4 | Delivered | Pending:Add Dependents |  | 2026-06-10 | Manjusha | 2026-06-19
IBP: FRONTEND | HR Portal View | Employee Search, Resend Email, Delete Employees, Extend Enrollment Windows, Reports, Bulk Email | IBP | Milestone 4 | Delivered |  |  | 2026-06-11 | Abhilash | 2026-06-19
IBP: Common Components | Simple Auth | Username and Password based authentication and RBAC on simple-auth users. Auth rules needs configuration capability. IBP - HR User Management | IBP | Milestone 4 | Delivered |  |  | 2026-06-12 | Abhilash | 2026-06-19
IBP: FRONTEND | My Documents | Document Hub - Covers Policies, Prescriptions, Reports | IBP | Milestone 4 | Delivered | Pending: Design |  | 2026-06-12 | Manjusha | 2026-06-19
IBP: SERVICES - Basic Modules | Document Mgmt for End User | Insurance, Health Reports and Prescriptions {No automatic pull from Partners} | IBP | Milestone 4 | Delivered | Pending: Design |  | 2026-06-12 | Manjusha | 2026-06-19
Framework | NFR_Usability | NFR-USA-018: The session management should be configurable from UI 23-May: Configure from UI & store in DB; When changed then restart server | IBP | Milestone 4 | Delivered |  |  | 2026-06-15 | Manjusha | 2026-06-19
IBP: FRONTEND | Policy Document | IBP-Risk Watch: Show the each policy document | IBP | Milestone 4 | Delivered |  |  | 2026-06-19 | Tharun | 2026-06-19
Framework | NFR_Usability | NFR-USA-015: The system must show personalized welcome messages and profile information based on locale. | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
Framework | NFR_Usability | NFR-USA-016: Notification banners must be dismissible and configurable based on role. | IBP | Milestone 4 | Delivered | No notifications in IBP |  |  |  | 2026-06-19
IBP: Common Components | Whitelabelling Support |  | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | Company Plans | 6 Policies - GMC, GPA, GTL, Parental Plicy, Top-ups, OPD Policy (Summary view of policies) | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | IBP Landing Page - Basic | Basic Landing Page with only company plans and summart | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | Contact Matrix View | Contact Matrix View for end user | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | Core Infrastructure | Core Infra | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | Per-policy Enrolment | Enrolment and addon policy selection | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | My Insurance | Part-1: Hub of all plans I have as an employee - Company provided. Mostly a navigational page | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: Services - Basic Modules | Basic Landing Page Services | Company provided plans only | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment | Enrollment (Adding Dependents, Choosing Options available). Submit the enrollment to Insurer or TPA 6 Types of Policies to be considered | IBP | Milestone 4 | Delivered | Need Confirmation: If scope has, Insurer & TPA integrations, then they are pending |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment Configurator | Enrollment Configurator (Set of benefits and type of Dependent combinations allowed etc). This is more of an Iwork feature to configure the policy | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | End User onboarding | Generate Users, Send Emails, Password Rest | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Contact Matrix Configuration | Matrix of Contact Infomration | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | HR/Admin Portal View | Supporting services for Admin Portal | IBP | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
| Wellness | IBP Portal Configure - Wellness - Buttons, CMS, & any other - Flag Driven | IBP | Milestone 4 | Delivered |  |  | 2026-06-22 | Manjusha | 2026-06-25
FRAMEWORK: Frontend | Localisation |  | Framework | Milestone 4 | Delivered - Deficit | Pending: Service Flow & IBP |  | 2026-07-15 | Karan | 2026-06-19
FRAMEWORK: Services - Larger Modules | Workflow Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Yet to start |  |  | 2026-06-10 | Nithin | 2026-06-19
FRAMEWORK: Services - Larger Modules | Rule Definition Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Yet to start |  |  | 2026-06-10 | Nithin | 2026-06-19
IBP: Services - Larger Modules | Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | IBP | Milestone 4 | Delivered | Pending: HR Module - Endorsement |  | 2026-07-02 | Ravi | 2026-06-19
iWork: Services - Basic Modules | Dashboard - FinOps Data | Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | iWork | Milestone 4 | Yet to start | Duplicate of reconcilation |  | 2026-06-10 |  | 2026-06-19
| Risk Watch - Endorsement - Documents & Communication | Risk Watch - Endorsement - Documents & Communication | IBP | Milestone 4 | Delivered |  |  | 2026-07-01 | Abhilash | 2026-06-25
iWork: Services - Basic Modules | Client - Associated Location (IBP HR Module) | IBP - HR: Policy Location - Add Company Associated Locations, Flow to Opty., Policy & Policy Config | IBP/iWork | Milestone 4 | Delivered |  |  | 2026-05-25 | Karan | 2026-06-19
IBP: FRONTEND | Company Plan Configurator | Admin side of IBP should configure (per Corporate) how to define a Policy and determine how it breaks down the Premium and Coverage rules | IBP/iWork | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | Auth Config UI | Config for Auth Rules setup | IBP/iWork | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | Contact Matrix | Configure the Conact Info Matrix (IBP Admin) | IBP/iWork | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | Whitelabelling | Whitelabelling based on Org needs (IBP Admin) | IBP/iWork | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
| Policy Component - Strapi | IBP Portal - Each card should have seperate points & Policy feature documents | IBP/iWork | Milestone 4 | Delivered |  |  | 2026-06-19 | Manjusha | 2026-06-25
iWORK: Services - Basic Modules | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | DPDP | Milestone 4 | Yet to start | Duplicate of Archival from NFR & DPDP |  | 2026-07-15 |  | 2026-06-19
Framework | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | IBP | Milestone 4 | Pre-PROD | Fine tuning the API's where there is a delay |  | 2026-06-10 | Akhila | 2026-06-19
|  | HRMS - integrations with enrolment portal (POC - with Zoho People), client mentioned that they have already integrated MB360 for HCL | IBP | Milestone 4 | Dev - WIP |  |  | 2026-06-10 | Ravi | 2026-06-25
IBP: Services - Larger Modules | Admin Reports | Services for multiple reports | IBP | Milestone 4 | Delivered - Deficit |  |  | 2026-06-10 | Abhilash | 2026-06-19
iWork: Services - Basic Modules | Reports - Biz Done | Bizonde filter/table - Add "Income type" | iWork | Milestone 4 | Delivered |  |  | 2026-05-26 | Karan | 2026-06-19
iWork: Services - Basic Modules | Opportunity | Opportunity History details are unavailable for the end user to view. Show TAT section (Planned date, Performed/Completed date, Approved date) for planned acitivites | iWork | Milestone 4 | Delivered |  |  | 2026-05-28 | Pushyami | 2026-06-19
iWork: Services - Basic Modules | Endorsement Mgmt | Additional columns in file like Department, DOJ, Emp. Location, Vertical, Others | iWork | Milestone 4 | Delivered |  |  | 2026-05-29 | Pushyami | 2026-06-19
iWork: Services - Basic Modules | Opportunity | RO Scheduler Enhancements | iWork | Milestone 4 | Delivered |  |  | 2026-05-29 | Jagadeesh | 2026-06-19
iWORK: Frontend | Knowledge Central | Grouped list of Documents/Resources, Add a Document, Remove a Document (Add/remove only for admins) | iWork | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Knowledge Central |  | iWork | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | TAT/SLA Mgmt (Including Service Score) |  | iWork | Milestone 4 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | VRK - PROD Feedback: 8-Jun-2026 TPA Integration Mgmt [Framework] | 1. Framework - KIT 2. WBS - with details -Medi Assist India Pvt. Ltd. -Family Health Plan Ltd. -Health India -MD India Healthcare Services (Pvt.) Ltd. -Vidal Health TPA Private Limited -Paramount Health Services Pvt. Ltd. | IBP/iWork | Milestone 4 | Dev - WIP | 9-Jun: Shared errors to Neeraj |  | 2026-06-10 | Abhilash | 2026-06-25
iWork: Services - Larger Modules | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | iWork | Milestone 4 | Yet to start |  |  | 2026-07-15 | Rama | 2026-07-06
iWORK: Frontend | View Service Score | Servicing Stats Dashboard - Single Table (drillable) to calculate an overall score | iWork | Milestone 4 | Delivered - Deficit | Pending: Meeting, MIR calculation |  | 2026-06-10 | Pushyami | 2026-06-19
| Security | InfoSec - IBP Portal (Security Issue) | IBP/iWork | Milestone 4 | Delivered |  |  | 2026-07-03 | Manjusha | 2026-06-25
Framework: DPDP | Enable SAST |  | DPDP | Milestone 5 | Delivered |  |  | 2026-06-15 |  | 2026-06-19
| IBP - Raise Ticket | Edit the ticket and update the status by the user | IBP/iWork | Milestone 4 | Yet to start |  |  | 2026-06-10 | Manjusha | 2026-06-25
Framework: DPDP | Integrate SSO / MFA |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-07-10 | Sunil | 2026-06-19
Framework: DPDP | Capture consent within app |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-07-10 | Sunil | 2026-06-19
Framework: DPDP | Allow easy consent withdrawal |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-07-10 | Sunil | 2026-06-19
Framework: DPDP | Approval workflow |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Show privacy notice with purpose, retention, rights |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-07-10 | Sunil | 2026-06-19
Framework: DPDP | App vulnerability scans |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Quarterly restore tests |  | DPDP | Milestone 5 | Pre-PROD |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Document Flows |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Perform security UAT |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Enforce business logic to restrict purpose |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Remove unnecessary fields |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-07-10 | Sunil | 2026-06-19
Framework: DPDP | Map PII tables |  | DPDP | Milestone 5 | QA - WIP |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Enable delete pipeline |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Allow user corrections |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Delete expired data |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Sign DPDP clauses |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-07-10 |  | 2026-06-19
IBP: Common Components | 3rd Party SSO | Props based SSO links to 3rd Parties | IBP | Milestone 5 | Delivered | SSO Framework implemented fro TPA |  | 2026-06-01 | Abhilash | 2026-06-19
| Wellness Banner & SSO | Add banner and SSO to Alyve Wellness (Only Banner) | IBP | Milestone 5 | Delivered |  |  | 2026-06-10 |  | 2026-06-19
IBP: SERVICES - Basic Modules | Hospital Network Mgmt | Based on the Insurer and TPA, network of hospitals needs to be presented in a consolidated view | IBP | Milestone 5 | Delivered |  |  | 2026-06-11 |  | 2026-06-19
IBP: FRONTEND | Static Info Sections - Landing | Benefits Guide, FAQs, Help | IBP | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
IBP: FRONTEND | Initiate Claim | Initiate claim for GMC (non-cashless), upload docs etc. | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations |  |  |  | 2026-06-19
IBP: FRONTEND | Claims Corner | View Claim Data for Individual Plans (if available), Track Status for Claims initiated from IBP for Group Plans, Track Status for Claims initiated with TPA directly, TAT reporting for Cashless (for Preauth and Discharge) | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Claims Mgmt | Part-1: Company Provided Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) | iWork | Milestone 5 | Dev - WIP |  |  | 2026-07-10 |  | 2026-06-19
iWORK: Frontend | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid | iWork | Milestone 5 | Yet to start |  |  | 2026-07-10 |  | 2026-06-19
iWORK: Services - Basic Modules | Reconciliation Mgmt |  | iWork | Milestone 5 | Yet to start |  |  | 2026-07-10 |  | 2026-06-19
iWORK: Services - Basic Modules | Insurer Integration Mgmt |  | iWork | Milestone 5 | Yet to start |  |  | 2026-07-15 |  | 2026-06-19
Framework: NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | NFR | Milestone 5 | Yet to start | Discussed this with Surya sir last visit to Divami office |  | 2026-07-10 |  | 2026-06-19
Framework: DPDP | Define archival |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-07-10 |  | 2026-06-19
IBP: FRONTEND | IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | IBP | Milestone 5 | Delivered - Deficit | Pending: Wellness Program related |  |  |  | 2026-06-19
IBP: FRONTEND | Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | IBP | Milestone 5 | Delivered - Deficit | Pending: Offers & Discuounts |  |  | Manjusha | 2026-06-19
IBP: FRONTEND | User Profile | Profile, Service Subscriptions, Feedback | IBP | Milestone 5 | Delivered - Deficit | Pending: Service Subscriptions, Feedback |  |  | Abhilash | 2026-06-19
IBP: SERVICES - Basic Modules | Benefits Summary | End User's Summary View | IBP | Milestone 5 | Delivered - Deficit | Pending: Retail Insurance |  |  |  | 2026-06-19
IBP: Services - Larger Modules | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | IBP | Milestone 5 | Delivered - Deficit | Pending: Offer, Feature flagging (UI) |  |  |  | 2026-06-19
IBP: FRONTEND | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | IBP | Milestone 5 | Yet to start | Retail insurance(facility to load user insurance policies) |  |  |  | 2026-06-19
IBP: FRONTEND | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | IBP | Milestone 5 | Yet to start |  |  |  | Manjusha | 2026-06-19
IBP: FRONTEND | Book Ambulance | Floater on the screen - Integrate to Ambulance Service | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: FRONTEND | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: FRONTEND | Wellness HR View | HR View of Wellness usage by Employees | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: FRONTEND | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: FRONTEND | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | IBP | Milestone 5 | Yet to start | Pending: Retail insurance |  |  | Abhilash | 2026-06-19
IBP: FRONTEND | Profile Migration | Request migration of Corporate Profile to Individual | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: FRONTEND | Profile Migration | Request migration of Individual Profile to Corporate | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: FRONTEND | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | IBP | Milestone 5 | Yet to start | Pending: Retail insurance |  |  | Manjusha | 2026-06-19
IBP: Services - AI Components | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | IBP | Milestone 5 | Yet to start | External chatbot integration? |  |  |  | 2026-06-19
IBP: SERVICES - Basic Modules | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: SERVICES - Basic Modules | Feedback Mgmt | User Feedback capture service | IBP | Milestone 5 | Yet to start | IBP support is already in place |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | TPA Integration Mgmt [GHPL] | Launch TPA - SSO Ecards API - Read & View Details Hospital Network Claims Status API - Read, Store & View Details Claim Intimation API Claim Live Status - Single Claim | IBP/iWork | Milestone 5 | Delivered |  |  | 2026-06-12 | Ravi | 2026-06-19
IBP: FRONTEND | IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | IBP/iWork | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
iWORK: Frontend | Claim Management (Add Claim, Import Claims & Claim Activities) | Basic Form with fields and upload for adding claim Bulk import to validate and map from TPA format to internal fields 3 stage workflow - each stage, update data on claim form | iWork | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | Report Hub | Landing Page and generic hub | iWork | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
iWORK: Frontend | CD Creation | Show current CD Balance against pooled/individual policies / Allow new CD creation, update CD balance and map policies to CD balances | iWork | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | CD Mgmt |  | iWork | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Reports |  | iWork | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
iWORK: Services - Basic Modules | Claim Mgmt |  | iWork | Milestone 5 | Delivered |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Evexia Club Integration | Integration to Evexia | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | IBP | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: Services - Larger Modules | Core Infrastructure | Core Infra | IBP/iWork | Milestone 5 | Delivered - Deficit | Pending: Mobile responsive |  |  |  | 2026-06-19
IBP: FRONTEND | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | IBP/iWork | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
IBP: FRONTEND | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | IBP/iWork | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
Framework: NFR | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure, which was broad symptom rather than a root cause. The renewed focus here is on failures related to cryptography which often leads to sensitive data exposure or system compromise. |  | NFR | Milestone 5 | Delivered |  |  | 2026-06-05 |  | 2026-06-19
Framework: NFR | NFR-COM-019: Terms and Conditions: The application must ensure require the customer to accept the Terms & Conditions at the first login to the application. This ensures compliance with PII regulations requiring Company group to inform the user of why Company is accessing/collecting personal data and why Company is using it. IIRM-4480 |  | NFR | Milestone 5 | Delivered |  |  | 2026-06-05 |  | 2026-06-19
iWORK: Frontend | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | iWork | Milestone 5 | Delivered - Deficit |  |  |  |  | 2026-06-19
| IIRM-10591 | IBP - Enrolment Journey - Reset | IBP | Milestone 6 | Delivered |  |  | 2026-06-09 | Abhilash | 2026-06-19
iWORK: Services - Basic Modules | HRMS Integration Mgmt | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? | iWork | Milestone 5 | Yet to start |  |  |  |  | 2026-06-19
SSO - MS AD Account | VRK - PROD Feedback: 10-Jun-2026 | iWork - SSO with Microsoft AD (POC) | iWork - CR | Milestone 6 | Dev - Done | Showed Demo to Venu |  | 2026-07-10 | Rama | 2026-06-22
| Claims Corner | Claims Corner - Screen Re-design | IBP | Milestone 6 | Dev - WIP |  |  | 2026-07-09 |  | 2026-06-19
|  | Based on recent billing - Identifying the gaps in Redis data storage and gaps in implementation | IBP/iWork | Milestone 6 | Delivered |  |  | 2026-06-08 | Tharun | 2026-06-19
| Policy Config | New Policy constraints 1. Allow first child as Twin 2. Allow second child as Triplet 3. SI per Dependent 4. Parent Lock-in period | IBP/iWork | Milestone 6 | Delivered |  |  | 2026-06-16 |  | 2026-06-19
| One URL multiple companies | Flexibility to configure multiple companies on a single domain | IBP/iWork | Milestone 6 | Delivered |  |  | 2026-06-17 |  | 2026-06-19
IBP: Services - AI Components | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | IBP - CR | Milestone 6 | Pre-PROD |  |  | 2026-07-09 | Tharun | 2026-06-19
iWork: Services - Basic Modules | Endorsement Mgmt | PROD Bug: Data Discrepancy - Inception/Endorsement vs Send to Client/Insurer (Preview & Excel) | iWork | Milestone 6 | Delivered |  |  | 2026-05-27 | Prathiphala | 2026-06-19
iWork: Services - Basic Modules | Endorsement Mgmt | PROD Bug: When download the TPA file, dependents are Missing in the file | iWork | Milestone 6 | Delivered |  |  | 2026-05-27 | Sunil | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | 2026-06-19
| IIRM-10588 | Hide "Manage Policy" in "Manage Placements" link. | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 | Pushyami | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 | Pushyami | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 | Pushyami | 2026-06-19
| VRK - PROD Feedback | Manage Insurer - Add Insurer Flow | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 | Pushyami | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 | Karan | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 | Pushyami | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 | Pushyami | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | iWork | Milestone 6 | Delivered |  |  | 2026-06-10 | Prathiphala | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | iWork | Milestone 6 | Delivered |  |  | 2026-06-10 |  | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | iWork | Milestone 6 | Delivered |  |  | 2026-06-10 | Jagadeesh | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | iWork | Milestone 6 | Delivered |  |  | 2026-06-10 | Jagadeesh | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | iWork | Milestone 6 | Delivered |  |  | 2026-06-12 | Prathiphala | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | iWork | Milestone 6 | Delivered |  |  | 2026-06-12 | Karan | 2026-06-19
| VRK - PROD Feedback | Opty. Flow - Add new Insurer Branch Details | iWork | Milestone 6 | Delivered |  |  | 2026-06-12 | Pushyami | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | iWork | Milestone 6 | Delivered |  |  | 2026-06-12 |  | 2026-06-19
| IIRM-10590 | Policy Config: Dependent Based Configurations - Per life depedent addition & increase SI - Apply Policy Parameters for dependents | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 | Jagadeesh | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 | Karan | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 | Karan | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 | Karan | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 |  | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 | Karan | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | iWork | Milestone 6 | Delivered |  |  | 2026-06-16 |  | 2026-06-19
| VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | iWork | Milestone 6 | Delivered |  |  | 2026-06-19 | Karan | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | iWork | Milestone 6 | Delivered |  |  | 2026-06-19 | Rama | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | iWork | Milestone 6 | Delivered |  |  | 2026-06-24 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | iWork | Milestone 6 | Delivered |  |  |  |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | iWork | Milestone 6 | Delivered | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only |  |  |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | iWork | Milestone 6 | Delivered |  |  | 2026-06-30 | Jagadeesh | 2026-06-19
| IIRM-10587 | Add new fields - Business Month & Date of Business - Capture in Opty. & Flow to Policy and add filters in BizDone --> Refer to Madhav email "Business Month Requirement" | iWork | Milestone 6 | Delivered | Pending: Additional filters |  | 2026-07-02 | Sunil | 2026-06-19
| Rewards | Rewards - Generic (Specific - Out of scope) | iWork | Milestone 6 | Delivered |  |  | 2026-07-01 | Karan | 2026-06-25
iWork: Services - Basic Modules | Cover Mgmt | Asset fields which are captured at Broking slip, few of the asset fields should not be printed at the time of Placement slip (example, no of members at inception, total lives, prev policy expiring year etc.) only for GMC | iWork - CR | Milestone 6 | Pre-PROD |  |  | 2026-07-07 | Karan | 2026-06-19
iWork: Services - Basic Modules | Policy Configuration | Using AI - Extract the Policy document and perform Policy Configuration (Premium, Family, Parameters, & Others) | iWork - CR | Milestone 6 | Delivered |  |  | 2026-07-01 | Jagadeesh | 2026-06-19
iWork: Services - Basic Modules | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | IBP/iWork | Milestone 6 | Yet to start |  |  | 2026-07-07 |  | 2026-06-25
| VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | iWork | Milestone 6 | Yet to start |  |  | 2026-07-07 | Sunil | 2026-06-19
iWork: Services - Basic Modules | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | iWork - CR | Milestone 6 | Yet to start |  |  | 2026-07-15 | Sunil | 2026-06-19
iWork: AI Components | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | iWork - CR | Milestone 6 | Yet to start | Need some information about the document rules that defines the idenity of it |  | 2026-07-10 | Jagadeesh | 2026-06-19
| IIRM-10666 | IBP - Policy Component Card Re-design | IBP | Milestone 6 | Yet to start |  |  |  |  | 2026-06-19
PROD-Bug | Export to Excel | Export to excel - iWork all the results table; Download is on Previlage | iWork | Milestone 6 | Yet to start |  |  |  |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | iWork | Milestone 6 | Delivered |  |  | 2026-07-02 |  | 2026-06-19
| VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | iWork | Milestone 6 | Not a bug |  |  |  |  | 2026-06-19
iWork: Services - Basic Modules | Endorsement Mgmt (Non-Group / Non-GMC / Non-EB) | Enhance the Non-GMC Process (Based on Kishore feedback) | iWork - CR | Milestone 6 | Delivered |  |  | 2026-05-28 | Pushyami | 2026-06-19
iWork: Services - Basic Modules | Insurer Management | Enhance Insurer - Add, Edit, & Contacts | iWork - CR | Milestone 6 | Delivered |  |  | 2026-06-09 | Pushyami | 2026-06-19
| IIRM-10667 | iWork - Knowledge Central Re-Design | iWork | Milestone 6 | Yet to start |  |  |  |  | 2026-06-19
| IIRM-10668 | iLearn: Document Preview in-app | iWork | Milestone 6 | Yet to start |  |  |  |  | 2026-06-19
2026-06-19 | Discuss with Madhav | Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard) Also, check if we are there are any data loads for 2025-26 | iWork | Milestone 6 | Yet to start |  |  |  |  | 2026-06-25
|  | Utility - Transformation - Make it Generic for Source to Destination columns | iWork | Milestone 6 | Yet to start |  |  |  |  | 2026-06-25
|  | Dashboard - Hide the widgets where there is NO data in the cards | iWork | Milestone 6 | Yet to start |  |  |  |  | 2026-06-25
|  | BizDone - New Role or Previlage - Show org. full data (Only data) | iWork | Milestone 6 | Yet to start |  |  |  |  | 2026-06-25
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | iWork | Milestone 6 | Delivered |  |  | 2026-07-01 | Pushyami | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | iWork | Milestone 6 | Delivered |  |  | 2026-07-01 | Pushyami | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | iWork | Milestone 6 | Delivered |  |  | 2026-07-01 | Pushyami | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | iWork | Milestone 6 | Delivered |  |  | 2026-07-01 | Pushyami | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | iWork | Milestone 6 | Delivered |  |  | 2026-07-01 | Pushyami | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | iWork | Milestone 6 | Delivered |  |  | 2026-07-01 | Pushyami | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Placement Funnel | iWork | Milestone 6 | Yet to start |  |  | 2026-07-06 | Pushyami | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | iWork | Milestone 6 | Dev - WIP |  |  | 2026-07-06 |  | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | iWork | Milestone 6 | Yet to start |  |  | 2026-07-07 |  | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | iWork | Milestone 6 | Yet to start |  |  | 2026-07-08 |  | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | iWork | Milestone 6 | Yet to start |  |  | 2026-07-08 |  | 2026-07-03
iWORK: Frontend | VRK - PROD Feedback: 23-Jun-2026 | Flexibility to configure multiple policies on a single domain | iWork | Milestone 6 | Dev - WIP |  |  | 2026-07-03 |  | 2026-07-03
iWORK: Frontend | Installment & Fee Requirements | Installments & Fee to BizDone | iWork | Milestone 6 | Yet to start |  |  |  |  | 2026-07-06
|  | IBP & HRMS Integration - HCL | IBP/iWork | Milestone 4 | Yet to start |  |  |  |  | 2026-07-06

## ① Executive Summary
PROJECT DELIVERY PLAN
iWork · IBP · Framework (IIRM SOW) ¦ Status Overview & Forward Roadmap · As of 21-May-2026
OVERALL COMPLETION | [6 empty] | REMAINING WORK
items still to deliver across all modules — broken down by milestone in the Pending Roadmap sheet
STATUS BREAKDOWN (all items)
Delivered |  |  | Dev Complete |  |  | In Development |  |  | In QA
Pre-PROD / UAT |  |  | Not Started |  |  | Partial Delivery |  |  | N/A
PROGRESS BY MODULE
Module | Type | Total | Delivered | Pending | N/A | % Complete | Progress
iWork (Backlog) | Backlog
iWork (Change Requests) | Change Request
IBP (Backlog) | Backlog
IBP (Change Requests) | Change Request
IBP / iWork (Shared) | Backlog
Framework | Backlog
DPDP | Backlog
NFR | Backlog
TOTAL | All
PENDING BY MILESTONE & MODULE
Milestone | iWork | iWork - CR | IBP | IBP - CR | IBP/iWork | Framework | DPDP | NFR | TOTAL PENDING
Milestone 1
Milestone 2
Milestone 3
Milestone 4
Milestone 5
Milestone 6
TOTAL
ITEMS BY MILESTONE & STATUS
Milestone | Delivered | Dev Complete | In Development | In QA | Pre-PROD / UAT | Not Started | Partial Delivery | TOTAL
Milestone 1
Milestone 2
Milestone 3
Milestone 4
Milestone 5
Milestone 6
TOTAL
WEEKLY INTAKE — items added (by Date Added)
Period | Added | Delivered | Pending | % Closed
Last week (29 Jun–05 Jul)
This week (06 Jul–12 Jul)
% Complete = Delivered ÷ (Delivered + Pending). N/A items (duplicates) are excluded from the calculation. All figures update live from the 'iWork,IBP & Framework_SOW Items' sheet.

## 📅 29-Jun
WEEK OF 29 Jun 2026 → 05 Jul 2026 — 9 items · 8 delivered · 1 pending · LAST WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | ETA | Resource | Remarks
1 | Framework | Data Security Considerations |  | Delivered | Milestone 2 | 30-Jun-2026 |  | Duplicate of Covers in DPDP items
2 | IBP | Risk Watch - Endorsement - Documents & Communication | Risk Watch - Endorsement - Documents & Communication | Delivered | Milestone 4 | 01-Jul-2026 | Abhilash
3 | iWork | Rewards | Rewards - Generic (Specific - Out of scope) | Delivered | Milestone 6 | 01-Jul-2026 | Karan
4 | iWork - CR | Policy Configuration | Using AI - Extract the Policy document and perform Policy Configuration (Premium, Family, Parameters, & Others) | Delivered | Milestone 6 | 01-Jul-2026 | Jagadeesh
5 | Framework | Usage Tracking System (Reports) | 23-May: Handle as a part of Reports | Delivered | Milestone 2 | 02-Jul-2026 |  | Pending: IBP usage
6 | IBP | Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | Delivered | Milestone 4 | 02-Jul-2026 | Ravi | Pending: HR Module - Endorsement
7 | iWork | IIRM-10587 | Add new fields - Business Month & Date of Business - Capture in Opty. & Flow to Policy and add filters in BizDone --> Refer to Madhav email "Business Month Requirement" | Delivered | Milestone 6 | 02-Jul-2026 | Sunil | Pending: Additional filters
8 | iWork | Cut Off Mgmt |  | Yet to start | Milestone 2 | 03-Jul-2026 |  | Need inputs related to the implementation
9 | IBP/iWork | Security | InfoSec - IBP Portal (Security Issue) | Delivered | Milestone 4 | 03-Jul-2026 | Manjusha

## 📍 06-Jul
WEEK OF 06 Jul 2026 → 12 Jul 2026 — 30 items · 5 delivered · 25 pending · CURRENT WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | ETA | Resource | Remarks
1 | iWork - CR | Cover Mgmt | Asset fields which are captured at Broking slip, few of the asset fields should not be printed at the time of Placement slip (example, no of members at inception, total lives, prev policy expiring year etc.) only for GMC | Pre-PROD | Milestone 6 | 07-Jul-2026 | Karan
2 | iWork | Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | Yet to start | Milestone 4 | 07-Jul-2026 | Karan
3 | IBP/iWork | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | Yet to start | Milestone 6 | 07-Jul-2026
4 | IBP - CR | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | Pre-PROD | Milestone 6 | 09-Jul-2026 | Tharun
5 | IBP | Claims Corner | Claims Corner - Screen Re-design | Dev - WIP | Milestone 6 | 09-Jul-2026
6 | Framework | Notification and Communication Management | 23-May: In-App, Emails, SMS, both or all. Template vs Channel Renewal reminders - ASAP | Delivered - Deficit | Milestone 2 | 10-Jul-2026 |  | Pending: Configuration UI
7 | DPDP | Define archival |  | Yet to start | Milestone 5 | 10-Jul-2026
8 | NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | Yet to start | Milestone 5 | 10-Jul-2026 |  | Discussed this with Surya sir last visit to Divami office
9 | iWork | Reconciliation Mgmt |  | Yet to start | Milestone 5 | 10-Jul-2026
10 | iWork | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid | Yet to start | Milestone 5 | 10-Jul-2026
11 | iWork | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) | Dev - WIP | Milestone 5 | 10-Jul-2026
12 | DPDP | Sign DPDP clauses |  | Dev - WIP | Milestone 5 | 10-Jul-2026
13 | DPDP | Delete expired data |  | Dev - WIP | Milestone 5 | 10-Jul-2026
14 | DPDP | Allow user corrections |  | Dev - WIP | Milestone 5 | 10-Jul-2026
15 | DPDP | Enable delete pipeline |  | Yet to start | Milestone 5 | 10-Jul-2026
16 | DPDP | Remove unnecessary fields |  | Dev - Done | Milestone 5 | 10-Jul-2026 | Sunil
17 | DPDP | Enforce business logic to restrict purpose |  | Dev - WIP | Milestone 5 | 10-Jul-2026
18 | DPDP | Perform security UAT |  | Dev - WIP | Milestone 5 | 10-Jul-2026
19 | DPDP | Document Flows |  | Dev - WIP | Milestone 5 | 10-Jul-2026
20 | DPDP | Quarterly restore tests |  | Pre-PROD | Milestone 5 | 10-Jul-2026
21 | DPDP | App vulnerability scans |  | Dev - WIP | Milestone 5 | 10-Jul-2026
22 | DPDP | Show privacy notice with purpose, retention, rights |  | Dev - WIP | Milestone 5 | 10-Jul-2026 | Sunil
23 | DPDP | Approval workflow |  | Dev - Done | Milestone 5 | 10-Jul-2026
24 | DPDP | Allow easy consent withdrawal |  | Dev - Done | Milestone 5 | 10-Jul-2026 | Sunil
25 | DPDP | Capture consent within app |  | Dev - Done | Milestone 5 | 10-Jul-2026 | Sunil
26 | DPDP | Integrate SSO / MFA |  | Dev - Done | Milestone 5 | 10-Jul-2026 | Sunil
27 | iWork | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | Yet to start | Milestone 3 | 10-Jul-2026 | Pushyami
28 | iWork | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | Yet to start | Milestone 3 | 10-Jul-2026 | Pushyami
29 | DPDP | Map PII tables |  | QA - WIP | Milestone 5 | 10-Jul-2026
30 | iWork - CR | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | Yet to start | Milestone 6 | 10-Jul-2026 | Jagadeesh | Need some information about the document rules that defines the idenity of it

## 📅 13-Jul
WEEK OF 13 Jul 2026 → 19 Jul 2026 — 8 items · 0 delivered · 8 pending
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | ETA | Resource | Remarks
1 | Framework | Accessibility |  | Yet to start | Milestone 4 | 15-Jul-2026
2 | IBP | NFR_Security | DPDP NFR | Yet to start | Milestone 4 | 15-Jul-2026 | Tharun
3 | IBP/iWork | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | Yet to start | Milestone 4 | 15-Jul-2026 | Tharun
4 | Framework | Localisation |  | Delivered - Deficit | Milestone 4 | 15-Jul-2026 | Karan | Pending: Service Flow & IBP
5 | DPDP | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | Yet to start | Milestone 4 | 15-Jul-2026 |  | Duplicate of Archival from NFR & DPDP
6 | iWork | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | Yet to start | Milestone 4 | 15-Jul-2026 | Rama
7 | iWork | Insurer Integration Mgmt |  | Yet to start | Milestone 5 | 15-Jul-2026
8 | iWork - CR | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | Yet to start | Milestone 6 | 15-Jul-2026 | Sunil

## 📋 iWork
IWORK — WEEKLY PLAN · 15 items · 3 delivered · 12 pending
⚠️ Static snapshot — module view, broken up by week. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | ETA | Resource | Remarks
📅 WEEK OF 29 Jun → 05 Jul 2026 · LAST WEEK · 4 items
1 | iWork | Rewards | Rewards - Generic (Specific - Out of scope) | Delivered | Milestone 6 | 01-Jul-2026 | Karan
2 | iWork | IIRM-10587 | Add new fields - Business Month & Date of Business - Capture in Opty. & Flow to Policy and add filters in BizDone --> Refer to Madhav email "Business Month Requirement" | Delivered | Milestone 6 | 02-Jul-2026 | Sunil | Pending: Additional filters
3 | iWork | Cut Off Mgmt |  | Yet to start | Milestone 2 | 03-Jul-2026 |  | Need inputs related to the implementation
4 | iWork - CR | Policy Configuration | Using AI - Extract the Policy document and perform Policy Configuration (Premium, Family, Parameters, & Others) | Delivered | Milestone 6 | 01-Jul-2026 | Jagadeesh
📍 WEEK OF 06 Jul → 12 Jul 2026 · CURRENT WEEK · 8 items
5 | iWork | Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | Yet to start | Milestone 4 | 07-Jul-2026 | Karan
6 | iWork | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | Yet to start | Milestone 3 | 10-Jul-2026 | Pushyami
7 | iWork | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | Yet to start | Milestone 3 | 10-Jul-2026 | Pushyami
8 | iWork | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) | Dev - WIP | Milestone 5 | 10-Jul-2026
9 | iWork | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid | Yet to start | Milestone 5 | 10-Jul-2026
10 | iWork | Reconciliation Mgmt |  | Yet to start | Milestone 5 | 10-Jul-2026
11 | iWork - CR | Cover Mgmt | Asset fields which are captured at Broking slip, few of the asset fields should not be printed at the time of Placement slip (example, no of members at inception, total lives, prev policy expiring year etc.) only for GMC | Pre-PROD | Milestone 6 | 07-Jul-2026 | Karan
12 | iWork - CR | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | Yet to start | Milestone 6 | 10-Jul-2026 | Jagadeesh | Need some information about the document rules that defines the idenity of it
📅 WEEK OF 13 Jul → 19 Jul 2026 · 3 items
13 | iWork | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | Yet to start | Milestone 4 | 15-Jul-2026 | Rama
14 | iWork | Insurer Integration Mgmt |  | Yet to start | Milestone 5 | 15-Jul-2026
15 | iWork - CR | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | Yet to start | Milestone 6 | 15-Jul-2026 | Sunil

## 📋 IBP
IBP — WEEKLY PLAN · 8 items · 3 delivered · 5 pending
⚠️ Static snapshot — module view, broken up by week. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | ETA | Resource | Remarks
📅 WEEK OF 29 Jun → 05 Jul 2026 · LAST WEEK · 3 items
1 | IBP | Risk Watch - Endorsement - Documents & Communication | Risk Watch - Endorsement - Documents & Communication | Delivered | Milestone 4 | 01-Jul-2026 | Abhilash
2 | IBP | Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | Delivered | Milestone 4 | 02-Jul-2026 | Ravi | Pending: HR Module - Endorsement
3 | IBP/iWork | Security | InfoSec - IBP Portal (Security Issue) | Delivered | Milestone 4 | 03-Jul-2026 | Manjusha
📍 WEEK OF 06 Jul → 12 Jul 2026 · CURRENT WEEK · 3 items
4 | IBP | Claims Corner | Claims Corner - Screen Re-design | Dev - WIP | Milestone 6 | 09-Jul-2026
5 | IBP - CR | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | Pre-PROD | Milestone 6 | 09-Jul-2026 | Tharun
6 | IBP/iWork | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | Yet to start | Milestone 6 | 07-Jul-2026
📅 WEEK OF 13 Jul → 19 Jul 2026 · 2 items
7 | IBP | NFR_Security | DPDP NFR | Yet to start | Milestone 4 | 15-Jul-2026 | Tharun
8 | IBP/iWork | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | Yet to start | Milestone 4 | 15-Jul-2026 | Tharun

## 📋 Framework, DPDP & NFR
FRAMEWORK, DPDP & NFR — WEEKLY PLAN · 24 items · 7 delivered · 17 pending
⚠️ Static snapshot — module view, broken up by week. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | ETA | Resource | Remarks
📅 WEEK OF 29 Jun → 05 Jul 2026 · LAST WEEK · 2 items
1 | Framework | Data Security Considerations |  | Delivered | Milestone 2 | 30-Jun-2026 |  | Duplicate of Covers in DPDP items
2 | Framework | Usage Tracking System (Reports) | 23-May: Handle as a part of Reports | Delivered | Milestone 2 | 02-Jul-2026 |  | Pending: IBP usage
📍 WEEK OF 06 Jul → 12 Jul 2026 · CURRENT WEEK · 19 items
3 | DPDP | Integrate SSO / MFA |  | Dev - Done | Milestone 5 | 10-Jul-2026 | Sunil
4 | DPDP | Capture consent within app |  | Dev - Done | Milestone 5 | 10-Jul-2026 | Sunil
5 | DPDP | Allow easy consent withdrawal |  | Dev - Done | Milestone 5 | 10-Jul-2026 | Sunil
6 | DPDP | Approval workflow |  | Dev - Done | Milestone 5 | 10-Jul-2026
7 | DPDP | Show privacy notice with purpose, retention, rights |  | Dev - WIP | Milestone 5 | 10-Jul-2026 | Sunil
8 | DPDP | App vulnerability scans |  | Dev - WIP | Milestone 5 | 10-Jul-2026
9 | DPDP | Quarterly restore tests |  | Pre-PROD | Milestone 5 | 10-Jul-2026
10 | DPDP | Document Flows |  | Dev - WIP | Milestone 5 | 10-Jul-2026
11 | DPDP | Perform security UAT |  | Dev - WIP | Milestone 5 | 10-Jul-2026
12 | DPDP | Enforce business logic to restrict purpose |  | Dev - WIP | Milestone 5 | 10-Jul-2026
13 | DPDP | Remove unnecessary fields |  | Dev - Done | Milestone 5 | 10-Jul-2026 | Sunil
14 | DPDP | Map PII tables |  | QA - WIP | Milestone 5 | 10-Jul-2026
15 | DPDP | Enable delete pipeline |  | Yet to start | Milestone 5 | 10-Jul-2026
16 | DPDP | Allow user corrections |  | Dev - WIP | Milestone 5 | 10-Jul-2026
17 | DPDP | Delete expired data |  | Dev - WIP | Milestone 5 | 10-Jul-2026
18 | DPDP | Sign DPDP clauses |  | Dev - WIP | Milestone 5 | 10-Jul-2026
19 | DPDP | Define archival |  | Yet to start | Milestone 5 | 10-Jul-2026
20 | Framework | Notification and Communication Management | 23-May: In-App, Emails, SMS, both or all. Template vs Channel Renewal reminders - ASAP | Delivered - Deficit | Milestone 2 | 10-Jul-2026 |  | Pending: Configuration UI
21 | NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | Yet to start | Milestone 5 | 10-Jul-2026 |  | Discussed this with Surya sir last visit to Divami office
📅 WEEK OF 13 Jul → 19 Jul 2026 · 3 items
22 | DPDP | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | Yet to start | Milestone 4 | 15-Jul-2026 |  | Duplicate of Archival from NFR & DPDP
23 | Framework | Accessibility |  | Yet to start | Milestone 4 | 15-Jul-2026
24 | Framework | Localisation |  | Delivered - Deficit | Milestone 4 | 15-Jul-2026 | Karan | Pending: Service Flow & IBP

## Unplanned (no ETA)
UNPLANNED — PENDING, NO ETA · 39 items
Pending items with no ETA yet. Assign an ETA in the source sheet to move an item into its week. Static snapshot — re-run to refresh.
# | Module | Feature | Functionality | Status | Milestone | ETA | Resource | Remarks
iWork · 10 items
1 | iWork | Discuss with Madhav | Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard) Also, check if we are there are any data loads for 2025-26 | Yet to start | Milestone 6
2 | iWork | Export to Excel | Export to excel - iWork all the results table; Download is on Previlage | Yet to start | Milestone 6
3 | iWork | HRMS Integration Mgmt | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? | Yet to start | Milestone 5
4 | iWork | IIRM-10667 | iWork - Knowledge Central Re-Design | Yet to start | Milestone 6
5 | iWork | IIRM-10668 | iLearn: Document Preview in-app | Yet to start | Milestone 6
6 | iWork | Installment & Fee Requirements | Installments & Fee to BizDone | Yet to start | Milestone 6
7 | iWork |  | Utility - Transformation - Make it Generic for Source to Destination columns | Yet to start | Milestone 6
8 | iWork |  | Dashboard - Hide the widgets where there is NO data in the cards | Yet to start | Milestone 6
9 | iWork |  | BizDone - New Role or Previlage - Show org. full data (Only data) | Yet to start | Milestone 6
10 | iWork | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | Delivered - Deficit | Milestone 5
IBP · 29 items
11 | IBP | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | Yet to start | Milestone 5 |  | Manjusha
12 | IBP | Book Ambulance | Floater on the screen - Integrate to Ambulance Service | Yet to start | Milestone 5
13 | IBP | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | Yet to start | Milestone 5
14 | IBP | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | Yet to start | Milestone 5 |  |  | External chatbot integration?
15 | IBP | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | Yet to start | Milestone 5
16 | IBP | Evexia Club Integration | Integration to Evexia | Yet to start | Milestone 5
17 | IBP | Feedback Mgmt | User Feedback capture service | Yet to start | Milestone 5 |  |  | IBP support is already in place
18 | IBP | IIRM-10666 | IBP - Policy Component Card Re-design | Yet to start | Milestone 6
19 | IBP | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | Yet to start | Milestone 5
20 | IBP | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | Yet to start | Milestone 5 |  | Manjusha | Pending: Retail insurance
21 | IBP | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | Yet to start | Milestone 5 |  | Abhilash | Pending: Retail insurance
22 | IBP | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | Yet to start | Milestone 5
23 | IBP | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | Yet to start | Milestone 5
24 | IBP | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | Yet to start | Milestone 5 |  |  | Retail insurance(facility to load user insurance policies)
25 | IBP | Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | Yet to start | Milestone 5
26 | IBP | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | Yet to start | Milestone 5
27 | IBP | Profile Migration | Request migration of Corporate Profile to Individual | Yet to start | Milestone 5
28 | IBP | Profile Migration | Request migration of Individual Profile to Corporate | Yet to start | Milestone 5
29 | IBP/iWork | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | Yet to start | Milestone 5
30 | IBP | Wellness HR View | HR View of Wellness usage by Employees | Yet to start | Milestone 5
31 | IBP/iWork | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | Yet to start | Milestone 5
32 | IBP | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | Yet to start | Milestone 5
33 | IBP/iWork |  | IBP & HRMS Integration - HCL | Yet to start | Milestone 4
34 | IBP | Benefits Summary | End User's Summary View | Delivered - Deficit | Milestone 5 |  |  | Pending: Retail Insurance
35 | IBP/iWork | Core Infrastructure | Core Infra | Delivered - Deficit | Milestone 5 |  |  | Pending: Mobile responsive
36 | IBP | Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | Delivered - Deficit | Milestone 5 |  | Manjusha | Pending: Offers & Discuounts
37 | IBP | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | Delivered - Deficit | Milestone 5 |  |  | Pending: Offer, Feature flagging (UI)
38 | IBP | IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | Delivered - Deficit | Milestone 5 |  |  | Pending: Wellness Program related
39 | IBP | User Profile | Profile, Service Subscriptions, Feedback | Delivered - Deficit | Milestone 5 |  | Abhilash | Pending: Service Subscriptions, Feedback

## VRK Feedbacks
VRK — PROD FEEDBACK TRACKER · 53 items · 45 delivered · 8 pending
All 'VRK - PROD Feedback:' items, broken up by week (status then ETA within a week). Excluded from the other views. Static snapshot.
# | Module | Feature | Functionality | Status | Milestone | ETA | Resource | Remarks
📅 WEEK OF 08 Jun → 14 Jun 2026 · PAST · 25 items
1 | IBP/iWork | VRK - PROD Feedback: 8-Jun-2026 TPA Integration Mgmt [Framework] | 1. Framework - KIT 2. WBS - with details -Medi Assist India Pvt. Ltd. -Family Health Plan Ltd. -Health India -MD India Healthcare Services (Pvt.) Ltd. -Vidal Health TPA Private Limited -Paramount Health Services Pvt. Ltd. | Dev - WIP | Milestone 4 | 10-Jun-2026 | Abhilash | 9-Jun: Shared errors to Neeraj
2 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | Delivered | Milestone 6 | 08-Jun-2026
3 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | Delivered | Milestone 6 | 08-Jun-2026
4 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | Delivered | Milestone 6 | 08-Jun-2026
5 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | Delivered | Milestone 6 | 08-Jun-2026
6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | Delivered | Milestone 6 | 08-Jun-2026
7 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | Delivered | Milestone 6 | 08-Jun-2026
8 | iWork | VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | Delivered | Milestone 6 | 08-Jun-2026
9 | iWork | VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | Delivered | Milestone 6 | 08-Jun-2026
10 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | Delivered | Milestone 6 | 08-Jun-2026
11 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | Delivered | Milestone 6 | 08-Jun-2026
12 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | Delivered | Milestone 6 | 08-Jun-2026
13 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | Delivered | Milestone 6 | 08-Jun-2026
14 | iWork | VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | Delivered | Milestone 6 | 09-Jun-2026 | Pushyami
15 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | Delivered | Milestone 6 | 09-Jun-2026 | Pushyami
16 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | Delivered | Milestone 6 | 09-Jun-2026 | Karan
17 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | Pushyami
18 | iWork | VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | Delivered | Milestone 6 | 09-Jun-2026 | Pushyami
19 | iWork | VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | Delivered | Milestone 6 | 10-Jun-2026 | Prathiphala
20 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | Delivered | Milestone 6 | 10-Jun-2026
21 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | Delivered | Milestone 6 | 10-Jun-2026 | Jagadeesh
22 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | Delivered | Milestone 6 | 10-Jun-2026 | Jagadeesh
23 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | Delivered | Milestone 6 | 12-Jun-2026 | Prathiphala
24 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | Delivered | Milestone 6 | 12-Jun-2026 | Karan
25 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | Delivered | Milestone 6 | 12-Jun-2026
📅 WEEK OF 15 Jun → 21 Jun 2026 · PAST · 8 items
26 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | Delivered | Milestone 6 | 15-Jun-2026 | Karan
27 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | Delivered | Milestone 6 | 15-Jun-2026 | Karan
28 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | Delivered | Milestone 6 | 15-Jun-2026 | Karan
29 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | Delivered | Milestone 6 | 15-Jun-2026
30 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | Delivered | Milestone 6 | 15-Jun-2026 | Karan
31 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | Delivered | Milestone 6 | 16-Jun-2026
32 | iWork | VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | Delivered | Milestone 6 | 19-Jun-2026 | Karan
33 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | Delivered | Milestone 6 | 19-Jun-2026 | Rama
📅 WEEK OF 22 Jun → 28 Jun 2026 · PAST · 1 item
34 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | Delivered | Milestone 6 | 24-Jun-2026
📅 WEEK OF 29 Jun → 05 Jul 2026 · LAST WEEK · 9 items
35 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Flexibility to configure multiple policies on a single domain | Dev - WIP | Milestone 6 | 03-Jul-2026
36 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | Delivered | Milestone 6 | 30-Jun-2026 | Jagadeesh
37 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | Delivered | Milestone 6 | 01-Jul-2026 | Pushyami
38 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | Delivered | Milestone 6 | 01-Jul-2026 | Pushyami
39 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | Delivered | Milestone 6 | 01-Jul-2026 | Pushyami
40 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 01-Jul-2026 | Pushyami
41 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 01-Jul-2026 | Pushyami
42 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | Delivered | Milestone 6 | 01-Jul-2026 | Pushyami
43 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | Delivered | Milestone 6 | 02-Jul-2026
📍 WEEK OF 06 Jul → 12 Jul 2026 · CURRENT WEEK · 7 items
44 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Placement Funnel | Yet to start | Milestone 6 | 06-Jul-2026 | Pushyami
45 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | Yet to start | Milestone 6 | 07-Jul-2026 | Sunil
46 | iWork | VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | Yet to start | Milestone 6 | 07-Jul-2026
47 | iWork | VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | Yet to start | Milestone 6 | 08-Jul-2026
48 | iWork | VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | Yet to start | Milestone 6 | 08-Jul-2026
49 | iWork | VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | Dev - WIP | Milestone 6 | 06-Jul-2026
50 | iWork - CR | VRK - PROD Feedback: 10-Jun-2026 | iWork - SSO with Microsoft AD (POC) | Dev - Done | Milestone 6 | 10-Jul-2026 | Rama | Showed Demo to Venu
🗓 No ETA assigned · 3 items
51 | iWork | VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | Delivered | Milestone 6
52 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | Delivered | Milestone 6 |  |  | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only
53 | iWork | VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | Not a bug | Milestone 6

## ③ Milestone Summary
MILESTONE SUMMARY — Pending Items by Milestone & Module
Counts show PENDING items only (Delivered & N/A excluded). Live from the SOW sheet.
Milestone | iWork (Backlog) | iWork (Change Requests) | IBP (Backlog) | IBP (Change Requests) | IBP / iWork (Shared) | Framework | DPDP | NFR | TOTAL PENDING
Milestone 1
Milestone 2
Milestone 3
Milestone 4
Milestone 5
Milestone 6
TOTAL
ITEMS BY MILESTONE & STATUS
Milestone | Delivered | Dev Complete | In Development | In QA | Pre-PROD / UAT | Not Started | Partial Delivery | TOTAL
Milestone 1
Milestone 2
Milestone 3
Milestone 4
Milestone 5
Milestone 6
TOTAL

## Helper (hidden)
Module | Phase | Status | Category | Bucket | DateAdded

## Config (hidden)
Status_Raw | Category | Bucket
Delivered | Delivered | Delivered
Dev - Done | Dev Complete | Delivered
Dev - WIP | In Development | Pending
QA - WIP | In QA | Pending
Pre-PROD | Pre-PROD / UAT | Pending
Yet to start | Not Started | Pending
Delivered - Deficit | Partial Delivery | Pending
Duplicate | N/A | N/A
Not a bug | Delivered | Delivered