## SOW, Feedbacks-Bug & CR_Items
Area | Feature | Functionality | Module | Phase | Status | Remarks | Requested Date | ETA | Priority | Start Date | End Date | Resource | Jira ID
FRAMEWORK: Frontend | Project setup | Basic project / Development environment setup | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-17
FRAMEWORK: Frontend | UI Approach Design System | Building Design System | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-734
FRAMEWORK: Frontend | Core Infrastructure | Core Infra | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Build UI components | This includes all the UI componnets to compose the application and module definitions: Form, Toast, Filter, Cards, Visualisation, Grid, Menu, Header, Footer, Maps Integration | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-836
FRAMEWORK: Frontend | UI Approach Style Establishment | UI Style Establishment | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-838
FRAMEWORK: Frontend | Service Workers Implementation |  | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-19
FRAMEWORK: Frontend | Core System |  | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-80
FRAMEWORK: Frontend | ACL & RBAC Control Framework |  | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-18
FRAMEWORK: Frontend | Micro Frontend Setup |  | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-15
FRAMEWORK: Frontend | Landing Page |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Services - Basic Modules | Access Control Management |  | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-1528
FRAMEWORK: Services - Larger Modules | Auth Module (Simple Auth) |  | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-62
FRAMEWORK: Services - Larger Modules | Micro Service Framework Setup |  | Framework | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-16, IIRM-834
iWORK: Services - Basic Modules | Employee Mgmt |  | iWork | Milestone 1 | Delivered | User deletion need to be handled | 2025-03-01 | 2026-06-12
iWORK: Common Components | Common - Audit Trail Mgmt - Becomes critical in this phase iteself |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Opportunity | Add Medium size form with 1->N list of Claims; Multiple drop downs Large View with several widgets, Simple Edit | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-740
iWORK: Frontend | Manage TPA/Insurer | Basic Add, View with edit of basic data, with lists of policies/companies | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-741, IIRM-742
iWORK: Frontend | Core Infra | Infrastructure | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Company | Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. Simple edit like Add; View is multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Insurer/TPA Hub | List with Filter/Search | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Contact | Simple edit like Add Contacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-1556
iWORK: Frontend | Company (Prospect) Hub | Top 10/Latest companies, with search/filter, Table of basic attributes with GPS etc. | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-1560
iWORK: Frontend | Contact Hub | Top 10/Latest Contacts, with search/filter, list with basic attributes | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Opportunity Hub | Top Opportunities with search/filter, List of opportunities with high level summaries | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-811
iWORK: Services - Basic Modules | Contact /Company/Insurer/TPA Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Task Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-738
iWORK: Services - Basic Modules | Meeting Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-738
iWORK: Services - Basic Modules | RBAC and ACL setup for Iwork Module |  | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-18
iWORK: Services - Basic Modules | Opportunity Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01 | [5 empty] | IIRM-740
FRAMEWORK: Frontend | Master Data Management |  | Framework | Milestone 2 | Delivered |  | 2025-04-16 | 2026-05-27 |  |  |  |  | IIRM-745
FRAMEWORK: Frontend | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion | 2025-04-16 | 2026-06-12 |  |  |  |  | IIRM-744
FRAMEWORK: Services - Basic Modules | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion | 2025-04-16 | 2026-06-12 |  |  |  |  | IIRM-744
FRAMEWORK: Services - Larger Modules | Data Security Considerations |  | Framework | Milestone 2 | Delivered | Duplicate of Covers in DPDP items | 2025-04-16 | 2026-06-30 |  |  |  |  | IIRM-749
FRAMEWORK: Frontend | Visualization framework | Charts and KPIs | Framework | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-743
FRAMEWORK: Frontend | Document Management | Create, Upload, Seach, Download | Framework | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-750
FRAMEWORK: Frontend | Caching of API Data |  | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Services - Basic Modules | Audit Data Capturing |  | Framework | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-4613
FRAMEWORK: Services - Larger Modules | CMS |  | Framework | Milestone 2 | Delivered | Used in IBP | 2025-04-16 | [5 empty] | IIRM-750
FRAMEWORK: Services - Basic Modules | Notification and Communication Management |  | Framework | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-746
FRAMEWORK: Services - Basic Modules | Usage Tracking System (Reports) | 23-May: Handle as a part of Reports | Framework | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Common Data Mapping Component | Map input fields to output fields & Order | iWork | Milestone 2 | Delivered | Pending: Additional/Dynamic columns | 2025-04-16 | 2026-06-09
iWORK: AI Components | AI - (Non-OCR) Digital Document Processing for Content recognition (Company/Opportunity/Contact Creation from Previous Policy Document, Bizcard document) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: AI Components | AI - OCR for Content Collection |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: AI Components | AI - Company Information by AI Search |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Common Components | Common, Contexual Upload Component |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Common Components | Common, Contexual Read and Spread Component (Utility) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Manage Stage Planning/Performance/Approval | Add iWork Stages (table) - Dates with each iWork Stage and who are the team members assigned to each Stage; Once all iWork stages are complete, ISG Team activities must be planned ISG Team can approve/reject each iWork Stage. Approving RFP Stage approves all iWork stages Completion of each iWork Stage (Activity) & ISG Stage - Comments, Attach Document, Date recorded, submit | iWork | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-752
iWORK: Frontend | Smart Add Component | Allow Upload of Document/Image, select what to create (Company/Contact/Opportunity) | iWork | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-754
iWORK: Frontend | Dashboard - Drilldowns | Drill down from the Tables (Targets vs. Actuals, Pending Activities, Followups, AR Report, Schedule) | iWork | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-751
iWORK: Frontend | Sales Team Hierarchy | Hierarchy / Org chart tied to Platform Users | iWork | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-753
iWORK: Frontend | View Policy | Long View, multiple widgets/entities, endorsements (each month), Claims, etc. | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Dashboard | Multiple KPI Cards: Business Performance, Svc Performance, Table of targets vs. actuals vs. lost, Sales Funnel, Renewal Funnel, Servce Funnel, AR from Insurers, Pending Activities(iWork Stages) Widget, Followups widget, Meetings widget Filters available (Geo, Branch, Team/Team Member, Dates), Approvals, iWork Stages, Tasks, Meetings | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Dashboard - Pending tasks, approvals | Pending tasks/approvals, | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Reports - Biz Done | Report View, Download, List of earlier snaps of the report, Search and Filter | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Core Infrastructure | Core Infra | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Organisation, Branch, Employee, & Hierarchy Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Dashboard (Place Holder) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Planning, Perform and Approval Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Policy Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Master Data Mgmt {Common, Contexual Master Data Mgmt} |  | iWork | Milestone 2 | Delivered |  | 2025-04-16 | [5 empty] | IIRM-745
iWORK: Services - Basic Modules | Cut Off Mgmt |  | iWork | Milestone 2 | Pre-PROD |  | 2025-04-16 | 2026-08-03 |  |  |  | Karan
FRAMEWORK: Services - Larger Modules | Document Generation |  | Framework | Milestone 3 | Delivered |  | 2025-05-16 | [5 empty] | IIRM-760
iWORK: Services - Basic Modules | Cover Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16 | 2026-06-10 |  |  |  | Karan
iWORK: Frontend | Manage Policy (Endorsements) | Add Endorsement - basic form with uploads of excel/document Validations of endorsement format - Map customer fields to internal fields Map internal fields to TPA fields (occasional per TPA) View/Update Endorsement, List View, Endorsement Performance | iWork | Milestone 3 | Delivered |  | 2025-05-16 | [5 empty] | IIRM-757
iWORK: Services - Basic Modules | Stage Mgmt (Activity/Transaction/Quote) |  | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Asset/Member Data Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16 | [5 empty] | IIRM-759
iWORK: Services - Basic Modules | Endorsement Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16 | [5 empty] | IIRM-757
iWORK: Frontend | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | iWork | Milestone 3 | Delivered |  | 2025-05-16 | 2026-07-22 |  |  |  | Sunil | IIRM-758
iWORK: Services - Basic Modules | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | iWork | Milestone 3 | Delivered |  | 2025-05-16 | 2026-07-22 |  |  |  | Sunil | IIRM-758
FRAMEWORK: Services - Basic Modules | Configuration Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-762
FRAMEWORK: Services - Basic Modules | Feature Flag Control Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Services - Larger Modules | Localistation Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-764
FRAMEWORK: Services - Larger Modules | Caching Implementation |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Frontend | Notifications Management | Different email notification - Madhav excel. 1. Renewal Reminders - ASAP 2. Instalment Reminders 3. Others | Framework | Milestone 4 | Pre-PROD |  | 2025-06-10 | 2026-08-03 |  |  |  | Pushyami | IIRM-761, IIRM-4740
FRAMEWORK: Services - Larger Modules | Workflow Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Not in scope | 23-Jul-2026: As per Gopal as this system custom and most of the data is driven from Master creating/plug any 3'rd Party will make complex. | 2025-06-10 | [5 empty] | IIRM-766
iWORK: Services - Basic Modules | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | DPDP | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-08-07 |  |  |  | Rama
FRAMEWORK: Services - Larger Modules | Rule Definition Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Not in scope | 23-Jul-2026: As per Gopal as this system custom and most of the data is driven from Master creating/plug any 3'rd Party will make complex. | 2025-06-10 | [5 empty] | IIRM-765
IBP: Services - Larger Modules | IBP - User Management | IBP: HR Portal - Company-Scoped Employee Access for Client HR (Ex. TeamLease's Customer) | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-05-26 |  |  |  |  | IIRM-10375
IBP: Services - Larger Modules | IBP - Portal Setup | Post policy creation, create default IBP Portal Config for all the company-policy(ies) | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-19 |  |  |  | Manjusha | IIRM-794
IBP: SERVICES - Basic Modules | Personal Profile Mgmt | Profile settings | IBP | Milestone 4 | Delivered | Pending:Add Dependents | 2025-06-10 | 2026-06-10 |  |  |  | Manjusha
IBP: FRONTEND | HR Portal View | Employee Search, Resend Email, Delete Employees, Extend Enrollment Windows, Reports, Bulk Email | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-11 |  |  |  | Abhilash | IIRM-776
IBP: Common Components | Simple Auth | Username and Password based authentication and RBAC on simple-auth users. Auth rules needs configuration capability. IBP - HR User Management | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-12 |  |  |  | Abhilash
IBP: FRONTEND | My Documents | Document Hub - Covers Policies, Prescriptions, Reports | IBP | Milestone 4 | Delivered | Pending: Design | 2025-06-10 | 2026-06-12 |  |  |  | Manjusha
IBP: SERVICES - Basic Modules | Document Mgmt for End User | Insurance, Health Reports and Prescriptions {No automatic pull from Partners} | IBP | Milestone 4 | Delivered | Pending: Design | 2025-06-10 | 2026-06-12 |  |  |  | Manjusha
Framework: NFR | NFR_Usability | NFR-USA-018: The session management should be configurable from UI 23-May: Configure from UI & store in DB; When changed then restart server | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-15 |  |  |  | Manjusha | IIRM-9912
IBP: FRONTEND | Policy Document | IBP-Risk Watch: Show the each policy document | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-19 |  |  |  | Tharun
Framework: NFR | NFR_Usability | NFR-USA-015: The system must show personalized welcome messages and profile information based on locale. | IBP | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-4477
Framework: NFR | NFR_Usability | NFR-USA-016: Notification banners must be dismissible and configurable based on role. | IBP | Milestone 4 | Delivered | No notifications in IBP | 2025-06-10 | [5 empty] | IIRM-4478
IBP: Common Components | Whitelabelling Support |  | IBP | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-775
IBP: FRONTEND | Company Plans | 6 Policies - GMC, GPA, GTL, Parental Plicy, Top-ups, OPD Policy (Summary view of policies) | IBP | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-774
IBP: FRONTEND | IBP Landing Page - Basic | Basic Landing Page with only company plans and summart | IBP | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-771
IBP: FRONTEND | Contact Matrix View | Contact Matrix View for end user | IBP | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-8036
IBP: FRONTEND | Core Infrastructure | Core Infra | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Per-policy Enrolment | Enrolment and addon policy selection | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | My Insurance | Part-1: Hub of all plans I have as an employee - Company provided. Mostly a navigational page | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Basic Modules | Basic Landing Page Services | Company provided plans only | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment | Enrollment (Adding Dependents, Choosing Options available). Submit the enrollment to Insurer or TPA 6 Types of Policies to be considered | IBP | Milestone 4 | Delivered | Need Confirmation: If scope has, Insurer & TPA integrations, then they are pending | 2025-06-10 | [5 empty] | IIRM-773
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment Configurator | Enrollment Configurator (Set of benefits and type of Dependent combinations allowed etc). This is more of an Iwork feature to configure the policy | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | End User onboarding | Generate Users, Send Emails, Password Rest | IBP | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-8572
IBP: Services - Larger Modules | Contact Matrix Configuration | Matrix of Contact Infomration | IBP | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-8036
IBP: Services - Larger Modules | HR/Admin Portal View | Supporting services for Admin Portal | IBP | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-776
IBP: Services - Larger Modules | Admin Reports | Services for multiple reports | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-10 |  |  |  | Abhilash | IIRM-778
IBP: FRONTEND | Wellness Discount List Management | Add/Remove/update Discount program benefits | IBP/iWork | Milestone 4 | Pre-PROD |  | 2025-06-10 | 2026-08-03
IBP: Services - Larger Modules | Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-07-02 |  |  |  | Ravi
iWork: Services - Basic Modules | Client - Associated Location (IBP HR Module) | IBP - HR: Policy Location - Add Company Associated Locations, Flow to Opty., Policy & Policy Config | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 |  |  |  |  | Karan | IIRM-10516
IBP: FRONTEND | Company Plan Configurator | Admin side of IBP should configure (per Corporate) how to define a Policy and determine how it breaks down the Premium and Coverage rules | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Auth Config UI | Config for Auth Rules setup | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Contact Matrix | Configure the Conact Info Matrix (IBP Admin) | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-8036
IBP: FRONTEND | Whitelabelling | Whitelabelling based on Org needs (IBP Admin) | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-775
iWORK: Common Components | Policy Component - Strapi | IBP Portal - Each card should have seperate points & Policy feature documents | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 |  |  |  |  | Manjusha
iWORK: Services - Basic Modules | TPA Integration Mgmt [Framework] | 1. Framework in iWork 2. Validate the integration for the existing 6 TPA's | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 | 2026-07-24 |  |  |  | Ravi | IIRM-783
FRAMEWORK: Frontend | Accessibility | 20-Jul: Jagadees --> Need More details | Framework | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-08-07 |  |  |  |  | IIRM-763
iWork: Services - Basic Modules | Reports - Biz Done | Bizonde filter/table - Add "Income type" | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  |  |  |  | Karan
iWork: Services - Basic Modules | Opportunity | Opportunity History details are unavailable for the end user to view. Show TAT section (Planned date, Performed/Completed date, Approved date) for planned acitivites | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  |  |  |  | Pushyami | IIRM-5292
iWork: Services - Basic Modules | Endorsement Mgmt | Additional columns in file like Department, DOJ, Emp. Location, Vertical, Others | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  |  |  |  | Pushyami
iWork: Services - Basic Modules | Opportunity | RO Scheduler Enhancements | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  |  |  |  | Jagadeesh | IIRM-10456
iWORK: Frontend | Knowledge Central | Grouped list of Documents/Resources, Add a Document, Remove a Document (Add/remove only for admins) | iWork | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-768
iWORK: Services - Basic Modules | Knowledge Central |  | iWork | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-768
iWORK: Services - Basic Modules | TAT/SLA Mgmt (Including Service Score) |  | iWork | Milestone 4 | Delivered |  | 2025-06-10 | [5 empty] | IIRM-769, IIRM-770
iWORK: Services - Basic Modules | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | IBP/iWork | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-08-07 |  |  |  | Rama
FRAMEWORK: Frontend | Localisation |  | Framework | Milestone 4 | Delivered - Deficit | Pending: Service Flow | 2025-06-10 | 2026-08-07 |  |  |  | Tharun | IIRM-764
IBP: FRONTEND | Upload from Partner of services bought on Partner site | Upload, listing, confirm & load into DB by an Iwork user. These are services purchased / discounts availed on partner sites by IBP corporate users | IBP/iWork | Milestone 4 | Pre-PROD |  | 2025-06-10 | 2026-08-03 |  |  |  |  | IIRM-793
iWork: Services - Larger Modules | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | iWork | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-08-07 |  |  |  | Rama
iWORK: Frontend | View Service Score | My Client Portfolio: Service Score - Single Table (drillable) to calculate an overall score Dashboard - Service Score - Widget | iWork | Milestone 4 | Delivered |  | 2025-06-10 | 2026-07-29 |  |  |  | Sunil
Framework: NFR | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | NFR | Milestone 4 | Delivered - Deficit | Pending: Provide the document on how do we store and view it | 2025-06-10 | 2026-08-07 |  |  |  | Rama | IIRM-4482
Framework: NFR | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | IBP | Milestone 4 | Pre-PROD | Fine tuning the API's where there is a delay | 2025-06-10 | 2026-08-07 |  |  |  | Akhila | IIRM-4473
iWORK: Frontend | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | iWork | Milestone 5 | Delivered - Deficit | Linked with Reconciliation Management & Commission | 2025-07-31 | 2026-08-05
IBP: SERVICES - Basic Modules | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | IBP | Milestone 5 | Pre-PROD |  | 2025-07-31 | 2026-08-03 |  |  |  | Manjusha
Framework: DPDP | Enable SAST |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-15
Framework: DPDP | Integrate SSO / MFA |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-04-30
Framework: DPDP | Capture consent within app |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-05-30 |  |  |  |  | IIRM-8015
Framework: DPDP | Allow easy consent withdrawal |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-05-30 |  |  |  |  | IIRM-8015
Framework: DPDP | Approval workflow |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-05-30
Framework: DPDP | Show privacy notice with purpose, retention, rights |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-05-30
Framework: DPDP | App vulnerability scans |  | DPDP | Milestone 5 | DEV - WIP |  | 2025-07-31 | 2026-08-07
Framework: DPDP | Document Flows |  | DPDP | Milestone 5 | DEV - WIP |  | 2025-07-31 | 2026-08-07
Framework: DPDP | Perform security UAT |  | DPDP | Milestone 5 | DEV - WIP |  | 2025-07-31 | 2026-08-07
Framework: DPDP | Remove unnecessary fields |  | DPDP | Milestone 5 | DEV - Done |  | 2025-07-31 | 2026-08-07
Framework: DPDP | Enforce business logic to restrict purpose |  | DPDP | Milestone 5 | DEV - WIP |  | 2025-07-31 | 2026-08-07
Framework: DPDP | Allow user corrections |  | DPDP | Milestone 5 | DEV - WIP |  | 2025-07-31 | 2026-08-07 |  |  |  |  | IIRM-8015
Framework: DPDP | Delete expired data |  | DPDP | Milestone 5 | DEV - WIP |  | 2025-07-31 | 2026-08-07 |  |  |  |  | IIRM-8015
Framework: DPDP | Map PII tables |  | DPDP | Milestone 5 | QA - WIP |  | 2025-07-31 | 2026-08-07 |  |  |  | Rama
Framework: DPDP | Enable delete pipeline |  | DPDP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-08-07 |  |  |  |  | IIRM-8015
IBP: FRONTEND | User Profile | Profile, Service Subscriptions, Feedback | IBP | Milestone 5 | Pre-PROD | Pending: Service Subscriptions, Feedback | 2025-07-31 | 2026-08-03 |  |  |  | Ravi
IBP: Services - Larger Modules | Evexia Club Integration | Integration to Evexia | IBP | Milestone 5 | Pre-PROD |  | 2025-07-31 | 2026-08-03 |  |  |  | Abhilash | IIRM-795
IBP: Services - Larger Modules | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 |  |  |  |  | Ravi
IBP: Services - Larger Modules | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31
IBP: Services - Larger Modules | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31
IBP: Common Components | 3rd Party SSO | Props based SSO links to 3rd Parties | IBP | Milestone 5 | Delivered | SSO Framework implemented fro TPA | 2025-07-31 |  |  |  |  | Abhilash | IIRM-10433
IBP: SERVICES - Basic Modules | Hospital Network Mgmt | Based on the Insurer and TPA, network of hospitals needs to be presented in a consolidated view | IBP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-11 |  |  |  |  | IIRM-7589
IBP: FRONTEND | Static Info Sections - Landing | Benefits Guide, FAQs, Help | IBP | Milestone 5 | Delivered |  | 2025-07-31 | [5 empty] | IIRM-791
IBP: FRONTEND | Initiate Claim | Initiate claim for GMC (non-cashless), upload docs etc. | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations | 2025-07-31
IBP: FRONTEND | Claims Corner | View Claim Data for Individual Plans (if available), Track Status for Claims initiated from IBP for Group Plans, Track Status for Claims initiated with TPA directly, TAT reporting for Cashless (for Preauth and Discharge) | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations | 2025-07-31 | [5 empty] | IIRM-7631
IBP: Services - Larger Modules | Claims Mgmt | Part-1: Company Provided Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Delivered |  | 2025-07-31
IBP: SERVICES - Basic Modules | Feedback Mgmt | User Feedback capture service | IBP | Milestone 5 | Delivered | IBP support is already in place | 2025-07-31
IBP: FRONTEND | IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | IBP | Milestone 5 | Delivered |  | 2025-07-31
IBP: FRONTEND | Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | IBP | Milestone 5 | Delivered | Pending: Offers & Discuounts | 2025-07-31 | 2026-04-10 |  |  |  | Manjusha | IIRM-791
IBP: Services - Larger Modules | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | IBP/iWork | Milestone 5 | Pre-PROD | Pending: Offer, Feature flagging (UI) | 2025-07-31 | 2026-08-03 |  |  |  | Manjusha | IIRM-794
IBP: SERVICES - Basic Modules | Benefits Summary | End User's Summary View | IBP | Milestone 5 | Pre-PROD |  | 2025-07-31 | 2026-08-03 |  |  |  | Ravi
IBP: FRONTEND | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | IBP | Milestone 5 | Pre-PROD | Wellness | 2025-07-31 | 2026-08-03 |  |  |  | Manjusha | IIRM-784
IBP: FRONTEND | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | IBP/iWork | Milestone 5 | Pre-PROD |  | 2025-07-31 | 2026-08-03 |  |  |  | Ravi | IIRM-790
IBP: FRONTEND | Book Ambulance | Floater on the screen - Integrate to Ambulance Service | IBP | Milestone 5 | Not in scope |  | 2025-07-31
IBP: Services - Larger Modules | Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | IBP | Milestone 5 | Not in scope |  | 2025-07-31 | [5 empty] | IIRM-792
IBP: Services - Larger Modules | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 |  |  |  | Ravi | IIRM-788
IBP: FRONTEND | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 |  |  |  | Ravi
IBP: FRONTEND | Wellness HR View | HR View of Wellness usage by Employees | IBP | Milestone 5 | Yet to start | Wellness | 2025-07-31 | 2026-08-07 |  |  |  | Manjusha | IIRM-785
IBP: FRONTEND | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | IBP | Milestone 5 | Yet to start | Wellness | 2025-07-31 | 2026-08-07 |  |  |  | Manjusha
IBP: FRONTEND | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 |  |  |  | Ravi | IIRM-788
IBP: FRONTEND | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 |  |  |  | Ravi
IBP: FRONTEND | Profile Migration | Request migration of Corporate Profile to Individual | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 |  |  |  | Abhilash
IBP: FRONTEND | Profile Migration | Request migration of Individual Profile to Corporate | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 |  |  |  | Abhilash
iWORK: Services - Basic Modules | TPA Integration Mgmt [GHPL] | Launch TPA - SSO Ecards API - Read & View Details Hospital Network Claims Status API - Read, Store & View Details Claim Intimation API Claim Live Status - Single Claim | IBP/iWork | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-12 |  |  |  | Ravi | IIRM-783
IBP: FRONTEND | IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | IBP/iWork | Milestone 5 | Yet to start |  | 2025-07-31 | [5 empty] | IIRM-786
iWORK: Frontend | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) Similar to TPA API Integration Framework for any 3'rd Party | iWork | Milestone 5 | Delivered |  | 2025-07-31 | 2026-07-24
IBP: FRONTEND | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | IBP/iWork | Milestone 5 | Yet to start | Wellness HR View | 2025-07-31 | 2026-08-07 |  |  |  | Manjusha | IIRM-785
iWORK: Frontend | Claim Management (Add Claim, Import Claims & Claim Activities) | Basic Form with fields and upload for adding claim Bulk import to validate and map from TPA format to internal fields 3 stage workflow - each stage, update data on claim form | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | Report Hub | Landing Page and generic hub | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | CD Creation | Show current CD Balance against pooled/individual policies / Allow new CD creation, update CD balance and map policies to CD balances | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | CD Mgmt |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | Reports |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | Claim Mgmt |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | Insurer Integration Mgmt | Can be used as a part of External API Intergration | iWork | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-08-07
iWORK: Frontend | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | iWork | Milestone 5 | Yet to start | Need inputs from Kapil | 2025-07-31 | 2026-08-07
Framework: DPDP | Sign DPDP clauses |  | DPDP | Milestone 5 | DEV - WIP |  | 2025-07-31 | 2026-08-07 |  |  |  |  | IIRM-8015
Framework: NFR | NFR-COM-019: Terms and Conditions: The application must ensure require the customer to accept the Terms & Conditions at the first login to the application. This ensures compliance with PII regulations requiring Company group to inform the user of why Company is accessing/collecting personal data and why Company is using it. IIRM-4480 |  | NFR | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-05 |  |  |  |  | IIRM-4480
iWORK: Services - Basic Modules | Reconciliation Mgmt |  | iWork | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-08-07
Framework: NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | NFR | Milestone 5 | Yet to start | Discussed this with Surya sir last visit to Divami office | 2025-07-31 | 2026-08-07 |  |  |  |  | IIRM-4533
Framework: NFR | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure, which was broad symptom rather than a root cause. The renewed focus here is on failures related to cryptography which often leads to sensitive data exposure or system compromise. |  | NFR | Milestone 5 | DEV - WIP |  | 2025-07-31 | 2026-08-07 |  |  |  |  | IIRM-4526
Framework: DPDP | Quarterly restore tests |  | DPDP | Milestone 5 | Pre-PROD |  | 2025-07-31 | 2026-08-07 |  |  |  | Rama
IBP: FRONTEND | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | IBP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-07-31 |  |  |  |  | IIRM-789
IBP: Services - AI Components | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | IBP | Milestone 5 | Delivered | External chatbot integration? | 2025-07-31 | 2026-07-31 |  |  |  | Abhilash
IBP: Services - Larger Modules | Core Infrastructure | Core Infra | IBP/iWork | Milestone 5 | Delivered | Pending: Mobile responsive | 2025-07-31 | 2026-07-31 |  |  |  | Velangini Raju
iWORK: Services - Basic Modules | HRMS Integration Mgmt Framework provided to link the HRMS portal in Risk Watch | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? HRMS - integrations with enrolment portal (POC - with Zoho People), client mentioned that they have already integrated MB360 for HCL IBP & HRMS Integration - HCL | iWork | Milestone 5 | Delivered |  | 2025-07-31 | 2026-07-31
Production - Feedback | Cover Mgmt | Asset fields which are captured at Broking slip, few of the asset fields should not be printed at the time of Placement slip (example, no of members at inception, total lives, prev policy expiring year etc.) only for GMC | iWork - CR | Milestone 6 | Delivered |  | 2026-02-17 | 2026-06-25 |  |  |  | Karan
Production - Feedback | Policy Configuration | DNV Group - Dependent based SI & Premium configuration | iWork - CR | Milestone 6 | Delivered |  | 2026-04-07 | 2026-07-16 |  |  |  | Jagadeesh
Production - Feedback | VRK - PROD Feedback | Manage Insurer - Add Insurer Flow | iWork | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-09 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback | Opty. Flow - Add new Insurer Branch Details | iWork | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-12 |  |  |  | Pushyami
Production - Feedback | Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | iWork - CR | Milestone 6 | Delivered |  | 2026-05-01 | 2026-07-09 |  |  |  | Karan
Production - Feedback | Insurer Management | Enhance Insurer - Add, Edit, & Contacts | iWork - CR | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-09 |  |  |  | Pushyami | IIRM-10435
Production - Feedback | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | iWork - CR | Milestone 6 | Yet to start |  | 2026-05-01 | 2026-08-07 |  |  |  | Sunil | IIRM-9443
Production - Feedback | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | IBP - CR | Milestone 6 | Pre-PROD |  | 2026-05-08 | 2026-08-03 |  |  |  | Abhilash
Production - Feedback | Policy Configuration | Using AI - Extract the Policy document and perform Policy Configuration (Premium, Family, Parameters, & Others) | iWork - CR | Milestone 6 | Delivered |  | 2026-05-08 | 2026-07-01 |  |  |  | Jagadeesh
Production - Feedback | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | iWork - CR | Milestone 6 | Yet to start | Need some information about the document rules that defines the idenity of it | 2026-05-08 | 2026-08-07
Production - Feedback | Endorsement Mgmt (Non-Group / Non-GMC / Non-EB) | Enhance the Non-GMC Process (Based on Kishore feedback) | iWork - CR | Milestone 6 | Delivered |  | 2026-05-21 | 2026-05-28 |  |  |  | Pushyami
Production - Bug | Endorsement Mgmt | PROD Bug: Data Discrepancy - Inception/Endorsement vs Send to Client/Insurer (Preview & Excel) | iWork | Milestone 6 | Delivered |  | 2026-05-25 | 2026-05-27 |  |  |  | Prathiphala | IIRM-10291
Production - Bug | Endorsement Mgmt | PROD Bug: When download the TPA file, dependents are Missing in the file | iWork | Milestone 6 | Delivered |  | 2026-05-25 | 2026-05-27 |  |  |  | Sunil
Production - Feedback | IIRM-10587 | Add new fields - Business Month & Date of Business - Capture in Opty. & Flow to Policy and add filters in BizDone --> Refer to Madhav email "Business Month Requirement" | iWork | Milestone 6 | Delivered | Pending: Additional filters | 2026-05-28 | 2026-07-02 |  |  |  | Sunil | IIRM-10587
Production - Feedback | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-01 | 2026-07-17 |  |  |  | Abhilash
Production - Feedback | IIRM-10591 | IBP - Enrolment Journey - Reset | IBP | Milestone 6 | Delivered |  | 2026-06-03 | 2026-06-09 |  |  |  | Abhilash | IIRM-10591
Production - Feedback | VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | iWork | Milestone 6 | Delivered |  | 2026-06-05 | 2026-06-08
Production - Feedback | SSO - MS AD Account | iWork - SSO with Microsoft AD (POC) | iWork - CR | Milestone 6 | DEV - WIP | 10-Jun-2026: POC Demo to Venu completed | 2026-06-05 | 2026-08-07 |  |  |  | Rama
Production - Bug | Infra & Setup | Based on recent billing - Identifying the gaps in Redis data storage and gaps in implementation | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-06 | 2026-06-08 |  |  |  | Tharun
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | IIRM-10588 | Hide "Manage Policy" in "Manage Placements" link. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-09 |  |  |  | Pushyami | IIRM-10588
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-09 |  |  |  | Karan | IIRM-10589
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-10
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-12 |  |  |  | Karan | IIRM-10589
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-12
Production - Bug | VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-19 |  |  |  | Rama
Production - Bug | VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-24
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-09
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | iWork | Milestone 6 | Not a bug | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-30 |  |  |  | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-07-02
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | iWork | Milestone 6 | Not a bug |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | iWork | Milestone 6 | Pre-PROD |  | 2026-06-09 | 2026-08-03 |  |  |  | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 |  |  |  | Pushyami | IIRM-10588
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 |  |  |  | Prathiphala
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 |  |  |  | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 |  |  |  | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-12 |  |  |  | Prathiphala
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 |  |  |  | Karan | IIRM-10589
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 |  |  |  | Karan | IIRM-10589
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 |  |  |  | Karan | IIRM-10589
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 |  |  |  |  | IIRM-10589
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 |  |  |  | Karan | IIRM-10589
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-16 |  |  |  |  | IIRM-10589
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-19 |  |  |  | Karan
Production - Feedback | Risk Watch - Endorsement - Documents & Communication | Risk Watch - Endorsement - Documents & Communication | IBP | Milestone 6 | Delivered |  | 2026-06-10 | 2026-07-01 |  |  |  | Abhilash
Production - Feedback | Wellness Banner & SSO | Add banner and SSO to Alyve Wellness (Only Banner) | IBP | Milestone 6 | Delivered |  | 2026-06-10 | 2026-06-10
Production - Bug | Security | InfoSec - IBP Portal (Security Issue) | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-11 | 2026-07-10 |  |  |  | Manjusha
Production - Feedback | IIRM-10590 | Policy Config: Dependent Based Configurations - Per life depedent addition & increase SI - Apply Policy Parameters for dependents | IBP/iWork - CR | Milestone 6 | Delivered |  | 2026-06-11 | 2026-06-15 |  |  |  | Jagadeesh | IIRM-10590
Production - Feedback | Policy Config | New Policy constraints 1. Allow first child as Twin 2. Allow second child as Triplet 3. SI per Dependent 4. Parent Lock-in period | IBP/iWork - CR | Milestone 6 | Delivered |  | 2026-06-15 | 2026-06-16
Production - Feedback | IIRM-10667 | iWork - Knowledge Central Re-Design | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-06-15 | 2026-08-07 |  |  |  |  | IIRM-10667
Production - Feedback | IIRM-10668 | iLearn: Document Preview in-app | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-06-15 | 2026-08-07 |  |  |  |  | IIRM-10668
Production - Bug |  | Dashboard - Hide the widgets where there is NO data in the cards | iWork | Milestone 6 | Delivered |  | 2026-06-15 | 2026-07-10
Production - Feedback | Discuss with Madhav | 19-Jun-2026: Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard) Also, check if we are there are any data loads for 2025-26 | iWork | Milestone 6 | Yet to start |  | 2026-06-15 | 2026-08-07
Production - Feedback | Rewards | Rewards - Generic (Specific - Out of scope) | iWork | Milestone 6 | Delivered |  | 2026-06-18 | 2026-07-01 |  |  |  | Karan
Production - Feedback |  | Risk Watch: Showing policy feature documents at each policy | IBP | Milestone 6 | Delivered |  | 2026-06-19 | 2026-06-19 |  |  |  | Ravi
Production - Feedback | Wellness | IBP Portal Configure - Wellness - Buttons, CMS, & any other - Flag Driven | IBP | Milestone 6 | Delivered |  | 2026-06-19 | 2026-06-22 |  |  |  | Manjusha
Production - Feedback | IIRM-10666 | IBP - Policy Component Card Re-design | IBP | Milestone 6 | Yet to start |  | 2026-06-21 | 2026-08-07 |  |  |  | Manjusha | IIRM-10666
Production - Feedback | Claims Corner | Claims Corner - Screen Re-design | IBP | Milestone 6 | DEV - WIP |  | 2026-06-21 | 2026-08-07 |  |  |  | Ravi | IIRM-9988
Production - Bug | Risk Watch - Enrolment Drive | Risk Watch - List view to see the list of enrolment drive | IBP | Milestone 6 | Delivered |  | 2026-06-22 | 2026-07-10 |  |  |  | Ravi
Production - Feedback | Claims Process | Process claims without TPA ID (GPA & GTL - flag based) | iWork - CR | Milestone 6 | Delivered |  | 2026-06-22 | 2026-07-01 |  |  |  | Jagadeesh
Production - Feedback | Teamlease - Request | Flexibility to configure multiple companies & policies on a single domain | IBP/iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 |  |  |  | Abhilash
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Additional section display: Placement Funnel, Schedule, Followup | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-30 |  |  |  | Karan
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-07 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-14 |  |  |  | Karan
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - Filter & drill-down | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-14 |  |  |  | Karan
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | iWork and iTicket should be accessible via VPN | iWork - CR | Milestone 6 | Yet to start |  | 2026-06-23 | 2026-08-07 |  |  |  | Pushyami
Production - Feedback | InsureEasy | InsureEasy Integration - Retail Business | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07
Production - Feedback | AI | Wherever AI is implemented, there should be fallback if one day we turnoff AI then there shouldn’t be any impact in the working functionality | iWork | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07 |  |  |  | Rama
Production - Bug | AI | AI Nudges are NOT working. If there is NO AI, then DB scripts should run and show data | iWork | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07 |  |  |  | Rama
Production - Feedback | Inception/Endorsement | Endorsement data upload related * Track-1: TeamLease - 2024-2025 Year policies * All endorsement -> Headers, Member data, & endorsement Document * Track-2: Old Financial data * Track-3: Current Financial data * Track-4: Handle the data in IBP-Risk Watch | iWork | Milestone 6 | DEV - WIP |  | 2026-06-25 | 2026-08-07 |  |  |  | Rama
Production - Bug | Service Flow - Upload Employee Details | Upsert logic - Tough there is an employee data historically, when user upload latest file we have to update the "Empolyee" or "Dependent" details with the latest information | IBP/iWork - CR | Milestone 6 | DEV - WIP |  | 2026-07-01 | 2026-08-04 |  |  |  | Jagadeesh
Production - Feedback | One URL multiple companies | Flexibility to configure multiple companies on a single domain | IBP/iWork | Milestone 6 | Delivered |  | 2026-07-01 | 2026-07-07 |  |  |  |  | IIRM-10609
Production - Feedback | Enrolment Journey | Add GPA note based on employee type (Leadership vs Employee) | IBP - CR | Milestone 6 | Delivered |  | 2026-07-03 | 2026-07-03 |  |  |  | Manjusha
Production - Feedback | No Policy Config - Enrolment Journey | Enrolment Journey - Collect Dependents Details ONLY | IBP/iWork - CR | Milestone 6 | Delivered | Only in IBP as there are changes for iWork which is seperate | 2026-07-04 | 2026-07-14 |  |  |  | Jagadeesh | IIRM-10764
Production - Feedback | Madhav & Veera | Data Load - Company, Policy, Broker & Insurer - 30 Files | iWork | Milestone 6 | Delivered |  | 2026-07-06 | 2026-07-12 |  |  |  | Rama
Production - Feedback | Neeraj Joshi | Policy - Inception/Endorsement - Data Load - 13 Files | iWork | Milestone 6 | Delivered |  | 2026-07-06 | 2026-07-12 |  |  |  | Rama
Production - Bug | Employee Details | Trim spaces in the dependent names | IBP | Milestone 6 | Delivered |  | 2026-07-07 | 2026-07-07 |  |  |  | Manjusha
Production - Bug | Employee Details | Show Insurer Policy Details | IBP | Milestone 6 | Delivered |  | 2026-07-07 | 2026-07-07 |  |  |  | Manjusha
Production - Bug | Employee Details | Hide DOJ as there is NO source for us. | IBP | Milestone 6 | Delivered |  | 2026-07-08 | 2026-07-08 |  |  |  | Manjusha
Production - Feedback | Toast Message - UI | Update the font & style for Toast message across application | IBP/iWork | Milestone 6 | Yet to start | Surya sir provided an idea via email to Me & Naveen | 2026-07-09 | 2026-08-07 |  |  |  | Tharun
Production - Feedback | IBP - Email Communication | Send employee emails - Either AWS or Send Grid - Company Config | IBP - CR | Milestone 6 | Delivered |  | 2026-07-10 | 2026-07-10 |  |  |  | Abhilash
Production - Bug | IBP - FAQ | Policy Level - FAQ | IBP | Milestone 6 | Delivered |  | 2026-07-11 | 2026-07-17 |  |  |  | Manjusha
Production - Feedback | Madhav & Veera | Data Load - Company, Policy, & Insurer - 38 Files | iWork | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-19 |  |  |  | Rama
Production - Feedback | Neeraj Joshi | Production Bugs - Via Emails/Tickets - 10 | iWork | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-19 |  |  |  | Rama
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Remove the Vertical section. Keep only Branch. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-13 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - Make the Funnel interactive so that clicking on each stage navigates to the corresponding enhanced screen. Also, when we click on "Numbers" also it has to move to respective screens | iWork - CR | Milestone 6 | Delivered | Pending: Becuase the enhanced screens are yet to Approve | 2026-07-13 | 2026-07-22 |  |  |  | Pushyami
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Organization-wise summary cards are not required. | iWork - CR | Milestone 6 | Not in scope | Madhav sir confirmed via Teams Chat | 2026-07-13
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Under PL, the bar chart should represent SO-level data instead of the currently displayed RO-level data. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-22 |  |  |  | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Remove the SO/RO labels from the bar charts. Display only the figures inside the bars, with the corresponding details available on mouse hover (tooltip). | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-14 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Review and correct the display of negative values for TeamLease under RO, particularly for Q3 bar-chart. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-14 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Brokerage Display - Display Brokerage information only. Hide Premium values in the enhanced screens. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | BizDone Enhanced Screen - Hide Premium. Display: RO Brokerage SO Brokerage | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Resolve the Premium value formatting issue. Values should be displayed consistently in Millions/Billions. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Display the Endorsement section above the section “Business Collection Summary”. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Move the Policy Type Distribution section above RO by SBU. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Rename/update the Policy Type names “Fire & Engineering”, “Speciality Lines - Liability” | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15 |  |  |  |  | IIRM-10765
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - The SO Activity Follow-up screen should not display ISG-related activities. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - When IIRM Holdings is selected, the Organization-level cards and graphs are not displayed. Verify and fix the issue. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-17
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Display the data using an Accordion layout in the following order: Company → SBU → Branch → Executive → Client → Policy | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-20 |  |  |  |  | IIRM-10765
Production - Feedback | Surya's feedback | Policy Details - Strip - Remove view more button and company is clickable | iWork | Milestone 6 | Delivered |  | 2026-07-14 | 2026-07-22 |  |  |  | Pushyami
Production - Bug | iWork - Report | When we generate 2025-2026 data for IIRM India then API request is a failure. Need to find a solution | iWork | Milestone 6 | Delivered |  | 2026-07-17 | 2026-07-18
Production - Feedback | Application Access similar to SysAdmin | Need one more user like SYSADMIN. This user to be below SYSADMIN - and should be 100% read-only user - access etc all like SYSADMIN including Bizdone report download etc Also, inpersonate the user and see the data | iWork | Milestone 6 | Delivered | 1. Kapil sir sent it via Teams Chat. 2. Surya sir mentioned this in Call on Saturday | 2026-07-20 | 2026-07-24 |  |  |  | Pushyami
Production - Feedback | IBP - Send "Welcome Emails" or any email from IBP to include CC by HR or CRM User | IBP - Send "Welcome Emails" or any email from IBP to include CC by HR or CRM User | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-21 |  |  |  | Ravi
Production - Feedback | BizDone & Dashboard - Data Issue | Delete demo company, Demo company, Dummy company, Nokia Corporation (ref number 22337) | iWork | Milestone 6 | Delivered | Instead of delete, we maked the status NOT to show in the BizDone & Dashboard | 2026-07-20 | 2026-07-21 |  |  |  | Karan
Production - Feedback | BizDone | Update the associate CRM and Lead CRM as per enclosed sheet. This sheet has policy data. As per this, related SO, RO, Company also to be updated. Their are few records without any associate CRM assignment. So leave them blank. -- Refer to Data update.msg & CRM-Update.xlsx | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-21 |  |  |  | Jagadeesh
Production - Feedback | BizDone | Update Net Premium, Brokerage %, Brokerage Amount, & Income Month -- Refer to Data update - Set 2.msg & cl-updated.xlsx | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-21 |  |  |  | Jagadeesh
Production - Feedback | Madhav & Veera | Data Load - Company, Policy, & Insurer - 38 Files | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-24 |  |  |  | Rama
Production - Feedback | Neeraj Joshi | Production Bugs - Via Emails/Tickets - 10 | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-24 |  |  |  | Rama
Production - Feedback | BizDone | Update Lead CRM as Policy Owner for the selected Policies provided by Kapil | iWork | Milestone 6 | Delivered |  | 2026-07-21 | 2026-07-21 |  |  |  | Jagadeesh
Production - Feedback | BizDone | Update Opty. Owner value to Lead CRM of the Company | iWork | Milestone 6 | Delivered |  | 2026-07-21 | 2026-07-21 |  |  |  | Jagadeesh
Production - Bug | IBP - Enrolment Journey | When user save & exit is considered as Enrolled | IBP | Milestone 6 | Yet to start | Jayakar reported | 2026-07-21 |  |  |  |  | Abhilash
Production - Bug | Access Issue | When a user above the hirerchary is accessing the data, application is throwing "unauthorized" message | iWork | Milestone 6 | Delivered |  | 2026-07-22 | 2026-07-22 |  |  |  | Pushyami
Production - Feedback | Kapil's feedback | Data change requests - Madhav's - Ass. CRM & Others - Refer to Jagadeesh email | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 |  |  |  | Jagadeesh
Production - Bug |  | Income month prefilling in endorsements | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 |  |  |  | Jagadeesh
Production - Feedback | UX issue | Display of complete amounts in KPI cards on hover | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 |  |  |  | Pushyami
Production - Bug |  | Dashboard and BizDone Brokerage mismatch | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 |  |  |  | Jagadeesh
Production - Feedback | Surya's feedback | Removal of + or - 5 days logic in the filters - Revert the logic | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 |  |  |  | Karan
Production - Feedback |  | In BizDone - Include Fee & Rewards in Total Brokerage | iWork | Milestone 6 | Delivered |  | 2026-07-24 |  |  |  |  | Pushyami
Production - Feedback |  | In Dashboard - Include Fee & Rewards in Achieved | iWork | Milestone 6 | Delivered | Rewards will be added in RO as per Surya's sir and mention a note. Later based on VRK's feedback we will update it. | 2026-07-24 |  |  |  |  | Pushyami
Production - Bug | Application Performance | IIRM-10799_Performance (Database & Infra) | IBP/iWork | Milestone 6 | Yet to start |  | 2026-07-24 | 2026-08-07 |  |  |  |  | IIRM-10799
Production - Feedback | IBP - Email Communication | For an enrolled employee with Dependents using Service, instead of Welcome Email they should get Confirmation email | IBP/iWork | Milestone 6 | Pre-PROD | API is ready. Need to add into Notification framework | 2026-07-25 | 2026-08-04 |  |  |  | Abhilash
Production - Feedback | Personal Line Data Integrations | DSR and iWork Integration Enablement | iWork | Milestone 6 | Yet to start | Madhav sent in IIRM email | 2026-07-25 | 2026-08-07
Production - Bug | My Client Portfolio | My Client Portfolio: issues - company search and brokerage | iWork | Milestone 6 | Delivered |  | 2026-07-27 | 2026-07-27 |  |  |  | Pushyami
Production - Feedback | ISG Flow Changes | Placement Slip flow - Terrorism premium in Insurer Sharing | iWork | Milestone 6 | Pre-PROD | Madhav sent in IIRM email | 2026-07-27 | 2026-08-03 |  |  |  | Karan
Production - Feedback | IBP - Email Communication | Enrollment reminders - Need another configuration "Every day" and send till last day of enrolment | IBP/iWork | Milestone 6 | Delivered |  | 2026-07-27 |  |  |  |  | Abhilash
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Enhanced screen: My Client Portfolio | iWork - CR | Milestone 6 | Delivered |  | 2026-07-27 | 2026-07-30 |  |  |  |  | IIRM-10765
Production - Bug | Dashboard | Dashboard issue - ISG planning count mismatch | iWork | Milestone 6 | Delivered |  | 2026-07-28 | 2026-07-28 |  |  |  | Pushyami
Production - Bug | Dashboard | Business Performance-breakup - count mismatch | iWork | Milestone 6 | Delivered |  | 2026-07-28 | 2026-07-28 |  |  |  | Pushyami
Production - Bug | Manage Insurer | Insurer-branch-edit | iWork | Milestone 6 | Delivered |  | 2026-07-29 | 2026-07-29
Production - Bug | Enrolment Journey - EMI's | Based on Employee's enrolment period, the EMI months should be pro-ration month. Ex: Day-1 should show the all months EMI. If someone enrol after 2-months then EMI should be based on that. | IBP/iWork | Milestone 6 | Delivered | Kriti raised | 2026-07-29 | 2026-07-31
Production - Bug | BizDone - Data Updates | Bizdone 2025-26 - Ass. CRM & Lead CRM Corrections | iWork | Milestone 6 | Delivered | Madhav sent in IIRM email | 2026-07-30 | 2026-07-31
Production - Bug | IBP - Enrolment Details | DVN Group - Dependent based on SI & Premium changes | iWork | Milestone 6 | DEV - WIP |  | 2026-08-01 | 2026-08-04 |  | 2026-08-03 | 2026-08-04 | Abhilash
Production - Feedback | IBP - Enrolment Journey | Using Policy Config, add only dependent & complete the enrolment. - Hide SI, Premiums, Rate Calculator - Endorsement - Employee only should support SI & Parameter | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-08-03 | 2026-08-05 |  | 2026-08-04 | 2026-08-05 | Jagadeesh
Stablization | Business Critical | Migration Data load should be always complete only after manual Performances Job Execution - Continous acitivity | iWork | Milestone 6 | DEV - WIP |  | 2026-08-01 | 2026-08-03 | High | 2026-08-03 | 2026-08-03 | Rama
Stablization | Business Critical | Dashboard: Having individual component loaders on the landing page for each component and web-socket framework to avoid long-loading blank page issue. | iWork | Milestone 6 | DEV - WIP |  | 2026-08-01 | 2026-08-04 | High | 2026-08-03 | 2026-08-04 | Manjusha
Stablization | Business Critical | BizDone & Dashboard: Filters Persistance | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-04 | High | 2026-08-04 | 2026-08-04 | Sunil
Stablization | Business Critical | BizDone - Download - User select the desired sheet | iWork - CR | Milestone 6 | DEV - WIP |  | 2026-08-01 | 2026-08-04 | High | 2026-08-04 | 2026-08-04 | Karan
Stablization | Business Critical | BizDone - Download - Indian template along with Localization fields | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-04 | High | 2026-08-04 | 2026-08-04 | Leela
Stablization | Business Critical | The owner selection process remains highly user-unfriendly, with a very small expand ('>') button, incomplete visibility of names, and insufficient hierarchy indentation. | iWork | Milestone 6 | Yet to start |  | 2026-07-18 | 2026-08-06 | High | 2026-08-04 | 2026-08-06 | Raju
Stablization | Business Critical | BizDone - Download - Performance (Offload Excel Generation) - API, Queue, Store in S3 & Download | iWork | Milestone 6 | DEV - WIP |  | 2026-08-01 | 2026-08-05 | High | 2026-08-03 | 2026-08-05 | Karan
Stablization | Business Critical | BizDone - Applied filters in the Downloaded file in Sheet-1 | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-05 | High | 2026-08-04 | 2026-08-05 | Sunil
Stablization | Business Critical | IBP - Risk Watch - Report Issues - Enrolment Drive - Validate, enhance, and document | IBP | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-05 | High | 2026-08-04 | 2026-08-05 | Ravikiran
Stablization | Operational | Job - Dashboard - Review, Enhance and document | iWork | Milestone 6 | Yet to start | Flag based development / remove job post approval | 2026-08-01 | 2026-08-05 | High | 2026-08-04 | 2026-08-05 | Sunil
Stablization | Operational | Personal Lines Data Integration (DSR and iWork) | iWork | Milestone 6 | Yet to start |  | 2026-07-25 | 2026-08-05 | High | 2026-08-04 | 2026-08-05 | Junaid
Stablization | Business Critical | BizDone - Old & Enhance Screens - For now both will be live | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-06 | High | 2026-08-05 | 2026-08-06 | Karan
Stablization | Business Critical | Dashboard & BizDone: Centralised code or utility to fetch the KPIs data for re-usability | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-06 | High | 2026-08-05 | 2026-08-06 | Sunil
Stablization | Operational | Demo Env. - Stop all the Job; Make sure emails & SMS are working as expected | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-06 | High | 2026-08-05 | 2026-08-06 | Tharun
Stablization | Business Critical | BizDone & Dashboard - Consider Fee & Rewards as "Brokerage" | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-07 | High | 2026-08-06 | 2026-08-07 | Sunil
Stablization | Business Critical | Dashboard: Implementation of the dynamic fetching of widgets data without depending on performance output cron job | iWork | Milestone 6 | DEV - WIP |  | 2026-08-01 | 2026-08-03 | High | 2026-08-06 | 2026-08-06 | Jagadeesh
Stablization | Business Critical | BizDone - Screen & Download data is not consistent | iWork | Milestone 6 | Yet to start |  | 2026-07-18 | 2026-08-07 | High | 2026-08-06 | 2026-08-07 | Karan
Stablization | Business Critical | IBP - Risk Watch - Company & Policy Levels are not matching (CD, Endorsement, Claims) | IBP | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-07 | High | 2026-08-06 | 2026-08-07 | Ravikiran
Stablization | Operational | PROD & Other env.: Database Vaccum - Schedule a periodic acitvity in all the env. | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-07 | High | 2026-08-06 | 2026-08-07 | Abhilash
Stablization | Business Critical | BizDone - Performance - Query Fine Tuning | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-10 | High | 2026-08-10 | 2026-08-10 | Karan
Stablization | Business Critical | BizDone & other filters - Multi-select for Vertical & Months | iWork | Milestone 6 | Yet to start |  | 2026-07-18 | 2026-08-11 | High | 2026-08-10 | 2026-08-11 | Sunil
Stablization | Operational | Demo Env. - Record the application/Infrastruction/DevOps situation when application is in Zero state | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-11 | High | 2026-08-10 | 2026-08-11 | Tharun / Jagadeesh
Stablization | Operational | PROD & Demo Env.: Database - Partitioning | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-11 | High | 2026-08-10 | 2026-08-11 | Abhilash
Stablization | Operational | Notification Mgmt - Turn on, Turn off, History, Approval, template changes | iWork/IBP | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-11 | High | 2026-08-11 | 2026-08-11 | Karan
Stablization | Business Critical | Dashboard - Performance - Query Fine Tuning | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-12 | High | 2026-08-12 | 2026-08-12 | Sunil
Stablization | Business Critical | BizDone - Download - Reduce the file size (Ex. Excel binary or others) | iWork - CR | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-12 | High | 2026-08-12 | 2026-08-12 | Karan
Stablization | Operational | PROD & Demo Env.: Database - Indexing | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-13 | High | 2026-08-12 | 2026-08-13 | Abhilash
Stablization | Operational | Job - Expiry Opportunity - Review, Enhance and document | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-12 | High | 2026-08-12 | 2026-08-12 | Karan
Stablization | Operational | Job - RO Creation - Review, Enhance and document | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-13 | High | 2026-08-13 | 2026-08-13 | Karan
Stablization | Operational | PROD & Demo Env.: Database - SQL Functions for all the reports | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-14 | High | 2026-08-14 | 2026-08-14 | Abhilash
Stablization | Business Critical | BizDone & Dashboard: Remove orphane Opportunities | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Business Critical | BizDone & Dashboard: Remove orphane Policies | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Business Critical | IBP - Email Notification - Company specific email templates for all types (Welcome, Confirmation, Reminder, Raise Ticket, & Others) | iWork/IBP | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Production - Bug | Business Critical | iWork/IBP - Claim Process - Intimation & Submission (Different Flows) | iWork/IBP | Milestone 6 | Yet to start |  | 2026-08-01
Production - Bug | Business Critical | Life Events - Create Endorsment & next steps; Notification to CRM/KAM Team | iWork/IBP | Milestone 6 | Yet to start |  | 2026-08-01
Stablization | Business Critical | Computed value & Reported values * Computed values - It’s the real-time values base on Policy inception/endorsement * Reported values - It’s validated by the mgmt. and share this number to update in the column. * Reported value MUST be used for the Dashboard & BizDone, which was declared by the company to public. * In the admin a feature to update the Reported values from the computed values * Legacy data - Premiums, Brokerage, CD Balance | iWork - CR | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07 | Medium
Stablization | Operational | PROD Bug: SCS - Notifications - Check what is the configuration. (Scenario: For the very first time Email or SMS is taking time then rest are instant) | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Infra - Season based bumping (Example: When policies are expiring, need to bump the infra/DB because load will be more). Identify the data and plan this acitivity. | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Optimal allocate the memory/infra size based on the service operational usage rather than generic size for all | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Split Service - Risk Watch because it should run on it own and NOT impact other iWork or IBP services | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Split Service - Identify service areas because either iWork or IBP utilization should not impact other services | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Reports - iWork - Validate, enhance, and document | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Operational | Policy Config - Premium Rater Table | iWork - CR | Milestone 6 | Yet to start |  | 2026-04-21 |  | Medium |  |  | Jagadeesh
Stablization | Operational | CMS - Policy Level - Component Notes from Stapi | iWork | Milestone 6 | Yet to start | Ex. TL - Parental 2-years Lock-in; SI may vary | 2026-07-31 |  | Low
Stablization | Operational | Automation process for Data Load (Gopal & Rama's Task) | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Production - Feedback | Operational | IBP - Emails: Dual approval/confirmation - Before sending to Employees. 1. 2 levels in iWork 2. CRM will submit & HR will approve in Risk Watch | IBP/iWork | Milestone 6 | Yet to start |  | 2026-07-14
Production - Feedback | Operational | IBP - Raise Ticket: Edit the ticket and update the status by the Lead CRM & System Admin Same funtionality should be there in iWork for internal purpose. Should send email notification when there are changes to status | IBP/iWork | Milestone 6 | Yet to start |  | 2026-07-01 |  |  |  |  | Manjusha
Stablization | Operational | Export to excel - iWork all the results table; Download is on Previlage | iWork | Milestone 6 | Yet to start |  | 2026-06-15 |  | Low
Stablization | Operational | Export - IBP-Risk Watch - All the results/Widget must be downloadable based onn Previlage | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Email Notifications - Opty. Lost/ Policy Renewals/ Instalments - CRM users | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Add/Update - Address & Contact - Across Application | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Maintenance | PROD: Health Check of the Application, Alert notification & Triage the situation | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Maintenance | Convert Policy from Active to Generated | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Maintenance | Delete - Policy Configuration | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Maintenance | Delete - Inception/Endorsement Data | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Maintenance | Employee Mgmt - Create, Update, Delete - Validate and document | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Maintenance | Hierarchy Mgmt - View & Update - Report & Visual Chart | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Maintenance | In any of the screen, we have to provide an info icon where it will help the users how critical fields in that screen are derieved or got populated | iWork | Milestone 6 | Yet to start |  | 2026-07-17 |  | Low
Stablization | Maintenance | IBP - Go-Live: Check-list document & SOP | iWork/IBP | Milestone 6 | Yet to start |  | 2026-04-20 |  | Low |  |  | Nithin
Stablization | Maintenance | iWork - Reports - View Dump for each download for comparision | iWork | Milestone 6 | Yet to start |  | 2026-04-20 |  | Medium
Stablization | Maintenance | iWork - Reports - Use BizDone framework | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium

## ① Executive Summary
PROJECT DELIVERY PLAN
iWork · IBP · Framework (IIRM SOW) ¦ Status Overview & Forward Roadmap · As of 07-Aug-2026
OVERALL COMPLETION | [6 empty] | REMAINING WORK
67.7% |  |  | 277 of 409 scope items delivered |  |  |  | 132 |  | items still to deliver across all modules — planned week by week in the weekly sheets
SOW SCOPE — ORIGINAL vs CURRENT ITEMS
Static comparison vs the 'SOW - Actual Items' reference sheet (original contracted scope). Matched by Module + Feature name. Recomputed on each re-run of the script.
Original SOW items | [5 empty] | 158
Currently tracked (all items) | [5 empty] | 409
— new: DPDP / NFR / Change Requests | [5 empty] | 77
— new: organic growth (existing modules) | [5 empty] | 182
Net growth vs original SOW (158 → 409) | [5 empty] | +251
⚠ 2 original SOW item(s) still need review — no matching row in the tracker and no mapping note yet.
🔗 15 item(s) already mapped by hand to a renamed/restructured tracker row — see notes in 'SOW - Actual Items'.
WEEKLY INTAKE — items requested (by Requested Date)
Period | Added | Delivered | Pending | % Closed
Before 01-Jun-2026 | 210 | 157 | 53 | 74.76%
Week of 01 Jun 2026 | 5 | 4 | 1 | 80%
Week of 08 Jun 2026 | 43 | 42 | 1 | 97.67%
Week of 15 Jun 2026 | 11 | 5 | 6 | 45.45%
Week of 22 Jun 2026 | 21 | 15 | 6 | 71.43%
Week of 29 Jun 2026 | 5 | 3 | 2 | 60%
Week of 06 Jul 2026 | 8 | 7 | 1 | 87.5%
Week of 13 Jul 2026 | 24 | 19 | 5 | 79.17%
Week of 20 Jul 2026 | 22 | 17 | 5 | 77.27%
Week of 27 Jul 2026 — last week | 59 | 8 | 51 | 13.56%
Week of 03 Aug 2026 — this week | 1 | 0 | 1 | 0%
Requested ahead (after 09 Aug) | 0 | 0 | 0 | 0%
No Requested Date | 0 | 0 | 0 | 0%
TOTAL | 409 | 277 | 132 | 67.73%
STATUS BREAKDOWN (all items)
276 |  |  | 1 |  |  | 18 |  |  | 1
Delivered |  |  | Dev Complete |  |  | In Development |  |  | In QA
17 |  |  | 93 |  |  | 3 |  |  | 0
Pre-PROD / UAT |  |  | Not Started |  |  | Partial Delivery |  |  | N/A
PROGRESS BY MODULE
Module | Type | Total | Delivered | Pending | N/A | % Complete | Progress
iWork (Backlog) | Backlog | 195 | 133 | 62 | 0 | 68.21% | 68.21%
iWork (Change Requests) | Change Request | 43 | 35 | 8 | 0 | 81.4% | 81.4%
IBP (Backlog) | Backlog | 71 | 49 | 22 | 0 | 69.01% | 69.01%
IBP (Change Requests) | Change Request | 3 | 2 | 1 | 0 | 66.67% | 66.67%
IBP / iWork (Shared) | Backlog | 27 | 15 | 12 | 0 | 55.56% | 55.56%
IBP / iWork (Shared CRs) | Change Request | 9 | 4 | 5 | 0 | 44.44% | 44.44%
Framework | Backlog | 34 | 31 | 3 | 0 | 91.18% | 91.18%
DPDP | Backlog | 18 | 7 | 11 | 0 | 38.89% | 38.89%
NFR | Backlog | 4 | 1 | 3 | 0 | 25% | 25%
TOTAL | All | 409 | 277 | 132 | 0 | 67.73% | 67.73%
PENDING BY MILESTONE & MODULE
Milestone | iWork | iWork - CR | IBP | IBP - CR | IBP/iWork | IBP/iWork - CR | Framework | DPDP | NFR | TOTAL PENDING
Milestone 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Milestone 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 4 | 1 | 0 | 1 | 0 | 3 | 0 | 3 | 1 | 1 | 10
Milestone 5 | 4 | 0 | 16 | 0 | 4 | 0 | 0 | 10 | 2 | 36
Milestone 6 | 56 | 8 | 5 | 1 | 5 | 5 | 0 | 0 | 0 | 80
TOTAL | 62 | 8 | 22 | 1 | 12 | 5 | 3 | 11 | 3 | 127
ITEMS BY MILESTONE & STATUS
Milestone | Delivered | Dev Complete | In Development | In QA | Pre-PROD / UAT | Not Started | Partial Delivery | TOTAL
Milestone 1 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 29
Milestone 2 | 31 | 0 | 0 | 0 | 1 | 0 | 0 | 32
Milestone 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Milestone 4 | 47 | 0 | 0 | 0 | 4 | 4 | 2 | 57
Milestone 5 | 30 | 1 | 8 | 1 | 8 | 18 | 1 | 67
Milestone 6 | 131 | 0 | 10 | 0 | 4 | 71 | 0 | 216
TOTAL | 276 | 1 | 18 | 1 | 17 | 93 | 3 | 409
% Complete = Delivered ÷ (Delivered + Pending). N/A items (duplicates) are excluded from the calculation. All figures update live from the 'SOW, Feedbacks-Bug & CR_Items' sheet.

## ② Stablization Summary
STABLIZATION — STATUS OVERVIEW
Stablization Area ¦ Break-up by Feature · As of 07-Aug-2026
OVERALL COMPLETION | [6 empty] | REMAINING WORK
0% |  |  | 0 of 57 Stablization items delivered |  |  |  | 57 |  | Stablization items still to deliver, broken up by Feature below
STATUS BREAKDOWN (Stablization items)
0 |  |  | 0 |  |  | 5 |  |  | 0
Delivered |  |  | Dev Complete |  |  | In Development |  |  | In QA
0 |  |  | 52 |  |  | 0 |  |  | 0
Pre-PROD / UAT |  |  | Not Started |  |  | Partial Delivery |  |  | N/A
BREAKDOWN BY FEATURE
Feature | Total | Delivered | Pending | N/A | % Complete | Progress
Business Critical | 23 | 0 | 23 | 0 | 0% | 0%
Maintenance | 10 | 0 | 10 | 0 | 0% | 0%
Operational | 24 | 0 | 24 | 0 | 0% | 0%
TOTAL | 57 | 0 | 57 | 0 | 0% | 0%
Scope: rows where Area = 'Stablization' in the source sheet. % Complete = Delivered ÷ (Delivered + Pending). N/A items excluded. Counts update live from the source sheet; re-run the script only if a new Feature value is added under this Area (to add its row here).
PRIORITY vs STATUS
Priority | Delivered | Dev Complete | In Development | In QA | Pre-PROD / UAT | Not Started | Partial Delivery | N/A | TOTAL
High | 0 | 0 | 5 | 0 | 0 | 25 | 0 | 0 | 30
Medium | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 13
Low | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14
TOTAL | 0 | 0 | 5 | 0 | 0 | 52 | 0 | 0 | 57
Scope: rows where Area = 'Stablization', grouped by the 'Priority' column. Counts update live from the source sheet; re-run the script only if a new Priority value is used (to add its row here).
DAILY PROGRESS — toward the 14-Aug-2026 deadline
Date | Total | Planned Delivered | Delivered | Planned Pending | Pending | Delivered Today | % Complete | Ahead/Behind Plan | Days Left | Req. Pace/day
2026-08-03 | 31 | 2 | 0 | 29 | 31 | — | 0% | -2 | 11 | 2.8
2026-08-04 | 31 | 6 | 0 | 25 | 31 | 0 | 0% | -6 | 10 | 3.1
2026-08-05 | — | 11 | — | 20 | — | — | — | — | 9 | —
2026-08-06 | — | 15 | — | 16 | — | — | — | — | 8 | —
2026-08-07 | — | 20 | — | 11 | — | — | — | — | 7 | —
2026-08-08 | — | 20 | — | 11 | — | — | — | — | 6 | —
2026-08-09 | — | 20 | — | 11 | — | — | — | — | 5 | —
2026-08-10 | — | 21 | — | 10 | — | — | — | — | 4 | —
2026-08-11 | — | 25 | — | 6 | — | — | — | — | 3 | —
2026-08-12 | — | 28 | — | 3 | — | — | — | — | 2 | —
2026-08-13 | — | 30 | — | 1 | — | — | — | — | 1 | —
2026-08-14 | — | 31 | — | 0 | — | — | — | — | 0 | —
Unplanned (no ETA / ETA beyond 14-Aug) |  | 26
Scope: only the 31 Stablization items with an ETA on or before 14-Aug-2026 — that's the actual plan for this deadline. Planned Delivered/Pending = cumulative count of those items due on or before that day, from their real ETA dates (not a smoothed ramp); recomputed every run, so it shifts if ETAs or the item set change. Ahead/Behind Plan = Delivered − Planned Delivered for that day. The 26 item(s) with no ETA (or an ETA after 14-Aug) are listed above, not counted toward this deadline.

## 📅 27-Jul
WEEK OF 27 Jul 2026 → 02 Aug 2026 — 11 items · 11 delivered · 0 pending · LAST WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 9 items · 9 delivered · 0 pending
1 | iWork | My Client Portfolio | My Client Portfolio: issues - company search and brokerage | Delivered | Milestone 6 | 27-Jul-2026 | 27-Jul-2026 | Pushyami
2 | iWork | Dashboard | Dashboard issue - ISG planning count mismatch | Delivered | Milestone 6 | 28-Jul-2026 | 28-Jul-2026 | Pushyami
3 | iWork | Dashboard | Business Performance-breakup - count mismatch | Delivered | Milestone 6 | 28-Jul-2026 | 28-Jul-2026 | Pushyami
4 | iWork | View Service Score | My Client Portfolio: Service Score - Single Table (drillable) to calculate an overall score Dashboard - Service Score - Widget | Delivered | Milestone 4 | 10-Jun-2025 | 29-Jul-2026 | Sunil
5 | iWork | Manage Insurer | Insurer-branch-edit | Delivered | Milestone 6 | 29-Jul-2026 | 29-Jul-2026
6 | IBP/iWork | Core Infrastructure | Core Infra | Delivered | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Velangini Raju | Pending: Mobile responsive
7 | iWork | HRMS Integration Mgmt Framework provided to link the HRMS portal in Risk Watch | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? HRMS - integrations with enrolment portal (POC - with Zoho People), client mentioned that they have already integrated MB360 for HCL IBP & HRMS Integration - HCL | Delivered | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
8 | IBP/iWork | Enrolment Journey - EMI's | Based on Employee's enrolment period, the EMI months should be pro-ration month. Ex: Day-1 should show the all months EMI. If someone enrol after 2-months then EMI should be based on that. | Delivered | Milestone 6 | 29-Jul-2026 | 31-Jul-2026 |  | Kriti raised
9 | iWork | BizDone - Data Updates | Bizdone 2025-26 - Ass. CRM & Lead CRM Corrections | Delivered | Milestone 6 | 30-Jul-2026 | 31-Jul-2026 |  | Madhav sent in IIRM email
IBP (Backlog & CRs) · 2 items · 2 delivered · 0 pending
10 | IBP | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | Delivered | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
11 | IBP | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | Delivered | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Abhilash | External chatbot integration?

## 📍 03-Aug
WEEK OF 03 Aug 2026 → 09 Aug 2026 — 84 items · 0 delivered · 84 pending · CURRENT WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 48 items · 0 delivered · 48 pending
1 | iWork | Cut Off Mgmt |  | Pre-PROD | Milestone 2 | 16-Apr-2025 | 03-Aug-2026 | Karan
2 | IBP/iWork | Wellness Discount List Management | Add/Remove/update Discount program benefits | Pre-PROD | Milestone 4 | 10-Jun-2025 | 03-Aug-2026
3 | IBP/iWork | Upload from Partner of services bought on Partner site | Upload, listing, confirm & load into DB by an Iwork user. These are services purchased / discounts availed on partner sites by IBP corporate users | Pre-PROD | Milestone 4 | 10-Jun-2025 | 03-Aug-2026
4 | IBP/iWork | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | Pre-PROD | Milestone 5 | 31-Jul-2025 | 03-Aug-2026 | Manjusha | Pending: Offer, Feature flagging (UI)
5 | IBP/iWork | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | Pre-PROD | Milestone 5 | 31-Jul-2025 | 03-Aug-2026 | Ravi
6 | iWork | ISG Flow Changes | Placement Slip flow - Terrorism premium in Insurer Sharing | Pre-PROD | Milestone 6 | 27-Jul-2026 | 03-Aug-2026 | Karan | Madhav sent in IIRM email
7 | iWork | Business Critical | Migration Data load should be always complete only after manual Performances Job Execution - Continous acitivity | DEV - WIP | Milestone 6 | 01-Aug-2026 | 03-Aug-2026 | Rama
8 | iWork | Business Critical | Dashboard: Implementation of the dynamic fetching of widgets data without depending on performance output cron job | DEV - WIP | Milestone 6 | 01-Aug-2026 | 03-Aug-2026 | Jagadeesh
9 | IBP/iWork - CR | Service Flow - Upload Employee Details | Upsert logic - Tough there is an employee data historically, when user upload latest file we have to update the "Empolyee" or "Dependent" details with the latest information | DEV - WIP | Milestone 6 | 01-Jul-2026 | 04-Aug-2026 | Jagadeesh
10 | IBP/iWork | IBP - Email Communication | For an enrolled employee with Dependents using Service, instead of Welcome Email they should get Confirmation email | Pre-PROD | Milestone 6 | 25-Jul-2026 | 04-Aug-2026 | Abhilash | API is ready. Need to add into Notification framework
11 | iWork | IBP - Enrolment Details | DVN Group - Dependent based on SI & Premium changes | DEV - WIP | Milestone 6 | 01-Aug-2026 | 04-Aug-2026 | Abhilash
12 | iWork | Business Critical | Dashboard: Having individual component loaders on the landing page for each component and web-socket framework to avoid long-loading blank page issue. | DEV - WIP | Milestone 6 | 01-Aug-2026 | 04-Aug-2026 | Manjusha
13 | iWork | Business Critical | BizDone & Dashboard: Filters Persistance | Yet to start | Milestone 6 | 01-Aug-2026 | 04-Aug-2026 | Sunil
14 | iWork - CR | Business Critical | BizDone - Download - User select the desired sheet | DEV - WIP | Milestone 6 | 01-Aug-2026 | 04-Aug-2026 | Karan
15 | iWork | Business Critical | BizDone - Download - Indian template along with Localization fields | Yet to start | Milestone 6 | 01-Aug-2026 | 04-Aug-2026 | Leela
16 | iWork | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 05-Aug-2026 |  | Linked with Reconciliation Management & Commission
17 | iWork | Operational | Personal Lines Data Integration (DSR and iWork) | Yet to start | Milestone 6 | 25-Jul-2026 | 05-Aug-2026 | Junaid
18 | iWork | Business Critical | BizDone - Download - Performance (Offload Excel Generation) - API, Queue, Store in S3 & Download | DEV - WIP | Milestone 6 | 01-Aug-2026 | 05-Aug-2026 | Karan
19 | iWork | Business Critical | BizDone - Applied filters in the Downloaded file in Sheet-1 | Yet to start | Milestone 6 | 01-Aug-2026 | 05-Aug-2026 | Sunil
20 | iWork | Operational | Job - Dashboard - Review, Enhance and document | Yet to start | Milestone 6 | 01-Aug-2026 | 05-Aug-2026 | Sunil | Flag based development / remove job post approval
21 | IBP/iWork - CR | IBP - Enrolment Journey | Using Policy Config, add only dependent & complete the enrolment. - Hide SI, Premiums, Rate Calculator - Endorsement - Employee only should support SI & Parameter | Yet to start | Milestone 6 | 03-Aug-2026 | 05-Aug-2026 | Jagadeesh
22 | iWork | Business Critical | The owner selection process remains highly user-unfriendly, with a very small expand ('>') button, incomplete visibility of names, and insufficient hierarchy indentation. | Yet to start | Milestone 6 | 18-Jul-2026 | 06-Aug-2026 | Raju
23 | iWork | Business Critical | BizDone - Old & Enhance Screens - For now both will be live | Yet to start | Milestone 6 | 01-Aug-2026 | 06-Aug-2026 | Karan
24 | iWork | Business Critical | Dashboard & BizDone: Centralised code or utility to fetch the KPIs data for re-usability | Yet to start | Milestone 6 | 01-Aug-2026 | 06-Aug-2026 | Sunil
25 | iWork | Operational | Demo Env. - Stop all the Job; Make sure emails & SMS are working as expected | Yet to start | Milestone 6 | 01-Aug-2026 | 06-Aug-2026 | Tharun
26 | IBP/iWork | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | Yet to start | Milestone 4 | 10-Jun-2025 | 07-Aug-2026 | Rama
27 | iWork | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | Yet to start | Milestone 4 | 10-Jun-2025 | 07-Aug-2026 | Rama
28 | IBP/iWork | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Manjusha | Wellness HR View
29 | iWork | Insurer Integration Mgmt | Can be used as a part of External API Intergration | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
30 | iWork | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 |  | Need inputs from Kapil
31 | iWork | Reconciliation Mgmt |  | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
32 | iWork - CR | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | Yet to start | Milestone 6 | 01-May-2026 | 07-Aug-2026 | Sunil
33 | iWork - CR | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | Yet to start | Milestone 6 | 08-May-2026 | 07-Aug-2026 |  | Need some information about the document rules that defines the idenity of it
34 | iWork - CR | SSO - MS AD Account | iWork - SSO with Microsoft AD (POC) | DEV - WIP | Milestone 6 | 05-Jun-2026 | 07-Aug-2026 | Rama | 10-Jun-2026: POC Demo to Venu completed
35 | IBP/iWork - CR | IIRM-10667 | iWork - Knowledge Central Re-Design | Yet to start | Milestone 6 | 15-Jun-2026 | 07-Aug-2026
36 | IBP/iWork - CR | IIRM-10668 | iLearn: Document Preview in-app | Yet to start | Milestone 6 | 15-Jun-2026 | 07-Aug-2026
37 | iWork | Discuss with Madhav | 19-Jun-2026: Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard) Also, check if we are there are any data loads for 2025-26 | Yet to start | Milestone 6 | 15-Jun-2026 | 07-Aug-2026
38 | IBP/iWork - CR | InsureEasy | InsureEasy Integration - Retail Business | Yet to start | Milestone 6 | 25-Jun-2026 | 07-Aug-2026
39 | iWork | AI | Wherever AI is implemented, there should be fallback if one day we turnoff AI then there shouldn’t be any impact in the working functionality | Yet to start | Milestone 6 | 25-Jun-2026 | 07-Aug-2026 | Rama
40 | iWork | AI | AI Nudges are NOT working. If there is NO AI, then DB scripts should run and show data | Yet to start | Milestone 6 | 25-Jun-2026 | 07-Aug-2026 | Rama
41 | iWork | Inception/Endorsement | Endorsement data upload related * Track-1: TeamLease - 2024-2025 Year policies * All endorsement -> Headers, Member data, & endorsement Document * Track-2: Old Financial data * Track-3: Current Financial data * Track-4: Handle the data in IBP-Risk Watch | DEV - WIP | Milestone 6 | 25-Jun-2026 | 07-Aug-2026 | Rama
42 | iWork - CR | Business Critical | Computed value & Reported values * Computed values - It’s the real-time values base on Policy inception/endorsement * Reported values - It’s validated by the mgmt. and share this number to update in the column. * Reported value MUST be used for the Dashboard & BizDone, which was declared by the company to public. * In the admin a feature to update the Reported values from the computed values * Legacy data - Premiums, Brokerage, CD Balance | Yet to start | Milestone 6 | 25-Jun-2026 | 07-Aug-2026
43 | IBP/iWork | Toast Message - UI | Update the font & style for Toast message across application | Yet to start | Milestone 6 | 09-Jul-2026 | 07-Aug-2026 | Tharun | Surya sir provided an idea via email to Me & Naveen
44 | iWork | Business Critical | BizDone - Screen & Download data is not consistent | Yet to start | Milestone 6 | 18-Jul-2026 | 07-Aug-2026 | Karan
45 | IBP/iWork | Application Performance | IIRM-10799_Performance (Database & Infra) | Yet to start | Milestone 6 | 24-Jul-2026 | 07-Aug-2026
46 | iWork | Personal Line Data Integrations | DSR and iWork Integration Enablement | Yet to start | Milestone 6 | 25-Jul-2026 | 07-Aug-2026 |  | Madhav sent in IIRM email
47 | iWork | Business Critical | BizDone & Dashboard - Consider Fee & Rewards as "Brokerage" | Yet to start | Milestone 6 | 01-Aug-2026 | 07-Aug-2026 | Sunil
48 | iWork | Operational | PROD & Other env.: Database Vaccum - Schedule a periodic acitvity in all the env. | Yet to start | Milestone 6 | 01-Aug-2026 | 07-Aug-2026 | Abhilash
IBP (Backlog & CRs) · 19 items · 0 delivered · 19 pending
49 | IBP | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | Pre-PROD | Milestone 5 | 31-Jul-2025 | 03-Aug-2026 | Manjusha
50 | IBP | User Profile | Profile, Service Subscriptions, Feedback | Pre-PROD | Milestone 5 | 31-Jul-2025 | 03-Aug-2026 | Ravi | Pending: Service Subscriptions, Feedback
51 | IBP | Evexia Club Integration | Integration to Evexia | Pre-PROD | Milestone 5 | 31-Jul-2025 | 03-Aug-2026 | Abhilash
52 | IBP | Benefits Summary | End User's Summary View | Pre-PROD | Milestone 5 | 31-Jul-2025 | 03-Aug-2026 | Ravi
53 | IBP | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | Pre-PROD | Milestone 5 | 31-Jul-2025 | 03-Aug-2026 | Manjusha | Wellness
54 | IBP - CR | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | Pre-PROD | Milestone 6 | 08-May-2026 | 03-Aug-2026 | Abhilash
55 | IBP | Business Critical | IBP - Risk Watch - Report Issues - Enrolment Drive - Validate, enhance, and document | Yet to start | Milestone 6 | 01-Aug-2026 | 05-Aug-2026 | Ravikiran
56 | IBP | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | Pre-PROD | Milestone 4 | 10-Jun-2025 | 07-Aug-2026 | Akhila | Fine tuning the API's where there is a delay
57 | IBP | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Ravi | Retail Business
58 | IBP | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Ravi | Retail Business
59 | IBP | Wellness HR View | HR View of Wellness usage by Employees | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Manjusha | Wellness
60 | IBP | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Manjusha | Wellness
61 | IBP | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Ravi | Retail Business
62 | IBP | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Ravi | Retail Business
63 | IBP | Profile Migration | Request migration of Corporate Profile to Individual | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Abhilash | Retail Business
64 | IBP | Profile Migration | Request migration of Individual Profile to Corporate | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Abhilash | Retail Business
65 | IBP | IIRM-10666 | IBP - Policy Component Card Re-design | Yet to start | Milestone 6 | 21-Jun-2026 | 07-Aug-2026 | Manjusha
66 | IBP | Claims Corner | Claims Corner - Screen Re-design | DEV - WIP | Milestone 6 | 21-Jun-2026 | 07-Aug-2026 | Ravi
67 | IBP | Business Critical | IBP - Risk Watch - Company & Policy Levels are not matching (CD, Endorsement, Claims) | Yet to start | Milestone 6 | 01-Aug-2026 | 07-Aug-2026 | Ravikiran
Framework (DPDP, NFR, Framework) · 17 items · 0 delivered · 17 pending
68 | Framework | Notifications Management | Different email notification - Madhav excel. 1. Renewal Reminders - ASAP 2. Instalment Reminders 3. Others | Pre-PROD | Milestone 4 | 10-Jun-2025 | 03-Aug-2026 | Pushyami
69 | DPDP | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | Yet to start | Milestone 4 | 10-Jun-2025 | 07-Aug-2026 | Rama
70 | Framework | Accessibility | 20-Jul: Jagadees --> Need More details | Yet to start | Milestone 4 | 10-Jun-2025 | 07-Aug-2026
71 | Framework | Localisation |  | Delivered - Deficit | Milestone 4 | 10-Jun-2025 | 07-Aug-2026 | Tharun | Pending: Service Flow
72 | NFR | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | Delivered - Deficit | Milestone 4 | 10-Jun-2025 | 07-Aug-2026 | Rama | Pending: Provide the document on how do we store and view it
73 | DPDP | App vulnerability scans |  | DEV - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
74 | DPDP | Document Flows |  | DEV - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
75 | DPDP | Perform security UAT |  | DEV - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
76 | DPDP | Enforce business logic to restrict purpose |  | DEV - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
77 | DPDP | Allow user corrections |  | DEV - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
78 | DPDP | Delete expired data |  | DEV - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
79 | DPDP | Map PII tables |  | QA - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Rama
80 | DPDP | Enable delete pipeline |  | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
81 | DPDP | Sign DPDP clauses |  | DEV - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
82 | NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | Yet to start | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 |  | Discussed this with Surya sir last visit to Divami office
83 | NFR | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure, which was broad symptom rather than a root cause. The renewed focus here is on failures related to cryptography which often leads to sensitive data exposure or system compromise. |  | DEV - WIP | Milestone 5 | 31-Jul-2025 | 07-Aug-2026
84 | DPDP | Quarterly restore tests |  | Pre-PROD | Milestone 5 | 31-Jul-2025 | 07-Aug-2026 | Rama

## 📅 10-Aug
WEEK OF 10 Aug 2026 → 16 Aug 2026 — 11 items · 0 delivered · 11 pending · NEXT WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 10 items · 0 delivered · 10 pending
1 | iWork | Business Critical | BizDone - Performance - Query Fine Tuning | Yet to start | Milestone 6 | 01-Aug-2026 | 10-Aug-2026 | Karan
2 | iWork | Business Critical | BizDone & other filters - Multi-select for Vertical & Months | Yet to start | Milestone 6 | 18-Jul-2026 | 11-Aug-2026 | Sunil
3 | iWork | Operational | Demo Env. - Record the application/Infrastruction/DevOps situation when application is in Zero state | Yet to start | Milestone 6 | 01-Aug-2026 | 11-Aug-2026 | Tharun / Jagadeesh
4 | iWork | Operational | PROD & Demo Env.: Database - Partitioning | Yet to start | Milestone 6 | 01-Aug-2026 | 11-Aug-2026 | Abhilash
5 | iWork | Business Critical | Dashboard - Performance - Query Fine Tuning | Yet to start | Milestone 6 | 01-Aug-2026 | 12-Aug-2026 | Sunil
6 | iWork - CR | Business Critical | BizDone - Download - Reduce the file size (Ex. Excel binary or others) | Yet to start | Milestone 6 | 01-Aug-2026 | 12-Aug-2026 | Karan
7 | iWork | Operational | Job - Expiry Opportunity - Review, Enhance and document | Yet to start | Milestone 6 | 01-Aug-2026 | 12-Aug-2026 | Karan
8 | iWork | Operational | PROD & Demo Env.: Database - Indexing | Yet to start | Milestone 6 | 01-Aug-2026 | 13-Aug-2026 | Abhilash
9 | iWork | Operational | Job - RO Creation - Review, Enhance and document | Yet to start | Milestone 6 | 01-Aug-2026 | 13-Aug-2026 | Karan
10 | iWork | Operational | PROD & Demo Env.: Database - SQL Functions for all the reports | Yet to start | Milestone 6 | 01-Aug-2026 | 14-Aug-2026 | Abhilash
Other / Unassigned · 1 item · 0 delivered · 1 pending
11 | iWork/IBP | Operational | Notification Mgmt - Turn on, Turn off, History, Approval, template changes | Yet to start | Milestone 6 | 01-Aug-2026 | 11-Aug-2026 | Karan

## 📅 Upcoming
UPCOMING (ETA beyond 10 Aug week) — 0 items · 0 delivered · 0 pending
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks

## Unplanned (no ETA)
UNPLANNED — PENDING, NO ETA · 35 items
Pending items with no ETA yet. Assign an ETA in the source sheet to move an item into its week. Static snapshot — re-run to refresh.
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 27 items
1 | IBP/iWork | IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | Yet to start | Milestone 5 | 31-Jul-2025
2 | iWork | Maintenance | iWork - Reports - View Dump for each download for comparision | Yet to start | Milestone 6 | 20-Apr-2026
3 | iWork - CR | Operational | Policy Config - Premium Rater Table | Yet to start | Milestone 6 | 21-Apr-2026 |  | Jagadeesh
4 | iWork | Operational | Export to excel - iWork all the results table; Download is on Previlage | Yet to start | Milestone 6 | 15-Jun-2026
5 | IBP/iWork | Operational | IBP - Raise Ticket: Edit the ticket and update the status by the Lead CRM & System Admin Same funtionality should be there in iWork for internal purpose. Should send email notification when there are changes to status | Yet to start | Milestone 6 | 01-Jul-2026 |  | Manjusha
6 | IBP/iWork | Operational | IBP - Emails: Dual approval/confirmation - Before sending to Employees. 1. 2 levels in iWork 2. CRM will submit & HR will approve in Risk Watch | Yet to start | Milestone 6 | 14-Jul-2026
7 | iWork | Maintenance | In any of the screen, we have to provide an info icon where it will help the users how critical fields in that screen are derieved or got populated | Yet to start | Milestone 6 | 17-Jul-2026
8 | iWork | Operational | CMS - Policy Level - Component Notes from Stapi | Yet to start | Milestone 6 | 31-Jul-2026 |  |  | Ex. TL - Parental 2-years Lock-in; SI may vary
9 | iWork | Business Critical | BizDone & Dashboard: Remove orphane Opportunities | Yet to start | Milestone 6 | 01-Aug-2026
10 | iWork | Business Critical | BizDone & Dashboard: Remove orphane Policies | Yet to start | Milestone 6 | 01-Aug-2026
11 | iWork | Operational | PROD Bug: SCS - Notifications - Check what is the configuration. (Scenario: For the very first time Email or SMS is taking time then rest are instant) | Yet to start | Milestone 6 | 01-Aug-2026
12 | iWork | Operational | Infra - Season based bumping (Example: When policies are expiring, need to bump the infra/DB because load will be more). Identify the data and plan this acitivity. | Yet to start | Milestone 6 | 01-Aug-2026
13 | iWork | Operational | Optimal allocate the memory/infra size based on the service operational usage rather than generic size for all | Yet to start | Milestone 6 | 01-Aug-2026
14 | iWork | Operational | Split Service - Risk Watch because it should run on it own and NOT impact other iWork or IBP services | Yet to start | Milestone 6 | 01-Aug-2026
15 | iWork | Operational | Split Service - Identify service areas because either iWork or IBP utilization should not impact other services | Yet to start | Milestone 6 | 01-Aug-2026
16 | iWork | Operational | Reports - iWork - Validate, enhance, and document | Yet to start | Milestone 6 | 01-Aug-2026
17 | iWork | Operational | Automation process for Data Load (Gopal & Rama's Task) | Yet to start | Milestone 6 | 01-Aug-2026
18 | iWork | Operational | Export - IBP-Risk Watch - All the results/Widget must be downloadable based onn Previlage | Yet to start | Milestone 6 | 01-Aug-2026
19 | iWork | Operational | Email Notifications - Opty. Lost/ Policy Renewals/ Instalments - CRM users | Yet to start | Milestone 6 | 01-Aug-2026
20 | iWork | Operational | Add/Update - Address & Contact - Across Application | Yet to start | Milestone 6 | 01-Aug-2026
21 | iWork | Maintenance | PROD: Health Check of the Application, Alert notification & Triage the situation | Yet to start | Milestone 6 | 01-Aug-2026
22 | iWork | Maintenance | Convert Policy from Active to Generated | Yet to start | Milestone 6 | 01-Aug-2026
23 | iWork | Maintenance | Delete - Policy Configuration | Yet to start | Milestone 6 | 01-Aug-2026
24 | iWork | Maintenance | Delete - Inception/Endorsement Data | Yet to start | Milestone 6 | 01-Aug-2026
25 | iWork | Maintenance | Employee Mgmt - Create, Update, Delete - Validate and document | Yet to start | Milestone 6 | 01-Aug-2026
26 | iWork | Maintenance | Hierarchy Mgmt - View & Update - Report & Visual Chart | Yet to start | Milestone 6 | 01-Aug-2026
27 | iWork | Maintenance | iWork - Reports - Use BizDone framework | Yet to start | Milestone 6 | 01-Aug-2026
IBP (Backlog & CRs) · 4 items
28 | IBP | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | Yet to start | Milestone 5 | 31-Jul-2025 |  | Ravi | Retail Business
29 | IBP | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | Yet to start | Milestone 5 | 31-Jul-2025 |  |  | Retail Business
30 | IBP | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | Yet to start | Milestone 5 | 31-Jul-2025 |  |  | Retail Business
31 | IBP | IBP - Enrolment Journey | When user save & exit is considered as Enrolled | Yet to start | Milestone 6 | 21-Jul-2026 |  | Abhilash | Jayakar reported
Other / Unassigned · 4 items
32 | iWork/IBP | Maintenance | IBP - Go-Live: Check-list document & SOP | Yet to start | Milestone 6 | 20-Apr-2026 |  | Nithin
33 | iWork/IBP | Business Critical | IBP - Email Notification - Company specific email templates for all types (Welcome, Confirmation, Reminder, Raise Ticket, & Others) | Yet to start | Milestone 6 | 01-Aug-2026
34 | iWork/IBP | Business Critical | iWork/IBP - Claim Process - Intimation & Submission (Different Flows) | Yet to start | Milestone 6 | 01-Aug-2026
35 | iWork/IBP | Business Critical | Life Events - Create Endorsment & next steps; Notification to CRM/KAM Team | Yet to start | Milestone 6 | 01-Aug-2026

## VRK Feedbacks
VRK — PROD FEEDBACK TRACKER · 68 items · 66 delivered · 2 pending
All 'VRK - PROD Feedback:' items, broken up by week (status then ETA within a week). Excluded from the other views. Static snapshot.
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
📅 WEEK OF 08 Jun → 14 Jun 2026 · PAST · 27 items
1 | iWork | VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | Delivered | Milestone 6 | 05-Jun-2026 | 08-Jun-2026
2 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
3 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
4 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
5 | iWork | VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
7 | iWork | VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
8 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
9 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
10 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
11 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
12 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | Delivered | Milestone 6 | 08-Jun-2026 | 09-Jun-2026 | Karan
13 | iWork | VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | Delivered | Milestone 6 | 08-Jun-2026 | 09-Jun-2026
14 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026
15 | iWork | VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
16 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
17 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
18 | iWork | VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
19 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | Delivered | Milestone 6 | 08-Jun-2026 | 10-Jun-2026
20 | iWork | VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Prathiphala
21 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Jagadeesh
22 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Jagadeesh
23 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | Delivered | Milestone 6 | 08-Jun-2026 | 12-Jun-2026 | Karan
24 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | Delivered | Milestone 6 | 08-Jun-2026 | 12-Jun-2026
25 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | Delivered | Milestone 6 | 09-Jun-2026 | 12-Jun-2026 | Prathiphala
26 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | Not a bug | Milestone 6 | 08-Jun-2026 | 08-Jun-2026 |  | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only
27 | iWork | VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | Not a bug | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
📅 WEEK OF 15 Jun → 21 Jun 2026 · PAST · 8 items
28 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
29 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
30 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
31 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026
32 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
33 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | Delivered | Milestone 6 | 09-Jun-2026 | 16-Jun-2026
34 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | Delivered | Milestone 6 | 08-Jun-2026 | 19-Jun-2026 | Rama
35 | iWork | VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | Delivered | Milestone 6 | 09-Jun-2026 | 19-Jun-2026 | Karan
📅 WEEK OF 22 Jun → 28 Jun 2026 · PAST · 1 item
36 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | Delivered | Milestone 6 | 08-Jun-2026 | 24-Jun-2026
📅 WEEK OF 29 Jun → 05 Jul 2026 · PAST · 8 items
37 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | Delivered | Milestone 6 | 08-Jun-2026 | 30-Jun-2026 | Jagadeesh
38 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
39 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
40 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
41 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
42 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
43 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
44 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | Delivered | Milestone 6 | 08-Jun-2026 | 02-Jul-2026
📅 WEEK OF 06 Jul → 12 Jul 2026 · PAST · 3 items
45 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 07-Jul-2026 | Pushyami
46 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Pushyami
47 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Pushyami
📅 WEEK OF 13 Jul → 19 Jul 2026 · PAST · 13 items
48 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Remove the Vertical section. Keep only Branch. | Delivered | Milestone 6 | 13-Jul-2026 | 13-Jul-2026
49 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 14-Jul-2026 | Karan
50 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - Filter & drill-down | Delivered | Milestone 6 | 23-Jun-2026 | 14-Jul-2026 | Karan
51 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Remove the SO/RO labels from the bar charts. Display only the figures inside the bars, with the corresponding details available on mouse hover (tooltip). | Delivered | Milestone 6 | 13-Jul-2026 | 14-Jul-2026
52 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Review and correct the display of negative values for TeamLease under RO, particularly for Q3 bar-chart. | Delivered | Milestone 6 | 13-Jul-2026 | 14-Jul-2026
53 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Brokerage Display - Display Brokerage information only. Hide Premium values in the enhanced screens. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
54 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | BizDone Enhanced Screen - Hide Premium. Display: RO Brokerage SO Brokerage | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
55 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Resolve the Premium value formatting issue. Values should be displayed consistently in Millions/Billions. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
56 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Display the Endorsement section above the section “Business Collection Summary”. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
57 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Move the Policy Type Distribution section above RO by SBU. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
58 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Rename/update the Policy Type names “Fire & Engineering”, “Speciality Lines - Liability” | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
59 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - The SO Activity Follow-up screen should not display ISG-related activities. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
60 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - When IIRM Holdings is selected, the Organization-level cards and graphs are not displayed. Verify and fix the issue. | Delivered | Milestone 6 | 13-Jul-2026 | 17-Jul-2026
📅 WEEK OF 20 Jul → 26 Jul 2026 · PAST · 3 items
61 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Display the data using an Accordion layout in the following order: Company → SBU → Branch → Executive → Client → Policy | Delivered | Milestone 6 | 13-Jul-2026 | 20-Jul-2026
62 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - Make the Funnel interactive so that clicking on each stage navigates to the corresponding enhanced screen. Also, when we click on "Numbers" also it has to move to respective screens | Delivered | Milestone 6 | 13-Jul-2026 | 22-Jul-2026 | Pushyami | Pending: Becuase the enhanced screens are yet to Approve
63 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Under PL, the bar chart should represent SO-level data instead of the currently displayed RO-level data. | Delivered | Milestone 6 | 13-Jul-2026 | 22-Jul-2026 | Jagadeesh
📅 WEEK OF 27 Jul → 02 Aug 2026 · LAST WEEK · 2 items
64 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Additional section display: Placement Funnel, Schedule, Followup | Delivered | Milestone 6 | 23-Jun-2026 | 30-Jul-2026 | Karan
65 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Enhanced screen: My Client Portfolio | Delivered | Milestone 6 | 27-Jul-2026 | 30-Jul-2026
📍 WEEK OF 03 Aug → 09 Aug 2026 · CURRENT WEEK · 2 items
66 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | iWork and iTicket should be accessible via VPN | Yet to start | Milestone 6 | 23-Jun-2026 | 07-Aug-2026 | Pushyami
67 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | Pre-PROD | Milestone 6 | 09-Jun-2026 | 03-Aug-2026 | Jagadeesh
🗓 No ETA assigned · 1 item
68 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Organization-wise summary cards are not required. | Not in scope | Milestone 6 | 13-Jul-2026 |  |  | Madhav sir confirmed via Teams Chat

## SOW - Actual Items
Module | Functionality | Module | Module | Match Status | Refer to "SOW, Feedbacks-Bug & CR_Items"
UI Approach Style Establishment | UI Style Establishment | Framework | Milestone 1 | ✓ Found in tracker
UI Approach Design System | Building Design System | Framework | Milestone 1 | ✓ Found in tracker
Project setup | Basic project / Development environment setup | Framework | Milestone 1 | ✓ Found in tracker
Build UI components | This includes all the UI componnets to compose the application and module definitions: Form, Toast, Filter, Cards, Visualisation, Grid, Menu, Header, Footer, Maps Integration | Framework | Milestone 1 | ✓ Found in tracker
Core System |  | Framework | Milestone 1 | ✓ Found in tracker
ACL & RBAC Control Framework |  | Framework | Milestone 1 | ✓ Found in tracker
Micro Frontend Setup |  | Framework | Milestone 1 | ✓ Found in tracker
Service Workers Implementation |  | Framework | Milestone 1 | ✓ Found in tracker
Landing Page |  | Framework | Milestone 1 | ✓ Found in tracker
Access Control Management |  | Framework | Milestone 1 | ✓ Found in tracker
Auth Module (Simple Auth) |  | Framework | Milestone 1 | ✓ Found in tracker
Micro Service Framework Setup |  | Framework | Milestone 1 | ✓ Found in tracker
Company (Prospect) Hub | Top 10/Latest companies, with search/filter, Table of basic attributes with GPS etc. | iWork | Milestone 1 | ✓ Found in tracker
Add/View/Edit Company | Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. Simple edit like Add; View is multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | iWork | Milestone 1 | ✓ Found in tracker
Contact Hub | Top 10/Latest Contacts, with search/filter, list with basic attributes | iWork | Milestone 1 | ✓ Found in tracker
Add/View/Edit Contact | Simple edit like Add Contacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | iWork | Milestone 1 | ✓ Found in tracker
Opportunity Hub | Top Opportunities with search/filter, List of opportunities with high level summaries | iWork | Milestone 1 | ✓ Found in tracker
Add/View/Edit Opportunity | Add Medium size form with 1->N list of Claims; Multiple drop downs Large View with several widgets, Simple Edit | iWork | Milestone 1 | ✓ Found in tracker
Insurer/TPA Hub | List with Filter/Search | iWork | Milestone 1 | ✓ Found in tracker
Manage TPA/Insurer | Basic Add, View with edit of basic data, with lists of policies/companies | iWork | Milestone 1 | ✓ Found in tracker
Contact /Company/Insurer/TPA Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
Task Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
Meeting Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
Employee Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
RBAC and ACL setup for Iwork Module |  | iWork | Milestone 1 | ✓ Found in tracker
Opportunity Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
Common - Audit Trail Mgmt - Becomes critical in this phase iteself |  | iWork | Milestone 1 | ✓ Found in tracker
Visualization framework | Charts and KPIs | Framework | Milestone 2 | ✓ Found in tracker
Visualization framework (mobile) | Charts and KPIs | Framework | Milestone 2 | 🔗 Mapped (see note) | Map to line number 35 in Sheet-SOW, Feedbacks-Bug & CR_Items
User Management |  | Framework | Milestone 2 | ✓ Found in tracker
Notifications Management |  | Framework | Milestone 2 | ✓ Found in tracker
Document Management | Create, Upload, Seach, Download | Framework | Milestone 2 | ✓ Found in tracker
Document Management (Mobile) | Create, Upload, Seach, Download | Framework | Milestone 2 | 🔗 Mapped (see note) | Map to line number 36 in Sheet-SOW, Feedbacks-Bug & CR_Items
Caching of API Data |  | Framework | Milestone 2 | ✓ Found in tracker
Caching of API Data (Mobile) |  | Framework | Milestone 2 | 🔗 Mapped (see note) | Map to line number 37 in Sheet-SOW, Feedbacks-Bug & CR_Items
Master Data Management |  | Framework | Milestone 2 | ✓ Found in tracker
User Management |  | Framework | Milestone 2 | ✓ Found in tracker
Notification and Communication Management |  | Framework | Milestone 2 | ✓ Found in tracker
Audit Data Capturing |  | Framework | Milestone 2 | ✓ Found in tracker
Usage Tracking System |  | Framework | Milestone 2 | 🔗 Mapped (see note) | Map to line number 41 in Sheet-SOW, Feedbacks-Bug & CR_Items
CMS |  | Framework | Milestone 2 | ✓ Found in tracker
Data Security Considerations | Data ca n be accessed only through the APIs and in the same network Database can be accessed on through Jumphost Database access is based on privilages | Framework | Milestone 2 | ✓ Found in tracker
Dashboard | Multiple KPI Cards: Business Performance, Svc Performance, Table of targets vs. actuals vs. lost, Sales Funnel, Renewal Funnel, Servce Funnel, AR from Insurers, Pending Activities(iWork Stages) Widget, Followups widget, Meetings widget Filters available (Geo, Branch, Team/Team Member, Dates), Approvals, iWork Stages, Tasks, Meetings | iWork | Milestone 2 | ✓ Found in tracker
Dashboard - Drilldowns | Drill down from the Tables (Targets vs. Actuals, Pending Activities, Followups, AR Report, Schedule) | iWork | Milestone 2 | ✓ Found in tracker
Dashboard - Pending tasks, approvals | Pending tasks/approvals, | iWork | Milestone 2 | ✓ Found in tracker
Manage Stage Planning/Performance/Approval | Add iWork Stages (table) - Dates with each iWork Stage and who are the team members assigned to each Stage; Once all iWork stages are complete, ISG Team activities must be planned ISG Team can approve/reject each iWork Stage. Approving RFP Stage approves all iWork stages Completion of each iWork Stage (Activity) & ISG Stage - Comments, Attach Document, Date recorded, submit | iWork | Milestone 2 | ✓ Found in tracker
Sales Team Hierarchy | Hierarchy / Org chart tied to Platform Users | iWork | Milestone 2 | ✓ Found in tracker
View Policy | Long View, multiple widgets/entities, endorsements (each month), Claims, etc. | iWork | Milestone 2 | ✓ Found in tracker
Common Data Mapping Component | Map input fields to output fields & Order | iWork | Milestone 2 | ✓ Found in tracker
Reports - Biz Done | Report View, Download, List of earlier snaps of the report, Search and Filter | iWork | Milestone 2 | ✓ Found in tracker
Smart Add Component | Allow Upload of Document/Image, select what to create (Company/Contact/Opportunity) | iWork | Milestone 2 | ✓ Found in tracker
Organisation, Branch, Employee, & Hierarchy Mgmt |  | iWork | Milestone 2 | ✓ Found in tracker
Cut Off Mgmt |  | iWork | Milestone 2 | ✓ Found in tracker
Dashboard (Place Holder) |  | iWork | Milestone 2 | ✓ Found in tracker
Planning, Perform and Approval Mgmt |  | iWork | Milestone 2 | ✓ Found in tracker
Policy Mgmt |  | iWork | Milestone 2 | ✓ Found in tracker
AI - (Non-OCR) Digital Document Processing for Content recognition (Company/Opportunity/Contact Creation from Previous Policy Document, Bizcard document) |  | iWork | Milestone 2 | ✓ Found in tracker
AI - OCR for Content Collection |  | iWork | Milestone 2 | ✓ Found in tracker
AI - Company Information by AI Search |  | iWork | Milestone 2 | ✓ Found in tracker
Common, Contexual Upload Component |  | iWork | Milestone 2 | ✓ Found in tracker
Common, Contexual Read and Spread Component |  | iWork | Milestone 2 | 🔗 Mapped (see note) | Map to line number 47 in Sheet-SOW, Feedbacks-Bug & CR_Items
HR/Admin Portal View | Supporting services for Admin Portal | IBP | Milestone 2 | ✓ Found in tracker
Document Generation |  | Framework | Milestone 3 | ✓ Found in tracker
Manage Policy (Endorsements) | Add Endorsement - basic form with uploads of excel/document Validations of endorsement format - Map customer fields to internal fields Map internal fields to TPA fields (occasional per TPA) View/Update Endorsement, List View, Endorsement Performance | iWork | Milestone 3 | ✓ Found in tracker
MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | iWork | Milestone 3 | ✓ Found in tracker
Master Data Mgmt {Common, Contexual Master Data Mgmt} |  | iWork | Milestone 3 | ✓ Found in tracker
Stage Mgmt (Activity/Transaction/Quote) |  | iWork | Milestone 3 | ✓ Found in tracker
Asset/Member Data Mgmt |  | iWork | Milestone 3 | ✓ Found in tracker
Cover Mgmt |  | iWork | Milestone 3 | ✓ Found in tracker
Endorsement Mgmt |  | iWork | Milestone 3 | ✓ Found in tracker
MIR Entry Mgmt | Module to manage MIR {Monthly Information Report} | iWork | Milestone 3 | ✓ Found in tracker
Accessibility |  | Framework | Milestone 4 | ✓ Found in tracker
Localisation |  | Framework | Milestone 4 | ✓ Found in tracker
Configuration Management |  | Framework | Milestone 4 | ✓ Found in tracker
Feature Flag Control Management |  | Framework | Milestone 4 | ✓ Found in tracker
Workflow Management |  | Framework | Milestone 4 | ✓ Found in tracker
Rule Definition Management |  | Framework | Milestone 4 | ✓ Found in tracker
Caching Implementation |  | Framework | Milestone 4 | ✓ Found in tracker
Localistation Management |  | Framework | Milestone 4 | ✓ Found in tracker
Knowledge Central | Grouped list of Documents/Resources, Add a Document, Remove a Document (Add/remove only for admins) | iWork | Milestone 4 | ✓ Found in tracker
View Service Score | Servicing Stats Dashboard - Single Table (drillable) to calculate an overall score | iWork | Milestone 4 | ✓ Found in tracker
Knowledge Central |  | iWork | Milestone 4 | ✓ Found in tracker
TAT/SLA Mgmt (Including Service Score) |  | iWork | Milestone 4 | ✓ Found in tracker
Country Handling {Data Source Mgmt} | Physical data storage is limiited to a particular country and can't be combined with other country data | iWork | Milestone 4 | 🔗 Mapped (see note) | Map to line number 115 in Sheet-SOW, Feedbacks-Bug & CR_Items
Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} |  | iWork | Milestone 4 | 🔗 Mapped (see note) | Map to line number 71 in Sheet-SOW, Feedbacks-Bug & CR_Items
IBP Landing Page - Basic | Basic Landing Page with only company plans and summary | IBP | Milestone 4 | ✓ Found in tracker
My Insurance | Hub of all plans I have as an employee - both Company provided and individually signed up. Mostly a navigational page | IBP | Milestone 4 | ✓ Found in tracker
Company Plans | 6 Policies - GMC, GPA, GTL, Parental Plicy, Top-ups, OPD Policy (Summary view of policies | IBP | Milestone 4 | ✓ Found in tracker
Per-policy Enrolment | Enrolment and addon policy selection | IBP | Milestone 4 | ✓ Found in tracker
Company Plan Configurator | Admin side of IBP should configure (per Corporate) how to define a Policy and determine how it breaks down the Premium and Coverage rules | IBP/iWork | Milestone 4 | ✓ Found in tracker
My Documents | Document Hub - covers Policies, Prescriptions, Reports | IBP | Milestone 4 | ✓ Found in tracker
User Profile | Profile, Service Subscriptions, Feedback | IBP | Milestone 4 | ✓ Found in tracker
Whitelabelling | Whitelabelling based on Org needs (IBP Admin) | IBP/iWork | Milestone 4 | ✓ Found in tracker
Contact Matrix | Configure the Conact Info Matrix (IBP Admin) | IBP/iWork | Milestone 4 | ✓ Found in tracker
Contact Matrix View | Contact Matrix View for end user | IBP | Milestone 4 | ✓ Found in tracker
Auth Config UI | Config for Auth Rules setup | IBP/iWork | Milestone 4 | ✓ Found in tracker
Wellness Discount List Management | Add/Remove/update Discount program benefits | IBP/iWork | Milestone 4 | ✓ Found in tracker | Map to line number 126 in Sheet-SOW, Feedbacks-Bug & CR_Items
HR Portal View | Employee Search, Resend Email, Update Employee Info, Delete Employees, Extend Enrollment Windows, Reports, Bulk Email | IBP | Milestone 4 | ✓ Found in tracker
Basic Landing Page Services | Company provided plans only | IBP | Milestone 4 | ✓ Found in tracker
Document Mgmt for End User | Insurance, Health Reports and Prescriptions {No automatic pull from Partners} | IBP | Milestone 4 | ✓ Found in tracker
Personal Profile Mgmt | Profile settings | IBP | Milestone 4 | ✓ Found in tracker
Group Policy Mgmt - Enrollment | Enrollment (Adding Dependents, Choosing Options available). Submit the enrollment to Insurer or TPA 6 Types of Policies to be considered | IBP | Milestone 4 | ✓ Found in tracker
Group Policy Mgmt - Enrollment Configurator | Enrollment Configurator (Set of benefits and type of Dependent combinations allowed etc). This is more of an Iwork feature to configure the policy | IBP/iWork | Milestone 4 | 🔗 Mapped (see note) | Map to line number 100 in Sheet-SOW, Feedbacks-Bug & CR_Items
Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | IBP | Milestone 4 | ✓ Found in tracker
Contact Matrix Configuration | Matrix of Contact Infomration | IBP | Milestone 4 | ✓ Found in tracker
Wellness Benefits Mgmt | Company Sponsered, Personal Discounted services | IBP | Milestone 4 | 🔗 Mapped (see note) | Map to line number 126 in Sheet-SOW, Feedbacks-Bug & CR_Items
End User onboarding | Generate Users, Send Emails, Password Rest | IBP | Milestone 4 | ✓ Found in tracker
Admin Reports | Services for multiple reports | IBP | Milestone 4 | ✓ Found in tracker
Simple Auth | Username and Password based authentication and RBAC on simple-auth users. Auth rules needs configuration capability | IBP | Milestone 4 | ✓ Found in tracker
Whitelabelling Support |  | IBP | Milestone 4 | ✓ Found in tracker
Reconciliation ManagementUpload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid | iWork | Milestone 5 | 🔗 Mapped (see note) | Map to line number 190 in Sheet-SOW, Feedbacks-Bug & CR_Items
Report Hub | Landing Page and generic hub | iWork | Milestone 5 | ✓ Found in tracker
Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | iWork | Milestone 5 | ✓ Found in tracker
CD Creation | Show current CD Balance against pooled/individual policies / Allow new CD creation, update CD balance and map policies to CD balances | iWork | Milestone 5 | ✓ Found in tracker
Claim Management (Add Claim, Import Claims & Claim Activities) | Basic Form with fields and upload for adding claim Bulk import to validate and map from TPA format to internal fields 3 stage workflow - each stage, update data on claim form | iWork | Milestone 5 | ✓ Found in tracker
Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) | iWork | Milestone 5 | ✓ Found in tracker
CD Mgmt |  | iWork | Milestone 5 | ✓ Found in tracker
Reports |  | iWork | Milestone 5 | ✓ Found in tracker
Claim Mgmt |  | iWork | Milestone 5 | ✓ Found in tracker
Reconciliation Mgmt |  | iWork | Milestone 5 | ✓ Found in tracker
Insurer Integration Mgmt |  | iWork | Milestone 5 | ✓ Found in tracker
TPA Integration Mgmt |  | iWork | Milestone 5 | 🔗 Mapped (see note) | Map to line number 114 in Sheet-SOW, Feedbacks-Bug & CR_Items
HRMS Integration Mgmt | Base framework needs to be built and actual integration shoudl be on need | iWork | Milestone 5 | ⚠ NOT in tracker
IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | IBP | Milestone 5 | ✓ Found in tracker
IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | IBP/iWork | Milestone 5 | ✓ Found in tracker
Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | IBP | Milestone 5 | ✓ Found in tracker
Static Info Sections - Landing | Benefits Guide, FAQs, Help | IBP | Milestone 5 | ✓ Found in tracker
Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | IBP | Milestone 5 | ✓ Found in tracker
Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | IBP | Milestone 5 | ✓ Found in tracker
Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | IBP | Milestone 5 | ✓ Found in tracker
Upload from Partner of services bought on Partner site | Upload, listing, confirm & load into DB by an Iwork user. These are services purchased / discounts availed on partner sites by IBP corporate users | IBP/iWork | Milestone 5 | ✓ Found in tracker | Map to line number 127 in Sheet-SOW, Feedbacks-Bug & CR_Items
Wellness Admin Configurator | Admin side of IBM (in iWork) needs to customize/configure the offerings/page per Corporate. | IBP/iWork | Milestone 5 | ✓ Found in tracker
Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | IBP/iWork | Milestone 5 | ✓ Found in tracker
Wellness HR View | HR View of Wellness usage by Employees | IBP | Milestone 5 | ✓ Found in tracker
Wellness Partner View | Partner/service provider view of the usage of their corresponding services | IBP | Milestone 5 | ✓ Found in tracker
Claims Corner | View Claim Data for Individual Plans (if available), Track Status for Claims initiated from IBP for Group Plans, Track Status for Claims initiated with TPA directly, TAT reporting for Cashless (for Preauth and Discharge) | IBP | Milestone 5 | ✓ Found in tracker
Initiate Claim | Initiate claim for GMC (non-cashless), upload docs etc. | IBP | Milestone 5 | ✓ Found in tracker
Profile Migration | Request migration of Corporate Profile to Individual | IBP | Milestone 5 | ✓ Found in tracker
Profile Migration | Request migration of Individual Profile to Corporate | IBP | Milestone 5 | ✓ Found in tracker
Book Ambulance | Floater on the screen - Integrate to Ambulance Service | IBP | Milestone 5 | ✓ Found in tracker
Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | IBP | Milestone 5 | ✓ Found in tracker
OPD Claims Process Mgmt | Claim initiation - some metadata and upload of documents | IBP | Milestone 5 | 🔗 Mapped (see note) | Map to line number 149 in Sheet-SOW, Feedbacks-Bug & CR_Items
2nd Opinion Claims Process Mgmt | Managing 2nd opinion - initiate with data and upload documents | IBP | Milestone 5 | 🔗 Mapped (see note) | Map to line number 149 in Sheet-SOW, Feedbacks-Bug & CR_Items
OPD & 2nd Opinon Claims Processing | A report or generated file to be sent through manual processing | IBP/iWork | Milestone 5 | 🔗 Mapped (see note) | Map to line number 149 in Sheet-SOW, Feedbacks-Bug & CR_Items
Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | IBP | Milestone 5 | ✓ Found in tracker
Benefits Summary | End User's Summary View | IBP | Milestone 5 | ✓ Found in tracker
Hospital Network Mgmt | Based on the Insurer and TPA, network of hospitals needs to be presented in a consolidated view | IBP | Milestone 5 | ✓ Found in tracker
My Services Mgmt | Summary view of the services subscribed (Wellness) | IBP | Milestone 5 | 🔗 Mapped (see note) | Map to line number 168 in Sheet-SOW, Feedbacks-Bug & CR_Items
Feedback Mgmt | User Feedback capture service | IBP | Milestone 5 | ✓ Found in tracker
Claims Mgmt | Company Provided and Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | ✓ Found in tracker
Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | IBP | Milestone 5 | ✓ Found in tracker
Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | IBP | Milestone 5 | ✓ Found in tracker
Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | IBP | Milestone 5 | ✓ Found in tracker
End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | IBP | Milestone 5 | ⚠ NOT in tracker
Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | IBP | Milestone 5 | ✓ Found in tracker
Evexia Club Integration | Integration to Evexia | IBP | Milestone 5 | ✓ Found in tracker
Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | IBP | Milestone 5 | ✓ Found in tracker
3rd Party SSO | Props based SSO links to 3rd Parties | IBP | Milestone 5 | ✓ Found in tracker

## Stablization Items
List of Stabilization Items
Sl. # | Module | Sub-Module | Item | Efforts (Hrs.) | Assigned To | Status | Start Date | End Date | Requested Date
1 | BizDone |  | Offload Excel Generation: Disconnect report generation from HTTP requests to prevent timeout issues. Use an asynchronous thread or long polling for status updates and file downloading.
| BizDone | 1-A | API Tweaks for making data request | 2 | Sunil | Yet to start | 2026-08-03 | 2026-08-03 | 2026-07-31
| BizDone |  | Implementing queue / query building | 10 | Sunil | Yet to start | 2026-08-03 | 2026-08-04 | 2026-07-31
| BizDone |  | Tweaks / Update Procees the data onto file and store / upload to storage | 8 | Sunil | Yet to start | 2026-08-04 | 2026-08-05 | 2026-07-31
| BizDone |  | Long Poling Implementation for Bizdone Download - Front End | 4 | Sunil | Yet to start | 2026-08-05 | 2026-08-05 | 2026-07-31
| BizDone | 1-B | Query Tuning for Binzdone Query, Dashboard Performances | 16 | Abhilash | Yet to start | 2026-08-03 | 2026-08-04 | 2026-07-31
| Dashboard | 1-C | Implementation of the dynamic fetching of the dashboard widgets data without depending on performance output cron job | 8 | Ravi | DEV - WIP | 2026-08-03 | 2026-08-03 | 2026-07-31
| Dashboard |  | Centralised code or util function to fetch the KPIs in biz done report and dashboard data for re-usability | 16 | Ravi | Yet to start | 2026-08-04 | 2026-08-05 | 2026-07-31
| BizDone | 1-D | Migration Data load Should be always complete only Performances Job Execution - Continous acitivity | 0 | Rama | Yet to start | 2026-08-03 | 2026-08-03 | 2026-07-31
2 | Dashboard |  | Having individual component loaders on the landing page for each component and web-socket framework to avoid long-loading blank page issue. |  |  | Yet to start |  |  | 2026-07-31
3 | Jobs |  | Process Jobs - Review, Enhance and document
| Jobs | 3-A | Job - Expiry Opportunity - Review and Enhance
| Jobs | 3-B | Job - Opportunity Creation - Review and Enhance
| Jobs | 3-C | Job - Dashboard
| Jobs | 3-D
| Jobs | 3-E
| Jobs | 3-F
| Jobs | 3-G
| Jobs | 3-H
4
5
6
7
8
9
10

## Jira Report
Sl. # | Jira ID | Issue Type | Summary | Status | Reporter | Product | Parent
1 | IIRM-4 | Story | ACL Establishment | Done | Sai Vamsee K | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
2 | IIRM-6 | Story | Architecture - iWork | Done | Sai Vamsee K |  | IIRM-64 — SOW#3 - Micro Service Framework
3 | IIRM-7 | Story | Implement simple authentication | Done | Sai Vamsee K | Framework | IIRM-62 — SOW#2 - Authentication
4 | IIRM-9 | Story | UX - Core System (Research & Documentation) | Done | Sai Vamsee K | Framework | IIRM-80 — SOW#4 - Core System
5 | IIRM-11 | Story | Design System - UI | Done | Sai Vamsee K | Framework | IIRM-734 — SOW#7 - UI Design System
6 | IIRM-13 | Story | Product Spec - iWork (Org Structure, RBAC, Contacts, TPA, Insurer and Broker) | Done | Sai Vamsee K | Framework | IIRM-80 — SOW#4 - Core System
7 | IIRM-14 | Story | UX/UI - Create/List and View Company | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
8 | IIRM-15 | Story | Frontend - Micro Frontend Setup | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
9 | IIRM-16 | Story | Micro Service Framework Setup | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
10 | IIRM-17 | Story | Core System - Overall Project setup | Done | Sai Vamsee K | Framework | IIRM-80 — SOW#4 - Core System
11 | IIRM-18 | Epic | SOW#1 - ACL & RBAC Control | Maintenance | Sai Vamsee K | Framework
12 | IIRM-19 | Story | Frontend - Service Workers Implementation | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
13 | IIRM-20 | Story | Core System - Tech Tool Decisions (TechStack & Integration Choices) | Done | Sai Vamsee K | Framework | IIRM-80 — SOW#4 - Core System
14 | IIRM-23 | Sub-task | UX/UI - Manage Company | Done | Sai Vamsee K | iWork | IIRM-14 — UX/UI - Create/List and View Company
15 | IIRM-30 | Sub-task | Setting up Repositories with Users and permissions | Done | Sai Vamsee K |  | IIRM-6 — Architecture - iWork
16 | IIRM-31 | Sub-task | Analyse the Design Patterns to be followed | Done | Sai Vamsee K |  | IIRM-6 — Architecture - iWork
17 | IIRM-32 | Sub-task | Analyse and Create the Architectural Flow | Done | Sai Vamsee K |  | IIRM-6 — Architecture - iWork
18 | IIRM-33 | Sub-task | Analyse the CommonLib Implemenetation and Functions to include | Done | Sai Vamsee K |  | IIRM-6 — Architecture - iWork
19 | IIRM-38 | Sub-task | Set Up API Gateway | Done | Sai Vamsee K | Framework | IIRM-16 — Micro Service Framework Setup
20 | IIRM-39 | Sub-task | Setup Auth Service as Microservice | Done | Sai Vamsee K | Framework | IIRM-16 — Micro Service Framework Setup
21 | IIRM-40 | Sub-task | Initialize Environment Configurations for Micro Services | Done | Sai Vamsee K | Framework | IIRM-16 — Micro Service Framework Setup
22 | IIRM-41 | Sub-task | Setup the Service registry for Micro services | Done | Sai Vamsee K |  | IIRM-1739 — Microservices Framework Setup - Service registry, Gateway Config, Service Discovery, Service Config
23 | IIRM-42 | Sub-task | Analyse and Database Schema Design | Done | Sai Vamsee K | Framework | IIRM-7 — Implement simple authentication
24 | IIRM-43 | Sub-task | API Development for Simple Auth Implementation | Done | Sai Vamsee K | Framework | IIRM-7 — Implement simple authentication
25 | IIRM-44 | Sub-task | Tokenizing Simple Auth Authentication | Done | Sai Vamsee K | Framework | IIRM-7 — Implement simple authentication
26 | IIRM-45 | Sub-task | Basic project / Development environment setup | Done | Sai Vamsee K | Framework | IIRM-17 — Core System - Overall Project setup
27 | IIRM-46 | Sub-task | Structurise the Frontend Micro Frontends | Done | Sai Vamsee K | Framework | IIRM-17 — Core System - Overall Project setup
28 | IIRM-47 | Sub-task | Setup the Environment Configurations | Done | Sai Vamsee K | Framework | IIRM-17 — Core System - Overall Project setup
29 | IIRM-48 | Sub-task | Define Micro Frontend Architecture and Structure | Done | Sai Vamsee K | Framework | IIRM-15 — Frontend - Micro Frontend Setup
30 | IIRM-49 | Sub-task | Set Up the Host Application | Done | Sai Vamsee K | Framework | IIRM-15 — Frontend - Micro Frontend Setup
31 | IIRM-50 | Sub-task | Service Worker Setup & Registration | Done | Sai Vamsee K | Framework | IIRM-19 — Frontend - Service Workers Implementation
32 | IIRM-51 | Sub-task | Caching Strategy & Static Asset Caching | Done | Sai Vamsee K | Framework | IIRM-19 — Frontend - Service Workers Implementation
33 | IIRM-57 | Sub-task | Define access control reqiurement | Done | VedaVyas | Framework | IIRM-4 — ACL Establishment
34 | IIRM-59 | Sub-task | Implementing Background Sync for Offline Actions | Done | tharun | Framework | IIRM-19 — Frontend - Service Workers Implementation
35 | IIRM-60 | Sub-task | Implement Push Notifications (8 hours) | Done | tharun | Framework | IIRM-19 — Frontend - Service Workers Implementation
36 | IIRM-61 | Sub-task | Testing, Debugging, and Optimizing Service Worker and Push Functionality | Done | tharun | Framework | IIRM-19 — Frontend - Service Workers Implementation
37 | IIRM-62 | Epic | SOW#2 - Authentication | Maintenance | VedaVyas | Framework
38 | IIRM-64 | Epic | SOW#3 - Micro Service Framework | WORK IN PROGRESS | VedaVyas | Framework
39 | IIRM-65 | Sub-task | Set Up User Roles and Permissions Model | Done | VedaVyas | Framework | IIRM-4 — ACL Establishment
40 | IIRM-66 | Sub-task | Integrate ACL Logic into Authentication and Authorization Flow | Done | VedaVyas | Framework | IIRM-4 — ACL Establishment
41 | IIRM-67 | Sub-task | Implement Role-Based Access Control UI | Done | VedaVyas | Framework | IIRM-4 — ACL Establishment
42 | IIRM-71 | Sub-task | Configure Microfrontend Projects | Done | VedaVyas | Framework | IIRM-15 — Frontend - Micro Frontend Setup
43 | IIRM-72 | Sub-task | Develop Microfrontend Components | Done | VedaVyas | Framework | IIRM-15 — Frontend - Micro Frontend Setup
44 | IIRM-73 | Sub-task | Implement Communication Between Microfrontends | Done | VedaVyas | Framework | IIRM-15 — Frontend - Micro Frontend Setup
45 | IIRM-74 | Sub-task | Set Up API Gateway configuration | Done | VedaVyas |  | IIRM-1739 — Microservices Framework Setup - Service registry, Gateway Config, Service Discovery, Service Config
46 | IIRM-75 | Sub-task | Set Up Service Discovery | Done | VedaVyas |  | IIRM-1739 — Microservices Framework Setup - Service registry, Gateway Config, Service Discovery, Service Config
47 | IIRM-76 | Sub-task | Implement Inter-Service Communication | Done | VedaVyas |  | IIRM-1739 — Microservices Framework Setup - Service registry, Gateway Config, Service Discovery, Service Config
48 | IIRM-77 | Sub-task | Define Microservice Architecture and Components and basic setup | Done | VedaVyas | Framework | IIRM-16 — Micro Service Framework Setup
49 | IIRM-78 | Sub-task | Break Down and Detail Architectural Flow | Done | VedaVyas |  | IIRM-6 — Architecture - iWork
50 | IIRM-79 | Sub-task | Develop CommonLib Functions and Utilities | Done | VedaVyas |  | IIRM-6 — Architecture - iWork
51 | IIRM-80 | Epic | SOW#4 - Core System | WORK IN PROGRESS | tharun | Framework
52 | IIRM-83 | Story | Grid component | Done | tharun | Framework | IIRM-733 — SOW#6 - UI Components
53 | IIRM-84 | Story | Form generation component and utils | Done | tharun | Framework | IIRM-733 — SOW#6 - UI Components
54 | IIRM-85 | Sub-task | Set Up the Table Component Skeleton | Done | tharun | Framework | IIRM-83 — Grid component
55 | IIRM-86 | Sub-task | Implement Sorting and Pagination Logic | Done | tharun | Framework | IIRM-83 — Grid component
56 | IIRM-87 | Sub-task | Implement Filtering and Data Population | Done | tharun | Framework | IIRM-83 — Grid component
57 | IIRM-88 | Sub-task | Add Custom Styling configuration and cell renderer templates | Done | tharun | Framework | IIRM-83 — Grid component
58 | IIRM-89 | Sub-task | Define the Object Structure for Form Generation | Done | tharun | Framework | IIRM-84 — Form generation component and utils
59 | IIRM-90 | Sub-task | Build Form Generation Logic | Done | tharun | Framework | IIRM-84 — Form generation component and utils
60 | IIRM-91 | Sub-task | Implement Validation Logic | Done | tharun | Framework | IIRM-84 — Form generation component and utils
61 | IIRM-92 | Sub-task | Create Utility Functions for Dynamic Form Handling | Done | tharun | Framework | IIRM-84 — Form generation component and utils
62 | IIRM-732 | Epic | SOW#5 - Access Control | WORK IN PROGRESS | Sidhant Kumar Das | Framework
63 | IIRM-733 | Epic | SOW#6 - UI Components | Draft | Sidhant Kumar Das | Framework
64 | IIRM-734 | Epic | SOW#7 - UI Design System | WORK IN PROGRESS | Sidhant Kumar Das | Framework
65 | IIRM-735 | Epic | SOW#8 - 11 Components / Modules | WORK IN PROGRESS | Sidhant Kumar Das | Framework
66 | IIRM-736 | Epic | SOW#9 - Add/Manage Company (Prospects) | Maintenance | Sidhant Kumar Das | iWork
67 | IIRM-737 | Epic | SOW#10 - Add/Manage Contact | Maintenance | Sidhant Kumar Das | iWork
68 | IIRM-738 | Epic | SOW#11 - Manage Tasks, Meetings | Maintenance | Sidhant Kumar Das | iWork
69 | IIRM-739 | Epic | SOW#12 - Manage Employees | Maintenance | Sidhant Kumar Das | iWork
70 | IIRM-740 | Epic | SOW#13 - Add/Manage Opportunity | Maintenance | Sidhant Kumar Das | iWork
71 | IIRM-741 | Epic | SOW#14 - Add/Manage Insurer | Maintenance | Sidhant Kumar Das | iWork
72 | IIRM-742 | Epic | SOW#15 - Add/Manage TPA | Maintenance | Sidhant Kumar Das | iWork
73 | IIRM-743 | Epic | SOW#16 - Data Visualization Components | WORK IN PROGRESS | Sidhant Kumar Das | Framework
74 | IIRM-744 | Epic | SOW#17 - User Management | Maintenance | Sidhant Kumar Das | Framework
75 | IIRM-745 | Epic | SOW#18 - Master Data | WORK IN PROGRESS | Sidhant Kumar Das | Framework
76 | IIRM-746 | Epic | SOW#19 - Notification and Communication Management | RELEASED | Sidhant Kumar Das | Framework
77 | IIRM-747 | Epic | SOW#20 - 11 Components / Modules | WORK IN PROGRESS | Sidhant Kumar Das | Framework
78 | IIRM-748 | Epic | SOW#21 - Usage & Audit | WORK IN PROGRESS | Sidhant Kumar Das | Framework
79 | IIRM-749 | Epic | SOW#22 - Data Security (NFR) | WORK IN PROGRESS | Sidhant Kumar Das | Framework
80 | IIRM-750 | Epic | SOW#23 - Document Management - CMS | WORK IN PROGRESS | Sidhant Kumar Das | Framework
81 | IIRM-751 | Epic | SOW#24 - Dashboard & Drilldowns | WORK IN PROGRESS | Sidhant Kumar Das | iWork
82 | IIRM-752 | Epic | SOW#25 - Manage iWork Stages (BD) | Maintenance | Sidhant Kumar Das | iWork
83 | IIRM-753 | Epic | SOW#26 - Sales Team Hierarchy | Maintenance | Sidhant Kumar Das | iWork
84 | IIRM-754 | Epic | SOW#27 - AI - Smart Adds | Maintenance | Sidhant Kumar Das | iWork
85 | IIRM-755 | Epic | SOW#28 - Manage BD 2 Stages & Policy Creation | Maintenance | Sidhant Kumar Das | iWork
86 | IIRM-756 | Epic | SOW#29 - Manage ISG Stages | Maintenance | Sidhant Kumar Das | iWork
87 | IIRM-757 | Epic | SOW#30 - Manage Policy Endorsements | WORK IN PROGRESS | Sidhant Kumar Das
88 | IIRM-758 | Epic | SOW#31 - MIR Entry Mgmt. (Monthly Information Report) | Draft | Sidhant Kumar Das
89 | IIRM-759 | Epic | SOW#32 - Asset/Member Data Mgmt | RELEASED | Sidhant Kumar Das
90 | IIRM-760 | Epic | SOW#33 - Document Generation | WORK IN PROGRESS | Sidhant Kumar Das
91 | IIRM-761 | Epic | SOW#34 - Notifications Management | WORK IN PROGRESS | Sidhant Kumar Das
92 | IIRM-762 | Epic | SOW#35 - Configuration Management | RELEASED | Sidhant Kumar Das
93 | IIRM-763 | Epic | SOW#36 - Accessibility | Draft | Sidhant Kumar Das
94 | IIRM-764 | Epic | SOW#37 - Localisation | WORK IN PROGRESS | Sidhant Kumar Das
95 | IIRM-765 | Epic | SOW#38 - Rule Definition Management | Draft | Sidhant Kumar Das
96 | IIRM-766 | Epic | SOW#39 - Workflow Management | Draft | Sidhant Kumar Das
97 | IIRM-767 | Epic | SOW#40 - Caching Localisation | Draft | Sidhant Kumar Das
98 | IIRM-768 | Epic | SOW#41 - Knowledge Central | Maintenance | Sidhant Kumar Das
99 | IIRM-769 | Epic | SOW#42 - TAT mgmt | Draft | Sidhant Kumar Das
100 | IIRM-770 | Epic | SOW#43 - SLA mgmt (Including Service Score) | Draft | Sidhant Kumar Das
101 | IIRM-771 | Epic | SOW#44 - IBP Landing Page (Design) | RELEASED | Sidhant Kumar Das
102 | IIRM-772 | Epic | SOW#45 - Document Management | Draft | Sidhant Kumar Das
103 | IIRM-773 | Epic | SOW#46 - Enrolment Portal | WORK IN PROGRESS | Sidhant Kumar Das
104 | IIRM-774 | Epic | SOW#47 - Company Plans | Draft | Sidhant Kumar Das
105 | IIRM-775 | Epic | SOW#48 - Whitelabelling | Draft | Sidhant Kumar Das
106 | IIRM-776 | Epic | SOW#49 - HR Portal View | Draft | Sidhant Kumar Das
107 | IIRM-777 | Epic | SOW#50 - Policy Configurator | RELEASED | Sidhant Kumar Das
108 | IIRM-778 | Epic | SOW#51 - Admin Reports | Draft | Sidhant Kumar Das
109 | IIRM-779 | Epic | SOW#52 - Receivables & Reconcilation | Draft | Sidhant Kumar Das
110 | IIRM-780 | Epic | SOW#53 - Report Hub & Reports | Draft | Sidhant Kumar Das
111 | IIRM-781 | Epic | SOW#54 - CD Management | WORK IN PROGRESS | Sidhant Kumar Das
112 | IIRM-782 | Epic | SOW#55 - Claim Management | WORK IN PROGRESS | Sidhant Kumar Das
113 | IIRM-783 | Epic | SOW#56 - Insurer / TPA integration | WORK IN PROGRESS | Sidhant Kumar Das
114 | IIRM-784 | Epic | SOW#57 - Basic Wellness Hub | Draft | Sidhant Kumar Das
115 | IIRM-785 | Epic | SOW#58 - Wellness Usage Analytics | Draft | Sidhant Kumar Das
116 | IIRM-786 | Epic | SOW#59 - IBP: Landing Page (Admin Module) | Draft | Sidhant Kumar Das
117 | IIRM-787 | Epic | SOW#60 - Claims Corner | WORK IN PROGRESS | Sidhant Kumar Das
118 | IIRM-788 | Epic | SOW#61 - Individual insurance Plan Mgmt | Draft | Sidhant Kumar Das
119 | IIRM-789 | Epic | SOW#62 - AI Chatbot | Draft | Sidhant Kumar Das
120 | IIRM-790 | Epic | SOW#63 - Wellness Admin Config | Draft | Sidhant Kumar Das
121 | IIRM-791 | Epic | SOW#64 - Dynamic & Static info sections | Draft | Sidhant Kumar Das
122 | IIRM-792 | Epic | SOW#65 - Online Pharmacy | Draft | Sidhant Kumar Das
123 | IIRM-793 | Epic | SOW#66 - Upload from Partner of services bought on Partner site | Draft | Sidhant Kumar Das
124 | IIRM-794 | Epic | SOW#67 - Portal Configuration | Draft | Sidhant Kumar Das
125 | IIRM-795 | Epic | SOW#68 - Evexia Club Integration | Draft | Sidhant Kumar Das
126 | IIRM-797 | Epic | SOW#69 - Manage Opportunities | WORK IN PROGRESS | Sidhant Kumar Das
127 | IIRM-811 | Story | Opportunity Hub | Done | Sidhant Kumar Das | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
128 | IIRM-813 | Story | Manage TPA Contact | Done | Sidhant Kumar Das | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
129 | IIRM-834 | Story | Backend - Micro Service Framework Setup | Done | Sidhant Kumar Das | Framework | IIRM-64 — SOW#3 - Micro Service Framework
130 | IIRM-836 | Story | Build UI components | Done | Sidhant Kumar Das | Framework | IIRM-733 — SOW#6 - UI Components
131 | IIRM-838 | Story | UI - Approach Style Establishment | Done | Sidhant Kumar Das | Framework | IIRM-734 — SOW#7 - UI Design System
132 | IIRM-1041 | Sub-task | UI Approach Style Establishment Option 1 | Done | Sidhant Kumar Das | Framework | IIRM-838 — UI - Approach Style Establishment
133 | IIRM-1043 | Sub-task | UI Approach Style Establishment Option 2 | Done | Sidhant Kumar Das | Framework | IIRM-838 — UI - Approach Style Establishment
134 | IIRM-1070 | Sub-task | Setup API Gate way | Done | Sidhant Kumar Das | Framework | IIRM-834 — Backend - Micro Service Framework Setup
135 | IIRM-1071 | Sub-task | Setup Auth Service as Microservice | Done | Sidhant Kumar Das | Framework | IIRM-834 — Backend - Micro Service Framework Setup
136 | IIRM-1072 | Sub-task | Initialize Environment Configurations for Micro Services | Done | Sidhant Kumar Das | Framework | IIRM-834 — Backend - Micro Service Framework Setup
137 | IIRM-1073 | Sub-task | Setup the Service registry for Micro services | Done | Sidhant Kumar Das | Framework | IIRM-834 — Backend - Micro Service Framework Setup
138 | IIRM-1104 | Sub-task | UI Components - Forms and Form Utils | Done | Sidhant Kumar Das | Framework | IIRM-836 — Build UI components
139 | IIRM-1105 | Sub-task | UI Components - Toast | Done | Sidhant Kumar Das | Framework | IIRM-836 — Build UI components
140 | IIRM-1109 | Sub-task | UI Components - Grid | Done | Sidhant Kumar Das | Framework | IIRM-836 — Build UI components
141 | IIRM-1110 | Sub-task | UI Components - Menu | Done | Sidhant Kumar Das | Framework | IIRM-836 — Build UI components
142 | IIRM-1111 | Sub-task | UI Components - Header | Done | Sidhant Kumar Das | Framework | IIRM-836 — Build UI components
143 | IIRM-1131 | Sub-task | Basic Add, View with edit of basic data, with lists of policies/companies | Done | Sidhant Kumar Das | iWork | IIRM-813 — Manage TPA Contact
144 | IIRM-1133 | Sub-task | Top Opportunities with search/filter, List of opportunities with high level summaries | Done | Sidhant Kumar Das | iWork | IIRM-811 — Opportunity Hub
145 | IIRM-1481 | Sub-task | RBAC mapping of branch, department, organisation, based on Roles and designation | Done | Sai Vamsee K | Framework | IIRM-9 — UX - Core System (Research & Documentation)
146 | IIRM-1483 | Sub-task | Workshop with chief designer & design strategist | Done | Sai Vamsee K | Framework | IIRM-838 — UI - Approach Style Establishment
147 | IIRM-1485 | Sub-task | Product Spec - Detailing RBAC | Done | Sai Vamsee K | Framework | IIRM-13 — Product Spec - iWork (Org Structure, RBAC, Contacts, TPA, Insurer and Broker)
148 | IIRM-1486 | Sub-task | Product Research & Analysis | Done | Sai Vamsee K | Framework | IIRM-13 — Product Spec - iWork (Org Structure, RBAC, Contacts, TPA, Insurer and Broker)
149 | IIRM-1488 | Sub-task | Functional flow understanding of opportunity | Done | Nandini Kataria | Framework | IIRM-9 — UX - Core System (Research & Documentation)
150 | IIRM-1489 | Sub-task | Adding of an employee based on RBAC | Done | Nandini Kataria | Framework | IIRM-9 — UX - Core System (Research & Documentation)
151 | IIRM-1490 | Sub-task | Understanding of IIRM org structure | Done | Nandini Kataria | Framework | IIRM-9 — UX - Core System (Research & Documentation)
152 | IIRM-1491 | Task | TC_001: Admin: Login with Valid Credentials | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
153 | IIRM-1492 | QAlity Test | TC_002: Admin: Login Attempt with Invalid Credentials | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
154 | IIRM-1493 | QAlity Test | TC_001: Admin: Login with Valid Credentials | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
155 | IIRM-1494 | QAlity Test | TC_003: RBAC: Employee Tries to Access Admin Panel | Draft | SaikumarMahanthi | iWork
156 | IIRM-1495 | Story | UX/UI - Manage Contact | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
157 | IIRM-1496 | Sub-task | Design System - 1 | Done | Sai Vamsee K | Framework | IIRM-11 — Design System - UI
158 | IIRM-1497 | Sub-task | Tech Tools Decision | Done | Sai Vamsee K | Framework | IIRM-20 — Core System - Tech Tool Decisions (TechStack & Integration Choices)
159 | IIRM-1514 | Task | Analyse and create Database Schema for Company Mgmt | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
160 | IIRM-1515 | Story | Analyse and create Database Schema for Contact /Company/Insurer/TPA Mgmt | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
161 | IIRM-1516 | Story | Analyse and Create Database Tables for Implementing Simple Auth | Done | Sai Vamsee K | Framework | IIRM-62 — SOW#2 - Authentication
162 | IIRM-1517 | Story | Analyse and create Masters and populate with data | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
163 | IIRM-1518 | Story | Analyse and Create the Architectural Flow | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
164 | IIRM-1519 | Story | Analyse and Create the master tables required for RBAC | Done | Sai Vamsee K | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
165 | IIRM-1521 | Story | Analyse the Database Shema and Create Tables | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
166 | IIRM-1522 | Story | Analyse the Database Shema and Create Tables for Employee Management | Done | Sai Vamsee K | iWork | IIRM-739 — SOW#12 - Manage Employees
167 | IIRM-1524 | Story | Analyse the Database Shema and Create Tables for Opportunity Management | Done | Sai Vamsee K | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
168 | IIRM-1525 | Story | Analyse the Design Patterns to be followed | Done | Sai Vamsee K | iWork | IIRM-64 — SOW#3 - Micro Service Framework
169 | IIRM-1526 | Story | Analysing Master required | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
170 | IIRM-1527 | Story | Analysisng Schema Tables required | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
171 | IIRM-1528 | Story | API development for Access Control Management | Done | Sai Vamsee K | Framework | IIRM-732 — SOW#5 - Access Control
172 | IIRM-1529 | Story | API development for Company Mgmt | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
173 | IIRM-1530 | Story | API development for Contact /Company/Insurer/TPA Mgmt | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
174 | IIRM-1531 | Story | API Development for Opportunity Management | Done | Sai Vamsee K | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
175 | IIRM-1534 | Story | API Development for Task Management for Employee Management | Done | Sai Vamsee K | iWork | IIRM-739 — SOW#12 - Manage Employees
176 | IIRM-1536 | Story | Authorzation Implementation as per ACL | Done | Sai Vamsee K | Framework | IIRM-732 — SOW#5 - Access Control
177 | IIRM-1537 | Story | Create an Populate the masters for ACL | Done | Sai Vamsee K | Framework | IIRM-732 — SOW#5 - Access Control
178 | IIRM-1538 | Story | Creating Database and Planning the roles | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
179 | IIRM-1539 | Task | Creating Database Users and Permissions | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
180 | IIRM-1540 | Story | Creating Schema Tables required | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
181 | IIRM-1541 | Story | Creating Scripts for Database | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
182 | IIRM-1542 | Story | Creating the Masters and lookups | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
183 | IIRM-1543 | Story | Encription and Tokenization Implementation | Done | Sai Vamsee K | Framework | IIRM-62 — SOW#2 - Authentication
184 | IIRM-1545 | Story | Initial Implementation of Design Pattern | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
185 | IIRM-1546 | Story | Initialize Environment Configurations for Micro Services | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
186 | IIRM-1547 | Task | Setting up Repositories with Users and permissions | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
187 | IIRM-1548 | Story | Setup API Gate way | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
188 | IIRM-1549 | Story | Setup Auth Service as Microservice | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
189 | IIRM-1550 | Story | Setup the iwork Microservice API | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
190 | IIRM-1551 | Story | Setup the Service registry for Micro services | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
191 | IIRM-1552 | Story | Structurise the iwork Microservice API with respective modules | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
192 | IIRM-1554 | Story | Tweak / Update / Create APIs for masters | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
193 | IIRM-1555 | Story | Add/View/Edit Company | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
194 | IIRM-1556 | Story | Add/View/Edit Contact | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
195 | IIRM-1557 | Story | Add/View/Edit Employee | Done | Sai Vamsee K | iWork | IIRM-739 — SOW#12 - Manage Employees
196 | IIRM-1560 | Story | Company (Prospect) Hub | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
197 | IIRM-1561 | Story | Contact Hub | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
198 | IIRM-1562 | Story | Core System - Frontend Setup | Done | Sai Vamsee K | Framework | IIRM-80 — SOW#4 - Core System
199 | IIRM-1563 | Story | Employee Hub | Done | Sai Vamsee K | iWork | IIRM-739 — SOW#12 - Manage Employees
200 | IIRM-1564 | Story | Landing Page - Engineering | Done | Sai Vamsee K | Framework | IIRM-80 — SOW#4 - Core System
201 | IIRM-1565 | Sub-task | Creating Database and Planning the roles | Done | Sai Vamsee K | Framework | IIRM-1538 — Creating Database and Planning the roles
202 | IIRM-1566 | Sub-task | Creating Database Users and Permissions | Done | Sai Vamsee K | Framework | IIRM-1539 — Creating Database Users and Permissions
203 | IIRM-1567 | Sub-task | Analysing Matser required | Done | Sai Vamsee K | Framework | IIRM-1526 — Analysing Master required
204 | IIRM-1568 | Sub-task | Creating the Masters | Done | Sai Vamsee K | Framework | IIRM-1542 — Creating the Masters and lookups
205 | IIRM-1569 | Sub-task | Analysisng Schema Tables required | Done | Sai Vamsee K | Framework | IIRM-1527 — Analysisng Schema Tables required
206 | IIRM-1570 | Sub-task | Creating Schema Tables required | Done | Sai Vamsee K | Framework | IIRM-1540 — Creating Schema Tables required
207 | IIRM-1571 | Sub-task | Creating Scripts for Database | Done | Sai Vamsee K | Framework | IIRM-1541 — Creating Scripts for Database
208 | IIRM-1572 | Sub-task | Analyse and create Masters for Application for master data | Done | Sai Vamsee K | iWork | IIRM-1517 — Analyse and create Masters and populate with data
209 | IIRM-1573 | Sub-task | Db Scripts aand and populate masters with data | Done | Sai Vamsee K | iWork | IIRM-1517 — Analyse and create Masters and populate with data
210 | IIRM-1574 | Sub-task | Create APIs for masters - Create | Done | Sai Vamsee K | iWork | IIRM-1554 — Tweak / Update / Create APIs for masters
211 | IIRM-1575 | Sub-task | Update / Disabling APIs for masters | Done | Sai Vamsee K | iWork | IIRM-1554 — Tweak / Update / Create APIs for masters
212 | IIRM-1576 | Sub-task | Create repository and have intital branches created | Done | Sai Vamsee K | Framework | IIRM-1547 — Setting up Repositories with Users and permissions
213 | IIRM-1577 | Sub-task | Add the users and apply permisiosn for the users | Done | Sai Vamsee K | Framework | IIRM-1547 — Setting up Repositories with Users and permissions
214 | IIRM-1578 | Sub-task | Analyse the Design Patterns to be followed | Done | Sai Vamsee K | Framework | IIRM-1525 — Analyse the Design Patterns to be followed
215 | IIRM-1579 | Sub-task | Initial Implementation of Design Pattern | Done | Sai Vamsee K | Framework | IIRM-1545 — Initial Implementation of Design Pattern
216 | IIRM-1580 | Sub-task | Analyse Architectural Flow | Done | Sai Vamsee K | Framework | IIRM-1518 — Analyse and Create the Architectural Flow
217 | IIRM-1581 | Sub-task | Create the Architectural Flow Diagrams | Done | Sai Vamsee K | Framework | IIRM-1518 — Analyse and Create the Architectural Flow
218 | IIRM-1582 | Sub-task | Verifying the structure of created project is as per the estimated architecture | Done | Sai Vamsee K | Framework | IIRM-1518 — Analyse and Create the Architectural Flow
219 | IIRM-1585 | Sub-task | Setup the iwork Microservice API | Done | Sai Vamsee K | Framework | IIRM-1550 — Setup the iwork Microservice API
220 | IIRM-1586 | Sub-task | Create the iwork Microservice API with respective modules | Done | Sai Vamsee K | iWork | IIRM-1552 — Structurise the iwork Microservice API with respective modules
221 | IIRM-1587 | Sub-task | Configure iwork Microservice with env variables required | Done | Sai Vamsee K | iWork | IIRM-1552 — Structurise the iwork Microservice API with respective modules
222 | IIRM-1588 | Sub-task | Plan the controllers for Iwork with respct to modules | Done | Sai Vamsee K | iWork | IIRM-1552 — Structurise the iwork Microservice API with respective modules
223 | IIRM-1589 | Sub-task | Analyse the masters for ACL | Done | Sai Vamsee K | Framework | IIRM-1537 — Create an Populate the masters for ACL
224 | IIRM-1590 | Sub-task | Create Masters for ACL | Done | Sai Vamsee K | Framework | IIRM-1537 — Create an Populate the masters for ACL
225 | IIRM-1591 | Sub-task | API Planning for Access Control Management | Done | Sai Vamsee K | Framework | IIRM-1528 — API development for Access Control Management
226 | IIRM-1592 | Sub-task | API development for Access Control Management - List | Done | Sai Vamsee K | Framework | IIRM-1528 — API development for Access Control Management
227 | IIRM-1593 | Sub-task | API development for Access Control Management - Update | Done | Sai Vamsee K | Framework | IIRM-1528 — API development for Access Control Management
228 | IIRM-1594 | Sub-task | Identify the routes to include and exclude for Authorization | Done | Sai Vamsee K | Framework | IIRM-1536 — Authorzation Implementation as per ACL
229 | IIRM-1595 | Sub-task | API Implementation of Authroization | Done | Sai Vamsee K | Framework | IIRM-1536 — Authorzation Implementation as per ACL
230 | IIRM-1596 | Sub-task | Validating the Implementation of Authorization | Done | Sai Vamsee K | Framework | IIRM-1536 — Authorzation Implementation as per ACL
231 | IIRM-1597 | Sub-task | Encription Analysis for data | Done | Sai Vamsee K | Framework | IIRM-1543 — Encription and Tokenization Implementation
232 | IIRM-1598 | Sub-task | Encription Implemenbtation for Data | Done | Sai Vamsee K | Framework | IIRM-1543 — Encription and Tokenization Implementation
233 | IIRM-1599 | Sub-task | Analyse and Create the master tables required for RBAC | Done | Sai Vamsee K | Framework | IIRM-1519 — Analyse and Create the master tables required for RBAC
234 | IIRM-1603 | Sub-task | Creating and Structuring API Gate way | Done | Sai Vamsee K | Framework | IIRM-1548 — Setup API Gate way
235 | IIRM-1604 | Sub-task | Configure API Gate way for Service Registry | Done | Sai Vamsee K | Framework | IIRM-1548 — Setup API Gate way
236 | IIRM-1605 | Sub-task | Implement the Initial required routes for API gateway | Done | Sai Vamsee K | Framework | IIRM-1548 — Setup API Gate way
237 | IIRM-1606 | Sub-task | Creating and Structuring Auth Micro service | Done | Sai Vamsee K | Framework | IIRM-1549 — Setup Auth Service as Microservice
238 | IIRM-1607 | Sub-task | Configure Service Registry Enpoint for Auth Service | Done | Sai Vamsee K | Framework | IIRM-1549 — Setup Auth Service as Microservice
239 | IIRM-1608 | Sub-task | Implement the Initial required routes for Auth Service | Done | Sai Vamsee K | Framework | IIRM-1549 — Setup Auth Service as Microservice
240 | IIRM-1609 | Sub-task | Setup Environment Configurations for Micro Services | Done | Sai Vamsee K | Framework | IIRM-1546 — Initialize Environment Configurations for Micro Services
241 | IIRM-1610 | Sub-task | Populate Environment Configuration Variables | Done | Sai Vamsee K | Framework | IIRM-1546 — Initialize Environment Configurations for Micro Services
242 | IIRM-1611 | Sub-task | Structurize the Service registry service | Done | Sai Vamsee K | Framework | IIRM-1551 — Setup the Service registry for Micro services
243 | IIRM-1612 | Sub-task | Endpoint development for microservices to get registered and to get searched | Done | Sai Vamsee K | Framework | IIRM-1551 — Setup the Service registry for Micro services
244 | IIRM-1613 | Sub-task | Analyze the Table schema for Simple Auth | Done | Sai Vamsee K | Framework | IIRM-1516 — Analyse and Create Database Tables for Implementing Simple Auth
245 | IIRM-1614 | Sub-task | Create a table for Simple Auth | Done | Sai Vamsee K | Framework | IIRM-1516 — Analyse and Create Database Tables for Implementing Simple Auth
246 | IIRM-1618 | Sub-task | Tokenizing Simple Auth Authentication | Done | Sai Vamsee K | Framework | IIRM-1543 — Encription and Tokenization Implementation
247 | IIRM-1619 | Sub-task | Analyze the shcema fro. Employe management schema | Done | Sai Vamsee K | iWork | IIRM-1522 — Analyse the Database Shema and Create Tables for Employee Management
248 | IIRM-1620 | Sub-task | Create the tables for Employee management | Done | Sai Vamsee K | iWork | IIRM-1522 — Analyse the Database Shema and Create Tables for Employee Management
249 | IIRM-1621 | Sub-task | Create API development for Employee management | Done | Sai Vamsee K | iWork | IIRM-1534 — API Development for Task Management for Employee Management
250 | IIRM-1622 | Sub-task | Update API development for Employee management | Done | Sai Vamsee K | iWork | IIRM-1534 — API Development for Task Management for Employee Management
251 | IIRM-1623 | Sub-task | List and serach API development for Employee management | Done | Sai Vamsee K | iWork | IIRM-1534 — API Development for Task Management for Employee Management
252 | IIRM-1624 | Sub-task | Delete API development for Employee management | Done | Sai Vamsee K | iWork | IIRM-1534 — API Development for Task Management for Employee Management
253 | IIRM-1625 | Sub-task | Analyse and create Database Schema for Company Mgmt | Done | Sai Vamsee K | iWork | IIRM-1514 — Analyse and create Database Schema for Company Mgmt
254 | IIRM-1626 | Sub-task | Create API development for Company Mgmt | Done | Sai Vamsee K | iWork | IIRM-1529 — API development for Company Mgmt
255 | IIRM-1627 | Sub-task | Update API development for Company Mgmt | Done | Sai Vamsee K | iWork | IIRM-1529 — API development for Company Mgmt
256 | IIRM-1628 | Sub-task | List and serach API development for Company Mgmt | Done | Sai Vamsee K | iWork | IIRM-1529 — API development for Company Mgmt
257 | IIRM-1629 | Sub-task | Analyse and create Database Schema for Contact /Company/Insurer/TPA Mgmt | Done | Sai Vamsee K | iWork | IIRM-1515 — Analyse and create Database Schema for Contact /Company/Insurer/TPA Mgmt
258 | IIRM-1630 | Sub-task | Create API development for Contact Management | Done | Sai Vamsee K | iWork | IIRM-1530 — API development for Contact /Company/Insurer/TPA Mgmt
259 | IIRM-1631 | Sub-task | Update API development for Contact /Company/Insurer/TPA Mgmt | Done | Sai Vamsee K | iWork | IIRM-1530 — API development for Contact /Company/Insurer/TPA Mgmt
260 | IIRM-1632 | Sub-task | List and serach API development for Contact /Company/Insurer/TPA Mgmt | Done | Sai Vamsee K | iWork | IIRM-1530 — API development for Contact /Company/Insurer/TPA Mgmt
261 | IIRM-1633 | Sub-task | Analyse and create Database Schema for Opportunity Mgmt | Done | Sai Vamsee K | iWork | IIRM-1524 — Analyse the Database Shema and Create Tables for Opportunity Management
262 | IIRM-1634 | Sub-task | Create API development for Opportunity Mgmt | Done | Sai Vamsee K | iWork | IIRM-1531 — API Development for Opportunity Management
263 | IIRM-1635 | Sub-task | Update API development for Opportunity Mgmt | Done | Sai Vamsee K | iWork | IIRM-1531 — API Development for Opportunity Management
264 | IIRM-1636 | Sub-task | List and serach API development for Opportunity Mgmt | Done | Sai Vamsee K | iWork | IIRM-1531 — API Development for Opportunity Management
265 | IIRM-1637 | Sub-task | Analyse the Database Shema and Create Tables for tasks | Done | Sai Vamsee K | iWork | IIRM-1521 — Analyse the Database Shema and Create Tables
266 | IIRM-1645 | Sub-task | UI Implementation - Build Table for list of employess based on login, with search/filter, list with basic attributes | Done | Sai Vamsee K | iWork | IIRM-1563 — Employee Hub
267 | IIRM-1646 | Sub-task | API data handling in all cases Build Table for list of employess based on login, with search/filter, list with basic attributes | Done | Sai Vamsee K | iWork | IIRM-1563 — Employee Hub
268 | IIRM-1647 | Sub-task | Handle the interactions built on table | Done | Sai Vamsee K | iWork | IIRM-1563 — Employee Hub
269 | IIRM-1648 | Sub-task | View mode - UI Implementation to look at the employee data | Done | Sai Vamsee K | iWork | IIRM-1557 — Add/View/Edit Employee
270 | IIRM-1649 | Sub-task | View mode - API integration - View mode to look at the employee data | Done | Sai Vamsee K | iWork | IIRM-1557 — Add/View/Edit Employee
271 | IIRM-1650 | Sub-task | Create - Form UI Implementation for create employee | Done | Sai Vamsee K | iWork | IIRM-1557 — Add/View/Edit Employee
272 | IIRM-1651 | Sub-task | Create - Form Data, interaction and validation handling for create employee | Done | Sai Vamsee K | iWork | IIRM-1557 — Add/View/Edit Employee
273 | IIRM-1652 | Sub-task | Create - API data handling for create employee | Done | Sai Vamsee K | iWork | IIRM-1557 — Add/View/Edit Employee
274 | IIRM-1653 | Sub-task | Edit UI and interactions for the selected fields on create employee form | Done | Sai Vamsee K | iWork | IIRM-1557 — Add/View/Edit Employee
275 | IIRM-1654 | Sub-task | Edit mode - API integration for employee details updation | Done | Sai Vamsee K | iWork | IIRM-1557 — Add/View/Edit Employee
276 | IIRM-1655 | Sub-task | Build Table for Top 10/Latest companies, with search/filter, GPS etc. | Done | Sai Vamsee K | iWork | IIRM-1560 — Company (Prospect) Hub
277 | IIRM-1656 | Sub-task | Handle the interactions built on table | Done | Sai Vamsee K | iWork | IIRM-1560 — Company (Prospect) Hub
278 | IIRM-1657 | Sub-task | API integration to load companies data on to the table | Done | Sai Vamsee K | iWork | IIRM-1560 — Company (Prospect) Hub
279 | IIRM-1658 | Sub-task | View mode - UI Implementation to look at the already created company data | Done | Sai Vamsee K | iWork | IIRM-1555 — Add/View/Edit Company
280 | IIRM-1659 | Sub-task | View mode - API integration - View mode to update the already created company data | Done | Sai Vamsee K | iWork | IIRM-1555 — Add/View/Edit Company
281 | IIRM-1660 | Sub-task | Create - Form UI Implementation - Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. | Done | Sai Vamsee K | iWork | IIRM-1555 — Add/View/Edit Company
282 | IIRM-1661 | Sub-task | Create - Form Data, interaction and validation handling - Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on ... | Done | Sai Vamsee K | iWork | IIRM-1555 — Add/View/Edit Company
283 | IIRM-1662 | Sub-task | Create - API integration - Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. | Done | Sai Vamsee K | iWork | IIRM-1555 — Add/View/Edit Company
284 | IIRM-1663 | Sub-task | Edit mode - Form UI Implementation - Edit feature View with multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | Done | Sai Vamsee K | iWork | IIRM-1555 — Add/View/Edit Company
285 | IIRM-1664 | Sub-task | Edit mode - Form Data, interaction and validation handling - Edit feature View with multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | Done | Sai Vamsee K | iWork | IIRM-1555 — Add/View/Edit Company
286 | IIRM-1665 | Sub-task | Edit mode - API integration - Edit multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | Done | Sai Vamsee K | iWork | IIRM-1555 — Add/View/Edit Company
287 | IIRM-1666 | Sub-task | UI Implementation - Build Table for Top 10/Latest Contacts, with search/filter, list with basic attributes | Done | Sai Vamsee K | iWork | IIRM-1561 — Contact Hub
288 | IIRM-1667 | Sub-task | Handle the interactions built on contacts table | Done | Sai Vamsee K | iWork | IIRM-1561 — Contact Hub
289 | IIRM-1668 | Sub-task | API Integration - Build Table for Top 10/Latest Contacts, with search/filter, list with basic attributes | Done | Sai Vamsee K | iWork | IIRM-1561 — Contact Hub
290 | IIRM-1669 | Sub-task | View mode - UI Implementation - List of all contacts | Done | Sai Vamsee K | iWork | IIRM-1556 — Add/View/Edit Contact
291 | IIRM-1670 | Sub-task | View mode - API Integration - List of all contacts | Done | Sai Vamsee K | iWork | IIRM-1556 — Add/View/Edit Contact
292 | IIRM-1671 | Sub-task | Create - Form UI Implementation - Simple AddContacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | Done | Sai Vamsee K | iWork | IIRM-1556 — Add/View/Edit Contact
293 | IIRM-1672 | Sub-task | Create - Form Data, interaction and validation handling - Simple edit like AddContacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | Done | Sai Vamsee K | iWork | IIRM-1556 — Add/View/Edit Contact
294 | IIRM-1673 | Sub-task | Create - API data handling in all cases Simple edit like AddContacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | Done | Sai Vamsee K | iWork | IIRM-1556 — Add/View/Edit Contact
295 | IIRM-1674 | Sub-task | Edit mode - Form UI Implementation - Simple AddContacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | Done | Sai Vamsee K | iWork | IIRM-1556 — Add/View/Edit Contact
296 | IIRM-1675 | Sub-task | Edit mode - Form Data, interaction and validation handling - Simple edit like AddContacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | Done | Sai Vamsee K | iWork | IIRM-1556 — Add/View/Edit Contact
297 | IIRM-1676 | Sub-task | Edit mode - API data handling in all cases Simple edit like AddContacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | Done | Sai Vamsee K | iWork | IIRM-1556 — Add/View/Edit Contact
298 | IIRM-1677 | Sub-task | Product Spec - Org Structure & RBAC | Done | Sai Vamsee K | Framework | IIRM-13 — Product Spec - iWork (Org Structure, RBAC, Contacts, TPA, Insurer and Broker)
299 | IIRM-1678 | Sub-task | Product Spec - Contacts, TPA, Insurer, Broker | Done | Sai Vamsee K | Framework | IIRM-13 — Product Spec - iWork (Org Structure, RBAC, Contacts, TPA, Insurer and Broker)
300 | IIRM-1679 | Sub-task | Product Spec - Company | Done | Sai Vamsee K | Framework | IIRM-13 — Product Spec - iWork (Org Structure, RBAC, Contacts, TPA, Insurer and Broker)
301 | IIRM-1681 | Sub-task | Folder Structure, and Global styling | Done | Sai Vamsee K | Framework | IIRM-1562 — Core System - Frontend Setup
302 | IIRM-1682 | Sub-task | Navigation/Routing | Done | Sai Vamsee K | Framework | IIRM-1562 — Core System - Frontend Setup
303 | IIRM-1683 | Sub-task | API Service using React Query | Done | Sai Vamsee K | Framework | IIRM-1562 — Core System - Frontend Setup
304 | IIRM-1684 | Sub-task | Error handling and logging | Done | Sai Vamsee K | Framework | IIRM-1562 — Core System - Frontend Setup
305 | IIRM-1685 | Sub-task | Basic Guideline Documentation | Done | Sai Vamsee K | Framework | IIRM-1562 — Core System - Frontend Setup
306 | IIRM-1686 | QAlity Test | TC_004: 365 Outh: Successful Login via Microsoft 365 Authentication | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
307 | IIRM-1687 | QAlity Test | TC_005: 365 Outh: Signout Functionality And OAuth Token Expiry Test | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
308 | IIRM-1688 | QAlity Test | TC_006: 365 Outh: Multi-Factor Authentication (MFA) Validation | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
309 | IIRM-1689 | Task | QA Test Strategy Document Preparation | Done | Sai Vamsee K | Framework | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
310 | IIRM-1690 | Task | Test Plan Documentation - ACL & RBAC | Done | Sai Vamsee K | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
311 | IIRM-1691 | Task | Test Case Documentation - ACL & RBAC | Done | Sai Vamsee K | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
312 | IIRM-1692 | Task | Amendments to Architecture - AWS cost calculator needs to be updated with all the new components | Done | Sai Vamsee K | Framework | IIRM-797 — SOW#69 - Manage Opportunities
313 | IIRM-1693 | QAlity Test | TC_007: RBAC: Verify Employee Role Assignment and Access Privileges | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
314 | IIRM-1694 | QAlity Test | TC_008: RBAC: Validate Organization Hierarchy and Entity-Level Access Restrictions | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
315 | IIRM-1695 | QAlity Test | TC_009: RBAC: Validate Super Admin Role & Unrestricted Access | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
316 | IIRM-1696 | QAlity Test | TC_010: RBAC: Verify Functional Admin’s Organization-Level Control | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
317 | IIRM-1697 | QAlity Test | TC_011: RBAC: Validate Organization Creation and Cross-Organization Access Control | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
318 | IIRM-1698 | QAlity Test | TC_012: RBAC: Validate Department Creation, Assignment, and Access Control | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
319 | IIRM-1699 | QAlity Test | TC_013: RBAC: Assign Employee to a Branch and Verify Branch Restrictions | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
320 | IIRM-1700 | QAlity Test | TC_014: RBAC: Validate Designation-Based Reporting Hierarchy and Scope of Access | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
321 | IIRM-1701 | Sub-task | Create API development for TPA Management | Done | VedaVyas | iWork | IIRM-1530 — API development for Contact /Company/Insurer/TPA Mgmt
322 | IIRM-1702 | Sub-task | Create API development for Insurer Management | Done | Rama K | iWork | IIRM-1530 — API development for Contact /Company/Insurer/TPA Mgmt
323 | IIRM-1703 | QAlity Test | ACL & RBAC | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
324 | IIRM-1704 | QAlity Test | TC_015: RBAC: Role Assignment Validations | Draft | SaikumarMahanthi | iWork
325 | IIRM-1705 | QAlity Test | TC_016: RBAC: Authentication & Unauthorized Access Prevention | Draft | SaikumarMahanthi | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
326 | IIRM-1706 | Task | Workshop with IIRM & Divami Team | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
327 | IIRM-1709 | Sub-task | Test Plan documentation | Done | SaikumarMahanthi | iWork | IIRM-1557 — Add/View/Edit Employee
328 | IIRM-1710 | Sub-task | Create an APIs for the creating, deleting and modifying the Master data into the Master tables | Done | VedaVyas | Framework | IIRM-1542 — Creating the Masters and lookups
329 | IIRM-1711 | Sub-task | Create an APIs for the creating, deleting and modifying the lookup data into the lookup table | Done | VedaVyas | Framework | IIRM-1542 — Creating the Masters and lookups
330 | IIRM-1712 | Task | QA - Employee create/ update/ delete | Done | meghana | iWork | IIRM-739 — SOW#12 - Manage Employees
331 | IIRM-1713 | Sub-task | Test data documentation | PENDING PEER or LEAD REVIEW | meghana | iWork | IIRM-1712 — QA - Employee create/ update/ delete
332 | IIRM-1714 | Sub-task | Test case documentation | PENDING PEER or LEAD REVIEW | meghana | iWork | IIRM-1712 — QA - Employee create/ update/ delete
333 | IIRM-1717 | Task | QA - Company create/ update/ delete | Done | meghana | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
334 | IIRM-1718 | Sub-task | Test plan documentation | Done | meghana | iWork | IIRM-1717 — QA - Company create/ update/ delete
335 | IIRM-1719 | Sub-task | Test case& test data documentation | Done | meghana | iWork | IIRM-1717 — QA - Company create/ update/ delete
336 | IIRM-1720 | Sub-task | Test cases Execution/Reporting bugs | Done | meghana | iWork | IIRM-2178 — CLONE - QA - Company create/ update/ delete-2
337 | IIRM-1721 | Sub-task | Bugfix Verification | Done | meghana | iWork | IIRM-2178 — CLONE - QA - Company create/ update/ delete-2
338 | IIRM-1722 | QAlity Test | TC_015: Company: Test data | Draft | SaikumarMahanthi | Framework
339 | IIRM-1723 | Sub-task | Employee login UI implementation | Done | Sai Vamsee K | Framework | IIRM-1564 — Landing Page - Engineering
340 | IIRM-1724 | Sub-task | Employee login API integration | Done | Sai Vamsee K | Framework | IIRM-1564 — Landing Page - Engineering
341 | IIRM-1725 | Sub-task | Swagger Integration into All the Backend services | Done | Rama K | Framework | IIRM-834 — Backend - Micro Service Framework Setup
342 | IIRM-1726 | Sub-task | API Development for Address Entity | Done | Rama K | iWork | IIRM-1529 — API development for Company Mgmt
343 | IIRM-1736 | Story | Creating Database and Planning the roles after Product Spec Analysis | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
344 | IIRM-1737 | Sub-task | CLONE - Creating Database and Planning the roles | Done | Sai Vamsee K | Framework | IIRM-1736 — Creating Database and Planning the roles after Product Spec Analysis
345 | IIRM-1738 | Story | Implement State Management across the application | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
346 | IIRM-1739 | Story | Microservices Framework Setup - Service registry, Gateway Config, Service Discovery, Service Config | Done | Sai Vamsee K | Framework | IIRM-64 — SOW#3 - Micro Service Framework
347 | IIRM-1742 | QAlity Test | Company: Verify Successful Company Creation | In Progress | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
348 | IIRM-1743 | QAlity Test | Company: Verify field validations with invalid formats | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
349 | IIRM-1744 | QAlity Test | Company: Verify duplicate & Empty filed validations | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
350 | IIRM-1745 | QAlity Test | Company: Verify AI-Based Auto-Filling from Tracxn | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
351 | IIRM-1746 | QAlity Test | Company: – Verify Company Group Association with an Existing Parent Company | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
352 | IIRM-1747 | QAlity Test | Company: Verify Multiple Address Addition with Address Type | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
353 | IIRM-1748 | QAlity Test | Company: Verify Document Attachment for a New Company | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
354 | IIRM-1749 | QAlity Test | Company: Verify Role-Based Editing Permissions an Existing Company | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
355 | IIRM-1750 | QAlity Test | Company: Verify Company Status Management: Approval, Closure, Merging, and Soft Deletion | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
356 | IIRM-1751 | QAlity Test | TC_025: Employee: Verify Successful Employee Creation | Draft | SaikumarMahanthi | iWork | IIRM-739 — SOW#12 - Manage Employees
357 | IIRM-1752 | QAlity Test | TC_026: Employee: Verify Successful Employee Editing with permission | Draft | SaikumarMahanthi | iWork | IIRM-739 — SOW#12 - Manage Employees
358 | IIRM-1753 | QAlity Test | TC_027: Employee: Verify Field Validations for Employee Creation | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
359 | IIRM-1754 | QAlity Test | TC_028: Employee: Validate UI/UX Consistency and Responsiveness for Employee Creation. | Draft | SaikumarMahanthi | iWork | IIRM-739 — SOW#12 - Manage Employees
360 | IIRM-1755 | QAlity Test | TC_029: Employee: Verify Employee Creation with Bulk Upload | Draft | SaikumarMahanthi | iWork | IIRM-739 — SOW#12 - Manage Employees
361 | IIRM-1756 | QAlity Test | IIRM : Employee Test data | Draft | SaikumarMahanthi | iWork | IIRM-739 — SOW#12 - Manage Employees
362 | IIRM-1757 | QAlity Test | Company: Verify Prioritization and Display of Companies | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
363 | IIRM-1758 | QAlity Test | Company: Verify Filtering, Sorting, Smart Search, Pagination, and Detailed View in Company List | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
364 | IIRM-1759 | QAlity Test | Company: Verify Default Metrics for Newly Created Roles in Company Hub | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
365 | IIRM-1760 | QAlity Test | Company: Verify Role-Specific Key Metrics in Company Hub | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
366 | IIRM-1761 | QAlity Test | Company: : Verify Referral Source, Ownership, and Currency Auto-Population | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
367 | IIRM-1762 | QAlity Test | Company: Verify Entity Relationships for Company and Associated Entities | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
368 | IIRM-1763 | QAlity Test | TC_036: Contact: Verify Contact Addition and Association with Company | Draft | SaikumarMahanthi | iWork
369 | IIRM-1764 | QAlity Test | TC_037: Contact: Verify Contact Search, Filtering, and List Pagination | Draft | SaikumarMahanthi | iWork
370 | IIRM-1765 | QAlity Test | TC_038: Contact: Verify Contact Details View Displays Correct Information | Draft | SaikumarMahanthi | iWork
371 | IIRM-1766 | QAlity Test | TC_039: Contact: Verify Contact Profile Actions (Edit, Restore, LinkedIn Profile Access) | Draft | SaikumarMahanthi | iWork
372 | IIRM-1767 | QAlity Test | TC_040: Contact: Test Case: Verify Contact Addition with All Functionalities | Draft | SaikumarMahanthi | iWork
373 | IIRM-1768 | QAlity Test | TC_037: Contact:Contact Management (Editing, Duplicate Prevention, Moving Companies, Inactivation, & Status Updates) | Draft | SaikumarMahanthi | iWork
374 | IIRM-1769 | QAlity Test | TC_041: Conatct: Verify Communication, Audit Trail, and Greetings for Contacts | Draft | SaikumarMahanthi | iWork
375 | IIRM-1774 | Clarification | Internal Dependencies List for IIRM | Draft | Sai Vamsee K | Framework
376 | IIRM-1775 | Sub-task | Template for Organisation list for employees | Pushed to Backlog | Sai Vamsee K | Framework | IIRM-1774 — Internal Dependencies List for IIRM
377 | IIRM-1779 | Task | QA - Lead Tasks | Done | Sai Vamsee K | iWork | IIRM-797 — SOW#69 - Manage Opportunities
378 | IIRM-1782 | Story | UX/UI - Create/List and View Tasks, Meetings | Done | Sai Vamsee K | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
379 | IIRM-1783 | Story | UX/UI - Create/List and View Employees | Done | Sai Vamsee K | iWork | IIRM-739 — SOW#12 - Manage Employees
380 | IIRM-1784 | Story | UX/UI - Create/List and View Opportunity | Done | Sai Vamsee K | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
381 | IIRM-1786 | Story | UX/UI - Create/List and View TPA | Done | Sai Vamsee K | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
382 | IIRM-1787 | Task | Prepare: Test data & RTM from Company hub | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
383 | IIRM-1788 | Story | Product Spec - iWork (Opportunities) | Done | Sai Vamsee K | Framework | IIRM-80 — SOW#4 - Core System
384 | IIRM-1789 | Sub-task | Product Spec - Manage Opportunities | Done | Sai Vamsee K | Framework | IIRM-1788 — Product Spec - iWork (Opportunities)
385 | IIRM-1791 | Sub-task | Implement the Auth gaurds for the validating the users and access permissions | Done | VedaVyas | Framework | IIRM-1536 — Authorzation Implementation as per ACL
386 | IIRM-1792 | QAlity Test | TC_042: Contact: Verify Contact Management Functionalities | Draft | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
387 | IIRM-1793 | QAlity Test | TC_043: Contact: Verify Contact Search and List Display | Draft | SaikumarMahanthi | iWork
388 | IIRM-1794 | QAlity Test | TC_044: Contact: Verify System Constraints for Contact Management | Draft | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
389 | IIRM-1795 | QAlity Test | TC_045: Contact: Verify Role-Based Access Control (RBAC) for Contact Management | Draft | SaikumarMahanthi | iWork
390 | IIRM-1796 | QAlity Test | TC_046: Contact: Verify Contact Search, Pagination, Sorting, and Contact Linking | Draft | SaikumarMahanthi | iWork
391 | IIRM-1797 | QAlity Test | TC_047: Contact: Creating a New Contact (Verifying All Functionality) | Draft | SaikumarMahanthi | iWork
392 | IIRM-1798 | QAlity Test | TC_048: Contact: Conditional Display of Fields Based on User's Country | Draft | SaikumarMahanthi | iWork
393 | IIRM-1799 | QAlity Test | TC_049: Contact: Managing Contact Status Based on Company Association | Draft | SaikumarMahanthi | iWork
394 | IIRM-1800 | QAlity Test | TC_050: Contact: Communication Tracking and Duplicate Contact Detection | Draft | SaikumarMahanthi | iWork
395 | IIRM-1801 | Task | Prepare Test cases for Add/ Edit Contact Screen | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
396 | IIRM-1802 | Sub-task | UX/UI - Manage Contact | Done | Sai Vamsee K | iWork | IIRM-1495 — UX/UI - Manage Contact
397 | IIRM-1803 | Task | User stories- TPA, Insurer, Broker, contact | Done | Sai Vamsee K | iWork | IIRM-783 — SOW#56 - Insurer / TPA integration
398 | IIRM-1804 | Task | Product Spec - Manage Tasks/Meetings | Done | Sai Vamsee K | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
399 | IIRM-1805 | Task | Product Spec - Manage Employees | Done | Sai Vamsee K | iWork | IIRM-797 — SOW#69 - Manage Opportunities
400 | IIRM-1806 | Sub-task | Test Scenarios for company hub | Done | SaikumarMahanthi | iWork | IIRM-1717 — QA - Company create/ update/ delete
401 | IIRM-1807 | Task | Prepare Test Scenarios for company | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
402 | IIRM-1866 | Story | Implementing business logic for Manage Company APIs - 1 | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
403 | IIRM-1867 | Story | Implementing business logic for Manage Company screens - 1 | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
404 | IIRM-1868 | Story | Implementing business logic for Manage Contact APIs - 1 | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
405 | IIRM-1869 | Story | Implementing business logic for Manage Contact screens | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
406 | IIRM-1873 | Sub-task | Modify the database table based on the spec. | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
407 | IIRM-1874 | Sub-task | Update create Company API. | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
408 | IIRM-1875 | Sub-task | Implement the businness logic for the update Company API. | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
409 | IIRM-1876 | Sub-task | Update get list of companies and get company by id API | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
410 | IIRM-1878 | Sub-task | Utiliy function for the gobal level search and filters for all the APIs | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
411 | IIRM-1879 | Sub-task | Analytics API for the individual company | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
412 | IIRM-1880 | Sub-task | Analytics API for the overall companies | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
413 | IIRM-1882 | Sub-task | Create a function to store the docs in the cloud | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
414 | IIRM-1883 | Sub-task | File uploading API | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
415 | IIRM-1884 | Sub-task | File deleting API | Done | Sai Vamsee K | iWork | IIRM-1866 — Implementing business logic for Manage Company APIs - 1
416 | IIRM-1895 | Sub-task | Create quick company KPI cards to show counts and percentage | Done | Sai Vamsee K | iWork | IIRM-1867 — Implementing business logic for Manage Company screens - 1
417 | IIRM-1897 | Sub-task | Smart search implementation | Done | Sai Vamsee K | iWork | IIRM-1867 — Implementing business logic for Manage Company screens - 1
418 | IIRM-1898 | Sub-task | update List of the companies (Company nameSales Opportunity countRenewal Opportunity countPolicy countSum InsuredAnnual PremiumTypePriorityIndustryCityLead CRMSentiment) | Done | Sai Vamsee K | iWork | IIRM-1867 — Implementing business logic for Manage Company screens - 1
419 | IIRM-1899 | Sub-task | Create a company section building | Done | Sai Vamsee K | iWork | IIRM-1867 — Implementing business logic for Manage Company screens - 1
420 | IIRM-1900 | Sub-task | Create a company details page | Done | Sai Vamsee K | iWork | IIRM-1867 — Implementing business logic for Manage Company screens - 1
421 | IIRM-1901 | Sub-task | Create a company details page API integration | Done | Sai Vamsee K | iWork | IIRM-1867 — Implementing business logic for Manage Company screens - 1
422 | IIRM-1902 | Sub-task | Analytics Graph component build | Done | Sai Vamsee K | iWork | IIRM-2111 — CLONE - Implementing business logic for Manage Company screens - 2
423 | IIRM-1904 | Sub-task | File upload, File preview, File listing | Done | Sai Vamsee K | iWork | IIRM-2111 — CLONE - Implementing business logic for Manage Company screens - 2
424 | IIRM-1905 | Sub-task | Modify the database table of contact based on the spec. | Done | Sai Vamsee K | iWork | IIRM-1868 — Implementing business logic for Manage Contact APIs - 1
425 | IIRM-1906 | Sub-task | Update create contact API. | Done | Sai Vamsee K | iWork | IIRM-1868 — Implementing business logic for Manage Contact APIs - 1
426 | IIRM-1907 | Sub-task | Implement the businness logic for the update contact API. | Done | Sai Vamsee K | iWork | IIRM-1868 — Implementing business logic for Manage Contact APIs - 1
427 | IIRM-1908 | Sub-task | Update get list of contact and get contact by id API | Done | Sai Vamsee K | iWork | IIRM-1868 — Implementing business logic for Manage Contact APIs - 1
428 | IIRM-1909 | Sub-task | Create contact KPI to show | Done | Sai Vamsee K | iWork | IIRM-1868 — Implementing business logic for Manage Contact APIs - 1
429 | IIRM-1912 | Sub-task | Create a function to store the docs in the cloud | Done | Sai Vamsee K | iWork | IIRM-1868 — Implementing business logic for Manage Contact APIs - 1
430 | IIRM-1917 | Sub-task | Create quick contact KPI cards to show counts and percentage(total contacts and total companies) | Done | Sai Vamsee K | iWork | IIRM-1869 — Implementing business logic for Manage Contact screens
431 | IIRM-1918 | Sub-task | modification of the create/edit contact form | Done | Sai Vamsee K | iWork | IIRM-1869 — Implementing business logic for Manage Contact screens
432 | IIRM-1919 | Sub-task | Smart search implementation | Done | Sai Vamsee K | iWork | IIRM-1869 — Implementing business logic for Manage Contact screens
433 | IIRM-1921 | Sub-task | update List of the contact (Company namePriority WebsiteIndustry SegmentDisplay nameAll the fields of potential opportunities sectionAll the fields of industry intelligence section) | Done | Sai Vamsee K | iWork | IIRM-1869 — Implementing business logic for Manage Contact screens
434 | IIRM-1922 | Sub-task | Create contact details page(Contact detailsCompany detailsMultiple email detailsMultiple phone number detailsContact AddressSales OpportunityRenewal OpportunityPolicyDocuments) | Done | Sai Vamsee K | iWork | IIRM-1869 — Implementing business logic for Manage Contact screens
435 | IIRM-1928 | Story | Implementing business logic for Manage Employee APIs | Done | meghana | iWork | IIRM-739 — SOW#12 - Manage Employees
436 | IIRM-1929 | Story | Implementing business logic for Manage Employee screens | Done | meghana | iWork | IIRM-739 — SOW#12 - Manage Employees
437 | IIRM-1932 | Task | QA - Opportunity create/ update/ delete | Done | Sai Vamsee K | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
438 | IIRM-1933 | Sub-task | Test data preparation | Done | Sai Vamsee K | iWork | IIRM-1932 — QA - Opportunity create/ update/ delete
439 | IIRM-1934 | Sub-task | Test cases Documentation & Update the test case | Done | Sai Vamsee K | iWork | IIRM-1932 — QA - Opportunity create/ update/ delete
440 | IIRM-1935 | Sub-task | Test cases Execution/Reporting bugs | Done | Sai Vamsee K | iWork | IIRM-1932 — QA - Opportunity create/ update/ delete
441 | IIRM-1936 | Sub-task | CLONE - Bugfix Verification | Done | Sai Vamsee K | iWork | IIRM-1932 — QA - Opportunity create/ update/ delete
442 | IIRM-1937 | Task | QA: Contact Test case & test data documentation | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
443 | IIRM-1938 | Sub-task | Test plan documentation | Done | Sai Vamsee K | iWork | IIRM-1937 — QA: Contact Test case & test data documentation
444 | IIRM-1939 | Sub-task | Test case & test data documentation | Done | Sai Vamsee K | iWork | IIRM-1937 — QA: Contact Test case & test data documentation
445 | IIRM-1940 | Sub-task | Test cases Execution/Reporting bugs | Done | Sai Vamsee K | iWork | IIRM-2116 — CLONE - QA: Contact Test case & test data documentation-2
446 | IIRM-1942 | QAlity Test | IIRM: Company Page: Quick Cards: By default correct data should get displayed in all cards | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
447 | IIRM-1943 | QAlity Test | IIRM: Company Page: Quick Cards: Correct data should get updated based on seach and filter results | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
448 | IIRM-1944 | QAlity Test | Company Page: Quick Cards: Count of newly added company is reflected in Quick Cards | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
449 | IIRM-1945 | QAlity Test | IIRM: Company Page: Quick Cards: Mark the company as inactive verify the KPI are upated | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
450 | IIRM-1946 | QAlity Test | IIRM: Company Page: List: Verify the companies associated with the currently logged-in user’s organisation are displayed | Draft | SaikumarMahanthi | iWork
451 | IIRM-1947 | QAlity Test | IIRM: Company Page: Manage Company: Restrict access to unauthorized users | Draft | SaikumarMahanthi | iWork
452 | IIRM-1948 | QAlity Test | IIRM: Company Page: Manage Company: UX: Verify that page design matches approved Figma screens | Draft | SaikumarMahanthi | iWork
453 | IIRM-1952 | QAlity Test | FR_COM_02: Company: Search: Seach for a company and edit details | Draft | SaikumarMahanthi | iWork
454 | IIRM-1954 | QAlity Test | FR_COM_02: Company: Edit: Open company details from different pages from sorted table and edit | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
455 | IIRM-1956 | QAlity Test | FR_COM_02: Company: Edit: Edit all permitted fields of the Company | Draft | SaikumarMahanthi | iWork
456 | IIRM-1957 | QAlity Test | FR_COM_02: RBAC: Company: Edit: Only current owner is able to edit company details | Draft | SaikumarMahanthi | iWork
457 | IIRM-1958 | QAlity Test | FR_COM_02: Company: Edit: Missing data from Tracxn can be added by user while adding a new Company | Draft | SaikumarMahanthi | iWork
458 | IIRM-1960 | QAlity Test | FR_COM_02: Company: Edit: User should be able to edit data captured from Tracxn while adding a new Company | Draft | SaikumarMahanthi | iWork
459 | IIRM-1961 | QAlity Test | FR_COM_02: Company: Edit: User should be able to edit data captured from Company Card while adding a new Company | Draft | SaikumarMahanthi | iWork
460 | IIRM-1962 | QAlity Test | FR_COM_02: Company: Add: Appropriate validations and errors are displayed when invalid data is input during Company creation | Draft | SaikumarMahanthi | iWork
461 | IIRM-1963 | QAlity Test | FR_COM_02: Company: Add: Appropriate error messages displayed when required inputs are missing during Company creation | Draft | SaikumarMahanthi | iWork
462 | IIRM-1965 | Task | QA - Add/Manage Insurer | Done | Sai Vamsee K | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
463 | IIRM-1966 | Sub-task | Test Data documentation | Done | Sai Vamsee K | iWork | IIRM-1965 — QA - Add/Manage Insurer
464 | IIRM-1967 | Sub-task | Test cases and scenarios authoring | Done | Sai Vamsee K | iWork | IIRM-1965 — QA - Add/Manage Insurer
465 | IIRM-1968 | Sub-task | Test cases Execution/Reporting bugs | Done | Sai Vamsee K | iWork | IIRM-1965 — QA - Add/Manage Insurer
466 | IIRM-1969 | Sub-task | Insurer Contact Test cases Execution | Done | Sai Vamsee K | iWork | IIRM-1965 — QA - Add/Manage Insurer
467 | IIRM-1970 | QAlity Test | TC - Dummy - ACL Establishment | Draft | Sai Vamsee K | Framework | IIRM-18 — SOW#1 - ACL & RBAC Control
468 | IIRM-1971 | Sub-task | UX/UI - Create/List and View Employees | Done | Sai Vamsee K | iWork | IIRM-1783 — UX/UI - Create/List and View Employees
469 | IIRM-1972 | Sub-task | UX/UI - Create/List and View Tasks, Meetings | Done | Sai Vamsee K | iWork | IIRM-1782 — UX/UI - Create/List and View Tasks, Meetings
470 | IIRM-1974 | Sub-task | sample RTM Strategy | Done | SaikumarMahanthi | iWork | IIRM-1779 — QA - Lead Tasks
471 | IIRM-1975 | Extension - Subtask | Style options 3 and 4 | Done | Nandini Kataria | iWork | IIRM-838 — UI - Approach Style Establishment
472 | IIRM-1976 | Sub-task | Breakdown Company and Contact requriemnts into test scenarios | Done | SaikumarMahanthi | iWork | IIRM-1779 — QA - Lead Tasks
473 | IIRM-1977 | QAlity Test | Company Page: Quick Cards: By default, correct data should be displayed on all cards | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
474 | IIRM-1978 | QAlity Test | Company Page: Quick Cards: Correct data should get updated based on search and filter results | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
475 | IIRM-1979 | QAlity Test | Company Page: Quick Cards: The count of newly added companies is reflected in Quick Cards | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
476 | IIRM-1980 | QAlity Test | Company Page: Quick Cards: Mark the company as inactive and verify the KPIs are updated | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
477 | IIRM-1982 | Task | NFR Review and Discussion | Done | Sidhant Kumar Das | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
478 | IIRM-1985 | QAlity Test | Company Page: Manage Company: UX: Verify that page design matches approved Figma screens | To Do | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
479 | IIRM-1989 | QAlity Test | Company: Search: Search for a company and edit details | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
480 | IIRM-1990 | QAlity Test | Company: Add: Display name gets pre-filled from the Company name and allows user to edit | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
481 | IIRM-1991 | QAlity Test | Company: Edit: Open company details from different pages from the sorted table and edit | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
482 | IIRM-1993 | QAlity Test | Company: Edit: Edit all permitted fields of the Company | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
483 | IIRM-1994 | QAlity Test | Company: Edit: RBAC: Only the current owner is able to edit company details | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
484 | IIRM-1996 | QAlity Test | Company: Edit: Missing data from the Company Card can be added by the user while adding a new Company | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
485 | IIRM-1999 | QAlity Test | Company: Add: Appropriate validations and errors are displayed when invalid data is input during Company creation | To Do | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
486 | IIRM-2000 | QAlity Test | Company: Add: Appropriate error messages displayed when required inputs are missing during Company creation | To Do | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
487 | IIRM-2001 | QAlity Test | Company: Add: User is not allowed to create Duplicate Companies | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
488 | IIRM-2002 | QAlity Test | Company: Edit: Only one user at a time can edit Company details | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
489 | IIRM-2003 | QAlity Test | Company: Edit: The user is not allowed to edit details of a Company that is not ACTIVE | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
490 | IIRM-2007 | QAlity Test | Company: List: RBAC: Manager: Manager roles can see all companies owned by them and their reporters companies | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
491 | IIRM-2008 | QAlity Test | Company: List: Search: Verify that a search on listed Companies yields correct results | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
492 | IIRM-2009 | QAlity Test | Company: List: Sort: Verify that sort operations on listed Companies yield correct results | To Do | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
493 | IIRM-2010 | QAlity Test | Company: List: Filter: Verify that filter operations on listed Companies yield correct results | To Do | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
494 | IIRM-2015 | QAlity Test | Company Record: Filter: Verify that correct data is retrieved based on the filter criteria across supported fields | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
495 | IIRM-2016 | QAlity Test | Company Record: Filter: Verify that the user is able to apply one or more filters and that the data is retrieved correctly | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
496 | IIRM-2017 | QAlity Test | Company Record: Search: Verify that correct data is retrieved based on the search criteria across supported fields | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
497 | IIRM-2019 | QAlity Test | Company List: Columns: Verify that the company list should be displayed with correct details across all expected columns | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
498 | IIRM-2020 | QAlity Test | Company List: Table: Table operations should work properly (draggable, pagination, sorting, filters, resize, scrolling) | To Do | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
499 | IIRM-2021 | QAlity Test | UX: Company List: Verify that page design matches approved Figma screens | To Do | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
500 | IIRM-2022 | QAlity Test | IIRM: Company: Verify that a company can be created with all fields, with multiple addresses | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
501 | IIRM-2023 | QAlity Test | IIRM: Company: Verify that a company can be created with only mandatory fields | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
502 | IIRM-2024 | QAlity Test | IIRM: Company: Verify that multiple contacts can be created for a company with mandatory fields | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
503 | IIRM-2025 | QAlity Test | Contact Page: Quick Cards: By default, correct data should be displayed in all cards | Completed | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
504 | IIRM-2028 | QAlity Test | Contact Page: Quick Cards: Correct data should get updated based on search and filter results | Draft | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
505 | IIRM-2030 | QAlity Test | Company Detail: Sections: Verify that company detail page should get displayed with correct details across all expected sections | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
506 | IIRM-2031 | QAlity Test | Company Detail: Verify that the user should be able to drill-down to respective entities from various sections of the company detail | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
507 | IIRM-2038 | QAlity Test | Mailbox: Receive: Verify all active users should be able to receive emails along with attachments using their own inbox | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
508 | IIRM-2039 | QAlity Test | Company: Verify that region-specific data is exposed to the user dynamically | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
509 | IIRM-2040 | QAlity Test | Company: Documents: Validation: Verify that authorized users only can upload files with valid file formats up to supported size limits. | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
510 | IIRM-2050 | QAlity Test | Company: Sales Opportunities: Verify that one or more Sales Opportunities can be associated with a Company with a separate label for each | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
511 | IIRM-2051 | QAlity Test | Company Records: Bulk: Verify that the system allows uploading an Excel/CSV for bulk company record entry | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
512 | IIRM-2052 | QAlity Test | Contact Page: Quick Cards: Count of newly added contact is reflected in Quick Cards | To Do | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
513 | IIRM-2056 | QAlity Test | Company Records: Bulk: Validations: Vefiy invalid cases(Size limit, upload limit, formats, types, fail in uploading etc.) | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
514 | IIRM-2057 | QAlity Test | Manage Contact: KPI: Total companies should only show unique companies of current user. | Draft | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
515 | IIRM-2061 | QAlity Test | Contact Page: List: All expected region-specific columns are present in Column list for Active contacts | Draft | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
516 | IIRM-2066 | QAlity Test | Company: Multiple Records: Verify that the system allows entering multiple insurers/borker/TPAs for different policy types | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
517 | IIRM-2068 | QAlity Test | Company Record: Validation: Verify data validation when entering insurers, brokers, and TPAs | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
518 | IIRM-2070 | QAlity Test | Contact Page: Manage Contact: UX: Verify that page design matches approved Figma screens | To Do | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
519 | IIRM-2071 | QAlity Test | Company: Add: Owner: Verify that when a new company is created, the system automatically tags the assigned owner as "Lead CRM." | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
520 | IIRM-2074 | QAlity Test | Contact: Add: Display name gets prefilled from Contact name and allows user to edit | Completed | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
521 | IIRM-2075 | QAlity Test | Contact: Add: Appropriate validations and errors are displayed when invalid data is input during TPA Contact creation | To Do | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
522 | IIRM-2076 | QAlity Test | Company: Owner: Validation: Verify that only one user can be tagged as "Lead CRM" for a company. | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
523 | IIRM-2081 | QAlity Test | Contact: Edit: RBAC: Remove, Delink and relink a Company for a Contact | Draft | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
524 | IIRM-2083 | QAlity Test | Contact: Add: User should be able to add one or more addresses of same Company for the Contact | To Do | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
525 | IIRM-2085 | QAlity Test | Contact: Edit: Appropriate validations and errors are displayed when invalid data is input while editing Contact details | To Do | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
526 | IIRM-2086 | QAlity Test | Contact: Search: Search for a contact on all supported search columns and edit details | Completed | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
527 | IIRM-2093 | QAlity Test | Company: RO Fields: RBAC: Verify that based on the permissions assigned to the user role restricted fields will be displayed read-only or hidden | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
528 | IIRM-2094 | QAlity Test | Company: Add: Verify that when multiple companies with same name exist | Completed | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
529 | IIRM-2098 | Task | User stories - company contacts and SO | Done | meghana | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
530 | IIRM-2099 | QAlity Test | Company: Add: Owner: Verify that when a new company is created, the system automatically tags the assigned owner as "Lead CRM." | To Do | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
531 | IIRM-2101 | QAlity Test | Company: Owner: Validation: Verify that only one user can be tagged as "Lead CRM" for a company. | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
532 | IIRM-2104 | QAlity Test | Contact: Whatsapp: Verify graceful handling of Whatsapp integration from various devices | Draft | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
533 | IIRM-2107 | Bug | IIRM:API: Company: Landing screen displays continuous loading | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
534 | IIRM-2109 | Bug | IIRM: Company: Create Company API fails with 502 error | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
535 | IIRM-2111 | Story | CLONE - Implementing business logic for Manage Company screens - 2 | Done | Sidhant Kumar Das | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
536 | IIRM-2116 | Task | CLONE - QA: Contact Test case & test data documentation-2 | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
537 | IIRM-2117 | Story | API - Implementing business logic for Manage opportunity | Done | Sai Vamsee K | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
538 | IIRM-2118 | Story | Implementing business logic for Manage opportunity screens | Done | Sai Vamsee K | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
539 | IIRM-2119 | Story | Implementing business logic for Manage TPA APIs - 1 | Done | Sai Vamsee K | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
540 | IIRM-2120 | Story | Implementing business logic for Manage TPA screens | Done | Sai Vamsee K | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
541 | IIRM-2121 | Story | Implementing business logic for Manage Insurer APIs - 1 | Done | Sai Vamsee K | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
542 | IIRM-2122 | Story | Implementing business logic for Manage Insurer screens | Done | Sai Vamsee K | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
543 | IIRM-2127 | Sub-task | API Development for List of the opportunity | Done | Sai Vamsee K | iWork | IIRM-2117 — API - Implementing business logic for Manage opportunity
544 | IIRM-2128 | Sub-task | Opportunity details page UI | Done | Sai Vamsee K | iWork | IIRM-2118 — Implementing business logic for Manage opportunity screens
545 | IIRM-2129 | Sub-task | Opportunity details page API integration | Done | Sai Vamsee K | iWork | IIRM-2118 — Implementing business logic for Manage opportunity screens
546 | IIRM-2131 | Sub-task | Create Opportunity(highlevel feilds as belowcomapny,contact,insurar,tpa,address,broker,detialsprevious policy details,mutiple challenges, from date , to date ,period, claim detial) | Done | Sai Vamsee K | iWork | IIRM-2118 — Implementing business logic for Manage opportunity screens
547 | IIRM-2132 | Sub-task | Reportee list | Done | Sai Vamsee K | iWork | IIRM-2118 — Implementing business logic for Manage opportunity screens
548 | IIRM-2133 | Sub-task | Analyse the KPI to fetch showcase the KPI data(companies,opportunity,primunm,sum insured) | Done | Sai Vamsee K | iWork | IIRM-2118 — Implementing business logic for Manage opportunity screens
549 | IIRM-2137 | Sub-task | Develop an functionality for the smart search | Done | Sai Vamsee K | iWork | IIRM-2118 — Implementing business logic for Manage opportunity screens
550 | IIRM-2145 | Sub-task | Modify the database table of TPA based on the spec. | Done | Sai Vamsee K | iWork | IIRM-2119 — Implementing business logic for Manage TPA APIs - 1
551 | IIRM-2146 | Sub-task | Update create TPA API. | Done | Sai Vamsee K | iWork | IIRM-2119 — Implementing business logic for Manage TPA APIs - 1
552 | IIRM-2147 | Sub-task | Implement the businness logic for the update TPA API. | Done | Sai Vamsee K | iWork | IIRM-2119 — Implementing business logic for Manage TPA APIs - 1
553 | IIRM-2148 | Sub-task | Update get list of contact and get TPA by id API | Done | Sai Vamsee K | iWork | IIRM-2119 — Implementing business logic for Manage TPA APIs - 1
554 | IIRM-2149 | Sub-task | Create TPA KPI to show | Done | Sai Vamsee K | iWork | IIRM-2119 — Implementing business logic for Manage TPA APIs - 1
555 | IIRM-2150 | Sub-task | Utiliy function for the gobal level search and filters for all the APIs | Done | Sai Vamsee K | iWork | IIRM-2119 — Implementing business logic for Manage TPA APIs - 1
556 | IIRM-2153 | Sub-task | Create quick TPA KPI cards to show counts and percentage(total contacts and total companies) | Done | Sai Vamsee K | iWork | IIRM-2120 — Implementing business logic for Manage TPA screens
557 | IIRM-2154 | Sub-task | modification of the create/edit TPA form | Done | Sai Vamsee K | iWork | IIRM-2120 — Implementing business logic for Manage TPA screens
558 | IIRM-2155 | Sub-task | Smart search implementation | Done | Sai Vamsee K | iWork | IIRM-2120 — Implementing business logic for Manage TPA screens
559 | IIRM-2156 | Sub-task | Create a common component for the Gobal level search (Contact nameCompany namePhone) and filter. | Done | Sai Vamsee K | iWork | IIRM-2120 — Implementing business logic for Manage TPA screens
560 | IIRM-2157 | Sub-task | update List of the TPA (Contact nameCompany namePhoneEmailDepartmentDesignationOwnerStatus) | Done | Sai Vamsee K | iWork | IIRM-2120 — Implementing business logic for Manage TPA screens
561 | IIRM-2158 | Sub-task | Create TPA details page(TPA NameDisplay NameCompany Type(Private/Public)WebsiteRemarksAddress TypeAddress (refer attributes table)) | Done | Sai Vamsee K | iWork | IIRM-2120 — Implementing business logic for Manage TPA screens
562 | IIRM-2160 | Sub-task | Modify the database table of Insurer based on the spec. | Done | Sai Vamsee K | iWork | IIRM-2121 — Implementing business logic for Manage Insurer APIs - 1
563 | IIRM-2161 | Sub-task | Update create Insurer API. | Done | Sai Vamsee K | iWork | IIRM-2121 — Implementing business logic for Manage Insurer APIs - 1
564 | IIRM-2162 | Sub-task | Implement the businness logic for the update Insurer API. | Done | Sai Vamsee K | iWork | IIRM-2121 — Implementing business logic for Manage Insurer APIs - 1
565 | IIRM-2163 | Sub-task | Update get list of Insurer and get Insurer by id API | Done | Sai Vamsee K | iWork | IIRM-2121 — Implementing business logic for Manage Insurer APIs - 1
566 | IIRM-2164 | Sub-task | Create Insurer KPI to show | Done | Sai Vamsee K | iWork | IIRM-2121 — Implementing business logic for Manage Insurer APIs - 1
567 | IIRM-2168 | Sub-task | Create quick Insurer KPI cards to show counts and percentage(total Insurers and total Insurers) | Done | Sai Vamsee K | iWork | IIRM-2122 — Implementing business logic for Manage Insurer screens
568 | IIRM-2169 | Sub-task | modification of the create/edit contact form | Done | Sai Vamsee K | iWork | IIRM-2122 — Implementing business logic for Manage Insurer screens
569 | IIRM-2170 | Sub-task | Smart search implementation | Done | Sai Vamsee K | iWork | IIRM-2122 — Implementing business logic for Manage Insurer screens
570 | IIRM-2171 | Sub-task | Create a common component for the Gobal level search (Contact nameCompany namePhoneStatus) and filter. | Done | Sai Vamsee K | iWork | IIRM-2122 — Implementing business logic for Manage Insurer screens
571 | IIRM-2172 | Sub-task | update List of the insurers (Company namePriority WebsiteIndustry SegmentDisplay nameAll the fields of potential opportunities sectionAll the fields of industry intelligence section) | Done | Sai Vamsee K | iWork | IIRM-2122 — Implementing business logic for Manage Insurer screens
572 | IIRM-2173 | Sub-task | Create insurers details page(Insurer nameInsurer BranchInsurer AddressCityStatePhoneEdit action) | Done | Sai Vamsee K | iWork | IIRM-2122 — Implementing business logic for Manage Insurer screens
573 | IIRM-2178 | Task | CLONE - QA - Company create/ update/ delete-2 | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
574 | IIRM-2179 | Task | Miscellanous - Tech Specs Walkthrough meeting | Done | Nikhil | iWork | IIRM-797 — SOW#69 - Manage Opportunities
575 | IIRM-2180 | Sub-task | Review and updated the TPA/Insurer/broker test cases | Done | SaikumarMahanthi | iWork | IIRM-1779 — QA - Lead Tasks
576 | IIRM-2181 | Task | API Testing: Prepare test scripts for Company hub | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
577 | IIRM-2182 | Bug | Company: API: Create company is not working | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
578 | IIRM-2183 | Bug | IIRM: Company: Company list view: Label displays 'Company Type' instead of 'Type' | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
579 | IIRM-2184 | Bug | IIRM: Company : Company list : Row selection cursor not appearing, default pointer shown instead | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
580 | IIRM-2185 | Bug | IIRM: Company : Search results do not match the entered search string | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
581 | IIRM-2186 | Bug | IIRM: Company : Quick cards: Company Quick Cards KPI count not updating based on data | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
582 | IIRM-2188 | Bug | IIRM: Company: Company list : In pagination we are not showing total count of company list. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
583 | IIRM-2189 | Bug | IIRM: Company : Create Company : Validation error on Date of Incorporation should not appear on first click of Create Company | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
584 | IIRM-2191 | Bug | IIRM: Company : Create company : Search in dropdown not visible when text entry is allowed | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
585 | IIRM-2192 | Bug | IIRM: Company : Create Company : GST : Empty GST fields should not get saved. | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
586 | IIRM-2193 | Bug | IIRM: Company : Create Company : GST : Instead of digits selected state and GST category should be shown | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
587 | IIRM-2194 | Bug | IIRM: Company : Create Company : View company details : Broker details displayed on View Company Details page despite not being added | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
588 | IIRM-2195 | Bug | IIRM : Company : Create Company : View company details page : Back navigation missing on Company Details page | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
589 | IIRM-2196 | Bug | IIRM: Create company : Validation error should only show for mandatory fields. | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
590 | IIRM-2197 | Bug | IIRM: Company : Create Company : Alphabetics should get restricted on phone number fields | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
591 | IIRM-2198 | Bug | IIRM:API: Company: Create company: Address update : Unable to update address with emails ID , thrown 400 on API response | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
592 | IIRM-2199 | Bug | IIRM: Company : Create Company : Reset functionality not working | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
593 | IIRM-2200 | Bug | IIRM: Company : Duplicate API calls triggered when clicking 'Cancel' on Create Company page | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
594 | IIRM-2201 | Bug | IIRM: Company : Back option : Back navigation not working as expected | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
595 | IIRM-2202 | Bug | IIRM: API: Contact: Contact view: Search functionality not working | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
596 | IIRM-2203 | Bug | IIRM: Contact: Quick cards CTA not working | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
597 | IIRM-2204 | Bug | IIRM: Contact: New Contact: ID's should not be shown on UI | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
598 | IIRM-2205 | Bug | IIRM: Contact: Create contact: Unable to create contact due to non-mandatory fields not being optional | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
599 | IIRM-2206 | Task | Company: API: Create Test scripts for Company Hub | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
600 | IIRM-2207 | Task | Contact: API: Create Test scripts for Contact Hub | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
601 | IIRM-2208 | Task | API Testing: Prepare test scripts for Add/Edit Contact | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
602 | IIRM-2209 | Task | user stories -meetings and tasks | Done | meghana | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
603 | IIRM-2210 | Story | Implementing business logic for the Employee -1 | Done | VedaVyas | iWork | IIRM-739 — SOW#12 - Manage Employees
604 | IIRM-2211 | Sub-task | Modify the employee create API based on the spec | Done | VedaVyas | iWork | IIRM-2210 — Implementing business logic for the Employee -1
605 | IIRM-2212 | Sub-task | Modify the employee update API based on the spec | Done | VedaVyas | iWork | IIRM-2210 — Implementing business logic for the Employee -1
606 | IIRM-2213 | Sub-task | Modify the TPA contact APIs | Done | VedaVyas | iWork | IIRM-2119 — Implementing business logic for Manage TPA APIs - 1
607 | IIRM-2214 | Sub-task | Modify the Insurar contact APIs | Done | VedaVyas | iWork | IIRM-2121 — Implementing business logic for Manage Insurer APIs - 1
608 | IIRM-2215 | Epic | Technical Debt | WORK IN PROGRESS | Gopal Gottumukkala | Framework
609 | IIRM-2216 | Story | Swagger - All services swagger docs to one accessible point | Done | Gopal Gottumukkala | Framework | IIRM-2215 — Technical Debt
610 | IIRM-2218 | Sub-task | UX- add, view, edit and list | Done | meghana | iWork | IIRM-1786 — UX/UI - Create/List and View TPA
611 | IIRM-2219 | Sub-task | UX/UI - Create/List and View Opportunity | Done | meghana | iWork | IIRM-1784 — UX/UI - Create/List and View Opportunity
612 | IIRM-2225 | Sub-task | UI- add, view, edit and list | Done | meghana | iWork | IIRM-1786 — UX/UI - Create/List and View TPA
613 | IIRM-2226 | QAlity Test | TPA Page: Manage TPA: UX: Verify that page design matches approved Figma screens | Draft | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
614 | IIRM-2227 | QAlity Test | TPA: Verify TPA Creation and verification in overview page,listpage and edit page | Draft | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
615 | IIRM-2232 | QAlity Test | TPA: Edit: Edit all permitted fields of the TPA | Draft | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
616 | IIRM-2235 | QAlity Test | TPA: Add: Appropriate validations and errors are displayed when invalid data is input during TPA creation | Draft | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
617 | IIRM-2236 | QAlity Test | TPA: Add: Appropriate error messages displayed when required inputs are missing during TPA creation | Draft | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
618 | IIRM-2238 | QAlity Test | TPA: Only authorized user can create a new TPA with only mandatory fields. | Draft | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
619 | IIRM-2239 | QAlity Test | TPA: Only authorized user can create a new TPA with all fields. | Draft | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
620 | IIRM-2246 | QAlity Test | TPA List: Table: Table operations should work properly (pagination, sorting, filters, resize, scrolling) | Draft | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
621 | IIRM-2252 | Bug | IIRM:API: Manage contact: Page refresh to load data on UI should not exceed 3secs | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
622 | IIRM-2264 | QAlity Test | TPA BrokerContact Page: Manage Contact: UX: Verify that page design matches approved Figma screens | Draft | Akhila Gattu | iWork
623 | IIRM-2268 | Bug | Company: API: Mapped Id values are not able to view(Values should be in String format) | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
624 | IIRM-2269 | QAlity Test | TPA_Insurer_Broker Contact: Add: Add contacts to TPA Companies. | Draft | Akhila Gattu | iWork
625 | IIRM-2270 | QAlity Test | Broker_Contact: Verify that user can create a Broker Contact for the selected Broker | Draft | Akhila Gattu | iWork
626 | IIRM-2271 | QAlity Test | Broker Contact: Add: Appropriate error messages displayed when required inputs are missing during Contact creation | Draft | Akhila Gattu | iWork
627 | IIRM-2274 | QAlity Test | TPA Contact: Edit: Authorized users can edit all permitted fields of the TPA Contact. | Draft | Akhila Gattu | iWork
628 | IIRM-2275 | QAlity Test | TPA Contact – Creation and Verification in Overview page,List page and Edit page . | Draft | Akhila Gattu | iWork
629 | IIRM-2277 | QAlity Test | TPA/Broker/Insurer Contact: Edit Verify that privileged user is able to edit all permitted fields | Draft | Akhila Gattu | iWork
630 | IIRM-2280 | QAlity Test | TPA_Insurer_Broker Contact: Search: Search for a contact on all supported search columns and edit details | Draft | Akhila Gattu | iWork
631 | IIRM-2282 | QAlity Test | TPA_Insurer_Broker Contact: Filter: filtered list should show based on the pagination count. | Draft | Akhila Gattu | iWork
632 | IIRM-2285 | QAlity Test | TPA_Insurer_Broker Contact: List: Sort order is preserved across pages | Draft | Akhila Gattu | iWork
633 | IIRM-2286 | QAlity Test | TPA_Contact: Create TPA Contact for each address of a TPA | Completed | Akhila Gattu | iWork
634 | IIRM-2288 | QAlity Test | Insurer_Contact: Verify that user can create a Insurer Contact for the selected Insurer | Draft | Akhila Gattu | iWork
635 | IIRM-2289 | QAlity Test | TPA BrokerContact Address: User should be able to residential address to TPA contact and that it can not be linked to TPA Company | Draft | Akhila Gattu | iWork
636 | IIRM-2292 | QAlity Test | TPA BrokerContact: Email: Send: Verify all active users should be able to send emails along with attachments using their own inbox. | Draft | Akhila Gattu | iWork
637 | IIRM-2293 | QAlity Test | TPA BrokerContact: Verify that region-specific data is exposed to the user dynamically | Draft | Akhila Gattu | iWork
638 | IIRM-2299 | QAlity Test | TPA Audit logs : All the events performance on TPA contact should be logged in chronological order. | Draft | Akhila Gattu | iWork
639 | IIRM-2300 | Bug | Company: API: The 'approverId' field should not be included in the payload when creating a company | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
640 | IIRM-2302 | QAlity Test | Insurer Page: Quick Cards: Correct data should get updated based on search and filter results | Draft | Akhila Gattu | iWork
641 | IIRM-2304 | QAlity Test | Insurer Page: Quick Cards: The count of Total Active Policies with Insurer is reflected in Quick Cards. | Draft | Akhila Gattu | iWork
642 | IIRM-2306 | QAlity Test | Insurer Page: Manage Insurer: UX: Verify that page design matches approved Figma screens | Draft | Akhila Gattu | iWork
643 | IIRM-2307 | QAlity Test | Insurer: Add: Verify that privillage user is able to add new Insurer | Draft | Akhila Gattu | iWork
644 | IIRM-2311 | QAlity Test | Insurer Creation: Verify in overview page,list page and edit page. | To Do | Akhila Gattu | iWork
645 | IIRM-2314 | QAlity Test | Insurer : Add: Appropriate validations and errors are displayed when invalid data is input during Insurer creation | To Do | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
646 | IIRM-2315 | QAlity Test | Insurer Contact : Add: Appropriate error messages displayed when required inputs are missing during Insurer Contact creation | Draft | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
647 | IIRM-2317 | QAlity Test | Insurer : Only authorized user can create a new Insurer with only mandatory fields. | Draft | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
648 | IIRM-2318 | QAlity Test | Insurer : Only authorized user can create a new Insurer with all fields. | Draft | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
649 | IIRM-2320 | QAlity Test | Insurer Record: Filter: Verify that correct data is retrieved based on the filter criteria across supported fields | Draft | Akhila Gattu | iWork
650 | IIRM-2325 | QAlity Test | Insurer List: Table: Table operations should work properly (draggable, pagination, sorting, filters, resize, scrolling) | Draft | Akhila Gattu | iWork
651 | IIRM-2327 | QAlity Test | Company Insurer : Authorized users are able to edit Insurers from list | Draft | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
652 | IIRM-2331 | Story | Implement business logic for the manage Broker APIs | Done | VedaVyas | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
653 | IIRM-2332 | Sub-task | Modify the Create Broker API based on the spec | Done | VedaVyas | iWork | IIRM-2331 — Implement business logic for the manage Broker APIs
654 | IIRM-2333 | Sub-task | Create and Modify Update and delete Broker API based on the spec | Done | VedaVyas | iWork | IIRM-2331 — Implement business logic for the manage Broker APIs
655 | IIRM-2334 | Sub-task | Create the Get broker and Get broker list APIs | Done | VedaVyas | iWork | IIRM-2331 — Implement business logic for the manage Broker APIs
656 | IIRM-2335 | Sub-task | Modify the Create and edit broker contact APIs accordingly to the spec | Done | VedaVyas | iWork | IIRM-2331 — Implement business logic for the manage Broker APIs
657 | IIRM-2337 | QAlity Test | Broker Page: Quick Cards: Correct data should get updated based on search and filter results | Draft | Akhila Gattu | iWork
658 | IIRM-2338 | QAlity Test | Broker Page: Quick Cards: The count of Total Active Brokers is reflected in Quick Cards | Draft | Akhila Gattu | iWork
659 | IIRM-2341 | QAlity Test | Broker Page: Manage Broker : UX: Verify that page design matches approved Figma screens | Draft | Akhila Gattu | iWork
660 | IIRM-2346 | QAlity Test | Broker : Edit: Edit details of a Broker from the filtered list | Draft | Akhila Gattu | iWork
661 | IIRM-2347 | QAlity Test | Insurer/Broker/TPA: Verify that privileged user can edit all permitted fields | Draft | Akhila Gattu | iWork
662 | IIRM-2350 | QAlity Test | Broker :Add: Appropriate error messages displayed when required inputs are missing during Broker creation | To Do | Akhila Gattu | iWork
663 | IIRM-2352 | QAlity Test | Broker :Only authorized user can create a new Broker with only mandatory fields. | Draft | Akhila Gattu | iWork
664 | IIRM-2354 | QAlity Test | Broker Record: Filter: Verify that correct data is retrieved based on the filter criteria across supported fields | Draft | Akhila Gattu | iWork
665 | IIRM-2356 | QAlity Test | Broker Record: Search: Verify that correct data is retrieved based on the search criteria across supported fields | Draft | Akhila Gattu | iWork
666 | IIRM-2363 | QAlity Test | Broker Creation: Verify in overview page,list page and edit page. | Draft | Akhila Gattu | iWork
667 | IIRM-2365 | Bug | Company: API: Correct the response body message when the group member ID does not exist | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
668 | IIRM-2366 | Bug | IIRM: Create Company: Newly created company appears in the middle of the list instead of at the beginning or end | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
669 | IIRM-2367 | Bug | IIRM: Create Company : Auto-generation interrupted when backspace is pressed during company name entry | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
670 | IIRM-2368 | Bug | IIRM: Company: Remove up/down arrow controls from DOI field as they are not used and affect user experience | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
671 | IIRM-2369 | Bug | IIRM: Create Company: Default text not centered within the input field | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
672 | IIRM-2370 | Bug | IIRM : Create company : Industry segment , Currency, Existing broker Dropdown selection causes overlapping of other fields | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
673 | IIRM-2371 | Bug | IIRM: Company: API : Company not created within the Remarks text Limit | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
674 | IIRM-2372 | Bug | IIRM:Company: API: Inconsistent key[StatusCode, Status] in response body | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
675 | IIRM-2373 | Bug | Company: API: Company creation is successful even when an invalid "companyTypeLid" is provided | Done - Not Reproducible | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
676 | IIRM-2374 | Task | Contact Test data Documentation | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
677 | IIRM-2375 | Task | Repo clone and Go through the code of iWork | Done | Gundam Sree Sahithi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
678 | IIRM-2376 | Sub-task | Requirement breakdown and Prepare Test scenarios for RBAC | Done | SaikumarMahanthi | iWork | IIRM-1779 — QA - Lead Tasks
679 | IIRM-2377 | Bug | Company: API: "503 - Error: Service Unavailable" message is received while creating a company | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
680 | IIRM-2378 | Bug | Company: UI:Company is not created with all required fields | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
681 | IIRM-2379 | Bug | IIRM: Add company could be within manage company | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
682 | IIRM-2381 | Bug | IIRM: Company: FR Comp15 and FR Comp 17 - search combination criteria is needed | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
683 | IIRM-2382 | Bug | IIRM: Company : FR Comp 27 sort functionality for each column within the company list is needed. Right now only the company column has it. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
684 | IIRM-2383 | Bug | IIRM: FR Comp 30 - Status -Active or Inactive(deleted) - Field is required (however it is only for specific users , ideally Managers and functional admins - it is needed and missing) | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
685 | IIRM-2384 | Bug | IIRM: Company: FR Comp 37 - From Company name drill down - Sales opportunity, renewal opportunity and policies and their respective fields should be here : refer attached image | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
686 | IIRM-2385 | Bug | IIRM: Company : FR Comp 37 Insurer broker TPA sections and fields - associated with the respective above opportunities (no.6) should be displayed | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
687 | IIRM-2386 | Bug | IIRM: Company : Document upload and document view functionality is missing | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
688 | IIRM-2387 | Bug | IIRM: Company : FR Comp 46 - +add button for adding multiple company contacts, SO , Insurer, Broker, TPA is needed within edit functionality of company. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
689 | IIRM-2388 | Bug | IIRM: Company: FR Comp 48 - Bulk upload button to upload a list of companies is missing and needed | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
690 | IIRM-2389 | Bug | IIRM: Company: FR comp 51 - From edit journey certain fields should be uneditable - refer FRCOMP51 . Right now , it is allowing the user to edit, Please change that. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
691 | IIRM-2390 | Bug | IIRM: Company : FR comp 53 should be considered for no.7 FR Comp 37 | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
692 | IIRM-2391 | Bug | IIRM: Company : Type , Tag , Priority and Industry Segment should be mandatory - refer 6.1 | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
693 | IIRM-2392 | Bug | IIRM: Company : In priority field IMP and LOW are missing refer 6.1 attributes table priority field. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
694 | IIRM-2393 | Bug | IIRM: Company : No. of employees, Date of Incorporation, Registration number are mandatory but they should be optional - refer 6.1 attributes table | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
695 | IIRM-2394 | Bug | IIRM: Company : Date of Incorporation - Still able to select future date . Flagging that. Please change | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
696 | IIRM-2395 | Bug | IIRM: Company : Annual Premium field is missing, Paid up capital should be taken out (not necessary). | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
697 | IIRM-2396 | Bug | IIRM: Company : Address type should be mandatory, Country should be mandatory , country LOVS missing and none within dropdown. State field is missing. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
698 | IIRM-2397 | Bug | IIRM: Company : Category field in GST section has following field e.g, GST , IGST, CGST refer 6.3 in company | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
699 | IIRM-2398 | Bug | Company: API: Not able to create a company through API | Done - Not Reproducible | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
700 | IIRM-2399 | Bug | IIRM: Company: API: Pincode is not automatically validated based on the selected State and City. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
701 | IIRM-2400 | Bug | IIRM: Company : Character count validation for Display Name does not match the required limit | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
702 | IIRM-2401 | Bug | IIRM: Company : Company Name field accepts more than 200 characters, exceeding the defined character limit. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
703 | IIRM-2403 | Bug | IIRM : Company : Registration number field allows only strict format (U12345AB1234PLC123456); throws error if any character deviates | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
704 | IIRM-2404 | Bug | IIRM: Company : Edit & Updated Functionality is not working | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
705 | IIRM-2405 | Bug | IIRM : Company : Unable to add new GST details during the company update process | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
706 | IIRM-2406 | Bug | IIRM: Update Company : Call-to-Action (CTA) button not functioning for Mail option | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
707 | IIRM-2407 | QAlity Test | SO: Create: Verify by creating opty from all entry points | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
708 | IIRM-2408 | QAlity Test | SO: Create :Verify that users can create a Sales Opportunity using the direct link from the Manage Opportunities | Completed | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
709 | IIRM-2409 | QAlity Test | SO: Create :Verify that users can create a Sales Opportunity from the Contact Detail page | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
710 | IIRM-2410 | Bug | Contact: Smart Search is not functioning on the Manage Contact page | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
711 | IIRM-2411 | Bug | Contact: Missing drill-down functionality for Company Name on Manage Contact page | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
712 | IIRM-2412 | Bug | Contact: Missing SO, RO, Policies, Whatsapp redirections are not implemneted in Contact details screen | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
713 | IIRM-2414 | Bug | Contact: WhatsApp button along with redirection is missing | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
714 | IIRM-2415 | Bug | Contact: Button(+add) is missing for adding multiple children within add personal contact information | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
715 | IIRM-2416 | Bug | IIRM: Contact: UI: Status -Active or Inactive(deleted) - Field (only for specific users , ideally Managers and functional admins is needed and missing) | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
716 | IIRM-2417 | Bug | Company/Contact: API are Failing Periodically | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
717 | IIRM-2418 | QAlity Test | So: Link company and company contact to new sales opportunities | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
718 | IIRM-2419 | QAlity Test | SO: Tags: Policy Type: Attach and Detach policy type Tage, a) Previous broker b) Previous Insurance company c) Previous TPA | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
719 | IIRM-2421 | QAlity Test | Opportunity: Edit Verify that privileged user is able to edit all permitted fields | Completed | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
720 | IIRM-2422 | QAlity Test | SO: List: Verify display, pagination, and sorting functionality of the Opportunities | To Do | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
721 | IIRM-2424 | QAlity Test | SO: Quick cards: company count: Verify correct data should get updated on Quick cards | To Do | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
722 | IIRM-2425 | QAlity Test | SO: Quick cards: SO count: Verfiy correct lost opty data is displayed | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
723 | IIRM-2426 | Task | Broker API: Prepare the test script for Broker API | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
724 | IIRM-2428 | QAlity Test | Manage.SO: Smart Search and table settings | To Do | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
725 | IIRM-2430 | Sub-task | Analyse and develop the create employee API | Done | VedaVyas | iWork | IIRM-1928 — Implementing business logic for Manage Employee APIs
726 | IIRM-2431 | QAlity Test | Manage SO: All Opty owned by the current user of the list | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
727 | IIRM-2432 | Sub-task | Analyse and create the list of employee API | Done | VedaVyas | iWork | IIRM-1928 — Implementing business logic for Manage Employee APIs
728 | IIRM-2434 | Sub-task | Analyse and create the update API for employee edit | Done | VedaVyas | iWork | IIRM-1928 — Implementing business logic for Manage Employee APIs
729 | IIRM-2435 | QAlity Test | Manage SO: Seach list columns: Each column captures correct data | To Do | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
730 | IIRM-2437 | Sub-task | Build screen to display the list of employee | Done | VedaVyas | iWork | IIRM-1929 — Implementing business logic for Manage Employee screens
731 | IIRM-2439 | Sub-task | Build the employee details page | Done | VedaVyas | iWork | IIRM-1929 — Implementing business logic for Manage Employee screens
732 | IIRM-2440 | QAlity Test | SO: Filter: Verify filter operations as per functionality | To Do | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
733 | IIRM-2441 | Sub-task | Build the employee create and update | Done | VedaVyas | iWork | IIRM-1929 — Implementing business logic for Manage Employee screens
734 | IIRM-2442 | QAlity Test | SO: Sort:Verify sort operations of all supported fields as per functionality | To Do | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
735 | IIRM-2443 | Sub-task | Update the test cases for the contact | Done | SaikumarMahanthi | iWork | IIRM-2116 — CLONE - QA: Contact Test case & test data documentation-2
736 | IIRM-2444 | QAlity Test | SO: Add: Verify that the system allows the complete creation of a new Sales Opportunity with all required linkages and default stage settings | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
737 | IIRM-2445 | Sub-task | Insurer API Testing: Test case Execution | Done | SaikumarMahanthi | iWork | IIRM-1965 — QA - Add/Manage Insurer
738 | IIRM-2448 | Sub-task | Review and updated Opportunity test cases | Done | SaikumarMahanthi | iWork | IIRM-1779 — QA - Lead Tasks
739 | IIRM-2452 | QAlity Test | SO: Mark SO as lost | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
740 | IIRM-2453 | Bug | IIRM: Manage Company: Search functionality not working as expected. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
741 | IIRM-2454 | QAlity Test | SO: View sales funnel based on stage or brokerage based on the filters selected. | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
742 | IIRM-2456 | Bug | API: Duplicate Role Details Returned in Login API Response | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
743 | IIRM-2457 | Bug | API: Security Concern – User Details Exposed in Login API Response | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
744 | IIRM-2459 | QAlity Test | SO: Drilldown: Verify that clicking on the Policy Type field drills down and navigates to the Opportunity Detail page | Completed | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
745 | IIRM-2461 | QAlity Test | SO: Details: Edit Fileds | Completed | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
746 | IIRM-2707 | Bug | Contact: Display name should be a combination of First Name and Last Name on the Add Contact screen | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
747 | IIRM-2709 | Bug | Contact: UI issues | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
748 | IIRM-2710 | Bug | IIRM: Contact: Relationship field is missing on the Add Contact screen | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
749 | IIRM-2711 | Bug | Contact: Not all cities are displayed based on selected Country and State | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
750 | IIRM-2712 | Bug | Contact: Missing LinkedIn profile field in the Create Contact form | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
751 | IIRM-2713 | Bug | Contacts: IDs are displayed instead of names in address fields | Done - Not Reproducible | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
752 | IIRM-2714 | Bug | Contact: Confirmation popup should be displayed before deleting a record on the Add Contact screen | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
753 | IIRM-2716 | Bug | IIRM: Contact: Sort functionality is not working on the Manage Contact screen | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
754 | IIRM-2718 | Bug | Contact: Remove Display Name and Tag columns from the Manage Contact list | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
755 | IIRM-2720 | Sub-task | UX/UI - Integrated flow for Opportunity - contacts and company | Done | Nandini Kataria | iWork | IIRM-1784 — UX/UI - Create/List and View Opportunity
756 | IIRM-2721 | Bug | Contact: Link functionality to select Company Address for Contact is missing | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
757 | IIRM-2722 | Bug | Contact: Functionality to add multiple Email and Phone number records is missing | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
758 | IIRM-2723 | Sub-task | Integrated flow of contacts | Done | Nandini Kataria | iWork | IIRM-1495 — UX/UI - Manage Contact
759 | IIRM-2724 | Sub-task | UI for adding, editing and viewing contact | Done | Nandini Kataria | iWork | IIRM-1495 — UX/UI - Manage Contact
760 | IIRM-2725 | Story | FR-COMP-01 As a user, I want to access the Manage Company page, so that I can view various sections such as Company Quick Cards, Company Search, and Company List. | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
761 | IIRM-2726 | Story | FR-COMP-02 As a user, I want to add, edit, and search company records, so that I can manage company data as per the application functionality. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
762 | IIRM-2727 | Story | FR-COMP-03 As a user, I should not be able to delete company records to maintain data integrity. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
763 | IIRM-2728 | Story | FR-COMP-04 As a user, I want to see Company Quick Cards categorized into My Leads, My Prospects, QCR, and My Clients, so that I can have an overview of different categories of companies. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
764 | IIRM-2729 | Story | FR-COMP-05 As a user, I want to view only the records I created or those created by users reporting to me, so that I can focus on relevant data. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
765 | IIRM-2730 | Story | FR-COMP-06 As a user, I want to filter the company records to view only the records I created or those created by users reporting to me, so that I can easily access relevant information. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
766 | IIRM-2731 | Story | FR-COMP-07 As a user, I want to see the name/owner of company records created by users reporting to me, so that I can identify who created a particular record. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
767 | IIRM-2732 | Story | FR-COMP-08 As a user, I want the My Leads quick card to show the count of companies with at least one sales opportunity that has not completed the meeting with KDM stage, so that I can track leads effectively. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
768 | IIRM-2733 | Story | FR-COMP-09 As a user, I want the My Prospects card to show the count of companies with at least one active sales opportunity that has completed the meeting with KDM stage, so that I can track prospects effectively. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
769 | IIRM-2734 | Story | FR-COMP-10 As a user, I want the QCR card to show the count of companies with at least one active sales opportunity that has completed the QCR stage, so that I can track quality checks effectively. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
770 | IIRM-2735 | Story | FR-COMP-11 As a user, I want the My Clients card to show the count of companies that have at least one active policy, so that I can track my active clients effectively. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
771 | IIRM-2736 | Bug | Contacts: Drill-down functionality for each record is missing | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
772 | IIRM-2737 | Story | FR-COMP-12 As a user, I want to see the total count of company records on all quick cards, so that I can have an overall view of the company records. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
773 | IIRM-2738 | Story | FR-COMP-13 As a user, I want to see the percentage of records shown in each quick card, so that I can understand the distribution of records across categories. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
774 | IIRM-2739 | Story | FR-COMP-14 As a user, I want the quick cards to reflect the counts based on the company records shown in the company list section, so that the counts are always accurate according to the displayed records. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
775 | IIRM-2740 | Story | FR-COMP-15 As a user, I want to filter company records based on search criteria in the Company Search section, so that I can narrow down the displayed results effectively. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
776 | IIRM-2741 | Story | FR-COMP-16 As a user, I want to search company records using various fields (Company name, Company type, Industry, Priority, City), so that I can retrieve relevant information easily. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
777 | IIRM-2742 | Story | FR-COMP-17 As a user, I want to view all company records in the Company List section, so that I can access the data relevant to the application functionality. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
778 | IIRM-2743 | Story | FR-COMP-18 As a user, I want to see the Company List within my scope of access | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
779 | IIRM-2744 | Story | FR-COMP-19 As a user, I want to see the details of each company record in the Company List section, so that I can quickly access relevant information. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
780 | IIRM-2745 | Story | FR-COMP-20 As a user, I want to view only the count of active sales opportunities in the Company List section, so that I can track active opportunities effectively. | Draft | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
781 | IIRM-2746 | Story | FR-COMP-21 As a user, I want to view only the count of active renewal opportunities in the Company List section, so that I can track renewal opportunities effectively. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
782 | IIRM-2747 | Story | FR-COMP-22 As a user, I want to view only the count of active policies in the Company List section, so that I can track active policies effectively. | Draft | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
783 | IIRM-2748 | Story | FR-COMP-23 As a user, I want to view the total sum insured for each company in the Company List section, so that I can track the insurance value accurately. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
784 | IIRM-2749 | Story | FR-COMP-24 As a user, I want to view the total annual premium for each company in the Company List section, so that I can track the premium value accurately. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
785 | IIRM-2750 | Story | FR-COMP-25 As a user, I want the Company List section to use pagination, so that I can easily navigate through a large number of records. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
786 | IIRM-2751 | Story | FR-COMP-26 As a user, I want to click on a company name in the Company List section to view its detailed information, so that I can easily access specific company details. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
787 | IIRM-2752 | Story | FR-COMP-27 As a user, I want to sort the records displayed in the Company List section, so that I can view the data in a preferred order. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
788 | IIRM-2753 | Story | FR-COMP-28 As a user, I want different colors to highlight the priority of company records in the Company List section, so that I can quickly identify high-priority records. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
789 | IIRM-2754 | Story | FR-COMP-29 As a user, I want to create a new company record, so that I can add company details to the system. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
790 | IIRM-2755 | Story | FR-COMP-30 As a user(applicable to limited users), I want to set the status of a company to Active, Deleted, or Under Review, so that I can manage the status of companies accurately. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
791 | IIRM-2756 | Story | FR-COMP-31 As a user, I want to prevent transactions from being created for companies marked as 'Under Review,' so that only approved companies can have related transactions. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
792 | IIRM-2758 | Story | FR-COMP-33 As a user, I want to approve companies marked as 'Under Review' so that they can be made active and usable in the system. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
793 | IIRM-2759 | Story | FR-COMP-34 As a user, I want to reject companies marked as 'Under Review' with a reason, so that inappropriate companies are not added to the system. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
794 | IIRM-2760 | Story | FR-COMP-35 As a user, I want to ensure companies marked as 'Deleted' are not displayed in the Company List section, so that only relevant companies are visible. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
795 | IIRM-2761 | Story | FR-COMP-36 As a user, I want to enter all the details while creating a new company, so that the company record is comprehensive and accurate. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
796 | IIRM-2762 | Story | FR-COMP-37 As a user, I want to view all the sections of company details, so that I can access all relevant information about a company. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
797 | IIRM-2763 | Story | FR-COMP-38 As a user, I want to create or edit records for various sections in company details, so that the information remains accurate and updated. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
798 | IIRM-2764 | Story | FR-COMP-39 As a user, I want to drill down from various sections of company details to their respective entities, so that I can view more detailed information. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
799 | IIRM-2765 | Story | FR-COMP-40 As a user, I want to view a portfolio overview of active policies, so that I can see the sum insured, premium amounts, and renewal calendar for the company. | Draft | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
800 | IIRM-2766 | Story | FR-COMP-41 As a user, I want to navigate to Tracxn from the specific company record, so that I can view company details within the Tracxn application. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
801 | IIRM-2767 | Story | FR-COMP-42 As a user, I want to see all incoming and outgoing mails related to a company, so that I can have a complete communication history. | Draft | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
802 | IIRM-2768 | Story | FR-COMP-43 As a user, I want the system to hide or display fields based on the country of the logged-in user, so that irrelevant fields are not shown. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
803 | IIRM-2769 | Story | FR-COMP-44 As a user, I want to upload relevant documents with appropriate document type segregation, so that files are organized properly. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
804 | IIRM-2770 | Story | FR-COMP-45 As a user, I want the system to pull data from external applications like ChatGPT based on the industry segment of the company, so that I can have relevant insights and suggestions. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
805 | IIRM-2771 | Story | FR-COMP-46 As a user, I want to add multiple records for specific sections (Company Contacts, Company Address, Sales Opportunity, Insurer, Broker, TPA, Documents), so that I can have comprehensive records for a company. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
806 | IIRM-2772 | Story | FR-COMP-47 As a user, I want to change the status of a company to 'Deleted' only if there are no active related transactions, so that data integrity is maintained. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
807 | IIRM-2773 | Story | FR-COMP-48 As a user, I want to upload company records in bulk from an Excel file, so that I can add multiple records efficiently. | Open | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
808 | IIRM-2774 | Story | FR-COMP-49 The system should have all the fields that are present in the iwork application and in the prototype application in addition to the specific fields mentioned in the requirements, if any. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
809 | IIRM-2775 | Story | FR-COMP-50 As a user, I want to see all company records with visibility controlled by ownership, so that I can view only the relevant records. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
810 | IIRM-2776 | Story | FR-COMP-51 As a user, I want to edit all company fields except restricted ones, so that sensitive data remains unchanged. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
811 | IIRM-2777 | Story | FR-COMP-52 As a user, I want the system to automatically populate the company display name based on the data entered in the company name, so that data entry is streamlined. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
812 | IIRM-2778 | Story | FR-COMP-53 As a user, I want to enter multiple records for insurers, brokers, and TPAs along with their policy types, so that I can maintain accurate relationships for each company. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
813 | IIRM-2779 | Story | FR-COMP-54 As a user, I want the system to tag the owner of a company as Lead CRM, so that the ownership structure is accurately reflected. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
814 | IIRM-2780 | Story | FR-Cntc-01 As a user, I should have access to the "Manage Contact" page that displays the Contact Quick Card, Contact Search, and Contact List sections. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
815 | IIRM-2781 | Story | FR-Cntc-02 As a user, I should be able to add, edit, and search contact records on the "Manage Contact" page. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
816 | IIRM-2782 | Story | FR-Cntc-03 As a user(limited), I should be able to make a contact inactive. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
817 | IIRM-2783 | Story | FR-Cntc-04 As a user, I should not be allowed to delete contact records | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
818 | IIRM-2784 | Story | FR-Cntc-05 As a user, I should not be allowed to create or edit a contact record without linking it to a company. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
819 | IIRM-2785 | Story | FR-Cntc-06 As a user, I should only see contacts that are linked with a valid company. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
820 | IIRM-2786 | Story | FR-Cntc-07 As a user, I should not be able to add a contact to a company that is under review. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
821 | IIRM-2787 | Story | FR-Cntc-08 As a user, I should see quick card metrics for total contacts and total companies in the "Manage Contact" page. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
822 | IIRM-2788 | Story | FR-Cntc-09 As a user, I should only see contacts that I own or those owned by my subordinates. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
823 | IIRM-2789 | Story | FR-Cntc-10 As a user, I should be able to filter contact records based on user ownership (logged-in user or subordinate). | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
824 | IIRM-2790 | Story | FR-Cntc-11 As a user, I should be able to view the contact owner’s name for subordinate-owned contact records. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
825 | IIRM-2791 | Story | FR-Cntc-12 As a user, I should see a quick card displaying the total number of contacts owned by me. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
826 | IIRM-2792 | Story | FR-Cntc-13 As a user, I should see a quick card displaying the total number of unique companies associated with contacts owned by me. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
827 | IIRM-2793 | Story | FR-Cntc-14 As a user, the quick card counts should update dynamically when filters are applied in the contact list. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
828 | IIRM-2794 | Story | FR-Cntc-15 As a user, I should be able to search for contacts by name, company, phone, and status. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
829 | IIRM-2795 | Story | FR-Cntc-16 As a user, I should be able to search for contacts using fields like contact name, company name, phone number, and status. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
830 | IIRM-2796 | Story | FR-Cntc-17 As a user, I should be able to search using multiple fields at once (e.g., name and company). | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
831 | IIRM-2797 | Story | FR-Cntc-18 As a user, I should be able to paginate through the contact list for better navigation. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
832 | IIRM-2798 | Story | FR-Cntc-19 As a user, I should be able to sort contact records by fields like name, company, phone, and status. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
833 | IIRM-2799 | Story | FR-Cntc-20 As a user, I should see contact details like name, company, phone, and email in the contact list. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
834 | IIRM-2800 | Story | FR-Cntc-21 As a user, I should be able to view a table displaying all the necessary attributes for a contact. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
835 | IIRM-2801 | Story | FR-Cntc-22 As a user, I should be able to link a contact to a company address when creating or editing a contact. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
836 | IIRM-2802 | Story | FR-Cntc-23 As a user, I should be able to add a new address for a contact under the linked company. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
837 | IIRM-2803 | Story | FR-Cntc-24 As a user, I should not be able to add duplicate addresses for a company when linking contacts. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
838 | IIRM-2804 | Story | FR-Cntc-25 As a user, I should be able to add a residential address separately from the business address for a contact. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
839 | IIRM-2805 | Story | FR-Cntc-26 As a user, I should be able to drill down into a contact's name in the contact list for more details. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
840 | IIRM-2806 | Story | FR-Cntc-27 As a user, I should be able to drill down into a company’s name to view detailed company information. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
841 | IIRM-2807 | Story | FR-Cntc-28 As a user, I should receive a notification when a contact’s information has been updated. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
842 | IIRM-2808 | Story | FR-Cntc-29 As a user, I should be able to view detailed sections of a contact's profile, including contact details, company details, multiple emails, phone numbers, and associated opportunities. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
843 | IIRM-2809 | Story | FR-Cntc-30 As a user, I should be able to view a contact's LinkedIn profile directly from their contact detail page. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
844 | IIRM-2810 | Story | FR-Cntc-31 As a user, I should be able to click on a contact's email in their contact detail page to open my email client with the contact’s email pre-populated in the "To" field. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
845 | IIRM-2811 | Story | FR-Cntc-32 As a user, I should be able to edit existing contact records for all sections (contact details, company, email, phone). | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
846 | IIRM-2812 | Story | FR-Cntc-33 As a user, I should be able to drill down into other entities (e.g., related sales opportunities, documents) from the contact detail page. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
847 | IIRM-2813 | Story | FR-Cntc-34 As a user, I should be able to view and hide certain fields based on the country of the logged-in user. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
848 | IIRM-2814 | Story | FR-Cntc-35 As a user, I should be able to add multiple records for contact details such as phone numbers, email addresses, and addresses. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
849 | IIRM-2815 | Story | FR-Cntc-36 As a user, I should be able to view all contact records, but access will be controlled based on ownership, as defined by the role-based access control (RBAC) system. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
850 | IIRM-2816 | Story | FR-Cntc-37 As a user, I should be able to make a contact inactive when it is delinked from a company. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
851 | IIRM-2817 | Story | FR-Cntc-38 As a user, I should be able to link an inactive contact back to a company. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
852 | IIRM-2818 | Story | FR-Cntc-39 As a user, I should be able to make an inactive contact active again when it is linked back to a company. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
853 | IIRM-2819 | Story | FR-Cntc-40 As a user, I should be able to change the company of an active contact. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
854 | IIRM-2820 | Story | FR-Cntc-41 As a user, I should be able to click on a contact’s phone number and open WhatsApp to send a message directly to the contact. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
855 | IIRM-2821 | Story | FR-Cntc-42 As a user, I should be able to capture the type of communication (e.g., email, call) for all outbound communication done with a contact. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
856 | IIRM-2822 | Story | FR-Cntc-43 As a system, I should be able to identify duplicate contacts based on the contact’s phone number within the same company. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
857 | IIRM-2823 | Story | FR-SO-01 As a user, I should be able to create sales opportunities from various sources, including the company and contact detail pages. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
858 | IIRM-2824 | Story | FR-SO-02 As a user, I should be able to create a new sales opportunity directly from the Sales Opportunity section in the company detail page. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
859 | IIRM-2825 | Story | FR-SO-03 As a user, I should be able to create a new sales opportunity directly from the Sales Opportunity section in the contact detail page. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
860 | IIRM-2826 | Story | FR-SO-04 As a user, I should be able to view the manage sales opportunity page, which includes the sales funnel graph, funnel effectiveness graph, opportunity quick cards, opportunity search, and opportunity list. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
861 | IIRM-2827 | Story | FR-SO-05 As a user, I should be able to add, edit, or search existing sales opportunity records from the manage opportunity page. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
862 | IIRM-2828 | Story | FR-SO-06 As a user, I should be able to view a sales funnel graph that shows the stage-wise distribution of sales opportunities versus brokerage percentage. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
863 | IIRM-2829 | Story | FR-SO-07 As a user, I should be able to create a new sales opportunity and link it to an existing account. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
864 | IIRM-2830 | Story | FR-SO-08 As a user, I should be able to create a new sales opportunity within the system. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
865 | IIRM-2831 | Story | FR-SO-09 As a user, I should be able to link a company and its associated contact while creating a new sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
866 | IIRM-2832 | Story | FR-SO-10 As a user, I should be able to select the contact name, address location, department, and designation while creating a new sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
867 | IIRM-2833 | Story | FR-SO-11 As a user, I should be able to use all the fields available in the iWork application and the Wireframe application, in addition to the specific fields mentioned in the document, when creating or managing a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
868 | IIRM-2834 | Story | FR-SO-12 As a user, I should be able to tag a policy type to a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
869 | IIRM-2835 | Story | FR-SO-13 As a user, I should be able to tag the previous insurance company, address location, and branch to a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
870 | IIRM-2836 | Story | FR-SO-14 As a user, I should be able to tag the previous broker company, address location, and branch to a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
871 | IIRM-2837 | Story | FR-SO-15 As a user, I should be able to tag the previous Third Party Administrator (TPA), company, address location, and branch to a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
872 | IIRM-2838 | Story | FR-SO-16 As a user, I should be able to select multiple address types (e.g., official, personal) for the company when creating a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
873 | IIRM-2839 | Story | FR-SO-17 As a user, I should be able to add previous policy and claim details of the company when creating a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
874 | IIRM-2840 | Story | FR-SO-18 As a user, I should be able to add various document types (e.g., contracts, reports) for the company when creating a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
875 | IIRM-2841 | Story | FR-SO-19 As a user, I should be able to add multiple challenges to a new sales opportunity upon its creation | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
876 | IIRM-2842 | Story | FR-SO-20 As a user, I should be able to view a quick card showing the count of companies based on sales opportunities that are neither won nor lost. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
877 | IIRM-2843 | Story | FR-SO-21 As a user, I should be able to view an opportunity card showing the count of sales opportunities that are neither won nor lost. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
878 | IIRM-2844 | Story | FR-SO-22 As a user, I should be able to view a Premium card showing the total premium from sales opportunities that are neither won nor lost. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
879 | IIRM-2845 | Story | FR-SO-23 As a user, I should be able to view a Sum Insured card showing the total sum insured from sales opportunities that are neither won nor lost. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
880 | IIRM-2846 | Story | FR-SO-24 As a user, I should be able to search for sales opportunities based on the value selected in one or more search fields. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
881 | IIRM-2847 | Story | FR-SO-25 As a user, I should be able to view all sales opportunity records in the company list section, based on the record display functionality and ownership settings. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
882 | IIRM-2848 | Story | FR-SO-26 As a user, I should be able to view the following details of the company in the sales opportunity search list: Company name, Priority, From Date, To Date, Period, Branch, Industry Segment, Assigned To, Activity, Stage, Contact. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
883 | IIRM-2849 | Story | FR-SO-27 As a user, I should be able to use the opportunity creation date to automatically populate the fields "From Date", "To Date", and "Period" for a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
884 | IIRM-2850 | Story | FR-SO-28 As a user, I should see my own name (self record) and the names of the users who report to me in the "Assigned To" field. If no users report to me, this field should remain empty. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
885 | IIRM-2851 | Story | FR-SO-29 As a user, I should be able to view a sales opportunity list that includes the following details: Company Name, Policy Type, Activity Name, Stage, Priority, Opportunity Creation Date, Assigned To, Branch, Expected Close Date, Premium, Sum Insu... | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
886 | IIRM-2852 | Story | FR-SO-30 As a user, I should be able to view the priority of the company linked to a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
887 | IIRM-2853 | Story | FR-SO-31 As a user, I should be able to click on the company field in the sales opportunity and be navigated directly to the company detail page. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
888 | IIRM-2854 | Story | FR-SO-32 As a user, I should be able to click on the Policy Type field and be navigated directly to the Opportunity detail page. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
889 | IIRM-2855 | Story | FR-SO-33 As a user, I should be able to click on the Contact field and navigate directly to the Contact detail page. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
890 | IIRM-2856 | Story | FR-SO-34 As a user, I should be able to navigate through the sales opportunity list using pagination when there are many records. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
891 | IIRM-2857 | Story | FR-SO-35 As a user, I should be able to view detailed information about a sales opportunity, including company, priority, contact, policy type, sum insured, premium, stage, status, expiry date, and related details (e.g., risk locations, claim details, ... | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
892 | IIRM-2858 | Story | FR-SO-36 As a user, I should be able to enter multiple records for related risk locations, claim details, documents, insurers, brokers, TPA, and challenges when creating or managing a sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
893 | IIRM-2859 | Story | FR-SO-37 As a user, I should be able to edit all the fields of a sales opportunity if its stage is set to "under planning." | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
894 | IIRM-2860 | Story | FR-SO-38 As a user, I should be able to capture the company's previous claim ratio details, including policy duration, nature of loss, premium, claim amount, and have the system automatically calculate the claim percentage. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
895 | IIRM-2861 | Story | FR-SO-39 As a user, I should be able to view a graphical representation of the Sales Funnel and Funnel Effectiveness on the dashboard. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
896 | IIRM-2862 | Story | FR-SO-40 As a user, I should not have the ability to delete a sales opportunity record in the system. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
897 | IIRM-2863 | Story | FR-SO-41 As a user, I should only be able to see sales opportunity records that I created or the records of users who report to me. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
898 | IIRM-2864 | Story | FR-SO-42 As a user, I should be able to filter records to view only those created by me or those of users who report to me. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
899 | IIRM-2865 | Story | FR-SO-43 As a user, I should be able to see the name or owner of the sales opportunity record for the records created by users reporting to me. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
900 | IIRM-2866 | Story | FR-SO-44 As a user, I should be able to see the updated count of records in various graphs and quick cards (e.g., sales funnel, funnel effectiveness, client CSAT score) as per the filtered records shown in the sales opportunity list. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
901 | IIRM-2867 | Story | FR-SO-45 As a user, I should be able to filter sales opportunity records in the sales opportunity list section based on the search criteria selected in the sales opportunity search section. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
902 | IIRM-2868 | Story | FR-SO-46 As a user, I should be able to sort the records displayed in the sales opportunity list section based on the fields shown in the list. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
903 | IIRM-2869 | Story | FR-SO-47 As a user, I should be able to mark a sales opportunity as lost if the stage is not "policy confirmation" and the expiry date has passed. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
904 | IIRM-2870 | Story | FR-SO-48 As a user, I should be able to delete a sales opportunity by selecting a mandatory deletion reason. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
905 | IIRM-2871 | Story | FR-SO-49 As a user, I should be able to automatically assign the "under planning" stage when creating a new sales opportunity. | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
906 | IIRM-2872 | Story | FR-TPA-01 As a user, I want to view the Manage TPA page, which should display sections for Quick Cards, Search, and List, so that I can easily navigate through TPA details. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
907 | IIRM-2873 | Story | FR-TPA-02 As a user, I want to see Quick Cards displaying total active TPAs and total active policies with TPAs, so that I can get an overview of the TPA data at a glance. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
908 | IIRM-2874 | Story | FR-TPA-03 As a user, I want to add, edit, and search TPA records, so that I can manage TPA data efficiently. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
909 | IIRM-2875 | Story | FR-TPA-04 As a user, I should not be able to delete a TPA record to maintain data integrity. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
910 | IIRM-2876 | Story | FR-TPA-05 As a user, I want to view a list of all TPAs with pagination, so that I can browse through all available TPAs. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
911 | IIRM-2877 | Story | FR-TPA-06 As a user, I want to search for TPA records by TPA name, so that I can quickly find a specific TPA. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
912 | IIRM-2878 | Story | FR-TPA-07 As a user, I want the TPA list to display relevant details like TPA name, address, city, state, and phone, so that I can quickly access key information about each TPA. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
913 | IIRM-2879 | Story | FR-TPA-08 As a user, I want to drill down on a TPA name to view all active policies linked to the TPA, so that I can see policy details such as Policy Number, Policy Type, Start Date, End Date, Sum Insured, and Premium. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
914 | IIRM-2880 | Story | FR-TPA-09 As a user, I want to add a new TPA record, so that I can create new TPA entries in the system. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
915 | IIRM-2881 | Story | FR-TPA-10 As a user, I want to provide details for the new TPA, such as TPA name, display name, company type, website, and address, so that I can accurately input TPA information. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
916 | IIRM-2882 | Story | FR-TPA-11 As a user, I want to update, edit, or delete addresses for a TPA, so that I can maintain accurate address records. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
917 | IIRM-2883 | Story | FR-TPA-12 As a user, I want to add contacts to a TPA record, so that I can link relevant contact information to the TPA. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
918 | IIRM-2884 | Story | FR-TPA-13 As a user, I want the system to ensure data integrity with duplicate checks during TPA record creation, so that I do not enter duplicate TPAs. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
919 | IIRM-2885 | Story | FR-INS-01 As a user, I want to view the Manage Insurer page, which should display sections for Quick Cards, Search, and List, so that I can efficiently manage Insurer data. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
920 | IIRM-2886 | Story | FR-INS-02 As a user, I want to see Quick Cards displaying total active Insurers and total active policies with Insurers, so that I can easily get an overview of the Insurer data. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
921 | IIRM-2887 | Story | FR-INS-03 As a user, I want to add, edit, and search Insurer records, so that I can manage Insurer data. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
922 | IIRM-2888 | Story | FR-INS-04 As a user, I should not be able to delete an Insurer record to preserve data integrity. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
923 | IIRM-2889 | Story | FR-INS-05 As a user, I want to view a list of all Insurers with pagination, so that I can browse through all available Insurers. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
924 | IIRM-2890 | Story | FR-INS-06 As a user, I want to search for Insurer records by name or tag (e.g., General, Preferred), so that I can quickly locate a specific Insurer. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
925 | IIRM-2891 | Story | FR-INS-07 As a user, I want the Insurer list to show relevant details like Insurer name, branch, address, and phone, so that I can easily manage Insurer information. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
926 | IIRM-2892 | Story | FR-INS-08 As a user, I want to drill down into an Insurer record to view all active policies linked to it, so that I can see detailed policy information such as policy number, type, and premium. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
927 | IIRM-2893 | Story | FR-INS-09 As a user, I want to add a new Insurer record, so that I can create new entries in the system. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
928 | IIRM-2894 | Story | FR-INS-10 As a user, I want to provide details for the new Insurer, such as Insurer name, display name, company type, and website, so that I can add accurate information. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
929 | IIRM-2895 | Story | FR-INS-11 As a user, I want to update or edit Insurer addresses, so that I can maintain accurate contact information. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
930 | IIRM-2896 | Story | FR-INS-12 As a user, I want to add contacts to the Insurer record, so that I can link relevant people or departments to the Insurer. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
931 | IIRM-2897 | Story | FR-INS-13 As a user, I want the system to check for duplicate Insurer records during creation to ensure data integrity. | Done | Sai Vamsee K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
932 | IIRM-2898 | Story | FR-BRO-01 As a user, I want to view the Manage Broker page, which should display sections for Quick Cards, Search, and List, so that I can efficiently manage Broker records. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
933 | IIRM-2899 | Story | FR-BRO-02 As a user, I want to see Quick Cards displaying the total number of Brokers, so that I can get an overview of the Brokers in the system. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
934 | IIRM-2900 | Story | FR-BRO-03 As a user, I want to add, edit, and search Broker records, so that I can manage Broker data effectively. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
935 | IIRM-2901 | Story | FR-BRO-04 As a user, I should not be able to delete a Broker record to maintain data integrity. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
936 | IIRM-2902 | Story | FR-BRO-05 As a user, I want to view a list of all Brokers with pagination, so that I can browse through all available Brokers. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
937 | IIRM-2903 | Story | FR-BRO-06 As a user, I want to search for Broker records by name, so that I can quickly locate a specific Broker. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
938 | IIRM-2904 | Story | FR-BRO-07 As a user, I want the Broker list to show relevant details like Broker name, branch, address, and phone, so that I can easily manage Broker information. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
939 | IIRM-2905 | Story | FR-BRO-08 As a user, I want to drill down on a Broker name to view all active policies linked to it, so that I can see detailed policy information. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
940 | IIRM-2906 | Story | FR-BRO-09 As a user, I want to add a new Broker record, so that I can create new entries in the system. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
941 | IIRM-2907 | Story | FR-BRO-10 As a user, I want to provide details for the new Broker, such as Broker name, display name, company type, and website, so that I can accurately input Broker information. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
942 | IIRM-2908 | Story | FR-BRO-11 As a user, I want to update or edit Broker addresses, so that I can maintain accurate contact information. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
943 | IIRM-2909 | Story | FR-BRO-12 As a user, I want the system to ensure data integrity with duplicate checks during Broker record creation, so that duplicate Brokers are not added. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
944 | IIRM-2910 | Story | FR-01 As a user, I want to access the respective contact management pages for TPA, Insurer, and Broker, where I can view contact details, search, and filter contacts. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
945 | IIRM-2911 | Story | FR-02 As a user, I want to add, edit, and search contact records for TPA, Insurer, and Broker. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
946 | IIRM-2912 | Story | FR-03 As a user, I want to mark a contact as inactive when it's no longer needed. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
947 | IIRM-2913 | Story | FR-04 As a user, I want the system to prevent the deletion of a contact. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
948 | IIRM-2914 | Story | FR-05 As a user, I want to link a contact with a TPA, Insurer, or Broker company when creating or editing contact information. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
949 | IIRM-2915 | Story | FR-06 As a user, I want the system to display only those contacts that are linked to the respective company (TPA, Insurer, Broker). | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
950 | IIRM-2916 | Story | FR-07 As a user, I want to see quick cards displaying the total number of contacts and companies for TPA, Insurer, and Broker. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
951 | IIRM-2917 | Story | FR-08 As a user, I want the quick card counts to update when I filter the contact list using search criteria. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
952 | IIRM-2918 | Story | FR-09 As a user, I want to filter TPA, Insurer, or Broker contacts by selected search criteria. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
953 | IIRM-2919 | Story | FR-10 As a user, I want the search section to include fields such as Contact Name, Company Name, and Tags. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
954 | IIRM-2920 | Story | FR-11 As a user, I want the ability to search using a combination of multiple criteria. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
955 | IIRM-2921 | Story | FR-12 As a user, I want the contact list to use pagination to handle large volumes of records. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
956 | IIRM-2922 | Story | FR-13 As a user, I want to sort the contact list by various fields (e.g., Name, Company, Status). | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
957 | IIRM-2923 | Story | FR-14 As a user, I want the contact list to display fields such as Contact Name, Company Name, Phone, Email, Department, and Designation. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
958 | IIRM-2924 | Story | FR-15 N/A | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
959 | IIRM-2925 | Story | FR-16 As a user, I want to link company addresses to contacts. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
960 | IIRM-2926 | Story | FR-17 As a user, I want to add a new address for a contact if it's not already added under the linked company. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
961 | IIRM-2927 | Story | FR-18 As a user, I want the system to prevent the creation of duplicate addresses for a contact linked to a TPA, Insurer, or Broker company. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
962 | IIRM-2928 | Story | FR-19 As a user, I want the ability to enter a residential address for a contact separately from the company address. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
963 | IIRM-2929 | Story | FR-20 As a user, I want to drill down into the contact name in the contact list to see detailed information for TPA, Insurer, or Broker contacts. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
964 | IIRM-2930 | Story | FR-21 As a user, I want to drill down into the company name in the contact list to see respective detailed company information for TPA, Insurer, or Broker. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
965 | IIRM-2931 | Story | FR-22 As a user, I should be able to enter all the required details when creating a new contact, including contact details, company details, and multiple communication methods (email, phone). | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
966 | IIRM-2932 | Story | FR-23 As a user, I want to view the contact details sections, which should include contact details, company details, multiple email details, multiple phone numbers, and contact address. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
967 | IIRM-2933 | Story | FR-24 As a user, I want to click on the contact’s email in the contact details and have it open the default email client with the contact’s email pre-filled in the "To" field. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
968 | IIRM-2934 | Story | FR-25 As a user, I should be able to create a new record or edit an existing contact’s information for all sections in the contact details. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
969 | IIRM-2935 | Story | FR-26 As a user, I want to drill down into various entities from the contact detail page, such as the company, sales opportunities, or related activities. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
970 | IIRM-2936 | Story | FR-27 As a user, I want the system to hide or display certain fields based on the country of the logged-in user. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
971 | IIRM-2937 | Story | FR-28 As a user, I want the system to allow adding multiple records for email, phone, and address in the contact details. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
972 | IIRM-2938 | Story | FR-29 As a user, I want the system to automatically make the contact inactive when it is delinked from the company. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
973 | IIRM-2939 | Story | FR-30 As a user, I want to be able to link inactive contacts back to a company. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
974 | IIRM-2940 | Story | FR-31 As a user, I want the system to activate a contact when it is linked to a company after being inactive. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
975 | IIRM-2941 | Story | FR-32 As a user, I want to be able to change the company of an active contact. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
976 | IIRM-2942 | Story | FR-33 As a user, I want to click on a contact’s phone number to open WhatsApp and send a message. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
977 | IIRM-2943 | Story | FR-34 As a user, I want the system to capture the type of communication for all outbound communications done with a contact. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
978 | IIRM-2944 | Story | FR-35 As a user, I want the system to identify duplicate contacts based on the contact’s phone number within the same company. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
979 | IIRM-2945 | Story | FR-36 As a user, I want the system to provide an audit trail for contact creation, editing, and communication logs. | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
980 | IIRM-2946 | Story | 1. Add Employee to the System (Super Admin)-As a Super Admin, I want to add a new employee to the system, so that they can be assigned roles and designations. | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
981 | IIRM-2947 | Story | 2. Assign Role to an Employee (Functional Admin)-As a Functional Admin, I want to assign a role to an employee, so that their access privileges can be controlled | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
982 | IIRM-2948 | Story | 3. Modify Role of Employee (Super Admin)-As a Super Admin, I want to modify the role of an employee to update their access privileges as required. | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
983 | IIRM-2949 | Story | 4. Assign Designation to Employee (Super Admin/Functional Admin)-As a Super Admin or Functional Admin, I want to assign a designation to an employee, so that their position within the organizational hierarchy is defined. | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
984 | IIRM-2950 | Story | 5.Create and Manage Organizations (Super Admin)-As a Super Admin, I want to create and manage organizations within the system, so that I can define the business entities within the company. | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
985 | IIRM-2951 | Story | 6. Create and Manage Departments (Super Admin/Functional Admin)-As a Super Admin or Functional Admin, I want to create and manage departments within an organization, so that employees can be grouped based on their business line. | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
986 | IIRM-2952 | Story | 7. Assign Employees to Branches (Super Admin/Functional Admin)-As a Super Admin or Functional Admin, I want to assign employees to branches within the organization, so that they can be mapped to a physical location or region. | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
987 | IIRM-2953 | Story | 8. Role-Based Access Control (RBAC) Enforcement (Super Admin/Functional Admin)-As a Super Admin or Functional Admin, I want to enforce role-based access control (RBAC) for employees, ensuring they can only access data that is appropriate for their role. | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
988 | IIRM-2954 | Story | 9. Audit Role and Access Modifications (Super Admin)-As a Super Admin, I want to maintain an audit log of all role and access modifications, so that I can track changes for security and compliance purposes. | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
989 | IIRM-2955 | Story | 10. Grant/Revoking Cross-Organization/Department Access (Super Admin/Functional Admin)-As a Super Admin or Functional Admin, I want to grant or revoke cross-organization or cross-department access to employees, so that their data access scope can be ad... | Done | Sai Vamsee K |  | IIRM-739 — SOW#12 - Manage Employees
990 | IIRM-2956 | Bug | Contact: Duplicate contact validation is missing while creating a new contact | Reopen | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
991 | IIRM-2957 | Bug | FR-03: Contact: Active or Inactive- Field (only for specific users , ideally Managers and functional admins is needed and missing) | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
992 | IIRM-2958 | Bug | Contact: Newly created contacts are not listed in the Reporting To/Assign Id dropdown | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
993 | IIRM-2959 | Sub-task | Updated feedback changes and insights from IIRM client meeting | Done | Nandini Kataria | iWork | IIRM-1495 — UX/UI - Manage Contact
994 | IIRM-2960 | Bug | IIRM: Create Company : Validation Error Message Not Clearing Automatically After Field Input | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
995 | IIRM-2961 | Sub-task | View with edit of basic data, with lists of companies | Done | Manjusha Paritala | iWork | IIRM-813 — Manage TPA Contact
996 | IIRM-2962 | Story | Insurer: Duplicate TPA& Address verifcation not happing | Done | Manjusha Paritala | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
997 | IIRM-2963 | Bug | Contact: Table column order is changeable | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
998 | IIRM-2964 | Sub-task | View with edit of basic data, with lists of companies | Done | Manjusha Paritala | iWork | IIRM-2962 — Insurer: Duplicate TPA& Address verifcation not happing
999 | IIRM-2965 | Sub-task | Basic Add and edit of basic data, with lists of companies | Done | Manjusha Paritala | iWork | IIRM-2962 — Insurer: Duplicate TPA& Address verifcation not happing
1000 | IIRM-2966 | Sub-task | Prepare Test Cases for Add / Edit Contact Screen | Done | Sai Vamsee K | iWork | IIRM-1801 — Prepare Test cases for Add/ Edit Contact Screen
1001 | IIRM-2967 | Bug | IIRM: Employee: Mismatch Between UI Validation Errors and API Response Errors | Done | Akhila Gattu | iWork | IIRM-739 — SOW#12 - Manage Employees
1002 | IIRM-2969 | Bug | IIRM: Employee: Search functionality not working as expected. | Done | Akhila Gattu | iWork | IIRM-739 — SOW#12 - Manage Employees
1003 | IIRM-2972 | Bug | IIRM: Employee: System allows self-assign as reporting manager during employee update | Done | Akhila Gattu | iWork | IIRM-739 — SOW#12 - Manage Employees
1004 | IIRM-2973 | Bug | IIRM: Employee: Mobile number field should not accepts non-numeric characters on paste | Done | Akhila Gattu | iWork | IIRM-739 — SOW#12 - Manage Employees
1005 | IIRM-2974 | Sub-task | UI components and stitching of the flows | Done | Nandini Kataria | iWork | IIRM-1784 — UX/UI - Create/List and View Opportunity
1006 | IIRM-2975 | Sub-task | UX- Manage Company | Done | gowtham | iWork | IIRM-14 — UX/UI - Create/List and View Company
1007 | IIRM-2976 | QAlity Test | IIRM: Employee: Quick cards, Search and list view functionality | Draft | Akhila Gattu | iWork
1008 | IIRM-2977 | Sub-task | Integrated flow | Done | gowtham | iWork | IIRM-1495 — UX/UI - Manage Contact
1009 | IIRM-2978 | Story | UX Design | Done | gowtham | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1010 | IIRM-2979 | Task | UX Design | Done | gowtham | iWork | IIRM-739 — SOW#12 - Manage Employees
1011 | IIRM-2980 | Sub-task | UX Design | Done | Sai Vamsee K | iWork | IIRM-2978 — UX Design
1012 | IIRM-2981 | Sub-task | Feedback changes | Done | gowtham | iWork | IIRM-1784 — UX/UI - Create/List and View Opportunity
1013 | IIRM-2982 | Sub-task | Feedback changes | Done | gowtham | iWork | IIRM-14 — UX/UI - Create/List and View Company
1014 | IIRM-2990 | Bug | Insurer: API: Incorrect response message displayed | Done | Leela Pakalapati | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1015 | IIRM-2991 | Bug | Insurer: API: address2 field is missing in Create insurer Request Body but presented in Get insurer response body | Done | Leela Pakalapati | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1016 | IIRM-2993 | Bug | Insurer: Autofilll display name not happening | Done | SaikumarMahanthi | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1017 | IIRM-2995 | Bug | Insurer: Contact linking functionality is not implemented with the insurer | Done | SaikumarMahanthi | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1018 | IIRM-2997 | Bug | IIRM: Insurer: Active Policy linking functionality is not there | Done | SaikumarMahanthi | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1019 | IIRM-2999 | Bug | Contact: Date is incorrectly displayed on Edit Contact screen after saving | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1020 | IIRM-3000 | Bug | Contact: Year of Qualification field auto-fills by default on creating, and Address2 value is not retained on Edit form | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1021 | IIRM-3002 | Sub-task | Update the test cases & Import into JIRA | Done | SaikumarMahanthi | iWork | IIRM-1965 — QA - Add/Manage Insurer
1022 | IIRM-3003 | Task | QA - Add/Manage Broker | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1023 | IIRM-3004 | Sub-task | Brocker: API: Creating API test scripts | Done | SaikumarMahanthi | iWork | IIRM-3003 — QA - Add/Manage Broker
1024 | IIRM-3005 | Sub-task | Brocker: API: Preparing Test Data | Done | SaikumarMahanthi | iWork | IIRM-3003 — QA - Add/Manage Broker
1025 | IIRM-3006 | Sub-task | Regression Testing on Company & Contact Module | Done | SaikumarMahanthi | iWork | IIRM-1779 — QA - Lead Tasks
1026 | IIRM-3007 | Bug | IIRM: Company : Company details page | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1027 | IIRM-3008 | Bug | IIRM: Company : Company update : PAN and embedded PAN in GSTIN not matching during input validation | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1028 | IIRM-3019 | Bug | IIRM: "Cancel button missing on Company Creation UI | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1029 | IIRM-3020 | Bug | IIRM: Company : Acquisition History and Service Performance data is not getting stored while and updating | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1030 | IIRM-3021 | Bug | IIRM : Create/ Update Company bugs | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1031 | IIRM-3022 | Bug | IIRM: Company : Add company: Date of Incorporation should not accept with current date. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1032 | IIRM-3023 | Bug | IIRM : Company : Create / Update company : No copy-paste is allowed in the entire application. | Open | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1033 | IIRM-3026 | Task | UI screens for opportunity - an integrated flow with cases | Done | Nandini Kataria | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1034 | IIRM-3027 | Sub-task | Review with IIRM team | Done | Nandini Kataria | iWork | IIRM-3026 — UI screens for opportunity - an integrated flow with cases
1035 | IIRM-3030 | Bug | IIRM : TPA contact : Create TPA contact Bugs | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1036 | IIRM-3031 | Bug | TPA: Creating TPA | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1037 | IIRM-3032 | Bug | IIRM: SO: Opportunities bugs | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1038 | IIRM-3033 | Bug | IIRM : Company : Create Company : Source and Address 1fields allows input beyond character limit without showing validation error | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1039 | IIRM-3035 | Bug | IIRM : Contact: Create contact bugs | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1040 | IIRM-3036 | Bug | IIRM: Broker: Failed to create Broker/Broker Contact | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1041 | IIRM-3037 | Bug | TPA: Manage TPA | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1042 | IIRM-3038 | Bug | TPA: Creating TPA | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1043 | IIRM-3039 | Bug | IIRM : Manage Broker: Pressing Enter in Search Field Resets Results Instead of Maintaining Filter. | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1044 | IIRM-3040 | Bug | IIRM : Broker : Contact Broker Address Appears in Manage Broker Details | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1045 | IIRM-3041 | Bug | IIRM: Broker Contact: Residence Address of Company Broker Should Not Be Linkable in Contact Broker Page | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1046 | IIRM-3046 | Bug | Company: API: API allows company creation with an invalid ID | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1047 | IIRM-3048 | Bug | IIRM: Create contact :Company Selection in Create Contact Flow Redirects to Error Page | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1048 | IIRM-3049 | Bug | IIRM: Company : Company details view is not displayed | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1049 | IIRM-3050 | Bug | IIRM: Broker/TPA/Insurer contact: Create contact fails -communication error | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1050 | IIRM-3052 | QAlity Test | TPA Page: Manage TPA: Verify the pagination functionality | Draft | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1051 | IIRM-3053 | Bug | IIRM : Company : Create company :Self Company Displayed When 'Group Company' Option is Set to Yes | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1052 | IIRM-3054 | Bug | IIRM : Company : Manage company issues | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1053 | IIRM-3056 | Bug | IIRM : Add Broker contact : Personal Address from Manage Broker Should Not Link in Add Broker Contact | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1054 | IIRM-3057 | Bug | IIRM : Opportunities: Updated Sum Assured and Annual Premium via Opportunities Not Reflecting on Company Profile | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1055 | IIRM-3059 | Story | Add / Manage Insurer | Done | Sai Vamsee K | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1056 | IIRM-3060 | Story | Add / Manage Broker | Done | Sai Vamsee K | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1057 | IIRM-3061 | Sub-task | Add / Manage Insurer | Done | Sai Vamsee K | iWork | IIRM-3059 — Add / Manage Insurer
1058 | IIRM-3062 | Bug | IIRM: Company : Accepting invalid URL on Website | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1059 | IIRM-3063 | Task | Prepare Test data documentation Employee | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1060 | IIRM-3064 | Task | IIRM:TPA/Insurer/broker Sanity testing | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1061 | IIRM-3065 | Task | IIRM: Contact : Bug fixes Verification and Regression Testing | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1062 | IIRM-3066 | Task | IIRM: API: Automation Scripst for Company & Contact features | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1063 | IIRM-3067 | Task | IIRM: TPA : Bug fixes Verification and Regression Testing | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1064 | IIRM-3068 | Task | IIRM: Prepare & Update Test artifacts for milestoneOne features | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1065 | IIRM-3069 | Task | IIRM: Bug fixes verification and Regression Testing Insurer/Insurer Contact | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1066 | IIRM-3070 | Task | IIRM: Bug fixes verification and Regression Testing Broker/Broker Contact | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1067 | IIRM-3071 | Task | IIRM: Update the Test cycle with latest results and link the Open bugs to respective test cases | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1068 | IIRM-3072 | Task | IIRM: Create Test data for TPA/TPA Contact | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1069 | IIRM-3073 | Sub-task | Insurer test data documentation | Done | SaikumarMahanthi | iWork | IIRM-1779 — QA - Lead Tasks
1070 | IIRM-3074 | Task | IIRM: Update the Test data for Company and Contact creation | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1071 | IIRM-3173 | QAlity Test | TPA Contact:Status : Inactive TPA contacts are linked with the TPA company and also delink TPA contacts from TPA Company | Draft | Leela Pakalapati | iWork
1072 | IIRM-3174 | Task | IIRM: Import & update the Test case for TPA/Insurer/Broker | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1073 | IIRM-3175 | Task | IIRM: Imoprt & update the contact and Insurer/broker/TPA test cases | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1074 | IIRM-3176 | Task | IIRM: Prepare Insurer and Contact Insurer Test data | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1075 | IIRM-3177 | Task | IIRM: Prepare Broker/Contact Broker Test data | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1076 | IIRM-3178 | Story | Manage Company | Done | Sai Vamsee K | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1077 | IIRM-3180 | Sub-task | Company details styling | Done | Sai Vamsee K | iWork | IIRM-3178 — Manage Company
1078 | IIRM-3181 | Sub-task | Company listing styling | Done | Sai Vamsee K | iWork | IIRM-3178 — Manage Company
1079 | IIRM-3182 | Sub-task | Company create/edit updates and styling | Done | Sai Vamsee K | iWork | IIRM-3178 — Manage Company
1080 | IIRM-3183 | Sub-task | API Tweaks for Company Work flow | Done | Sai Vamsee K | iWork | IIRM-3178 — Manage Company
1081 | IIRM-3185 | Story | UI - Manage Contact Updates | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1082 | IIRM-3186 | Sub-task | Contact listing styling | Done | Sai Vamsee K | iWork | IIRM-3185 — UI - Manage Contact Updates
1083 | IIRM-3187 | Sub-task | Contact create/edit updates and styling | Done | Sai Vamsee K | iWork | IIRM-3185 — UI - Manage Contact Updates
1084 | IIRM-3188 | Sub-task | Contact details styling | Done | Sai Vamsee K | iWork | IIRM-3185 — UI - Manage Contact Updates
1085 | IIRM-3189 | Sub-task | API Tweaks for Create Contact Work flow | Done | Sai Vamsee K | iWork | IIRM-3405 — API - Manage Contacts Update
1086 | IIRM-3190 | Sub-task | API Tweaks for Update Contact Work flow | Done | Sai Vamsee K | iWork | IIRM-3405 — API - Manage Contacts Update
1087 | IIRM-3191 | Story | UI - Manage Insurer/TPA/Broker | Done | Sai Vamsee K | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1088 | IIRM-3192 | Sub-task | Insurer/TPA/Broker listing styling | Done | Sai Vamsee K | iWork | IIRM-3191 — UI - Manage Insurer/TPA/Broker
1089 | IIRM-3193 | Sub-task | Insurer/TPA/Broker create/edit updates and styling | Done | Sai Vamsee K | iWork | IIRM-3546 — UI - Manage TPA/Broker/Insurer - Test
1090 | IIRM-3194 | Sub-task | Insurer/TPA/Broker details styling | Done | Sai Vamsee K | iWork | IIRM-3191 — UI - Manage Insurer/TPA/Broker
1091 | IIRM-3195 | Sub-task | API Tweaks for Insurer Work flow | Done | Sai Vamsee K | iWork | IIRM-3406 — API - Manage Insurer , TPA, Broker
1092 | IIRM-3196 | Sub-task | API Tweaks for TPA Work flow | Done | Sai Vamsee K | iWork | IIRM-3406 — API - Manage Insurer , TPA, Broker
1093 | IIRM-3197 | Sub-task | API Tweaks for Broker Work flow | Done | Sai Vamsee K | iWork | IIRM-3406 — API - Manage Insurer , TPA, Broker
1094 | IIRM-3198 | Story | Manage Employee | Done | Sai Vamsee K | iWork | IIRM-739 — SOW#12 - Manage Employees
1095 | IIRM-3199 | Sub-task | API Tweaks for Employee Work flow | Done | Sai Vamsee K | iWork | IIRM-3198 — Manage Employee
1096 | IIRM-3200 | Sub-task | Employee List and Details styling | Done | Sai Vamsee K | iWork | IIRM-3198 — Manage Employee
1097 | IIRM-3201 | Sub-task | Employee create/edit updates and styling | Done | Sai Vamsee K | iWork | IIRM-3198 — Manage Employee
1098 | IIRM-3203 | Story | Common Module | Done | Sai Vamsee K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1099 | IIRM-3204 | Sub-task | Develop Global level style classess as per Designs | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1100 | IIRM-3205 | Sub-task | Smart Filter UI Tweaks and Implementation | Done | Sai Vamsee K | iWork | IIRM-3402 — Common Stepper and Smart Search
1101 | IIRM-3206 | Sub-task | Create Header menu | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1102 | IIRM-3207 | Sub-task | Design system - Grid, Based on UI Designs | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1103 | IIRM-3208 | Sub-task | Grid settings and functional implementations | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1104 | IIRM-3209 | Sub-task | Design system - Text Input and Rich Text | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1105 | IIRM-3210 | Sub-task | Create Side bar along with Icons As per Design | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1106 | IIRM-3211 | Sub-task | Design system - Select Dropdown | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1107 | IIRM-3212 | Sub-task | Design system - Breadcrumb, RadioButtons and Buttons | Done | Sai Vamsee K | iWork | IIRM-3402 — Common Stepper and Smart Search
1108 | IIRM-3213 | Sub-task | Design system - Stepper with Progress Indications | Done | Sai Vamsee K | iWork | IIRM-3402 — Common Stepper and Smart Search
1109 | IIRM-3214 | Sub-task | Design system - Toggle, Tabs, KPI cards and Cards | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1110 | IIRM-3215 | Sub-task | Tweak Common function to get the list from the entities based on the filters and RBAC | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1111 | IIRM-3216 | Sub-task | API - File Uploading Tweaks | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1112 | IIRM-3217 | Sub-task | Smart Search and Sort for Grid data API Update | Done | Sai Vamsee K | iWork | IIRM-3203 — Common Module
1113 | IIRM-3219 | Story | BD Stages - UX/UI | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1114 | IIRM-3220 | Story | ISG Stages - UX/UI | Done | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1115 | IIRM-3221 | Sub-task | UX - Validating data collected from the company | Done | Sai Vamsee K | iWork | IIRM-3219 — BD Stages - UX/UI
1116 | IIRM-3222 | Sub-task | UX - KDM Meeting | Done | Sai Vamsee K | iWork | IIRM-3219 — BD Stages - UX/UI
1117 | IIRM-3223 | Sub-task | UX - Company gives a mandate that IIRM can contact insurers behalf of the company for any kind of policy or a specific policy and date | Done | Sai Vamsee K | iWork | IIRM-3219 — BD Stages - UX/UI
1118 | IIRM-3224 | Sub-task | UX - Enter details given by the company in the RFP | Done | Sai Vamsee K | iWork | IIRM-3219 — BD Stages - UX/UI
1119 | IIRM-3225 | Sub-task | UI - Validating data collected from the company | Done | Sai Vamsee K | iWork | IIRM-3219 — BD Stages - UX/UI
1120 | IIRM-3226 | Sub-task | UI - KDM Meeting | Done | Sai Vamsee K | iWork | IIRM-3219 — BD Stages - UX/UI
1121 | IIRM-3227 | Sub-task | UI - Company gives a mandate that IIRM can contact insurers behalf of the company for any kind of policy or a specific policy and date | Done | Sai Vamsee K | iWork | IIRM-3219 — BD Stages - UX/UI
1122 | IIRM-3228 | Sub-task | UI - Enter details given by the company in the RFP | Done | Sai Vamsee K | iWork | IIRM-3219 — BD Stages - UX/UI
1123 | IIRM-3229 | Sub-task | UX - Generate Broking Slip by adding all the covers and other details | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1124 | IIRM-3230 | Sub-task | UX - Enter quotes received from insurers - multiple quotes by single or multiple insurers | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1125 | IIRM-3231 | Sub-task | UX - Generate a Quote comparison report | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1126 | IIRM-3232 | Sub-task | UX - Schedule a meeting with insurers for final negotiation | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1127 | IIRM-3233 | Sub-task | UX - Generate placement slip to share it with the insurer | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1128 | IIRM-3234 | Sub-task | UX - Calculation of premium and entering employees details | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1129 | IIRM-3235 | Sub-task | UI - Generate Broking Slip by adding all the covers and other details | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1130 | IIRM-3236 | Sub-task | UI - Enter quotes received from insurers - multiple quotes by single or multiple insurers | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1131 | IIRM-3237 | Sub-task | UI - Generate a Quote comparison report | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1132 | IIRM-3238 | Sub-task | UI - Schedule a meeting with insurers for final negotiation | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1133 | IIRM-3239 | Sub-task | UI - Generate placement slip to share it with the insurer | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1134 | IIRM-3240 | Sub-task | UI - Calculation of premium and entering employees details | Done | Sai Vamsee K | iWork | IIRM-3220 — ISG Stages - UX/UI
1135 | IIRM-3241 | Task | Design Solutioning for Manage Opportunitites & RBAC | Done | Sai Vamsee K | iWork | IIRM-18 — SOW#1 - ACL & RBAC Control
1136 | IIRM-3242 | Sub-task | Design Solutioning for Manage Opportunities | Done | Sai Vamsee K | iWork | IIRM-3241 — Design Solutioning for Manage Opportunitites & RBAC
1137 | IIRM-3243 | Sub-task | Design Solutioning for RBAC | Done | Sai Vamsee K | iWork | IIRM-3241 — Design Solutioning for Manage Opportunitites & RBAC
1138 | IIRM-3244 | Story | Design- Manage Tasks & Meetings | Done | Sai Vamsee K | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
1139 | IIRM-3245 | Sub-task | UX - Manage Tasks & Meetings | Done | Sai Vamsee K | iWork | IIRM-3244 — Design- Manage Tasks & Meetings
1140 | IIRM-3246 | Sub-task | UI - Manage Tasks & Meetings | Done | Sai Vamsee K | iWork | IIRM-3244 — Design- Manage Tasks & Meetings
1141 | IIRM-3248 | Task | Milestone 2 Product Spec (Manage Opty, Approvals, Sales Hierarchy, User Management, AI Smart Ads) | Done | Sai Vamsee K | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1142 | IIRM-3249 | Sub-task | Test data documentation with latest changes | Done | SaikumarMahanthi | iWork | IIRM-3178 — Manage Company
1143 | IIRM-3250 | Sub-task | API Test script for both positive and negative cases | Done | SaikumarMahanthi | iWork | IIRM-3178 — Manage Company
1144 | IIRM-3251 | Sub-task | Executing API &Bug logging | Done | SaikumarMahanthi | iWork | IIRM-3178 — Manage Company
1145 | IIRM-3252 | Sub-task | Upated UI Test cases | Done | SaikumarMahanthi | iWork | IIRM-3178 — Manage Company
1146 | IIRM-3254 | Sub-task | Test data documentation | Done | SaikumarMahanthi | iWork | IIRM-3405 — API - Manage Contacts Update
1147 | IIRM-3255 | Sub-task | API Test scrpit preparation | Done | SaikumarMahanthi | iWork | IIRM-3185 — UI - Manage Contact Updates
1148 | IIRM-3256 | Sub-task | API Test cases & Scripts Execution | Done | SaikumarMahanthi | iWork | IIRM-3185 — UI - Manage Contact Updates
1149 | IIRM-3257 | Sub-task | UI Test cases update with latest changes | Done | SaikumarMahanthi | iWork | IIRM-3185 — UI - Manage Contact Updates
1150 | IIRM-3258 | Sub-task | UI-Test execution | Done | SaikumarMahanthi | iWork | IIRM-3185 — UI - Manage Contact Updates
1151 | IIRM-3259 | Sub-task | Test Data documentation | Done | SaikumarMahanthi | iWork | IIRM-3191 — UI - Manage Insurer/TPA/Broker
1152 | IIRM-3260 | Sub-task | Test script preparation | Done | SaikumarMahanthi | iWork | IIRM-3546 — UI - Manage TPA/Broker/Insurer - Test
1153 | IIRM-3261 | Sub-task | API-Test execution | Done | SaikumarMahanthi | iWork | IIRM-3546 — UI - Manage TPA/Broker/Insurer - Test
1154 | IIRM-3262 | Sub-task | UI-Test execution and bugs logging | Done | SaikumarMahanthi | iWork | IIRM-3546 — UI - Manage TPA/Broker/Insurer - Test
1155 | IIRM-3263 | Sub-task | UI Test cases Execution for TPA/Broker | Done | SaikumarMahanthi | iWork | IIRM-3546 — UI - Manage TPA/Broker/Insurer - Test
1156 | IIRM-3264 | Sub-task | integrated flow upload - manual and drop flow | Done | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1157 | IIRM-3265 | Sub-task | table settings and list view | Pushed to Backlog | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1158 | IIRM-3266 | Sub-task | smart filter - expand and collapse view | Done | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1159 | IIRM-3267 | Sub-task | stepper enhancement | Done | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1160 | IIRM-3268 | Sub-task | company details | Done | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1161 | IIRM-3269 | Sub-task | feedback updates from Naveen | Done | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1162 | IIRM-3270 | Sub-task | brainstorming on timeline view of opty | Done | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1163 | IIRM-3271 | Sub-task | Engineering KT | Done | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1164 | IIRM-3272 | Sub-task | acknowledgement screens | Done | Sai Vamsee K |  | IIRM-838 — UI - Approach Style Establishment
1165 | IIRM-3274 | Task | Review and updated the TPA/Insurer/broker Test data | Done | SaikumarMahanthi |  | IIRM-742 — SOW#15 - Add/Manage TPA
1166 | IIRM-3303 | Story | FR-MOPTY-01 Plan BD Activities | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1167 | IIRM-3311 | Story | UX/UI for BD Stages 2 | Done | Sai Vamsee K | iWork | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
1168 | IIRM-3341 | Sub-task | UX - Held Cover Note Provisional policy document to share with the company | Done | Sai Vamsee K | iWork | IIRM-3311 — UX/UI for BD Stages 2
1169 | IIRM-3357 | Sub-task | UX- Plan Activity | Done | gowtham | iWork | IIRM-3219 — BD Stages - UX/UI
1170 | IIRM-3358 | Sub-task | UX- Feedback Changes | Done | gowtham | iWork | IIRM-3219 — BD Stages - UX/UI
1171 | IIRM-3359 | Task | Design - Lead Tasks | Done | Sai Vamsee K |  | IIRM-742 — SOW#15 - Add/Manage TPA
1172 | IIRM-3360 | Story | UI Manage Opportunity updates | Done | Sai Vamsee K | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1173 | IIRM-3361 | Sub-task | Tweaks for API in Opportunity Create as per updated design flow | Done | Sai Vamsee K | iWork | IIRM-3404 — API - Manager Opportunity Updates
1174 | IIRM-3362 | Sub-task | DB Schema Tweaks for Opportunity as per updated design flow | Done | Sai Vamsee K | iWork | IIRM-3404 — API - Manager Opportunity Updates
1175 | IIRM-3363 | Sub-task | UI Changes in Opportunity Details and Create / Edit Update as per updated design flow | Done | Sai Vamsee K | iWork | IIRM-3360 — UI Manage Opportunity updates
1176 | IIRM-3364 | Sub-task | Opportunities Listing Page Styling Changes | Done | Sai Vamsee K | iWork | IIRM-3360 — UI Manage Opportunity updates
1177 | IIRM-3365 | Sub-task | Apply the UI Styling for Components As per figma | Done | Rama K |  | IIRM-3203 — Common Module
1178 | IIRM-3366 | Task | IIRM: SO: Test cases Authoring for Manage Opportunity | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1179 | IIRM-3367 | Sub-task | Test cases documentation | Done | SaikumarMahanthi |  | IIRM-3244 — Design- Manage Tasks & Meetings
1180 | IIRM-3368 | Bug | IIRM : Create company : API: Unable to create company thrown 400 | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1181 | IIRM-3369 | Sub-task | Timeline creation, page layout and foundation of flow | Done | Nandini Kataria |  | IIRM-1784 — UX/UI - Create/List and View Opportunity
1182 | IIRM-3370 | Sub-task | Test Script for Broker | Done | SaikumarMahanthi |  | IIRM-3546 — UI - Manage TPA/Broker/Insurer - Test
1183 | IIRM-3371 | Sub-task | Test Script for Insurer | Done | SaikumarMahanthi |  | IIRM-3191 — UI - Manage Insurer/TPA/Broker
1184 | IIRM-3372 | Sub-task | Update the Sort and Searching for Company API | Done | Rama K |  | IIRM-3203 — Common Module
1185 | IIRM-3373 | Sub-task | Update the Sort and Search for Insurer TPA and broker APIs | Done | Rama K |  | IIRM-3203 — Common Module
1186 | IIRM-3374 | Sub-task | Update Sort and Search for Contact APIs | Done | Rama K |  | IIRM-3402 — Common Stepper and Smart Search
1187 | IIRM-3375 | Bug | IIRM: Company: API: Enforce to update GSTIN number while udpating a company | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1188 | IIRM-3376 | Bug | IIRM: Company API: Incorrect Response Message When Address Fields Are Missing in Request | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1189 | IIRM-3377 | Bug | IIRM: Company: API: Able to create a company without Group Company ID | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1190 | IIRM-3378 | Task | Create Masters | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1191 | IIRM-3379 | Task | Opty API Tweaks | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1192 | IIRM-3380 | Task | Opty Activities | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1193 | IIRM-3381 | Task | Opty Covers | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1194 | IIRM-3382 | Task | User Management & RBAC | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1195 | IIRM-3383 | Sub-task | Analyse and Identify the Stages of Opportunity and create Masters - Must have sequence and role based access | Done | Sai Vamsee K | iWork | IIRM-3378 — Create Masters
1196 | IIRM-3384 | Sub-task | Analyse and identify the Activities of Opportunity and create a Master. | Done | Sai Vamsee K | iWork | IIRM-3378 — Create Masters
1197 | IIRM-3385 | Sub-task | "Analyse and Identify the Covers of Opportunity and create Masters - Must have sequence and role based access " | Done | Sai Vamsee K | iWork | IIRM-3378 — Create Masters
1198 | IIRM-3386 | Sub-task | Create daatabase tables based on the analyse schema and respective entites of Opty Stages , Activities , Covers | Done | Sai Vamsee K | iWork | IIRM-3378 — Create Masters
1199 | IIRM-3387 | Sub-task | Tweaks for create the opportunity POST API | Done | Sai Vamsee K | iWork | IIRM-3379 — Opty API Tweaks
1200 | IIRM-3388 | Sub-task | Analyse and create a function for the storing opportunity activities on opportunity creation | Done | Sai Vamsee K | iWork | IIRM-3380 — Opty Activities
1201 | IIRM-3389 | Sub-task | Develop an API to get the opportunity activity meta from the opportunity activities table | Done | Sai Vamsee K | iWork | IIRM-3380 — Opty Activities
1202 | IIRM-3390 | Sub-task | Analyse and create a function for getting opportunity activities meta | Done | Sai Vamsee K | iWork | IIRM-3380 — Opty Activities
1203 | IIRM-3391 | Sub-task | Analyse and create a function for the storing covers for the opportunity | Done | Sai Vamsee K | iWork | IIRM-3381 — Opty Covers
1204 | IIRM-3392 | Sub-task | Develop an API to get the opportunity covers from the opportunity activities table | Done | Sai Vamsee K | iWork | IIRM-3381 — Opty Covers
1205 | IIRM-3393 | Sub-task | RBAC Implement on API for Activity were participants need to edit the activity | Pushed to Backlog | Sai Vamsee K | iWork | IIRM-3965 — RBAC Backend
1206 | IIRM-3394 | Sub-task | RBAC Implement on API for Activity were hirerachy | Pushed to Backlog | Sai Vamsee K | iWork | IIRM-3965 — RBAC Backend
1207 | IIRM-3395 | Sub-task | RBAC Implement on API for Activity were custom and tagged permissions | Pushed to Backlog | Sai Vamsee K | iWork | IIRM-3965 — RBAC Backend
1208 | IIRM-3396 | Sub-task | Develop an update API to store the opportunity activities while planning | Done | Sai Vamsee K | iWork | IIRM-3303 — FR-MOPTY-01 Plan BD Activities
1209 | IIRM-3397 | Sub-task | Analyse and create a function to store the transaction/data of the opportunity activities and planning | Done | Sai Vamsee K | iWork | IIRM-3303 — FR-MOPTY-01 Plan BD Activities
1210 | IIRM-3398 | Sub-task | Develop an API to store the activity details for the opportunity | Done | Sai Vamsee K | iWork | IIRM-3303 — FR-MOPTY-01 Plan BD Activities
1211 | IIRM-3400 | Bug | IIRM: Company: API: The "landmark" field provided in the API is not being captured in UI | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1212 | IIRM-3401 | Sub-task | Implement complex password for login | Done | Rama K |  | IIRM-3241 — Design Solutioning for Manage Opportunitites & RBAC
1213 | IIRM-3402 | Story | Common Stepper and Smart Search | Done | Rama K |  | IIRM-737 — SOW#10 - Add/Manage Contact
1214 | IIRM-3404 | Story | API - Manager Opportunity Updates | Done | Rama K | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1215 | IIRM-3405 | Story | API - Manage Contacts Update | Done | Rama K | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1216 | IIRM-3406 | Story | API - Manage Insurer , TPA, Broker | Done | Rama K | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1217 | IIRM-3407 | Task | Approval Management | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1218 | IIRM-3408 | Task | Meetings & Tasks | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1219 | IIRM-3409 | Task | Document Upload | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1220 | IIRM-3411 | Sub-task | Analyse and create API for Appropving the stages when required | Pushed to Backlog | Sai Vamsee K | iWork | IIRM-3407 — Approval Management
1221 | IIRM-3412 | Sub-task | Analyse and create Database Tables fro Meetings and Tasks | Done | Sai Vamsee K | iWork | IIRM-3408 — Meetings & Tasks
1222 | IIRM-3413 | Sub-task | Analyse and create APIs for Meetings and tasks | Done | Sai Vamsee K | iWork | IIRM-3408 — Meetings & Tasks
1223 | IIRM-3414 | Sub-task | Tweaks for Upload Document API (PDF, Excel , Word) | Done | Sai Vamsee K | iWork | IIRM-3409 — Document Upload
1224 | IIRM-3415 | Sub-task | Analyse and create a function for getting cover of the activities of the opportunity | Done | Sai Vamsee K | iWork | IIRM-3381 — Opty Covers
1225 | IIRM-3419 | Story | FR-MOPTY-02 Data Validation | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1226 | IIRM-3420 | Story | FR-MOPTY-03 Meeting with KDM | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1227 | IIRM-3421 | Story | FR-MOPTY-04 Mandate Details Entry | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1228 | IIRM-3422 | Story | FR-MOPTY-05 RFP Data Collection | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1229 | IIRM-3423 | Story | FR-MOPTY-06 RFP Details Entry | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1230 | IIRM-3424 | Story | FR-MOPTY-08 Opportunity Assignment - Manager | WORK IN PROGRESS | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1231 | IIRM-3425 | Story | FR-MOPTY-09 Manage Quotes | Done | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1232 | IIRM-3426 | Story | FR-MOPTY-10 Broking Slip Generation | Done | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1233 | IIRM-3427 | Story | FR-MOPTY-11 Enter Quote | Done | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1234 | IIRM-3428 | Story | FR-MOPTY-12 QCR Generation | Done | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1235 | IIRM-3429 | Story | FR-MOPTY-13 Meeting for Final Negotiation | Done | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1236 | IIRM-3430 | Story | FR-MOPTY-14 Placement Slip Generation | Done | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1237 | IIRM-3431 | Story | FR-MOPTY-15 Premium Calculation (TBD) | Done | Sai Vamsee K | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
1238 | IIRM-3432 | Story | FR-MOPTY-16 Held Cover Note | Done | Sai Vamsee K | iWork | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
1239 | IIRM-3433 | Story | FR-MOPTY-17 Policy Hard Copy Receipt | Done | Sai Vamsee K | iWork | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
1240 | IIRM-3434 | Story | FR-MOPTY-18 Policy Confirmation | Done | Sai Vamsee K | iWork | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
1241 | IIRM-3435 | Story | FR-MOPTY-19 Policy Docket | Done | Sai Vamsee K | iWork | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
1242 | IIRM-3436 | Story | FR-MOPTY-20 Hand Over Meet | Done | Sai Vamsee K | iWork | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
1243 | IIRM-3437 | Story | FR-MOPTY-21 Opportunity Lost | Done | Sai Vamsee K | iWork | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
1244 | IIRM-3439 | Task | Common Form | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1245 | IIRM-3440 | Task | Common UI Components | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1246 | IIRM-3442 | Task | Document Upload | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1247 | IIRM-3443 | Sub-task | UI Implementing Approvals from Manager | Pushed to Backlog | Sai Vamsee K | iWork | IIRM-3424 — FR-MOPTY-08 Opportunity Assignment - Manager
1248 | IIRM-3444 | Sub-task | UI for Assign Another Executive | Done | Sai Vamsee K | iWork | IIRM-3303 — FR-MOPTY-01 Plan BD Activities
1249 | IIRM-3445 | Sub-task | UI for BD & ISG Activities Plan | Done | Sai Vamsee K | iWork | IIRM-3303 — FR-MOPTY-01 Plan BD Activities
1250 | IIRM-3446 | Sub-task | Analyse & Document the JSON sturcture for creating form controls | Done | Sai Vamsee K | iWork | IIRM-3439 — Common Form
1251 | IIRM-3447 | Sub-task | Display the input text controls based on JSON config | Done | Sai Vamsee K | iWork | IIRM-3439 — Common Form
1252 | IIRM-3448 | Sub-task | Display the dropdowns, radio buttons, checkbox controls based on JSON config | Done | Sai Vamsee K | iWork | IIRM-3439 — Common Form
1253 | IIRM-3450 | Sub-task | UI for Document Uploading | Done | Sai Vamsee K | iWork | IIRM-3442 — Document Upload
1254 | IIRM-3451 | Sub-task | UI - Grid to Display Opty stages/activity list for plan and perform | Done | Sai Vamsee K | iWork | IIRM-3440 — Common UI Components
1255 | IIRM-3452 | Sub-task | UI to Show the Progress Tabs - the Current Stage of Opty | Done | Sai Vamsee K | iWork | IIRM-3440 — Common UI Components
1256 | IIRM-3454 | Sub-task | Analyse and create a function to Data Validation | Done | Sai Vamsee K | iWork | IIRM-3419 — FR-MOPTY-02 Data Validation
1257 | IIRM-3455 | Sub-task | UI for Opportunity Data Validation activity | PENDING PEER or LEAD REVIEW | Sai Vamsee K | iWork | IIRM-3419 — FR-MOPTY-02 Data Validation
1258 | IIRM-3456 | Sub-task | Analyse and create a function to KDM Meeting | Done | Sai Vamsee K | iWork | IIRM-3420 — FR-MOPTY-03 Meeting with KDM
1259 | IIRM-3457 | Sub-task | UI for Meeting With KDM | PENDING PEER or LEAD REVIEW | Sai Vamsee K | iWork | IIRM-3420 — FR-MOPTY-03 Meeting with KDM
1260 | IIRM-3458 | Sub-task | Analyse and create a function to Mandate Form | Done | Sai Vamsee K | iWork | IIRM-3421 — FR-MOPTY-04 Mandate Details Entry
1261 | IIRM-3459 | Sub-task | Analyse and create function for getting the existing madate form | Done | Sai Vamsee K | iWork | IIRM-3421 — FR-MOPTY-04 Mandate Details Entry
1262 | IIRM-3460 | Sub-task | UI for Mandate Details Entry | Done | Sai Vamsee K | iWork | IIRM-3421 — FR-MOPTY-04 Mandate Details Entry
1263 | IIRM-3461 | Sub-task | Analyse and create a function to store the transaction/data of the covers of the opportunity | Done | Sai Vamsee K | iWork | IIRM-3422 — FR-MOPTY-05 RFP Data Collection
1264 | IIRM-3462 | Sub-task | Analyse and create a function to store the transaction/version of the RFP Data Collection | Done | Sai Vamsee K | iWork | IIRM-3422 — FR-MOPTY-05 RFP Data Collection
1265 | IIRM-3463 | Sub-task | UI For RFP Data Collection | Done | Sai Vamsee K | iWork | IIRM-3422 — FR-MOPTY-05 RFP Data Collection
1266 | IIRM-3464 | Sub-task | Analyse and identify the RFP version tables Activities | Done | Sai Vamsee K | iWork | IIRM-3423 — FR-MOPTY-06 RFP Details Entry
1267 | IIRM-3465 | Sub-task | Create daatabase tables based on the analyse schema and respective entites | Done | Sai Vamsee K | iWork | IIRM-3423 — FR-MOPTY-06 RFP Details Entry
1268 | IIRM-3466 | Sub-task | Analyse and create a function to store the transaction/version of the RFP Detail Entry | Done | Sai Vamsee K | iWork | IIRM-3423 — FR-MOPTY-06 RFP Details Entry
1269 | IIRM-3467 | Sub-task | UI for RFP Details Entry | Done | Sai Vamsee K | iWork | IIRM-3423 — FR-MOPTY-06 RFP Details Entry
1270 | IIRM-3468 | Sub-task | UI for RFP Approval | Done | Sai Vamsee K | iWork | IIRM-3423 — FR-MOPTY-06 RFP Details Entry
1271 | IIRM-3469 | Sub-task | Analyse and create a function to broking slip generation | Done | Sai Vamsee K | iWork | IIRM-3426 — FR-MOPTY-10 Broking Slip Generation
1272 | IIRM-3470 | Sub-task | UI for Broking slip generation | Done | Sai Vamsee K | iWork | IIRM-3426 — FR-MOPTY-10 Broking Slip Generation
1273 | IIRM-3471 | Sub-task | Analyse and create a function to QCR Data Entry | Done | Sai Vamsee K | iWork | IIRM-3427 — FR-MOPTY-11 Enter Quote
1274 | IIRM-3472 | Sub-task | UI for Manage Quotes | Done | Sai Vamsee K | iWork | IIRM-3427 — FR-MOPTY-11 Enter Quote
1275 | IIRM-3473 | Sub-task | Analyse and Identify the QCR version tables Activities | Done | Sai Vamsee K | iWork | IIRM-3428 — FR-MOPTY-12 QCR Generation
1276 | IIRM-3474 | Sub-task | Create daatabase tables based on the analyse schema and respective entites | Done | Sai Vamsee K | iWork | IIRM-3428 — FR-MOPTY-12 QCR Generation
1277 | IIRM-3475 | Sub-task | Analyse and create a function to store the transaction/version of the QCR of the opportunity activities and planning | Done | Sai Vamsee K | iWork | IIRM-3428 — FR-MOPTY-12 QCR Generation
1278 | IIRM-3476 | Sub-task | Analyse and create a function to QCR generation | Done | Sai Vamsee K | iWork | IIRM-3428 — FR-MOPTY-12 QCR Generation
1279 | IIRM-3477 | Sub-task | UI for QCR generation | Done | Sai Vamsee K | iWork | IIRM-3428 — FR-MOPTY-12 QCR Generation
1280 | IIRM-3478 | Sub-task | Analyse and create function for Final negatiation | Done | Sai Vamsee K | iWork | IIRM-3429 — FR-MOPTY-13 Meeting for Final Negotiation
1281 | IIRM-3479 | Sub-task | UI for Final negatiation meeting | Done | Sai Vamsee K | iWork | IIRM-3429 — FR-MOPTY-13 Meeting for Final Negotiation
1282 | IIRM-3480 | Sub-task | Analyse and create a function to Placement slip generation | Done | Sai Vamsee K | iWork | IIRM-3430 — FR-MOPTY-14 Placement Slip Generation
1283 | IIRM-3481 | Sub-task | UI for Placement Slip generation | Done | Sai Vamsee K | iWork | IIRM-3430 — FR-MOPTY-14 Placement Slip Generation
1284 | IIRM-3482 | Sub-task | Analyse and create a function to Premium Calculation | Done | Sai Vamsee K | iWork | IIRM-3431 — FR-MOPTY-15 Premium Calculation (TBD)
1285 | IIRM-3483 | Sub-task | UI for Premium Calculation | Done | Sai Vamsee K | iWork | IIRM-3431 — FR-MOPTY-15 Premium Calculation (TBD)
1286 | IIRM-3484 | Sub-task | Anlyse and create function for Policy Data Entry & creation | Done | Sai Vamsee K | iWork | IIRM-3434 — FR-MOPTY-18 Policy Confirmation
1287 | IIRM-3485 | Sub-task | UI for Policy Confirmation | Done | Sai Vamsee K | iWork | IIRM-3434 — FR-MOPTY-18 Policy Confirmation
1288 | IIRM-3486 | Sub-task | Analyse and create a function to Policy held Cover note | Done | Sai Vamsee K | iWork | IIRM-3432 — FR-MOPTY-16 Held Cover Note
1289 | IIRM-3487 | Sub-task | UI for Held Cover Note | Done | Sai Vamsee K | iWork | IIRM-3432 — FR-MOPTY-16 Held Cover Note
1290 | IIRM-3488 | Sub-task | Analyse and create a function to Policy Hard Copy reciept | Done | Sai Vamsee K | iWork | IIRM-3433 — FR-MOPTY-17 Policy Hard Copy Receipt
1291 | IIRM-3489 | Sub-task | UI for Policy Hard Copy Receipt Generation | Done | Sai Vamsee K | iWork | IIRM-3433 — FR-MOPTY-17 Policy Hard Copy Receipt
1292 | IIRM-3490 | Sub-task | Analyse and create a function to Policy docket | Done | Sai Vamsee K | iWork | IIRM-3435 — FR-MOPTY-19 Policy Docket
1293 | IIRM-3491 | Sub-task | UI for Policy Docket Management | Done | Sai Vamsee K | iWork | IIRM-3435 — FR-MOPTY-19 Policy Docket
1294 | IIRM-3492 | Sub-task | Analyse and create a function to Handover meet | Done | Sai Vamsee K | iWork | IIRM-3436 — FR-MOPTY-20 Hand Over Meet
1295 | IIRM-3493 | Sub-task | UI for Handover Meet | Done | Sai Vamsee K | iWork | IIRM-3436 — FR-MOPTY-20 Hand Over Meet
1296 | IIRM-3494 | Bug | IIRM: Company: API Retrieves a paginated list of companies API's returns 10 results without applying any filters or parameters | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1297 | IIRM-3495 | Sub-task | Analyse and create API for Appropving the stages when required | Done | Sai Vamsee K | iWork | IIRM-3424 — FR-MOPTY-08 Opportunity Assignment - Manager
1298 | IIRM-3496 | Story | FR-MOPTY-01a Plan ISG Activities | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1299 | IIRM-3497 | Story | FR-MOPTY-01b Perform BD & ISG Activities | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1300 | IIRM-3498 | Story | FR-MOPTY-07 RFP Details Entry Approval | Done | Sai Vamsee K | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1301 | IIRM-3514 | Task | Internal Demo Feedback on Manage Company Demo [2nd May] | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1302 | IIRM-3515 | Sub-task | Existing company check to be added while adding a company. This validation to happen in the beginning of the creation rather than waiting until submit to check validation | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1303 | IIRM-3516 | Sub-task | UX of interlinked - opportunity, company and contact flow to be implemented | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1304 | IIRM-3517 | Sub-task | Don't show the toast message let's build your profile. | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1305 | IIRM-3518 | Sub-task | In stepper, change label from "Translation" to "Regulation" | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1306 | IIRM-3519 | Sub-task | Remove validation for GST. Make non-mandatory validations as non-mandatory | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1307 | IIRM-3520 | Sub-task | Make all text-areas as expandable text areas. | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1308 | IIRM-3521 | Sub-task | While viewing, text areas also to be expandable text areas. | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1309 | IIRM-3522 | Sub-task | In list view, clickable items - on hover should change the hand-pointer | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1310 | IIRM-3523 | Sub-task | In company details, take out mailbox | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1311 | IIRM-3524 | Sub-task | In company overview, in address details. branch should be there. Also remove the 2nd label called"address" since the header anyways says "Address Details" | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1312 | IIRM-3525 | Sub-task | Company Name in UI is much larger in the new UI. Change this UI in Engineering | Done | Sai Vamsee K |  | IIRM-3514 — Internal Demo Feedback on Manage Company Demo [2nd May]
1313 | IIRM-3529 | Sub-task | Test data & Test script preparation for Broker contact | Done | SaikumarMahanthi |  | IIRM-3406 — API - Manage Insurer , TPA, Broker
1314 | IIRM-3530 | Sub-task | Test data & Test script preparation for TPA contact | Done | SaikumarMahanthi |  | IIRM-3406 — API - Manage Insurer , TPA, Broker
1315 | IIRM-3531 | Sub-task | Test data & Test script preparation for Insurer contact | Done | SaikumarMahanthi |  | IIRM-3406 — API - Manage Insurer , TPA, Broker
1316 | IIRM-3532 | Sub-task | Test data and Test script for Broker | Pushed to Backlog | SaikumarMahanthi |  | IIRM-3406 — API - Manage Insurer , TPA, Broker
1317 | IIRM-3533 | Sub-task | Test data and Test script for TPA | Done | SaikumarMahanthi |  | IIRM-3406 — API - Manage Insurer , TPA, Broker
1318 | IIRM-3534 | Sub-task | UX Feedback | Done | gowtham |  | IIRM-3220 — ISG Stages - UX/UI
1319 | IIRM-3535 | Sub-task | UX - Policy Hard Copy Receipt After receiving policy hard copy from the insurer, | Done | Sai Vamsee K |  | IIRM-3311 — UX/UI for BD Stages 2
1320 | IIRM-3536 | Sub-task | UX - Policy Docket Defining dates for document submission | Done | Sai Vamsee K |  | IIRM-3311 — UX/UI for BD Stages 2
1321 | IIRM-3537 | Sub-task | UX - Hand Over Meet Schedule a physical meeting with the company to handover the policy docket. | Done | Sai Vamsee K |  | IIRM-3311 — UX/UI for BD Stages 2
1322 | IIRM-3538 | Sub-task | UI - Held Cover Note Provisional policy document to share with the company | Done | Sai Vamsee K |  | IIRM-3311 — UX/UI for BD Stages 2
1323 | IIRM-3539 | Sub-task | UI - Policy Hard Copy Receipt After receiving policy hard copy from the insurer, | Done | Sai Vamsee K |  | IIRM-3311 — UX/UI for BD Stages 2
1324 | IIRM-3540 | Sub-task | UI - Policy Docket Defining dates for document submission | Done | Sai Vamsee K |  | IIRM-3311 — UX/UI for BD Stages 2
1325 | IIRM-3541 | Sub-task | UI - Hand Over Meet Schedule a physical meeting with the company to handover the policy docket. | Done | Sai Vamsee K |  | IIRM-3311 — UX/UI for BD Stages 2
1326 | IIRM-3542 | Task | PO - Product Spec for Endorsements, Dashboards, Notifications | Done | Sai Vamsee K |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
1327 | IIRM-3543 | Sub-task | Product Spec for Dashboards & Drilldowns | Done | Sai Vamsee K |  | IIRM-3542 — PO - Product Spec for Endorsements, Dashboards, Notifications
1328 | IIRM-3544 | Sub-task | Product Spec for Notifications | Done | Sai Vamsee K |  | IIRM-3542 — PO - Product Spec for Endorsements, Dashboards, Notifications
1329 | IIRM-3545 | Sub-task | Product Spec for Endorsements | Done | Sai Vamsee K |  | IIRM-3542 — PO - Product Spec for Endorsements, Dashboards, Notifications
1330 | IIRM-3546 | Task | UI - Manage TPA/Broker/Insurer - Test | Done | Rama K |  | IIRM-741 — SOW#14 - Add/Manage Insurer
1331 | IIRM-3547 | Bug | IIRM: Contact: API: Date field accepts invalid/multiple date formats" | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1332 | IIRM-3548 | Bug | IIRM: Contact: API: Able to create a Company Contact with invalid linkedIn URL | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1333 | IIRM-3549 | Bug | IIRM: Contact: API: "Contact Query creation failed" error message is displayed | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1334 | IIRM-3550 | Bug | IIRM: Contact: API: Able to create a contact without contactTypeId | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1335 | IIRM-3551 | Bug | IIRM: Contact: API: "Location" field is missing in request payload | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1336 | IIRM-3552 | Bug | IIRM: Contact: API: Able to create a contact without Address | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1337 | IIRM-3553 | Bug | IIRM: Contact: API: Unable to create a contact with different phone number formats | Reopen | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1338 | IIRM-3554 | Sub-task | Test Execution for TPA/Insurer/Broker | Done | SaikumarMahanthi |  | IIRM-3406 — API - Manage Insurer , TPA, Broker
1339 | IIRM-3555 | Story | Database Tables Cleanup | Draft | Gopal Gottumukkala |  | IIRM-2215 — Technical Debt
1340 | IIRM-3556 | Sub-task | Remove unused tables | WORK IN PROGRESS | Gopal Gottumukkala |  | IIRM-3555 — Database Tables Cleanup
1341 | IIRM-3557 | Sub-task | Rename inappropriately named tables | WORK IN PROGRESS | Gopal Gottumukkala |  | IIRM-3555 — Database Tables Cleanup
1342 | IIRM-3558 | Sub-task | Rename inappropriately named columns | WORK IN PROGRESS | Gopal Gottumukkala |  | IIRM-3555 — Database Tables Cleanup
1343 | IIRM-3559 | Sub-task | Test data and Test script for Insurer contact , TPA contact , Broker Contact | Pushed to Backlog | SaikumarMahanthi |  | IIRM-3406 — API - Manage Insurer , TPA, Broker
1344 | IIRM-3560 | Sub-task | Test case Ececution for Insuer contact, broker contact, TPA conact | Done | SaikumarMahanthi |  | IIRM-3406 — API - Manage Insurer , TPA, Broker
1345 | IIRM-3561 | Bug | IIRM: Contact: API: UI: 400 thrown on Create Contact Without Qualification Details | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1346 | IIRM-3562 | Bug | IIRM : Contact: API: Get Contact API Failed to Retrieve Data | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1347 | IIRM-3563 | Bug | IIRM :Contact: Next Button Stuck on Loading After Validation Errors | Done | Akhila Gattu |  | IIRM-737 — SOW#10 - Add/Manage Contact
1348 | IIRM-3565 | Bug | IIRM: Contact: Unable to Select Year after 1900 in Professional Experience Calendar | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1349 | IIRM-3566 | Sub-task | Company contact Test cases execution | Done | SaikumarMahanthi |  | IIRM-3185 — UI - Manage Contact Updates
1350 | IIRM-3567 | Bug | IIRM: Company: API: "noOfEmployees" field is accepting Negative numbers | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1351 | IIRM-3568 | Sub-task | Update API Test scripts and Execute test cases | Done | SaikumarMahanthi |  | IIRM-3178 — Manage Company
1352 | IIRM-3569 | Bug | IIRM :Contact: UI : System Allows Duplicate Contact Creation | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1353 | IIRM-3570 | Bug | IIRM: Contact: Contact Details Missing in List View for UI-Based contact creation | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1354 | IIRM-3575 | Bug | IIRM : Contact: UI: API : Thrown 400 error on Search by Contact name and Search by Branch Functionality | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1355 | IIRM-3576 | Bug | IIRM: Contact: UI : Invalid Linked URL Thrown on Contact Update | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1356 | IIRM-3577 | Bug | IIRM: Contact: UI: Self-User Appears in ReportingTo List When Editing Contact | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1357 | IIRM-3579 | Bug | Company : List page: Company Type Filter is missing for smart seach | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1358 | IIRM-3580 | Bug | IIRM: Company: "Group Company" and "Status" Fields Should Be in switch Format Instead of Dropdown | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1359 | IIRM-3581 | Bug | IIRM: Company: API: Country details are displayed as null by providing invalid ID | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1360 | IIRM-3582 | Bug | Company Create Page: Dollar Symbol ($) Displayed on "Annual Premium" Field for INR Currency | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1361 | IIRM-3583 | Bug | IIRM: Company: API: Error message is not user friendly | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1362 | IIRM-3584 | Bug | IIRM: Contact: UI : Display name not getting updated on editing first and last names | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1363 | IIRM-3585 | Bug | Manage Company List Page: "RO" Column Missing in Table but Available in Filters | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1364 | IIRM-3586 | Bug | IIRM: Company: API: "SentimentId" details are missing in the response payload | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1365 | IIRM-3587 | Bug | IIRM: Contact: Edit: Updated Personal Details Not Reflected After Saving Contact Edit | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1366 | IIRM-3588 | Bug | IIRM: Company: API: Able to create a company with invalid Email format and Phone number | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1367 | IIRM-3590 | Bug | IIRM: Contact: Edit: Edit Action Does Not Preserve Active Tab – Always Opens First Tab | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1368 | IIRM-3591 | Sub-task | Excute UI Test Cases for company | Done | SaikumarMahanthi |  | IIRM-3178 — Manage Company
1369 | IIRM-3592 | Bug | IIRM: Contact:Company: TPA: Insurer: Broker: Next Button Becomes Unresponsive When Remarks Field Reaches Max Characters with Styling Applied | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1370 | IIRM-3593 | Bug | IIRM: Contact: Personal details: Date of wedding Field Not Disabled When Marital Status Is Set to Single | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1371 | IIRM-3599 | Task | Json formConfig and common form component refactor to separate the json and methods in it | Done | Gundam Sree Sahithi |  | IIRM-797 — SOW#69 - Manage Opportunities
1372 | IIRM-3600 | Task | POC - Quote Entry form | Done | Gundam Sree Sahithi |  | IIRM-797 — SOW#69 - Manage Opportunities
1373 | IIRM-3601 | Bug | IIRM: Opportunity: Unable to create Opportunity with mandatory fields | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1374 | IIRM-3602 | Task | UI - Insurer/TPA/Broker contact listing updates and styling | Done | Rama K |  | IIRM-783 — SOW#56 - Insurer / TPA integration
1375 | IIRM-3603 | Bug | IIRM : Create company : Checkbox Missing for Selecting Newly Created/existing Company | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1376 | IIRM-3604 | Sub-task | Execute Test cases | Done | SaikumarMahanthi |  | IIRM-3360 — UI Manage Opportunity updates
1377 | IIRM-3605 | Bug | IIRM: Insurer: TPA: Broker: Unable to Create Manage Insurer/TPA/Broker Without Providing Alternate Phone Number | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1378 | IIRM-3606 | Bug | IIRM: TPA: Broker: Insurer: Incorrect Validation Error When Phone Number and Email is Null in Communication Details | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1379 | IIRM-3607 | Bug | IIRM: TPA: Insurer: Contact: Bugs on Create and Edit process | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1380 | IIRM-3608 | Bug | IIRM: TPA: Broker: Insurer: Search Returns "No Data to Show" Despite Existing Records | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1381 | IIRM-3612 | Bug | IIRM_Contact_API: Create Contact API issues | Done | SaikumarMahanthi |  | IIRM-737 — SOW#10 - Add/Manage Contact
1382 | IIRM-3613 | Task | Stepper functionality - Integration flow for Creating - Company - Contact- Opportunity | Done | Rama K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1383 | IIRM-3614 | Task | UI - Integration flow for Creating - Company - Contact- Opportunity | Done | Rama K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1384 | IIRM-3615 | Task | Company : API: Test data and test script for negative scenarios | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1385 | IIRM-3616 | Sub-task | FR-MOPTY-01a Plan ISG Activities | Done | meghana |  | IIRM-3496 — FR-MOPTY-01a Plan ISG Activities
1386 | IIRM-3617 | Sub-task | FR-MOPTY-01b Perform BD & ISG Activities | Done | meghana |  | IIRM-3497 — FR-MOPTY-01b Perform BD & ISG Activities
1387 | IIRM-3618 | Sub-task | FR-MOPTY-07 RFP Details Entry Approval | Done | meghana |  | IIRM-3498 — FR-MOPTY-07 RFP Details Entry Approval
1388 | IIRM-3619 | Sub-task | FR-MOPTY-09 Manage Quotes | Done | meghana |  | IIRM-3425 — FR-MOPTY-09 Manage Quotes
1389 | IIRM-3620 | Bug | IIRM: Company : Default Suggestions Overlap with Other Form Fields | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1390 | IIRM-3626 | Story | Mail Box Integration - Integrate Email Inbox of the attached company | Draft | Gopal Gottumukkala |  | IIRM-797 — SOW#69 - Manage Opportunities
1391 | IIRM-3627 | Story | Traxcn Database Integration | Done | Gopal Gottumukkala |  | IIRM-797 — SOW#69 - Manage Opportunities
1392 | IIRM-3629 | Bug | IIRM: Company: Functional: Inconsistency in Cancel Functionality in Smart Search Section | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1393 | IIRM-3630 | Bug | IIRM: Opportunities: Search functionality: Based on the search data Quick cards should get updated | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1394 | IIRM-3632 | Bug | IIRM: Company: Functional: Atleast one column option should be checked | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1395 | IIRM-3633 | Bug | IIRM: Opportunities : Edit issues | QA in Progress | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1396 | IIRM-3634 | Bug | IIRM: Opportunities : UI Issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1397 | IIRM-3635 | Bug | IIRM: Company: UI: Manage Company | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1398 | IIRM-3636 | Bug | IIRM: Company: Contact: Manage partners: UI issues | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1399 | IIRM-3637 | Bug | IIRM: Company: UI: Manage Company UI Issues | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1400 | IIRM-3638 | Bug | IIRM: Contact: "N/A" Displayed When Multiple Emails or Phone Numbers Are Provided | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1401 | IIRM-3639 | Task | UI - Update the UI changes for Insurer / TPA / Broker Contact Form as per Figma Designs | Done | Rama K |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
1402 | IIRM-3640 | Bug | IIRM: Contact: Address: Address Details >1 address Not Displayed on Overview Page After Adding or Updating Contact | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1403 | IIRM-3641 | Bug | IIRM: TPA : Toolbar Formatting Not Reflected on Overview Page (e.g., Bold Text in Remarks) | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1404 | IIRM-3642 | Task | Side menu will change - names and structure. The required structure is as follows: | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1405 | IIRM-3643 | Task | Industry Intelligence – This section should have following sub headings to display the content: | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1406 | IIRM-3644 | Task | Sales Pitch – this section should have following sub headings to display the content: | Done | Sai Vamsee K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1407 | IIRM-3645 | Task | Potential Opportunities - this section should list all the potential opportunities as per company industry segment. For example: | Done | Sai Vamsee K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1408 | IIRM-3646 | Task | In Insurer, instead of asking “is Life”, ask what type of insurance company with defined values in LOV. | Done | Sai Vamsee K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1409 | IIRM-3647 | Task | In SO & RO – provide functionality of defining the sales pitch. It will be user entry field. | Done | Sai Vamsee K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1410 | IIRM-3648 | Task | Login Page Design: A fresh and visually appealing design is needed for the login page. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1411 | IIRM-3649 | Task | Look and Feel: We need to finalize the colour combination for the overall look and feel of the application | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1412 | IIRM-3650 | Task | Label and Value Colour Differentiation: Clear differentiation between labels and values using distinct colours | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
1413 | IIRM-3651 | Task | Company and Contact Section: These elements should be emphasized, with sizes similar to the 'Lovable' layout | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
1414 | IIRM-3652 | Task | Additional Colours: Incorporate more colours to enhance the design. | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1415 | IIRM-3653 | Task | Manage Companies: The cards should be larger, and excessive white space should be minimized for a cleaner look | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1416 | IIRM-3654 | Task | Task and Meeting Notes: Notes related to tasks and meetings should be integrated into the Company and Contact pages | Done | Sai Vamsee K |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
1417 | IIRM-3655 | Task | Motivation Messages: These should be more prominent and visually highlighted. | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
1418 | IIRM-3656 | Task | Tracxn Button Position: The Tracxn button should be moved to the right for better alignment | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
1419 | IIRM-3657 | Task | Contacts Section: A new tab called "Add Contacts" should be added to the Contacts section for easier access | Done | Sai Vamsee K |  | IIRM-737 — SOW#10 - Add/Manage Contact
1420 | IIRM-3658 | Task | Knowledge Central: A new tab for "Knowledge Central" should be included for seamless navigation. | Done | Sai Vamsee K |  | IIRM-768 — SOW#41 - Knowledge Central
1421 | IIRM-3659 | Sub-task | CR - Change the Stepper % Calculation formula while creation of company, contact, opportunity, TPA, Insurer, Broker | Pushed to Backlog | Sai Vamsee K |  | IIRM-5477 — CR In IIRM
1422 | IIRM-3661 | Task | Internal Demo Feedback on Milestone 1.1 - 8th May | Done | Sai Vamsee K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1423 | IIRM-3662 | Sub-task | Quick Cards - percentage of leads is not shown | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1424 | IIRM-3663 | Sub-task | Order of filters and snapshot (when collapsed) is different | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1425 | IIRM-3664 | Sub-task | Default order of the table to be changed as per the design | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1426 | IIRM-3665 | Sub-task | Profile should be initials of the executive, it is BD right now | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1427 | IIRM-3666 | Sub-task | While sorting with priority level, Vimp should be the 1st one ** | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1428 | IIRM-3667 | Sub-task | When 0 is present for any field, sorting is not working | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1429 | IIRM-3668 | Sub-task | Add company details to “Company name” | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1430 | IIRM-3669 | Sub-task | CTAs should be : Save & Exit, Cancel, Next should be there | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1431 | IIRM-3670 | Sub-task | All fields are editable except Company Primary Name, currency and Country | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1432 | IIRM-3671 | Sub-task | Lead CRM name should be displayed | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1433 | IIRM-3672 | Sub-task | CTAs should be : Save & Exit, Cancel, Next should be there | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1434 | IIRM-3673 | Sub-task | All fields are editable except Company Primary Name, currency and Country | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1435 | IIRM-3674 | Sub-task | Lead CRM name should be displayed | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1436 | IIRM-3675 | Sub-task | Once next is clicked, go to top of the page | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1437 | IIRM-3676 | Sub-task | Currency symbol should be picked up from currency | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1438 | IIRM-3677 | Sub-task | Opportunities, policies tabs missing | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1439 | IIRM-3678 | Sub-task | Website link should display the actual website and not as ‘Website link’ | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1440 | IIRM-3679 | Sub-task | Company’s website to Website, Company’s Number to Phone Number | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1441 | IIRM-3680 | Sub-task | If the form is not filled, exclamation should be shown instead of tick mark in the header | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1442 | IIRM-3681 | Sub-task | Phone number field names - Phone number, Alternate Phone Number | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1443 | IIRM-3682 | Sub-task | Show phone numbers against each address | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1444 | IIRM-3683 | Sub-task | Address Type: Branch, HQ, Warehouse, Factory, Corporate Office | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1445 | IIRM-3684 | Sub-task | Order of address is changing every time - so company contact number is changing (Primary address should be marked) | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1446 | IIRM-3685 | Sub-task | Country should be locked in the address details | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1447 | IIRM-3686 | Sub-task | Parent company LOV - remove companies which are already a group company | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1448 | IIRM-3687 | Sub-task | Personal Details: Spouse Section is different | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1449 | IIRM-3688 | Sub-task | Contact Information: Company Name is not there | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1450 | IIRM-3689 | Sub-task | Contact Information: LinkedIn link text is interfering with the next field value | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1451 | IIRM-3690 | Sub-task | email should be clickable (future scope) | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1452 | IIRM-3691 | Sub-task | Contact Details and Communication Details is confusing - Communication Details come under | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1453 | IIRM-3692 | Sub-task | Contact Name should be Display Name ideally | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1454 | IIRM-3693 | Sub-task | Search should be expanded to contact name, display name, Department, Designation, Phone number, email, company Name | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1455 | IIRM-3694 | Sub-task | Status should go to Filter | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1456 | IIRM-3695 | Sub-task | Organisation Name should be Company Name | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1457 | IIRM-3696 | Sub-task | Department should be a freeform text | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1458 | IIRM-3697 | Sub-task | Designation should be a freeform text | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1459 | IIRM-3698 | Sub-task | Reporting to: List should not include self | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1460 | IIRM-3699 | Sub-task | Relation Type to Relationship type | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1461 | IIRM-3700 | Sub-task | Hide Tag (Remove Tag in Backlog) | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1462 | IIRM-3701 | Sub-task | LinkedIn URL validation - tool tip is wrong | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1463 | IIRM-3702 | Sub-task | Company Location: Location drop down should have address type+line 1+city | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1464 | IIRM-3703 | Sub-task | Address Type: Contact Address Type should show Residence in LOV | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1465 | IIRM-3704 | Sub-task | No multiple addresses in Contact - Remove + Icon | Done | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1466 | IIRM-3705 | Sub-task | Spouse's Name Date of Birth - Change to 'Spouse's Date of Birth' | Pushed to Backlog | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1467 | IIRM-3706 | Sub-task | Professional Experience: From Date should not be greater than To date | Pushed to Backlog | Sai Vamsee K |  | IIRM-3661 — Internal Demo Feedback on Milestone 1.1 - 8th May
1468 | IIRM-3707 | Sub-task | Regression Testing on Company/Contact/TPA/Insuer/Broker | Done | SaikumarMahanthi |  | IIRM-1779 — QA - Lead Tasks
1469 | IIRM-3708 | Story | UI - Milestone-1 Refactoring | Done | Rama K
1470 | IIRM-3709 | Bug | Company: Sum of Sum Insured of SO,RO , Policy is not updated on company details screen | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1471 | IIRM-3711 | Task | UI changes as per meeting on 12th May - Data Validation, KDM Meeting, Mandate Entry | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1472 | IIRM-3712 | Story | UI: Implementing Contacts Sections | Done | Nikhil V
1473 | IIRM-3713 | Story | UI: Implementing Profiles Sections | Done | Nikhil V
1474 | IIRM-3714 | Task | CLONE - UI changes as per meeting on 12th May - Data Validation, KDM Meeting, Mandate Entry | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1475 | IIRM-3715 | Story | AI Smart Addon Integration for Card and Document Reading | Done | Rama K |  | IIRM-754 — SOW#27 - AI - Smart Adds
1476 | IIRM-3716 | Sub-task | Implement the Regulatory Details and GST cards | Done | Karan Agarwal |  | IIRM-3708 — UI - Milestone-1 Refactoring
1477 | IIRM-3717 | Task | Company details | Done | meghana | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1478 | IIRM-3718 | Task | Feedback updates and enhancements | Done | meghana | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1479 | IIRM-3719 | Task | Knowledge Transfer to Dev for activities | Done | meghana | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1480 | IIRM-3720 | Bug | Company: Manage and Create page UI issues | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1481 | IIRM-3721 | Bug | Contact : Create and Manage list page issues | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1482 | IIRM-3722 | Bug | Company : Company details page Issues | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1483 | IIRM-3723 | Bug | Opportunity Issues | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1484 | IIRM-3724 | Sub-task | Opportunity: Requirement Analysis | Done | SaikumarMahanthi |  | IIRM-3360 — UI Manage Opportunity updates
1485 | IIRM-3725 | Sub-task | Opportunity: API: Preparing Test Scripts and Documenting Test Data | Done | SaikumarMahanthi |  | IIRM-3360 — UI Manage Opportunity updates
1486 | IIRM-3726 | Task | Company_Contact_API: Bug fix verification and regression testing | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1487 | IIRM-3727 | Task | IIRM: Create and update the test cycle for Oppotunity creation | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
1488 | IIRM-3728 | Task | Verify client feedback and link all open issues to the existing ones | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1489 | IIRM-3729 | Task | Opportunity requriments and UX descussion | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
1490 | IIRM-3730 | Sub-task | Removal of unused files and variables | Done | Manjusha Paritala |  | IIRM-3708 — UI - Milestone-1 Refactoring
1491 | IIRM-3731 | Sub-task | Implement the Sentiment Chip based on the Figma. | Done | Manjusha Paritala |  | IIRM-3708 — UI - Milestone-1 Refactoring
1492 | IIRM-3732 | Bug | Create Company : Default Country | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1493 | IIRM-3733 | Bug | CREATE COMPANY_Inactive Status | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1494 | IIRM-3734 | Bug | CREATE COMPANY_Inactive Status | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1495 | IIRM-3735 | Bug | Multiple company creation on registration number | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1496 | IIRM-3737 | Bug | Unable to change status of the company to inactive | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1497 | IIRM-3738 | Bug | document upload option is missing | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1498 | IIRM-3739 | Bug | date of birth should not take todays date | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1499 | IIRM-3740 | Bug | pincode can be taken 000 or any 6 digit number | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1500 | IIRM-3741 | Bug | mobile number can be taken any like 5555 | Done | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1501 | IIRM-3742 | Bug | IIRM: Search : Filter icon fails to display upon search collapse action. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1502 | IIRM-3743 | Bug | Create Company - Two companies with same registration no can be created | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1503 | IIRM-3744 | Bug | For create company for address options extension is added but can't be collapsed if we want to delete it | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1504 | IIRM-3745 | Bug | Create company - duplicate gst and PAN isnt accepted but registration number is accepted | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1505 | IIRM-3746 | Bug | Priority is changing-: Sometimes the priority is changing automatically | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1506 | IIRM-3747 | Bug | Company List-:When we try to click the count in list view of company it is freezed | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1507 | IIRM-3748 | Bug | Create Contact - Company name must be freezed while creating contact however any company can be selected from the drop down currently | Done | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1508 | IIRM-3749 | Bug | portfolio-: Sometimes details entered during company creation aren't visible like contact mail and phone | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1509 | IIRM-3750 | Bug | After creating a company there should be a pop-up for successful creation | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1510 | IIRM-3751 | Bug | Manage Company -Randomly an error occurred while creating a company. "Found company for selection" | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1511 | IIRM-3752 | Bug | portfolio-:sometimes details entered during company creation aren't visible like contact mail and phone | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1512 | IIRM-3753 | Bug | Menu navigation is tedious everytime. Menu bar does not display description when cursor placed on any icon. The arrow at the bottom needs to be clicked every time. Also, it must be sequential | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1513 | IIRM-3754 | Bug | Company & Contact Creation-: Once a company is created and add contact option is displayed the blue arrow doesn’t work. Also there is a radio button which is not clickable | Done | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1514 | IIRM-3755 | Clarification | Currency should mandatory as per the localization aspects | RELEASED | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1515 | IIRM-3756 | Bug | Company Quick Cards-: % option not available | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1516 | IIRM-3757 | Clarification | What is the logic applied to display the names of "Lead CRM" | RELEASED | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1517 | IIRM-3758 | Clarification | What is the logic applied to display the names of "Account Manager" | RELEASED | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1518 | IIRM-3759 | Clarification | company creted with the name LIBAS is showing image for original LIBAS. IS there any logic to control this | RELEASED | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1519 | IIRM-3760 | Bug | Role based login credentials must be available | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1520 | IIRM-3761 | Bug | Manage company- Edit company, enables Basic, Regulatory, Profile and Strategy section editable but seems modifying the data inernally eventhough there is no modification in all the sections. | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1521 | IIRM-3762 | Sub-task | API integration for Placement Slip Generation | Done | meghana |  | IIRM-3430 — FR-MOPTY-14 Placement Slip Generation
1522 | IIRM-3763 | Sub-task | API integration for Final Negotiation | Done | meghana |  | IIRM-3429 — FR-MOPTY-13 Meeting for Final Negotiation
1523 | IIRM-3764 | Sub-task | API integration for Opty Planning | Done | meghana |  | IIRM-3303 — FR-MOPTY-01 Plan BD Activities
1524 | IIRM-3765 | Sub-task | API intergration for Data Validation | PENDING PEER or LEAD REVIEW | meghana |  | IIRM-3419 — FR-MOPTY-02 Data Validation
1525 | IIRM-3766 | Sub-task | API integration for Mandate Form | Done | meghana |  | IIRM-3421 — FR-MOPTY-04 Mandate Details Entry
1526 | IIRM-3767 | Bug | IIRM : Opportunity: Overview page: Linked Contact Details Not Displayed on Opportunity Overview Page | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1527 | IIRM-3769 | Sub-task | API integration for KDM Meeting | Done | meghana |  | IIRM-3420 — FR-MOPTY-03 Meeting with KDM
1528 | IIRM-3770 | Sub-task | API integration for RFP Data Entry | Done | meghana |  | IIRM-3423 — FR-MOPTY-06 RFP Details Entry
1529 | IIRM-3771 | Sub-task | API integration for Broking slip generation | Done | meghana |  | IIRM-3426 — FR-MOPTY-10 Broking Slip Generation
1530 | IIRM-3772 | Sub-task | API integration for for Manage Quotes | Done | meghana |  | IIRM-3427 — FR-MOPTY-11 Enter Quote
1531 | IIRM-3773 | Sub-task | Integration for QCR generation | Done | meghana |  | IIRM-3428 — FR-MOPTY-12 QCR Generation
1532 | IIRM-3774 | Sub-task | Integration for Premium Calculation | Done | meghana |  | IIRM-3431 — FR-MOPTY-15 Premium Calculation (TBD)
1533 | IIRM-3775 | Sub-task | Integration for Policy Confirmation | Done | meghana |  | IIRM-3434 — FR-MOPTY-18 Policy Confirmation
1534 | IIRM-3776 | Sub-task | Integration for Held Cover Note | Done | meghana |  | IIRM-3432 — FR-MOPTY-16 Held Cover Note
1535 | IIRM-3777 | Sub-task | Integration for Policy Hard Copy | Done | meghana |  | IIRM-3433 — FR-MOPTY-17 Policy Hard Copy Receipt
1536 | IIRM-3778 | Task | IIRM: Test cases Execution for Company And Contact | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1537 | IIRM-3779 | Sub-task | API integration for RFP Data Collection | Done | meghana |  | IIRM-3422 — FR-MOPTY-05 RFP Data Collection
1538 | IIRM-3780 | Bug | IIRM: Company: Quick cards: The system should also show the percentage of the records shown in each quick card. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1539 | IIRM-3781 | Bug | IIRM: Company: Company should have status values. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1540 | IIRM-3782 | Bug | IIRM: Company : The system should not display company record having status as Inactive in the company list section. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1541 | IIRM-3783 | Bug | IIRM: Company : Company details sections missing | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1542 | IIRM-3784 | Bug | IIRM: Company : The system should allow creation of new records or edit of existing data for all the sections in company detail. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1543 | IIRM-3785 | Bug | IIRM : Company : The system should allow drill-down to respective entities from the various sections of company detail. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1544 | IIRM-3786 | Bug | IIRM: Company : The system should allow to upload the relevant documents with appropriate segregation of the document type. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1545 | IIRM-3787 | Bug | IIRM: Company: The system should allow addition of multiple records for the sections of company details. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1546 | IIRM-3788 | Bug | IIRM: Contact: The system should have the functionality of making a contact as inactive contact. | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1547 | IIRM-3789 | Bug | IIRM: Contact : Update the hint text of the search field. | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1548 | IIRM-3790 | Bug | IIRM: Contacts: Few fields were missing on contact list view page. | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1549 | IIRM-3791 | Task | Prepare API collection for performance testing | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1550 | IIRM-3794 | Bug | URL ISSUE | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1551 | IIRM-3795 | Bug | Contact Name - Special Characters | Done | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1552 | IIRM-3796 | Bug | change the word reporting told in pop-up | Done | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1553 | IIRM-3797 | Task | Update the test script and test data for TPA/Insurer/Broker | Done | Akhila Gattu |  | IIRM-742 — SOW#15 - Add/Manage TPA
1554 | IIRM-3798 | Task | Retesting the bugs on Company/Contact/TPA/Insurer/Broker | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1555 | IIRM-3799 | Bug | In contact information the email is not update after adding data to the email field in mange contact page | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1556 | IIRM-3800 | Bug | Font size options not there in drop down | Done | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1557 | IIRM-3801 | Bug | Child gender is not getting captured | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1558 | IIRM-3802 | Bug | Smart Search Editing issue | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1559 | IIRM-3803 | Bug | reporting to | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1560 | IIRM-3804 | Bug | Contact Status- Inactive | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1561 | IIRM-3805 | Bug | Duplicate contact | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1562 | IIRM-3806 | Task | Contact Search dept | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1563 | IIRM-3807 | Task | IIRM: Verify QA Ready on both company and contact and update the environment data on postman | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1564 | IIRM-3808 | Task | Prepare testcases for manage BD stages | Done | Akhila Gattu | iWork | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
1565 | IIRM-3810 | Bug | Manage Contact - Tag can be seen in contact details but there is no field to add tag. Please confirm | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1566 | IIRM-3811 | Sub-task | UI Workshop and UI tweaks | Done | Karan Agarwal |  | IIRM-3708 — UI - Milestone-1 Refactoring
1567 | IIRM-3814 | Bug | IIRM : Company : Unable to submit company creation. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1568 | IIRM-3815 | Bug | IIRM : Contact: Residence option should be shown on selecting address type. | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1569 | IIRM-3816 | Bug | IIRM: Opportunities: Saved Sales Pitch Details Not Displayed on Opportunity Overview Page | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1570 | IIRM-3817 | Epic | Data Migration | WORK IN PROGRESS | meghana | IBP
1571 | IIRM-3818 | Task | Data Migrations - Expediting migration specs (static data (LOVs etc) + Company, contact, TPA, Insure for UAT) | WORK IN PROGRESS | meghana |  | IIRM-3817 — Data Migration
1572 | IIRM-3819 | Task | Data Migrations - Close the final specs to migrate the transactional date | WORK IN PROGRESS | meghana |  | IIRM-3817 — Data Migration
1573 | IIRM-3820 | Task | UAT setup readiness | Done | meghana |  | IIRM-3817 — Data Migration
1574 | IIRM-3821 | Task | Data Migrations - Masters screens with latest UI for feedback | Done | meghana |  | IIRM-3817 — Data Migration
1575 | IIRM-3822 | Task | Static dashboards specs | Done | meghana |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
1576 | IIRM-3823 | Task | Data Migrations - Transaction screens with latest UI for feedback | Done | meghana |  | IIRM-3817 — Data Migration
1577 | IIRM-3824 | Task | Data Migrations - Policy configurator link for trials | WORK IN PROGRESS | meghana |  | IIRM-3817 — Data Migration
1578 | IIRM-3825 | Task | Data Migrations - Link for enrolment based on policy configurator | Done | meghana |  | IIRM-3817 — Data Migration
1579 | IIRM-3826 | Bug | IIRM: Across the application on the listing pages, there is no visual indication that the table is horizontally scrollable | Done | Prabhakar Mantripragada | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1580 | IIRM-3827 | Bug | Company Search - Display name | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1581 | IIRM-3828 | Bug | Can't create Add company | Done - Not Reproducible | sathyusha |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1582 | IIRM-3829 | Task | Verified build with - QA Ready bugs, Figma comparison. | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1583 | IIRM-3830 | Bug | IIRM: TPA Contact: Unable to add a new TPA/Broker/Insurer Contact | Done | Prabhakar Mantripragada |  | IIRM-742 — SOW#15 - Add/Manage TPA
1584 | IIRM-3831 | Story | UI: Implementing Client feedback changes | Done | Nikhil V
1585 | IIRM-3832 | Bug | IIRM: Contact: Insurer: Broker:TPA: Unable to create Insurer contact | Done - Not Reproducible | Akhila Gattu |  | IIRM-741 — SOW#14 - Add/Manage Insurer
1586 | IIRM-3833 | Bug | IIRM_Company_UI: Company Flow UI Issues | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1587 | IIRM-3834 | Bug | IIRM: Manage contact: UI issues | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1588 | IIRM-3835 | Bug | IIRM_Company: Opportunity Details are not populated in the opportunity tab of company details | Done | Leela Pakalapati |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1589 | IIRM-3836 | Bug | IIRM: Broker: Company type details not showning on Basic details card | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1590 | IIRM-3837 | Sub-task | CLONE - Company contact Test cases execution | Done | meghana |  | IIRM-3838 — QA- UI - Manage Contact Updates
1591 | IIRM-3838 | Story | QA- UI - Manage Contact Updates | Done | meghana |  | IIRM-737 — SOW#10 - Add/Manage Contact
1592 | IIRM-3839 | Sub-task | CLONE - Execute Test cases | Done | meghana |  | IIRM-3842 — QA- UI Manage Opportunity updates
1593 | IIRM-3840 | Sub-task | Opportunity: Requirement Analysis & Test cases Preparation | Done | meghana |  | IIRM-3842 — QA- UI Manage Opportunity updates
1594 | IIRM-3841 | Sub-task | Opportunity: API: Preparing Test Scripts and Documenting Test Data | Done | meghana |  | IIRM-3842 — QA- UI Manage Opportunity updates
1595 | IIRM-3842 | Story | QA- UI Manage Opportunity updates | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
1596 | IIRM-3843 | Bug | IIRM_Company_Pagination: Pagination Not Updating Correctly When Changing Records Per Page when user is on Last Page | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1597 | IIRM-3844 | Process | Process Adherence - Sprint IIRM Sprint 7 | Draft | Automation for Jira
1598 | IIRM-3845 | Process Sub Task | Daily Standup | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1599 | IIRM-3846 | Process Sub Task | Daily Status Email from TL to PM | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1600 | IIRM-3847 | Process Sub Task | Daily Status Email from PM to Client | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1601 | IIRM-3848 | Process Sub Task | Log Hours in JIRA Tickets | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1602 | IIRM-3849 | Process Sub Task | Approve Timesheets | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1603 | IIRM-3850 | Process Sub Task | Design Review | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1604 | IIRM-3851 | Process Sub Task | Weekly Internal Demo | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1605 | IIRM-3852 | Process Sub Task | Create JIRA Tickets with acceptance criteria | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1606 | IIRM-3853 | Process Sub Task | Strategy Meeting with DM | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1607 | IIRM-3854 | Process Sub Task | Sprint Planning | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1608 | IIRM-3855 | Process Sub Task | Sprint Plan Presentation | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1609 | IIRM-3856 | Process Sub Task | Sprint Retrospective | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1610 | IIRM-3857 | Process Sub Task | Sprint Kickoff | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1611 | IIRM-3858 | Process Sub Task | Sprint Goals Email | Draft | Automation for Jira |  | IIRM-3844 — Process Adherence - Sprint IIRM Sprint 7
1612 | IIRM-3859 | Story | UX - User Management | Done | meghana |  | IIRM-744 — SOW#17 - User Management
1613 | IIRM-3860 | Sub-task | UX- User Management | Done | meghana |  | IIRM-3859 — UX - User Management
1614 | IIRM-3861 | Sub-task | UI- User Management | Done | meghana |  | IIRM-3859 — UX - User Management
1615 | IIRM-3862 | Story | UX - Dashboards | Done | meghana |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
1616 | IIRM-3863 | Sub-task | UX- Dashboards | Done | meghana |  | IIRM-3862 — UX - Dashboards
1617 | IIRM-3864 | Sub-task | UI- Dashboards | Done | meghana |  | IIRM-3862 — UX - Dashboards
1618 | IIRM-3865 | Bug | IIRM: Contact: TPA: Broker: Insurer: Bugs | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1619 | IIRM-3866 | Sub-task | Integration for Policy Docket | Done | meghana |  | IIRM-3435 — FR-MOPTY-19 Policy Docket
1620 | IIRM-3867 | Sub-task | Integration for Handover Meet | Done | meghana |  | IIRM-3436 — FR-MOPTY-20 Hand Over Meet
1621 | IIRM-3868 | Bug | IIRM: Insurer: Create insurer and edit insurer issues | Done | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1622 | IIRM-3869 | Bug | IIRM: Contact Insurer : Create and edit bugs | QA in Progress | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1623 | IIRM-3870 | Bug | IIRM_AllFeatures: Common functional issues in all features | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1624 | IIRM-3871 | Bug | IIRM: Company : Strategy page: Text color not maintains same on potential opportunity field | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1625 | IIRM-3872 | Bug | IIRM_Insurer/Broker/TPA: UI Issues | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1626 | IIRM-3873 | Bug | IIRM_TPA/Insurer/Broker: Company name is not displayed in contact view details page | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1627 | IIRM-3874 | Task | UI- Login Screen | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
1628 | IIRM-3875 | Task | UI- Feedback Changes | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
1629 | IIRM-3876 | Bug | Company was added without submitting the details. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1630 | IIRM-3877 | Bug | UI adjustment | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1631 | IIRM-3878 | Bug | Dollar signs mentioned in pre-fill. | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1632 | IIRM-3879 | Bug | Deleted companies are still visible in the company selection. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1633 | IIRM-3880 | Bug | IIRM: Contact creation: inactive companies should not be available for contact creation | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1634 | IIRM-3881 | Bug | Contact : Edit: Status is not updated on editing a contact | Done | SaikumarMahanthi |  | IIRM-737 — SOW#10 - Add/Manage Contact
1635 | IIRM-3882 | Bug | IIRM: Company: Company got created without provided Area field on address. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1636 | IIRM-3883 | Bug | IIRM_Company_API: "department and designation" values are displayed as objects | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1637 | IIRM-3884 | Bug | IIRM: Random console errors | Reopen | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1638 | IIRM-3885 | Bug | Provide clickable link for +2 more in smart search section | Done | Prabhakar Mantripragada |  | IIRM-754 — SOW#27 - AI - Smart Adds
1639 | IIRM-3886 | Bug | IIRM: Floater duration should get increase | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1640 | IIRM-3887 | Bug | IIRM: Opportunities: Sum assured digits not getting restricted | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1641 | IIRM-3888 | Bug | Company: Arrow not clickable after company create , only proceed is clickable | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1642 | IIRM-3889 | Bug | IIRM: Stepper Percentage 75& need to be Bright | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1643 | IIRM-3890 | Bug | IIRM_Company: Comma separator should be applied based on Currency Format after tab-out | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1644 | IIRM-3891 | Bug | IIRM: Opportunity: Filters: Contact dropdown lists Companies | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1645 | IIRM-3892 | Bug | Opportunity: Automatic claim% should be displayed on claim experience page | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1646 | IIRM-3893 | Sub-task | Bug Fixes | Done | Karan Agarwal |  | IIRM-3708 — UI - Milestone-1 Refactoring
1647 | IIRM-3894 | Bug | IIRM_Company: Creating a company with current logged in user should be the lead CRM of the company | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1648 | IIRM-3895 | Bug | IIRM: Perf: API: Multiple calls for APIs are made | Reopen | Prabhakar Mantripragada |  | IIRM-64 — SOW#3 - Micro Service Framework
1649 | IIRM-3896 | Bug | IIRM_Company_Contact_Opportunity_API: Correct the date format to dd/mm/yyyy format | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1650 | IIRM-3897 | Bug | IIRM_Opportunity_API: Date fields are accepting Present and future dates | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1651 | IIRM-3898 | Bug | Unable to go ahead and create an opportunity | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1652 | IIRM-3899 | Bug | IIRM_Opportinities_ API: API allows to create opportunity with negative values | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1653 | IIRM-3900 | Bug | No Option to create opportunity from portfolio | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1654 | IIRM-3901 | Bug | IIRM_Opportunity_API: Able to create an opportunity with null value to the field "opportunityTypeLid" | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1655 | IIRM-3902 | Bug | IIRM_Opportunities_ API: Source field allows creation of an SO with Max+1 characters | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1656 | IIRM-3903 | Bug | Create Opportunity - Risk Location | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1657 | IIRM-3904 | Bug | Create Opportunity - Contact details not visible | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1658 | IIRM-3905 | Bug | Not able add new company because of unknow pop-up | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1659 | IIRM-3906 | Bug | Green ticks for stages not completed is visible in progress bar | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1660 | IIRM-3907 | Bug | IIRM: Opportunity : On update Opportunity SO expiry date shows validation error | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1661 | IIRM-3908 | Bug | Create Opportunity - RO option freezed in the menu bar | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1662 | IIRM-3909 | Bug | Empty fields in list View- SO | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1663 | IIRM-3910 | Bug | company name can be change in EDIT SO | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1664 | IIRM-3911 | Bug | IIRM: Opportunity : Decimal values are getting captured in the Sum Insured field | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1665 | IIRM-3912 | Bug | Add a word limit to the all text box like sales pitch,remarks in SO module, | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1666 | IIRM-3913 | Bug | Company Status - Under review | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1667 | IIRM-3914 | Bug | IIRM_Opportunity_API: Invalid Status Code and Status text is displayed | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1668 | IIRM-3915 | Bug | Not able search with contact in manage insurer | Done | Prajakta Vijay Kadam |  | IIRM-741 — SOW#14 - Add/Manage Insurer
1669 | IIRM-3916 | Bug | There is no option to make contact as in-active | Done | Prajakta Vijay Kadam |  | IIRM-742 — SOW#15 - Add/Manage TPA
1670 | IIRM-3917 | Bug | When user click on Designation to sort, the data disappears and keeps on loading. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1671 | IIRM-3918 | Bug | Broker Branch issue | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1672 | IIRM-3919 | Bug | Inactive contact | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1673 | IIRM-3920 | Bug | The functionality to open WhatsApp Web when clicking on Contact is missing. | Done | Prajakta Vijay Kadam |  | IIRM-737 — SOW#10 - Add/Manage Contact
1674 | IIRM-3921 | Bug | On same contact user can create multiple insure contact | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1675 | IIRM-3922 | Story | UI- Development Tasks and Meetings | Done | Rama K |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
1676 | IIRM-3923 | Sub-task | UI - Screen Development for Tasks | Done | Rama K |  | IIRM-3922 — UI- Development Tasks and Meetings
1677 | IIRM-3924 | Sub-task | UI - Screen Development for Meetings | Done | Rama K |  | IIRM-3922 — UI- Development Tasks and Meetings
1678 | IIRM-3925 | Sub-task | UI - Screen Development for Notes | Done | Rama K |  | IIRM-3922 — UI- Development Tasks and Meetings
1679 | IIRM-3926 | Sub-task | UI - Integrate API for Tasks , Meetings and Notes | Done | Rama K |  | IIRM-3922 — UI- Development Tasks and Meetings
1680 | IIRM-3927 | Bug | Opportunity: Blank screen displayed on selecting policy type in Opportunity List page | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1681 | IIRM-3928 | Bug | IIRM: Create company: For filters we don't have a cancel option to close the filter | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1682 | IIRM-3929 | Sub-task | Login Page creation and dashboard screen | Done | Karan Agarwal |  | IIRM-3708 — UI - Milestone-1 Refactoring
1683 | IIRM-3930 | Bug | IIRM: Company: Floater issues | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1684 | IIRM-3931 | Bug | IIRM: Login page: Login details were not center aligned. | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1685 | IIRM-3932 | Bug | IIRM: Company: No Toast Message or Field Navigation on Validation Failure | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1686 | IIRM-3933 | Bug | IIRM: Opportunity: Commas not showing for Estimated fee field on overview page | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1687 | IIRM-3934 | Bug | IIRM: Company: Overview page issues | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1688 | IIRM-3935 | Bug | IIRM: All Features : Sales Pitch Details(Rich Text Fields) Displaying with HTML Tags (e.g., <p>) Instead of Rendered Text | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1689 | IIRM-3936 | Task | IIRM: Company & Contact test cases Execution and updated test cycle | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1690 | IIRM-3937 | Task | IIRM: TPA/Insurer/Broker test case Exection and upadate test cycle | Done | SaikumarMahanthi |  | IIRM-783 — SOW#56 - Insurer / TPA integration
1691 | IIRM-3938 | Task | IIRM: Opportunity test cases execution and update the test cycle | Done | SaikumarMahanthi |  | IIRM-742 — SOW#15 - Add/Manage TPA
1692 | IIRM-3939 | Bug | Smart Search Options | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1693 | IIRM-3940 | Task | IIRM: Bugfixes verification and regression testing on UAT issues | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1694 | IIRM-3941 | Bug | Create Opportunities - Contact not populated in SO | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1695 | IIRM-3942 | Bug | SO smartsearch filter - contact | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1696 | IIRM-3943 | Bug | System log out | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1697 | IIRM-3944 | Bug | SO Smart Search - Leads filter is not showing and leads | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1698 | IIRM-3945 | Bug | Date Selection | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1699 | IIRM-3946 | Bug | IIRM_Opportunity_API: Correct the error messages | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1700 | IIRM-3947 | Bug | Lead CRM in SO details view is blank | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1701 | IIRM-3948 | Bug | Add contacts - Multiple email and phone nos entry | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1702 | IIRM-3949 | Bug | IIRM_Opportunity_UI & API: Company Name field should be disable while editing the opportunity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1703 | IIRM-3950 | Sub-task | Defining global configuration to get and store RBAC data | Done | meghana |  | IIRM-3382 — User Management & RBAC
1704 | IIRM-3951 | Sub-task | Defining and Implementation of AuthGuards for all the necessary pages | Done | meghana |  | IIRM-3382 — User Management & RBAC
1705 | IIRM-3952 | Sub-task | RBAC Framework Implementation | Done | meghana |  | IIRM-3382 — User Management & RBAC
1706 | IIRM-3953 | Sub-task | Defining and implementing access restriction functionality on interactions all over the application - Company,Contact | Done | meghana |  | IIRM-3382 — User Management & RBAC
1707 | IIRM-3954 | Sub-task | RBAC Implementation on Each API by Auth and Role gaurds | Done | meghana |  | IIRM-3382 — User Management & RBAC
1708 | IIRM-3955 | Sub-task | Defining and implementing access restriction functionality on interactions all over the application - TPA, Broker, Insurer | Done | meghana |  | IIRM-3382 — User Management & RBAC
1709 | IIRM-3956 | Sub-task | RBAC Master setup/Update master tables and insert the seed data | Done | meghana |  | IIRM-3382 — User Management & RBAC
1710 | IIRM-3957 | Sub-task | Defining and implementing access restriction functionality on interactions all over the application - Opportunity create and manage | Done | meghana |  | IIRM-3382 — User Management & RBAC
1711 | IIRM-3958 | Sub-task | Common API to fetch the RBAC details by page, by entity, or overall details | Done | meghana |  | IIRM-3382 — User Management & RBAC
1712 | IIRM-3959 | Sub-task | RBAC tagging and custom access | Done | meghana |  | IIRM-3382 — User Management & RBAC
1713 | IIRM-3960 | Sub-task | Entity approval process based on the RBAC and ACL hierarchy | Done | meghana |  | IIRM-3382 — User Management & RBAC
1714 | IIRM-3961 | Sub-task | API to fetch the user hierarchy | Done | meghana |  | IIRM-3382 — User Management & RBAC
1715 | IIRM-3962 | Sub-task | Apply filters based on the org hierarchy | Done | meghana |  | IIRM-3382 — User Management & RBAC
1716 | IIRM-3963 | Sub-task | Validating and testing the RBAC with all possible user roles and access privileges | Done | meghana |  | IIRM-3382 — User Management & RBAC
1717 | IIRM-3964 | Bug | IIRM_Company_API: Able to create a company with invalid Ids | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1718 | IIRM-3965 | Task | RBAC Backend | Done | meghana |  | IIRM-18 — SOW#1 - ACL & RBAC Control
1719 | IIRM-3966 | Bug | Dates displayed in SO details | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1720 | IIRM-3967 | Task | Company : Error messgae text correction on create company form | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1721 | IIRM-3968 | Bug | IIRM: Login page: Intelligence-related text is not displayed in a single line | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1722 | IIRM-3969 | Bug | IIRM: Company : Lead CRM is not shown by default during company creation | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1723 | IIRM-3970 | Bug | Company Creation- No error displayed | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1724 | IIRM-3971 | Sub-task | UI- screen dev for display of tasks | Done | meghana |  | IIRM-3922 — UI- Development Tasks and Meetings
1725 | IIRM-3972 | Sub-task | UI- screen dev for display of meetings and notes | Done | meghana |  | IIRM-3922 — UI- Development Tasks and Meetings
1726 | IIRM-3974 | Story | Knowledge Central | Done | meghana |  | IIRM-750 — SOW#23 - Document Management - CMS
1727 | IIRM-3975 | Sub-task | Backend- Knowledge Central | Done | meghana |  | IIRM-3974 — Knowledge Central
1728 | IIRM-3976 | Sub-task | Frontend- Knowledge Central | Done | meghana |  | IIRM-3974 — Knowledge Central
1729 | IIRM-3977 | Bug | Manage Broker - Cannot search by department and Designation | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1730 | IIRM-3978 | Bug | unable fetch the data if user search with full TPA contact name | Done | Prajakta Vijay Kadam |  | IIRM-742 — SOW#15 - Add/Manage TPA
1731 | IIRM-3979 | Bug | IIRM_Opportunity_API: Failed to retrieve opportunities list | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1732 | IIRM-3980 | Bug | Phone no not synced in broker details | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1733 | IIRM-3981 | Bug | IIRM_Company_API: Mismatch between create company API request and response body fields | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1734 | IIRM-3982 | Bug | Filter are not available in TPA CONTACT | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-742 — SOW#15 - Add/Manage TPA
1735 | IIRM-3983 | Bug | manage broker, insurer& tpa | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1736 | IIRM-3984 | Bug | IIRM_Opportunity_API: previousPlacementDetails are displayed twice in opportunity response body | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1737 | IIRM-3985 | Bug | Manage: So: Planing Stage UI issues | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1738 | IIRM-3986 | Bug | Manage SO: Data validation and KDM meeting UI/UX Mismatch | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1739 | IIRM-3987 | Bug | IIRM: Contact: Missing 'Residence' in Address Type and Remarks Not Displayed on Contact Overview Page | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1740 | IIRM-3988 | Bug | IIRM: Opportunities: Opty Stages UI issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1741 | IIRM-3989 | Task | Additional Participants UI control should show only the firstname | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
1742 | IIRM-3990 | Task | Target Date for the activities - second condition to be fixed - allow users to change the date after the lead days from opty start date. | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
1743 | IIRM-3991 | Task | Make planning stages clickable to navigate to the corresponding sections | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
1744 | IIRM-3992 | Task | Number the according control labels from 1..15 | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
1745 | IIRM-3993 | Task | Users need to create the tasks | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
1746 | IIRM-3994 | Task | Users can create the tasks from anywhere | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
1747 | IIRM-3995 | Task | Blanks on the right side should be covered | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
1748 | IIRM-3996 | Sub-task | UX - Creation View | Done | gowtham |  | IIRM-1782 — UX/UI - Create/List and View Tasks, Meetings
1749 | IIRM-3997 | Sub-task | UX - Calendar view | Done | gowtham |  | IIRM-1782 — UX/UI - Create/List and View Tasks, Meetings
1750 | IIRM-3999 | Sub-task | Feedback changes | Done | gowtham |  | IIRM-1782 — UX/UI - Create/List and View Tasks, Meetings
1751 | IIRM-4000 | Bug | IIRM: Opportunity: Linked opportunities associated with a company are not visible on the Create Company page | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1752 | IIRM-4001 | Task | UI: Contacts & Company Bugs Management | Done | Nikhil V |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1753 | IIRM-4002 | Task | IIRM: Insuer/TPA/Broker contact PI test cases updation with latest changes | Done | SaikumarMahanthi | iWork | IIRM-783 — SOW#56 - Insurer / TPA integration
1754 | IIRM-4003 | Sub-task | dev support | PENDING PEER or LEAD REVIEW | Nandini Kataria |  | IIRM-3359 — Design - Lead Tasks
1755 | IIRM-4004 | Bug | IIRM: Opportunity stages: UI issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1756 | IIRM-4005 | Bug | IIRM: Login page and Dashboard page as per Kapil's recommendation | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1757 | IIRM-4006 | Bug | IIRM: Stepper field names are not fully visible on Create/Edit page | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1758 | IIRM-4007 | Bug | The date of incorporate is limited to 1900. However, there are some famous companies which were incorporated in the 19th century. If this is as per requirement no changes required. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1759 | IIRM-4008 | Story | AI - Smart Adds | Done | meghana |  | IIRM-754 — SOW#27 - AI - Smart Adds
1760 | IIRM-4009 | Sub-task | Smart Assistance Design | Done | meghana |  | IIRM-4008 — AI - Smart Adds
1761 | IIRM-4010 | Sub-task | Smart Assistance Engineering | Done | meghana |  | IIRM-4008 — AI - Smart Adds
1762 | IIRM-4011 | Sub-task | KT to dev team | Done | Nandini Kataria |  | IIRM-3359 — Design - Lead Tasks
1763 | IIRM-4012 | Process | Process Adherence - Sprint IIRM Sprint 8 | Draft | Automation for Jira
1764 | IIRM-4013 | Process Sub Task | Daily Standup | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1765 | IIRM-4014 | Process Sub Task | Daily Status Email from TL to PM | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1766 | IIRM-4015 | Process Sub Task | Daily Status Email from PM to Client | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1767 | IIRM-4016 | Process Sub Task | Log Hours in JIRA Tickets | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1768 | IIRM-4017 | Process Sub Task | Approve Timesheets | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1769 | IIRM-4018 | Process Sub Task | Design Review | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1770 | IIRM-4019 | Process Sub Task | Weekly Internal Demo | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1771 | IIRM-4020 | Process Sub Task | Create JIRA Tickets with acceptance criteria | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1772 | IIRM-4021 | Process Sub Task | Strategy Meeting with DM | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1773 | IIRM-4022 | Process Sub Task | Sprint Planning | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1774 | IIRM-4023 | Process Sub Task | Sprint Plan Presentation | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1775 | IIRM-4024 | Process Sub Task | Sprint Retrospective | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1776 | IIRM-4025 | Process Sub Task | Sprint Kickoff | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1777 | IIRM-4026 | Process Sub Task | Sprint Goals Email | Draft | Automation for Jira |  | IIRM-4012 — Process Adherence - Sprint IIRM Sprint 8
1778 | IIRM-4027 | Bug | IIRM: Company Create: Address Fields Not Retained When Navigating Back Basic Details | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1779 | IIRM-4028 | Bug | IIRM: Edit Company: Jerk shown on edit company(name) details page | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1780 | IIRM-4044 | Bug | The Date of Incorporation changes automatically when clicking on Annual Premium field. | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1781 | IIRM-4045 | Story | Map Integrations | Draft | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
1782 | IIRM-4046 | Story | Whatsapp Integrations | Draft | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
1783 | IIRM-4048 | Story | Notifications | Done | Sai Vamsee K
1784 | IIRM-4050 | Bug | IIRM: Opty stages: Unable to Expand Stages When Clicking on Opty Activities | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1785 | IIRM-4052 | Bug | In the create contact , the placeholder says "Create Company" instead of "Create Contact", which is confusing for users. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1786 | IIRM-4053 | Bug | The "Manage Placement" dropdown should be disabled or shown in a light color, since it's not used right now and may confuse users. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1787 | IIRM-4054 | Bug | IIRM: Opportunity: Oops something went wrong show on edit Opportunity details. | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1788 | IIRM-4055 | Bug | There’s no scroll bar on the home page to view all the text. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1789 | IIRM-4056 | Bug | navigation issue in add contact | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1790 | IIRM-4057 | Task | In the SO screen, when an SO expired date is selected and the user clicks on the Premium Paid field, the date changes automatically. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1791 | IIRM-4058 | Bug | Unable submit MY SO because of pop-up appeared "can't PUT /opportunity" | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1792 | IIRM-4059 | Bug | unable to edit my so (opportunity) | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1793 | IIRM-4060 | Bug | The Sales Funnel Graph and Funnel Effective Graph are missing from the Manage Opportunity screen. These graphs are mentioned in FR-SO-04 but are not currently visible in the UI. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1794 | IIRM-4061 | Bug | In the My SO screen, when using the filter and selecting a contact, it only shows the first three digits of the contact number. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1795 | IIRM-4062 | Bug | In the My SO screen, the contact number is not displayed in the contact row. The field appears completely blank even though a contact is linked. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1796 | IIRM-4063 | Bug | Keep a scrollbar in the left handside menu | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1797 | IIRM-4064 | Bug | TPA - City search | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1798 | IIRM-4065 | Bug | SO Header space | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1799 | IIRM-4066 | Bug | If the target date is greater than the expiry date, show a popup saying: "Target Date cannot be greater than Expiry Date." ONLY BD activity. | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1800 | IIRM-4067 | Bug | There is not option of tagging previous insurance address,company.etc. option as per BRD FR-SO-13 IN MY SO | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1801 | IIRM-4068 | Bug | There is no option of tagging pervious broker address ,company etc as per BRD FR-SO-14 IN MY SO | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1802 | IIRM-4069 | Bug | There is no option of tagging perviousTPA address ,company etc as per BRD FR-SO-15 IN my SO | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1803 | IIRM-4070 | Bug | all field data are missing in previous placement details in MY SO | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1804 | IIRM-4071 | Bug | IIRM: Broker: Validation error for display name is not getting removed on Create Broker process | Open | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1805 | IIRM-4072 | Bug | IIRM: Manage SO: Fail to retrive the data while opening "My SO" page | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1806 | IIRM-4073 | Bug | multiple address can't be able added and lot of confusion for the user after adding the address in risk location | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1807 | IIRM-4074 | Bug | Claim percentage is not automatically calculated based on the premium amount in SO | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1808 | IIRM-4075 | Bug | The Contact field is showing the Company Name in the filters on the My Opportunity screen. | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1809 | IIRM-4076 | Task | IIRM: Broker: Automation scripts for broker test cases | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1810 | IIRM-4077 | Task | IIRM: Broker: Automation scripts for broker contact test cases | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1811 | IIRM-4078 | Task | IIRM: TPA/Insuer/broker and contact bugfixes verification and regression tesing | Done | SaikumarMahanthi | iWork | IIRM-783 — SOW#56 - Insurer / TPA integration
1812 | IIRM-4079 | Task | IIRM:Automation test script for Insurer test cases | Done | SaikumarMahanthi | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1813 | IIRM-4080 | Task | IIRM:Automation test script for Insurer contact test cases | Done | SaikumarMahanthi | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1814 | IIRM-4081 | Task | IIRM: Company and Contact bugfixes and regression testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1815 | IIRM-4082 | Bug | IIRM: Support contact number not displayed on Overview page | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1816 | IIRM-4083 | Task | Task and meetings Drag n drop feature | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
1817 | IIRM-4084 | Task | Localization of Srilanka | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
1818 | IIRM-4085 | Bug | IIRM: TPA: Requirement missing | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1819 | IIRM-4086 | Task | Client Feedback - 29th May | Done | meghana |  | IIRM-764 — SOW#37 - Localisation
1820 | IIRM-4087 | Sub-task | Company - When you are creating a company and reaching a contact we need messaging | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1821 | IIRM-4088 | Sub-task | Company- Dev application - exit (from integrated flow) | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1822 | IIRM-4089 | Sub-task | Company- Extra screens for business card flow in integrated flow ( just for showcase) | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1823 | IIRM-4090 | Sub-task | Company- Breadcrumb messaging and exit - check | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1824 | IIRM-4091 | Sub-task | Company- Rename exit to cancel and go back to where we started | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1825 | IIRM-4092 | Sub-task | Company- Give a back button for the previous step (can be fixed with breadcrumb) | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1826 | IIRM-4093 | Sub-task | Company- Extra screens for filtering task message etc on side panel ( just for showcase) | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1827 | IIRM-4094 | Sub-task | Knowledge Central- Reverse sort by uploaded date | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1828 | IIRM-4095 | Sub-task | Knowledge Central- Add document upload (for people with privilege) | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1829 | IIRM-4096 | Sub-task | Knowledge Central- Side panel as well with doc type | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1830 | IIRM-4097 | Sub-task | Knowledge Central- Edit Privilege opens side panel and re-upload doc | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1831 | IIRM-4098 | Sub-task | Knowledge Central- Selected state of KC - top nav | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1832 | IIRM-4099 | Sub-task | Knowledge Central- Distinction between sections | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1833 | IIRM-4100 | Sub-task | Task and Meetings- Drag n drop | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1834 | IIRM-4101 | Sub-task | Task and Meetings- Survey of the meeting | Done | meghana |  | IIRM-4086 — Client Feedback - 29th May
1835 | IIRM-4102 | Bug | IIRM: Insurer: Requirements missing | Reopen | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1836 | IIRM-4103 | Bug | IIRM: Broker: Requirement missing | Reopen | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1837 | IIRM-4104 | Story | LinkedIn Integration (out of scope) | Draft | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
1838 | IIRM-4105 | Bug | IIRM: TPA Contact: Requirements missing | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1839 | IIRM-4106 | Bug | IIRM: InsurerContact: Requirements missing | Done | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
1840 | IIRM-4107 | Bug | IIRM: BrokerContact: Requirements missing | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
1841 | IIRM-4108 | Task | UI Changes- Company, Contact, Opportunity | Done | meghana |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1842 | IIRM-4109 | Bug | SO: Create: Edited opportunity details are not reflected on the Opportunity Details page | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1843 | IIRM-4110 | Bug | RO: List : Contact drill-down is not working on RO list page | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1844 | IIRM-4111 | Bug | So:Create:UI glitch observed after submitting Create SO form | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
1845 | IIRM-4112 | Bug | IIRM_Contact_UI: Manage Contact flow issue | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1846 | IIRM-4113 | Bug | IIRM_Company: Error Message indication is not displayed for the Invalid data GST field | Reopen | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1847 | IIRM-4114 | Bug | IIRM: Calendar: Past dates are visible in "To" calendar after selecting a "From" date | Reopen | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1848 | IIRM-4115 | Bug | Validation missing Contact name, address location, department, designation for user selection while creating a new Sales opportunity. | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1849 | IIRM-4116 | Bug | IIRM: Company : Edit Company Name is incorrectly shown during Company Creation flow | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1850 | IIRM-4117 | Bug | IIRM_Company_Contact: Manage Company Flow Error Messages | Done - Not Reproducible | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1851 | IIRM-4118 | Bug | IIRM: Company & Contacts: Display order of the details are based on the created order | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1852 | IIRM-4119 | Bug | IIRM_Company: Data inconsistency in Lead CRM Field | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1853 | IIRM-4120 | Bug | IIRM_Company: Residence option is displayed for Address Type dropdown | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1854 | IIRM-4121 | Bug | IIRM_All Features: The search functionality is not working | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1855 | IIRM-4122 | Task | IIRM: Automation Test script for TPA | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1856 | IIRM-4123 | Task | IIRM: Automation Test script for TPA Contact | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1857 | IIRM-4124 | Bug | IIRM_Company: Table setting are getting reset after browser refresh | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1858 | IIRM-4125 | Bug | IIRM_Contact: Contact Linking Flow with Company | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1859 | IIRM-4126 | Sub-task | UI Testing | Done | SaikumarMahanthi |  | IIRM-3303 — FR-MOPTY-01 Plan BD Activities
1860 | IIRM-4127 | Sub-task | UI Testing | Done | SaikumarMahanthi |  | IIRM-3419 — FR-MOPTY-02 Data Validation
1861 | IIRM-4128 | Sub-task | UI Testing | Done | SaikumarMahanthi |  | IIRM-3420 — FR-MOPTY-03 Meeting with KDM
1862 | IIRM-4129 | Task | IIRM: UAT Bug fix verification and Regression testing on latest build | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1863 | IIRM-4130 | Bug | IIRM_Insurer/Broker/TPA: Not able to create an Insurer/Broker/TPA | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1864 | IIRM-4131 | Bug | IIRM: TPA : Insurer: Broker: Contacts: Default country should be show on Address card | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1865 | IIRM-4132 | Bug | IIRM: Opty stages: Stages order mismatch | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1866 | IIRM-4133 | Bug | IIRM: OptyStages: Company Validation Fails During Data Validation Stage | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1867 | IIRM-4134 | Bug | IIRM: OptyStages: Oops something went wrong shown on selecting mandate details entry | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1868 | IIRM-4135 | Bug | IIRM: Opty stages: NO option to select * fields on Held cover note | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1869 | IIRM-4136 | Bug | IIRM: Opty stages: Policy hard copy stage failed | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1870 | IIRM-4137 | Bug | IIMR: Optystages: Policy Docket Handover and Policy Confirmation Stages Failing | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1871 | IIRM-4138 | Bug | IIMR: Contact: Inactive Companies and Contacts Not Displayed in List View | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1872 | IIRM-4139 | Bug | IIRM_Contacts: Inactive contacts are not displayed in the contact listing page | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1873 | IIRM-4140 | Bug | IIRM_Contact_UI: UI is Breaking when a contact display name with Max characters in Reporting To field | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
1874 | IIRM-4141 | Bug | IIRM: Opportunity: Company name field should get default, If SO is getting created through company portfolio | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1875 | IIRM-4142 | Bug | IIRM: Unable to create Contact>TPA:Insurer:Broker: | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1876 | IIRM-4143 | Bug | Commas to be there in Sum Insured/premium wherever applicable | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1877 | IIRM-4144 | Bug | Empty space in the box while company creation | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1878 | IIRM-4145 | Bug | Default currency to be INR instead of GBP | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1879 | IIRM-4146 | Bug | Incorrect Validation message | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1880 | IIRM-4147 | Bug | Add another contact | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1881 | IIRM-4148 | Bug | Personal history is 499 characters still maximum character validation | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1882 | IIRM-4149 | Bug | COuntry is hardcoded as India. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1883 | IIRM-4150 | Bug | Risk location details are not properly displayed in Overview | Done | Prajakta Vijay Kadam |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1884 | IIRM-4151 | Bug | Company name not autopopulating | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1885 | IIRM-4152 | Bug | IIRM: SO: Drill down not working for contact column in SO list view | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1886 | IIRM-4153 | Bug | When the user enters a comma in the "Annual Premium" field (like 10,000), and then goes to the next page and comes back using the "Previous" button, the field becomes empty. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1887 | IIRM-4154 | Bug | When the user enters data in the Profile or Strategy screen, then goes to the next page and clicks the Previous button, the entered data disappears. | Done | Prajakta Vijay Kadam |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1888 | IIRM-4155 | Sub-task | Design- Knowledge Central | Done | meghana |  | IIRM-3974 — Knowledge Central
1889 | IIRM-4156 | Bug | The user can add an opportunity without adding a contact to the company. | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1890 | IIRM-4157 | Bug | Company name already present | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1891 | IIRM-4158 | Task | IIRM: Insurer/TPA/Broker Spec wise testing and verify existing bugs | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1892 | IIRM-4159 | Task | IIRM: TPA/Insurer/Broker Contact Spec wise tesing and all bugfixes verification | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
1893 | IIRM-4160 | Bug | need to change the text in add contact page when navigate from add opportunity | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1894 | IIRM-4161 | Bug | BD can plan all activities in the application | Done | Keerthi Polepalle |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1895 | IIRM-4162 | Bug | Add status in manage companies | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
1896 | IIRM-4163 | Bug | Filter Scope - RBAC - User's and reporting user's companies/ contacts/ optys | Reopen | Keerthi Polepalle |  | IIRM-18 — SOW#1 - ACL & RBAC Control
1897 | IIRM-4164 | Bug | Contacts in Opportunity | Reopen | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1898 | IIRM-4165 | Bug | Add opty from company overview - take to wizard with selected company | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
1899 | IIRM-4166 | Bug | need to change the flow for cancel and back button | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1900 | IIRM-4167 | Bug | Opty Expriy date should not be editable once planning is done | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1901 | IIRM-4168 | Bug | IIRM: Smart Assistance: Let us help you create an opportunity should be shown on clicking Add SO from Smart Assistance | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1902 | IIRM-4169 | Task | Backlog Items - Company | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1903 | IIRM-4170 | Task | Backlog Items - Contact | Done | Keerthi Polepalle |  | IIRM-737 — SOW#10 - Add/Manage Contact
1904 | IIRM-4171 | Task | Backlog Items - TPA/Insurer/Broker | Done | Keerthi Polepalle |  | IIRM-783 — SOW#56 - Insurer / TPA integration
1905 | IIRM-4172 | Task | Backlog Items - Manage So | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1906 | IIRM-4173 | Story | Code Refactoring for AI generated - Tasks Meetings UI & APIs | Done | Rama K
1907 | IIRM-4174 | QAlity Test | IIRM: Opty View: Verify that user can navigate to the Opportunity Page and view all associated BD stages and activities. | Draft | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1908 | IIRM-4175 | QAlity Test | Opty: Broking Slip View | Draft | Leela Pakalapati | iWork
1909 | IIRM-4176 | QAlity Test | IIRM: Opty: Verify that user with access privilege can plan & complete the BD activities | Draft | Akhila Gattu |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1910 | IIRM-4177 | QAlity Test | IIRM: Opty: View and Confirm Policy Details | Draft | SaikumarMahanthi | iWork
1911 | IIRM-4178 | QAlity Test | IIRM: Opty: Verify that ISG user can navigate to the Opportunity Page and update default dates and assign executives for each activity. | Draft | Akhila Gattu |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1912 | IIRM-4179 | QAlity Test | Opty: Broking Slip Edit & Versioning | Draft | Leela Pakalapati | iWork
1913 | IIRM-4180 | QAlity Test | IIRM:Opty: Document Upload: Verify that user can upload required documents for a specific activity. | Draft | Akhila Gattu |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1914 | IIRM-4181 | QAlity Test | IIRM: Opty: Submit Policy Confirmation & Add Remarks | Draft | SaikumarMahanthi | iWork
1915 | IIRM-4182 | QAlity Test | IIRM:Opty: Save Activity Progress: Verify that user can save the entered data in an activity form without submitting it. | Draft | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1916 | IIRM-4183 | QAlity Test | IIRM:Opty: Submit for Approval: Verify that user can submit the activity data if the activity requires approval. | Draft | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1917 | IIRM-4184 | QAlity Test | IIRM:Opty: Mark Activity Complete: Verify that user can mark the activity as complete when submission or approval is not required. | Draft | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1918 | IIRM-4185 | QAlity Test | Opty: Broking Slip Additional Details & Approval | Draft | Leela Pakalapati | iWork
1919 | IIRM-4186 | QAlity Test | IIRM: Perform BD Opportunity Activties with privillaged user | Draft | Akhila Gattu | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
1920 | IIRM-4188 | QAlity Test | IIRM:Opty: Data Validation Edit: Verify that user with edit privileges can update opportunity and company details | Draft | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1921 | IIRM-4190 | QAlity Test | IIRM: RFP Policy Covers: Verify adding RFP collection through existing covers deatils | Draft | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1922 | IIRM-4191 | QAlity Test | IIRM:Opty: KDM Meeting: Schedule a meeting in real-time with valid KDM Meeting and verify the details | Draft | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1923 | IIRM-4192 | QAlity Test | IIRM: Opty: Schedule Hand Over Meet and verify the details in meeting | Draft | SaikumarMahanthi
1924 | IIRM-4193 | QAlity Test | IIRM:Opty: Mandate Details: Verify in mandate details received from the company into the system. | Draft | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1925 | IIRM-4195 | QAlity Test | Opty: Quote Entry – Insurer Selection & Details Entry | Draft | Leela Pakalapati | iWork
1926 | IIRM-4196 | QAlity Test | Opty: Quote Upload – Document & Remarks | Draft | Leela Pakalapati | iWork
1927 | IIRM-4197 | QAlity Test | Opty: Quote Entry Without Insurer Selection | Draft | Leela Pakalapati | iWork
1928 | IIRM-4198 | QAlity Test | IIRM:Opty: Upload Policy Document & Compare with Held Cover Note | Draft | SaikumarMahanthi | iWork
1929 | IIRM-4199 | QAlity Test | Opty: Quote Upload Without Document | Draft | Leela Pakalapati | iWork
1930 | IIRM-4201 | QAlity Test | Opty: Quote Entry – Multiple Insurers | Draft | Leela Pakalapati | iWork
1931 | IIRM-4203 | QAlity Test | IIRM: Opty: Upload Held Cover Note & Compare with Placement Slip | Draft | SaikumarMahanthi | iWork
1932 | IIRM-4204 | QAlity Test | IIRM: Opty: Capture Deviation Details | Draft | SaikumarMahanthi | iWork
1933 | IIRM-4205 | QAlity Test | Opty: QCR Policy & Quote Selection – Multiple Quotes | Draft | Leela Pakalapati | iWork
1934 | IIRM-4206 | QAlity Test | Opty: QCR Export – Excel & CSV | Draft | Leela Pakalapati | iWork
1935 | IIRM-4207 | QAlity Test | Verify that the system prevents QCR generation if no quotes are selected and displays an appropriate error message | Draft | Leela Pakalapati | iWork
1936 | IIRM-4209 | QAlity Test | Verify that QCR is generated even if some selected quotes are missing optional fields (e.g., remarks, clauses) and these are clearly indicated. | Draft | Leela Pakalapati | iWork
1937 | IIRM-4210 | QAlity Test | Opty: QCR With Large Number of Quotes | Draft | Leela Pakalapati | iWork
1938 | IIRM-4211 | QAlity Test | Opty: Meeting Scheduling & Stakeholder Selection | Draft | Leela Pakalapati | iWork
1939 | IIRM-4214 | QAlity Test | Opty: View Broking Slip & Generate Placement Slip | Draft | Leela Pakalapati | iWork
1940 | IIRM-4216 | QAlity Test | Opty: Placement Slip Submission & Manager Approval | Draft | Leela Pakalapati | iWork
1941 | IIRM-4217 | QAlity Test | Opty: Placement Slip Approval/Rejection Workflow | Draft | Leela Pakalapati | iWork
1942 | IIRM-4218 | QAlity Test | IIRM: Verify that when the self or dependent details are updated, the premium calculator automatically recalculates the premium correctly.. | Draft | SaikumarMahanthi | iWork
1943 | IIRM-4219 | QAlity Test | Opty: ISG: Verfiy the Notifications after optys internal transfer(BD to ISG) | Draft | Leela Pakalapati | iWork
1944 | IIRM-4220 | QAlity Test | Opty: ISG: Verify transformed optys should be assigned to stage Executives | Draft | Leela Pakalapati | iWork
1945 | IIRM-4221 | QAlity Test | Opty: ISG Quotes View: Verify that the user can view all quotes or opportunities assigned to them after the RFP stage is marked as complete. | Draft | Leela Pakalapati | iWork
1946 | IIRM-4222 | QAlity Test | Opty: ISG Plan Activities: Verify that the user can select an opportunity from the Manage Quotes section and plan ISG activities relevant to their role. | Draft | Leela Pakalapati | iWork
1947 | IIRM-4223 | QAlity Test | IIRM: Perform ISG Opportunity Activities with privileged user | Draft | Leela Pakalapati | iWork
1948 | IIRM-4224 | Task | Backlog for the PR-904 code refractoring | Done | VedaVyas |  | IIRM-749 — SOW#22 - Data Security (NFR)
1949 | IIRM-4225 | Task | Backlog for the PR-901 code refractoring | Done | VedaVyas |  | IIRM-749 — SOW#22 - Data Security (NFR)
1950 | IIRM-4226 | Bug | IIRM: Opportunities: While editing the opportunity details -> header should get display as edit Opportunity details | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1951 | IIRM-4227 | Bug | IIRM: Opty Stages: Validation error is not user friendly while Opportunity expiry date exceeds Opty stages | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1952 | IIRM-4228 | Bug | IIRM: Opty stages: Data validation : data validation not found thrown , on submitting data validation form | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1953 | IIRM-4229 | Bug | IIRM: Opty stages: KDM meeting: "Oops, Something Went Wrong" Error Displayed on Clicking KDM Meeting | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1954 | IIRM-4230 | Bug | IIRm: Opty Stages: Mandate entry details: Opportunity table not found error thrown on submitting mandate details | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1955 | IIRM-4231 | Bug | IIRM: Opty stages: RFP Data collection: RFP details entry: Empty page shown on RFP data collection stage | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1956 | IIRM-4232 | Bug | IIRM: Tasks & Notes issues | Done | SaikumarMahanthi | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
1957 | IIRM-4233 | Bug | IIRM: My Meetings" and "My Tasks" are both pointing to "my-meetings" page. | Done | SaikumarMahanthi | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
1958 | IIRM-4234 | Bug | IIRM: Opty stages: Planning stage: Cant update the planning stage once planning stage activities got successfully updated | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
1959 | IIRM-4235 | Bug | Planning of activity - Error showing up even if the date is before SO expiry date - "Date cannot exceed expiry Date" | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
1960 | IIRM-4237 | Bug | Add Contact - Address should be optional and should have only Residence | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
1961 | IIRM-4238 | Bug | Planning Default dates exceeding expiry date | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
1962 | IIRM-4239 | Bug | Address in ad company has residence in LOV | Done - Not Reproducible | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1963 | IIRM-4240 | Bug | Issue while creating task | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1964 | IIRM-4241 | Bug | IIRM: Knowledge central issues | Open | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
1965 | IIRM-4242 | Task | Side Menu & Top Menu Bar Changes | Done | Sai Vamsee K |  | IIRM-797 — SOW#69 - Manage Opportunities
1966 | IIRM-4318 | Bug | application logout by default when user add new document in knowledge center | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1967 | IIRM-4387 | Bug | IIRM: Company: Default Currency Selection Not Persisting When Navigating Using Previous/Next Options | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
1968 | IIRM-4388 | Bug | functionality of show completed check box was not working properly and user Confusion | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1969 | IIRM-4389 | Bug | Notes are not updating after submit; they appear only after a refresh. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1970 | IIRM-4390 | Bug | List view needs to be corrected. eg. latest companies created must be on top. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
1971 | IIRM-4459 | Story | <Place holder: Use it> | WORK IN PROGRESS | Sai Vamsee K
1972 | IIRM-4460 | Story | <Place Holder: Use it> | Open | Sai Vamsee K
1973 | IIRM-4461 | Story | <Place Holder: Use it> | Draft | Sai Vamsee K
1974 | IIRM-4462 | Story | <Place Holder: Use It> | Open | Sai Vamsee K
1975 | IIRM-4463 | Story | <Place Holder: Use It> | Open | Sai Vamsee K
1976 | IIRM-4464 | Story | <Place Holder: Use It> | Open | Sai Vamsee K
1977 | IIRM-4465 | Story | <Place holder: Use it> | Open | Sai Vamsee K
1978 | IIRM-4466 | Story | NFR-USA-001: Logout should invalidate the JWT tokenSession timeout also should clear the JWT token | Done | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1979 | IIRM-4467 | Story | NFR-USA-002: Captcha Implementation on Login Screen (Non Intrusive)MFA for login, forgot password rate limiting on Login, forgot password and logout pages, All these on any public pages in the application if they | Open | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1980 | IIRM-4468 | Story | NFR-USA-005: Terms and Conditions | PENDING PEER or LEAD REVIEW | Sai Vamsee K | IBP | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1981 | IIRM-4469 | Story | NFR-USA-007: The application cannot be opened in more than one browser in a system | Done | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1982 | IIRM-4470 | Story | NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc | Done | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1983 | IIRM-4471 | Story | NFR-USA-009: The module must be available 99.5% of the time, excluding scheduled maintenance | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1984 | IIRM-4472 | Story | NFR-USA-010: The system must maintain consistency of data during updates, merges, or concurrent access. | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1985 | IIRM-4473 | Story | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1986 | IIRM-4474 | Story | NFR-USA-012: The system shall respond to user actions within 3 seconds. | Open | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1987 | IIRM-4475 | Story | NFR-USA-013: The application must provide a common user interface for all user roles. | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1988 | IIRM-4476 | Story | NFR-USA-014: Dynamic logos and institution names must be context-sensitive and role-based - White labelling in Portal Configuration for IBP | Open | Sai Vamsee K | IBP | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1989 | IIRM-4477 | Story | NFR-USA-015: The system must show personalized welcome messages and profile information based on locale | Open | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1990 | IIRM-4478 | Story | NFR-USA-016: Notification banners must be dismissible and configurable based on role. | Open | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1991 | IIRM-4479 | Story | NFR-USA-017: Menus must be role-based and collapsible to improve navigation | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1992 | IIRM-4480 | Story | NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1993 | IIRM-4481 | Story | NFR-USA-020: In case of an exception, a proper error page with the relevant error code and message should be displayed | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1994 | IIRM-4482 | Story | NFR-USA-021: Guidelines for document management should be provided | Done | Sai Vamsee K | iWork | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1995 | IIRM-4483 | Story | NFR-USA-022: Bulk document download facility should be available | Done | Sai Vamsee K | iWork | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1996 | IIRM-4484 | Story | NFR-USA-024 - All telemetry data should be captured - Document explaining on how to reach to the telemtrics reports | Done | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1997 | IIRM-4485 | Story | NFR-USA-025: Teams Calendar and meeting integration in iWork | Draft | Sai Vamsee K | iWork | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1998 | IIRM-4486 | Story | NFR-USA-026: Data archival facility for all the logs should be available - Configuration notes to be captured as document for log retention and archival | Done | Sai Vamsee K | None | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
1999 | IIRM-4487 | Story | NFR-SEC-001: All categories of roles and permissions must be defined at the level of user creation - RBAC and Scope of Data Implementation | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2000 | IIRM-4488 | Story | NFR-SEC-002: SSO( Single Sign-On) or MFA(Multi-Factor Authentication) feature must be implemented based on the availability/requirement. | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2001 | IIRM-4489 | Story | NFR-SEC-005: The application must data loss or data corruption preventions - All the communication external to application and with in must be SSL driven | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2002 | IIRM-4490 | Story | NFR-SEC-006: Password encryption - Password must be stored in encrypted and hashed manner. Should never be able to decrypted | Duplicate | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2003 | IIRM-4491 | Story | NFR-SEC-008: On inactivity, session should timeout and logout the user. Time out period must be coming from configuration | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2004 | IIRM-4492 | Story | NFR-SEC-009: Authentication credentials like user ID and password cannot be displayed - Do not allow save password as much as possible | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2005 | IIRM-4493 | Story | NFR-SEC-015: The application must online Key Distribution - Use secure mechanism to expose API Keys for external party connecting to the platform. Expose the API keys only via https driven UI and must have timeout associated | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2006 | IIRM-4494 | Story | NFR-SEC-016: The application must manual Key loading process - Use salt along with secure key where encryption is being implemented | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2007 | IIRM-4495 | Story | NFR-SEC-017: PBE password distribution - Do not share the password when document is password protected. How the password must be constructed using PII information has to be via a different email | PENDING PEER or LEAD REVIEW | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2008 | IIRM-4496 | Story | NFR-SEC-018: The application must certificates Validation - Periodic 3rd party certificates validation needs to be implemented | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2009 | IIRM-4497 | Story | NFR-SEC-023: System-to-System Authentication - Any 3rd party communication must be passed only when there is an authentication layer is involved. Do not build open access 3rd party connectors | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2010 | IIRM-4498 | Story | NFR-SEC-024: Web Login: The login page must be on the version of SSL/TLS to protect authentication credentials in transit - Must use SSL and with approved versionsPassword must not be readable in transit | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2011 | IIRM-4499 | Story | NFR-SEC-025: Session Identifier Generation: The application must generate session identifiers (IDs) using a cryptographically secure pseudo-random number generator | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2012 | IIRM-4500 | Story | NFR-SEC-026: Session Identifier Passage: The application must prevent session identifiers from being passed over unencrypted channels | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2013 | IIRM-4501 | Story | NFR-SEC-031: Database Authentication: Application must use a common database Functional ID to connect to the database rather than passing through end user credentials to the database for access | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2014 | IIRM-4502 | Story | NFR-SEC-032: Database Password Protection in Storage: Database connection strings contain authentication data and, therefore, must be encrypted in storage. | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2015 | IIRM-4503 | Story | NFR-SEC-033: Database Password Protection in Transit: Application must enable/implement a secure protocol (e.g., SSL) to protect database passwords in transit | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2016 | IIRM-4504 | Story | NFR-SEC-034: Database Authorization: If the application uses a common database Functional ID, the application must conduct authorization checks on user actions for more granular user access control to the database | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2017 | IIRM-4505 | Story | NFR-SEC-044: PIN/Password Display: The application must prevent the echo of the PIN/Password upon entry | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2018 | IIRM-4506 | Story | NFR-SEC-047: PINS for Backend Authentication - Password should be accepted with NOT PII info in or as part of it. Maintain password policy to prevent this | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2019 | IIRM-4507 | Story | NFR-SEC-052: Cross Frame Scripting (XFS) | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2020 | IIRM-4508 | Story | NFR-SEC-053: SQL Injection Controls | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2021 | IIRM-4509 | Story | NFR-SEC-054: The application must ensure that the Business does not periodically remind its customers that manually changing their static passwords provides greater security | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2022 | IIRM-4510 | Story | NFR-SEC-059: The Open Web Application Security Project (OWASP) found top 10 steps are most effective ways to make the web applications/code to be more secured. | Duplicate | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2023 | IIRM-4511 | Story | NFR-SEC-060: The application must insecure Design is a new category currently, with a focus on risks related to design flaws | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2024 | IIRM-4512 | Story | NFR-SEC-062: The application must identification and Authentication Failures was previously Broken Authentication and is sliding down from the second position | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2025 | IIRM-4513 | Story | NFR-SEC-063: The application must software and Data Integrity Failures is a new category for 2021, focusing on making assumptions related to software updates, critical data, and CI/CD pipelines without verifying integrity. | Open | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2026 | IIRM-4514 | Story | NFR-SEC-064: iWork Application should not allow right click, copy(ctrl+c) and contents capturing, print screen functionality across all the forms in application. | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2027 | IIRM-4515 | Story | NFR-SEC-066: The platform must support Single Sign-On (SSO) using OAuth2, OpenID Connect, or LDAP | Done | Sai Vamsee K | None | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2028 | IIRM-4516 | Story | NFR-OTH-001: The application must ensure that Any application should pass the VAPT assessment test. Assessment is subjected with in the lines of the client/customer or end user requirements | Duplicate | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2029 | IIRM-4517 | Story | NFR-OTH-002: Application Identity | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2030 | IIRM-4518 | Story | NFR-OTH-003: The application must perimeter Security | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2031 | IIRM-4519 | Story | NFR-OTH-004: Input Length: The application must limit the length of each user input field and validate the length of the supplied input on the server side of the connection. | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2032 | IIRM-4520 | Story | NFR-OTH-005: The application must prevent 'redirect' (i.e., 302 Object moved) | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2033 | IIRM-4521 | Story | NFR-OTH-006: The application must file Upload | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2034 | IIRM-4522 | Story | NFR-OTH-009: The application must acceptable SMS Uses. On consent only. | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2035 | IIRM-4523 | Story | NFR-OTH-010: Sensitivity of Embedded Files: Embedded files in the application must be implemented, if used, limited to files with data classified as Public only | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2036 | IIRM-4524 | Story | NFR-OTH-011: The application must secondary Channel for SMS | PENDING PEER or LEAD REVIEW | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2037 | IIRM-4525 | Story | NFR-OTH-012: Generic Error Messages | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2038 | IIRM-4526 | Story | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure | Open | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2039 | IIRM-4527 | Story | NFR-OTH-016: The application must injection slides. Security Scan of Code periodically | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2040 | IIRM-4528 | Story | NFR-OTH-017: The application must security Misconfiguration | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2041 | IIRM-4529 | Story | NFR-OTH-018: The application must server-Side Request Forgery is added from the Top 10 community survey (#1) - RBAC on APIs | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2042 | IIRM-4530 | Story | NFR-OTH-019: The platform must support distributed caching and CDN integration for improved performance | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2043 | IIRM-4531 | Story | NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution. | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2044 | IIRM-4532 | Story | NFR-OTH-021: The system must support localization including language translation, currency, tax ID formats, and timezone handling. | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2045 | IIRM-4533 | Story | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. | Open | Sai Vamsee K | iWork | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2046 | IIRM-4534 | Story | NFR-OTH-023: The platform must provide centralized logging, error codes, and alert mechanisms. | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2047 | IIRM-4535 | Story | NFR-OTH-024: The system must generate structured logs compatible with ELK stack or Datadog. | Done | Sai Vamsee K | None | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
2048 | IIRM-4536 | Story | NFR-MAI-002: Secrets should not be part of code and must be coming from key value kind of service | Done | Sai Vamsee K | None | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
2049 | IIRM-4537 | Story | NFR-MAI-004: Application Integrity. There must be a mechanism implemented to protect application configuration stores and maintain the integrity of critical application files | Done | Sai Vamsee K | None | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
2050 | IIRM-4538 | Story | NFR-MAI-005: Audit/Logging of SMS: The application must capture SMS messages in audit logs | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
2051 | IIRM-4539 | Story | NFR-MAI-006: Sensitive Data Logging Prevention | Duplicate | Sai Vamsee K | None | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
2052 | IIRM-4540 | Story | NFR-MAI-007: The application must protection of Source Code | Done | Sai Vamsee K | None | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
2053 | IIRM-4541 | Story | NFR-MAI-012: The application must support global platform configurations including module enable/disable, API Gateway and Communication Gateway settings. | Done | Sai Vamsee K | None | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
2054 | IIRM-4542 | Story | NFR-MAI-014: Any long running query should be terminated in 300 seconds. It should be configurable. | WORK IN PROGRESS | Sai Vamsee K | None | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
2055 | IIRM-4543 | Story | NFR-INT-003 - 3rd party communication must not go through customer infra. Access must be via credentail driven for SCP, SFTP or API based or any other access. All these must be via publicly accessible end points on | Draft | Sai Vamsee K | None | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
2056 | IIRM-4544 | Story | NFR-INT-006: The application must patch Management | Open | Sai Vamsee K | None | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
2057 | IIRM-4545 | Story | NFR-INT-008 - Connector framework driven 3rd party access must be implemented. This gateway must be configurable for credentials, access point changes. Attribute mapping should be supported | Done | Sai Vamsee K | None | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
2058 | IIRM-4546 | Story | NFR-INT-009 - Should support Email, In App Notifications | Done | Sai Vamsee K | None | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
2059 | IIRM-4547 | Story | NFR-INT-010: API kit documentation should be available - Application must expose API docs as Swagger docs for all the environments except Production | Done | Sai Vamsee K | None | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
2060 | IIRM-4548 | Story | NFR-INT-011 - Telemtry of all the services of application must be available | Done | Sai Vamsee K | None | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
2061 | IIRM-4549 | Story | NFR-DAT-001: Backup and Recovery must be configured of the data sources (Database, Filesystem)Period recovery trails (mock drills) needs to be performed | Done | Sai Vamsee K | None | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
2062 | IIRM-4550 | Story | NFR-DAT-016: Periodic Security Scan and RBAC valiadtion on None UI and APIs must be done | Done | Sai Vamsee K | None | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
2063 | IIRM-4551 | Story | NFR-COM-001 - Data change needs to be captured in audit history | Done | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2064 | IIRM-4552 | Story | NFR-COM-004 - Sensitive data must not go to Audit History capture | Done | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2065 | IIRM-4553 | Story | NFR-COM-005: Data pertaining to PII must be protected by RBAC, Scoping and Masking | PENDING PEER or LEAD REVIEW | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2066 | IIRM-4554 | Story | NFR-COM-006: Make sure Keys are taken from AWS and are being maintained via key valut, this avoid the need of self key generation | Done | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2067 | IIRM-4555 | Story | NFR-COM-007: The application must password Based Encryption (PBE) | Done | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2068 | IIRM-4556 | Story | NFR-COM-008: Key Backup and Archiving - Data archival/backup process should have recovery mock drills and the same must be preserved (recovery drill logs) | Done | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2069 | IIRM-4557 | Story | NFR-COM-009: The application must prevent unauthorized access | Done | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2070 | IIRM-4558 | Story | NFR-COM-011: Secure Cookies: Application uses cookies containing Confidential or higher information | Open | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2071 | IIRM-4559 | Story | NFR-COM-012 - Avoid local storage for sensitive data in browser | Done | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2072 | IIRM-4560 | Story | NFR-COM-013: The application must sensitive Data Protection: Does the application encrypt sensitive data such as PII , authentication data and business sensitive information during transit | PENDING PEER or LEAD REVIEW | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2073 | IIRM-4561 | Story | NFR-COM-014: The application must sensitive Data Protection at Rest. Does the application encrypt sensitive data such as PII, authentication data and business sensitive information during storage? | PENDING PEER or LEAD REVIEW | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2074 | IIRM-4562 | Story | NFR-COM-020: Push Notification Controls - Must use an established provide for push notification | Open | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2075 | IIRM-4563 | Story | NFR-COM-022: Information Classification | Open | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2076 | IIRM-4564 | Story | NFR-COM-025 - Consent management must include display, revoke, and audit trail of actions based on consent. | Done | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2077 | IIRM-4565 | Story | NFR-COM-026 - The system must handle PII with consent-based processing, auto-de linking of data based on the consent, and anonymization. | Open | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2078 | IIRM-4566 | Story | NFR-COM-027 - Audit History must also capture user actions, related API usage and Module interactions Separate these data capture form entity level audit capture | Draft | Sai Vamsee K | None | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
2079 | IIRM-4567 | Bug | unable to create meeting becuase of un -related pop-up | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2080 | IIRM-4568 | Bug | In create meeting attachment is mandatory with out attachment user unable create meeting | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2081 | IIRM-4569 | Bug | +2 tag is not working knowledge center screen | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2082 | IIRM-4570 | Bug | once time selected there no option to change the time in all time selection of my task . | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2083 | IIRM-4571 | Bug | Getting error while clicked o task checkbox | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2084 | IIRM-4572 | Bug | IIRM_Tasks: The number values should display with the comma | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2085 | IIRM-4573 | Bug | IIRM_Tasks: The Created Tasks/Changes are reflecting after the browser refresh | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2086 | IIRM-4574 | Bug | IIRM: Tasks: Value of the Priority dropdown is not retained after save | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2087 | IIRM-4575 | Bug | IIRM_Tasks: The clickable functionality of the Right Arrow in the Tasks card is not working | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2088 | IIRM-4576 | Bug | IIRM: Tasks & Meetings: UI: UI Issues | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2089 | IIRM-4577 | Bug | IIRM_Taks: Error Messages are not user friendly | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2090 | IIRM-4578 | Bug | IIRM_Tasks: Able to create a task without providing data to the Description field | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2091 | IIRM-4579 | Bug | IIRM_Tasks: The task created on the 7th day is reflecting in the Future column in task listing page | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2092 | IIRM-4580 | Bug | IIRM_Tasks: Order of the Task cards should be as per the Task Due Date | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2093 | IIRM-4581 | Bug | IIRM: Tasks: Incorrect Tab Highlights on "My Calendar" from side navigationbar | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2094 | IIRM-4582 | Bug | IIRM: Opty stages: Selected Dates Not Persisting in Planning Stage | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2095 | IIRM-4583 | Bug | IIRM: Opty stages: Few stages were blocked to test | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2096 | IIRM-4584 | Bug | IIRM: Tasks & Meeting: Able to create a Task and Meetings for current date | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2097 | IIRM-4585 | Bug | IIRM: Notes: Previously opened tab is displaying when we open the Note to edit | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2098 | IIRM-4586 | Bug | IIRM: Opty stages: Data validation issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2099 | IIRM-4587 | Bug | IIRM: Opty stages: KDM meeting issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2100 | IIRM-4588 | Bug | IIRM: Opty stages: Mandate details entry issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2101 | IIRM-4589 | Story | Policy Creation Post Placement Slip | Done | Sai Vamsee K |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2102 | IIRM-4590 | Bug | IIMR: Opty stages: RFP Data Collection | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2103 | IIRM-4591 | Bug | IIRM: Opty stages: RFP data entry issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2104 | IIRM-4592 | Story | State Model: Manage Sales Opportunity State Transitions | Done | Sai Vamsee K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2105 | IIRM-4593 | Bug | IIRM: Opty stages: Premium calculation issues | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2106 | IIRM-4594 | Story | View Policies in Manage Policies | Open | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2107 | IIRM-4595 | Bug | IIRM: Opty stages: Held Cover issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2108 | IIRM-4596 | Bug | IIRM: Opty Stages: policy hard cover Receipt issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2109 | IIRM-4597 | Bug | Due date error | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2110 | IIRM-4598 | Bug | IIRM: Opty stages: Policy Docket hand over issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2111 | IIRM-4599 | Bug | IIRM: Opty stages: Hand Over meet issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2112 | IIRM-4600 | Bug | If future dates are disabled in the opportunity planning screen, the user won't be able to select them. So, to allow planning, future dates should be enabled. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2113 | IIRM-4601 | Task | Data archival | Done | meghana |  | IIRM-749 — SOW#22 - Data Security (NFR)
2114 | IIRM-4602 | Task | Bulk Messaging Mechanisms | Draft | meghana |  | IIRM-761 — SOW#34 - Notifications Management
2115 | IIRM-4603 | Bug | Company Name must be freezed in Opty | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2116 | IIRM-4604 | Bug | Employee participants selection issue | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2117 | IIRM-4605 | Bug | Unable to submit activities | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2118 | IIRM-4606 | Bug | Fetch mandate not working | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2119 | IIRM-4607 | Bug | Error while saving mandate | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2120 | IIRM-4608 | Bug | RFP Details Entry issues | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2121 | IIRM-4609 | Bug | Premium calculation activity submit issue | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2122 | IIRM-4610 | Task | Service-Registry health issue devOps config | Done | VedaVyas |  | IIRM-797 — SOW#69 - Manage Opportunities
2123 | IIRM-4611 | Bug | IIRM: Tasks & Meeting: Scroll bar issues | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2124 | IIRM-4612 | Bug | IIRM: Knowledge Central: Task menu is overlapped with Add Documents overlay | Done | Leela Pakalapati | iWork | IIRM-768 — SOW#41 - Knowledge Central
2125 | IIRM-4613 | Task | Audit Data Capturing | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2126 | IIRM-4614 | Task | Handling PII data mechanism | Draft | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2127 | IIRM-4615 | Bug | IIRM_Notes: Not able to view the created notes in the Notes List | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2128 | IIRM-4616 | Bug | IIRM: SO: Opty Creation: Unauthorized Access shown after filling basic details | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2129 | IIRM-4617 | Bug | IIRM: Opty stages: 400 Error Thrown While Fetching Stages Data | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2130 | IIRM-4618 | Bug | Date format standardization across the application | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2131 | IIRM-4619 | Bug | Display all participants added in planning on the activity along with the owner | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2132 | IIRM-4620 | Bug | Allow typing within the multi-select menus & display the selected values below the menu | Done | Keerthi Polepalle |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2133 | IIRM-4621 | Bug | Font size to be increased for headings | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2134 | IIRM-4622 | Bug | Feedback from IIRM: Expand the side nav bar whenever an icon is clicked | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2135 | IIRM-4623 | Bug | 105% on header on opty completion | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2136 | IIRM-4624 | Bug | Risk location to display address line 1 along with city | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2137 | IIRM-4625 | Bug | When opening an existing meeting or task, a pop-up appears on the right side with a button labelled 'Create' | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2138 | IIRM-4626 | Bug | "When we create an activity plan, color dots are shown on the calendar to indicate the planned dates. However, if multiple plans fall on the same day or overlap with previous (past) dates, the UI becomes cluttered and visually disturbed." | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2139 | IIRM-4627 | Bug | IIRM_Knowledge Central: Created document is not reflecting on the UI | Done | Leela Pakalapati | iWork | IIRM-768 — SOW#41 - Knowledge Central
2140 | IIRM-4628 | Bug | Error while saving activity | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2141 | IIRM-4629 | Task | IIRM: Opportunites first set of stages testing | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2142 | IIRM-4630 | Task | IIRM: Opportunites secound set of Stages testing | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2143 | IIRM-4631 | Task | IIRM: Task & Notes Testing | Done | SaikumarMahanthi |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2144 | IIRM-4632 | Task | IIRM: Task & Meetings, Notes Testing & Bug Fixes verification | Done | SaikumarMahanthi |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2145 | IIRM-4633 | Task | IIRM: Knowledge central UI Verification | Done | SaikumarMahanthi |  | IIRM-768 — SOW#41 - Knowledge Central
2146 | IIRM-4634 | Task | IIRM: Knowledge central Bugfixes and regression testing | Done | SaikumarMahanthi |  | IIRM-768 — SOW#41 - Knowledge Central
2147 | IIRM-4635 | Bug | Error on submission of KDM Meeting | Done - Not Reproducible | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2148 | IIRM-4636 | Task | IIRM: Opportunites Stages Bugfixes Verification & Regression testing | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2149 | IIRM-4637 | QAlity Test | IIRM: Knowledge Central: Verify category-based document upload, display, and download | Draft | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
2150 | IIRM-4638 | QAlity Test | IIRM: KnowledgeCentral: Verify document search and filtering by name and category | Draft | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
2151 | IIRM-4639 | QAlity Test | IIRM: Knowledge Central: Verify document management actions (add, delete, category change) by Admin | Draft | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
2152 | IIRM-4640 | QAlity Test | IIRM: Knowledge Central: Verify restricted access for non-admin users | Draft | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
2153 | IIRM-4641 | QAlity Test | IIRM: Knowledge Central: Verify recent and popular document widgets display correctly | Draft | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
2154 | IIRM-4642 | QAlity Test | IIRM: Knowledge Central: Verify adding a new document with category selection, file validations, and permissions | Draft | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
2155 | IIRM-4643 | Bug | IIRM: Dropdown Search Should Display All Records from DB, Not Limited by Pagination | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2156 | IIRM-4644 | Bug | document upload is mandatory in "planning" ,can't upload mandatory | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2157 | IIRM-4645 | Bug | kdm meeting can't be submit because of the selection issues in fields | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2158 | IIRM-4646 | Bug | "When all fields in an existing record are updated, the meeting is not syncing properly." | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2159 | IIRM-4647 | Task | Localization code need to refractor | Done | VedaVyas |  | IIRM-764 — SOW#37 - Localisation
2160 | IIRM-4648 | Bug | IIRM: Company creation : Searched string is getting changed | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2161 | IIRM-4649 | Bug | IIRM: Knowledge Central: Unable to upload the document: Internal Server Error | Done - Not Reproducible | Prabhakar Mantripragada |  | IIRM-768 — SOW#41 - Knowledge Central
2162 | IIRM-4650 | Bug | IIRM: SO: "Cannot PUT /opportunity" error message is displayed | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2163 | IIRM-4651 | Bug | Unable to create opty for any company | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2164 | IIRM-4652 | Bug | IIRM: All Features: "Add Opportunity" button is missing in Company View details screen | Done | Leela Pakalapati |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2165 | IIRM-4653 | Bug | STatus ID issue in RFP Data collection stage | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2166 | IIRM-4654 | Bug | ISG planning shows not yet planned | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2167 | IIRM-4655 | Bug | IIRM: All Features: Data is not displayed in the quick cards | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
2168 | IIRM-4656 | Bug | No Option to mark the task, meeting or notes as complete | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2169 | IIRM-4657 | Bug | Dropdown values getting blank while updating meetings and tasks | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2170 | IIRM-4658 | Bug | IIRM: Company allowed to be marked Inactive while Active optys are linked to it | Done | Prabhakar Mantripragada |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2171 | IIRM-4659 | Bug | IIRM: Contacts: Static values shown in "Departments" dropdown | Done | Leela Pakalapati |  | IIRM-737 — SOW#10 - Add/Manage Contact
2172 | IIRM-4660 | Bug | IIRM: opportunity: "Oops! Something went wrong" screen is displayed | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2173 | IIRM-4661 | Bug | IIRM: Opty Stages: Credit sharing% is not allowing decimals | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2174 | IIRM-4662 | Bug | IIRM: Knowledge Central: Missing Confirmation Alert on Document Create and Delete Actions | Done | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
2175 | IIRM-4663 | Bug | IIRM: Knowledge Central: Duplicate Tags Are Being Added When Editing a Document | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-768 — SOW#41 - Knowledge Central
2176 | IIRM-4664 | Bug | IIRM: Task: Unable to edit the tasks from All tab | Done | Akhila Gattu | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2177 | IIRM-4665 | Bug | IIRM: Meeting: Deleted Meeting Persists on UI Until Page Reload | Done | Akhila Gattu | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2178 | IIRM-4666 | Bug | IIRM: Meeting: Meeting Type Not Updating and Company Contacts State Not Retained During Meeting Update | Done | Akhila Gattu | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2179 | IIRM-4667 | Bug | IIRM: Task: Created Task Gets Removed When Updating Task Date | Done | Akhila Gattu | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2180 | IIRM-4668 | Bug | IIRM: Meeting: Unable to update meeting if location got changed | Done | Akhila Gattu | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2181 | IIRM-4669 | Bug | IIRM: Opportunities: Oops something went wrong shown after update opportunity. | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2182 | IIRM-4670 | Bug | IIRM: Company create is not working Error->Property "state" was not found in "OrgBranch | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2183 | IIRM-4671 | Task | Refactoring for CD in Placmentslip - Schema level and Transactions to be maitained | Open | Rama K |  | IIRM-781 — SOW#54 - CD Management
2184 | IIRM-4672 | Bug | No users are shown in additional participants drop down. | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2185 | IIRM-4673 | Bug | Future date selection is not allowed in planning | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2186 | IIRM-4674 | Bug | IIRM: Access Denied Error After Submitting Opportunity Activities | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2187 | IIRM-4675 | Bug | IIRM: Company Creation Fails Due to Invalid URL Error | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2188 | IIRM-4676 | Bug | IIRM: Contact list are not displayed on so contact filters | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2189 | IIRM-4677 | Bug | IIRM: BD Planing is not working error->Opportunity status with key OPPORTUNITY_STATUS_SUBMITTED not found | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2190 | IIRM-4678 | Bug | IIRM: Reset Password: Not able to reset the password | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2191 | IIRM-4679 | Bug | IIRM: Reset Password: UI | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2192 | IIRM-4680 | Bug | IIRM: Opportunity: Assigned To field missing on create opportunity | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2193 | IIRM-4681 | Bug | IIRM: Broker Slip generation stage save version & submit not working | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2194 | IIRM-4682 | Bug | IIRM: Opty stages: Held cover note on submit error shown as Unsupported opportunity table | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2195 | IIRM-4683 | Bug | IIRM: Opty stages: Policy Hard copy receipt error shown Unsupported opportuity table | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2196 | IIRM-4684 | Bug | IIRM: Opty stages: Policy Docket hand over error shown on UI " Unsupported opportunity table " | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2197 | IIRM-4685 | Bug | IIMR:Hand Over met: Handover error shown s "Unsupported opportunity table" | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2198 | IIRM-4686 | Bug | IIRM: Opty stages: Opportunity Lost shown as : Unsupported opportunity table | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2199 | IIRM-4687 | Bug | IIRM: Opty stages: Policy confirmation : on clicking submit "Property entry deviation config should not exist" shown | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2200 | IIRM-4688 | Task | IIRM: Regression testing and UAT Bugfixes verification | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2201 | IIRM-4689 | Task | IIRM: Testing Smart Assistant and Create Wizard flow | Done | SaikumarMahanthi | iWork | IIRM-754 — SOW#27 - AI - Smart Adds
2202 | IIRM-4690 | Sub-task | Feedback changes | Done | gowtham |  | IIRM-1786 — UX/UI - Create/List and View TPA
2203 | IIRM-4691 | Task | Feedback changes | Done | gowtham |  | IIRM-739 — SOW#12 - Manage Employees
2204 | IIRM-4692 | Bug | Unable to view Opty | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2205 | IIRM-4693 | Bug | Department dropdown in smart srch filter are not available while creating contact | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2206 | IIRM-4694 | Bug | In priority dropdown All & default values have been added | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2207 | IIRM-4695 | Bug | State Option is only British COlumbia while creating company | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2208 | IIRM-4696 | Bug | Page unresponsive | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2209 | IIRM-4697 | Bug | city filter is showing wrong data in company screen | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2210 | IIRM-4698 | Bug | Personal History in contact details | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2211 | IIRM-4699 | Bug | not able to save or submit activity | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2212 | IIRM-4700 | Task | IIRM: Notification Issues | Done | SaikumarMahanthi | iWork | IIRM-761 — SOW#34 - Notifications Management
2213 | IIRM-4701 | Bug | IIRM: Updated Details Are Reflected on Task Update | Done | SaikumarMahanthi | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2214 | IIRM-4702 | Bug | Java script errors need to be addressed | Done - Not Reproducible | Neeraj Joshi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2215 | IIRM-4703 | Bug | Create Insurer - Insurance company type | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2216 | IIRM-4704 | Bug | Edit option not available | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2217 | IIRM-4705 | Bug | Company location is blank while add contact | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2218 | IIRM-4706 | Bug | Cannot add opty as contacts are not visible | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2219 | IIRM-4707 | Bug | Unable to create meeting- company participants not visible | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2220 | IIRM-4708 | Bug | IIRM: UAT: Company: LOV's are missing in the Parent Company Name in UAT environment | Done - Not Reproducible | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2221 | IIRM-4709 | Bug | IIRM: UAT: RBAC: Previous user details are populated | Done | Leela Pakalapati | iWork | IIRM-18 — SOW#1 - ACL & RBAC Control
2222 | IIRM-4710 | Bug | IIRM: UAT: opportunity: Inactive users are displayed in the Assigned To field in Opty filters | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2223 | IIRM-4711 | Bug | IIRM: UAT: opportunity: Change label name from Assigned To to BD_CRM | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2224 | IIRM-4712 | Bug | IIRM: UAT: opportunity: Changes Label names from Opportunity type to SO and select SO option by default and make it readonly | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2225 | IIRM-4713 | Bug | IIRM: Create wizard: "Unknown" text is displayed instead of the company's country | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2226 | IIRM-4714 | Bug | IIRM:Show completed should not shown on tasks tab | Done | Akhila Gattu | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2227 | IIRM-4715 | Bug | IIRM: RBAC: The Contact list should display for all users in the Create Wizard screen | Done | Leela Pakalapati | iWork | IIRM-18 — SOW#1 - ACL & RBAC Control
2228 | IIRM-4716 | Bug | IIRM: UAT: Count is not updating in the company quick cards | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2229 | IIRM-4717 | Bug | IIRM:UAT: Opty Stages: "Oops Something went wrong!" screen is displayed by clicking on the Premium Calculation tab | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2230 | IIRM-4718 | Bug | IIRM: UAT: RBAC: The Contact list should display for all users in the Create Wizard screen | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2231 | IIRM-4719 | Bug | IIRM: UAT: Company: "Unknown" text is displayed instead of the company's country | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2232 | IIRM-4720 | Bug | IIRM: Invalid state shown on GST card. | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2233 | IIRM-4721 | Bug | IIRM: Company: Invalid limit count shown on strategy page | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2234 | IIRM-4722 | Bug | IIRM: Company: LOV's are missing in the State Dropdown for GST Details section | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2235 | IIRM-4723 | Bug | IIRM: UI: Inconsistency message text is displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2236 | IIRM-4724 | Bug | IIRM: Company: "The id 31 does not match a valid look value for statusLid." message is displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2237 | IIRM-4725 | Bug | IIRM: Opty Stages: The activity planned date is not auto updating till screen refreshes | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2238 | IIRM-4726 | Bug | IIRM: Opty Stages: Data Validation: Able to submit the Data validation step without validating the data | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2239 | IIRM-4727 | Bug | IIRM: opportunity: "Unsupported opportunity table: opportunity_rfp_cover_detail" message is displayed while saving RFP Data Collection activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2240 | IIRM-4728 | Bug | IIRM: Opty stages: RFP Details Entry error thrown on submit | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2241 | IIRM-4729 | Bug | IIRM: Contact: Company should get auto prefill while creating contact | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2242 | IIRM-4730 | Bug | IIRM: Company: Default 0 showing on Annual premium | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2243 | IIRM-4731 | Bug | IIRM: Default $ symbol showing on compensation payable filed | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2244 | IIRM-4732 | Bug | IIRM: Opty stages: Unsupported opportunity table: opportunity_rfp_cover_detail error shown for RFP Data collection | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2245 | IIRM-4733 | Bug | IIRM: Opty stages: Unable to submit Enter Quote stage | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2246 | IIRM-4734 | Bug | IIRM: Opty stages: QCR Generation stage not working | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2247 | IIRM-4735 | Bug | IIRM: Tasks & Meetings: All the companies are not listed in the company dropdown | Done | Leela Pakalapati | IBP | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2248 | IIRM-4736 | Bug | IIMR: Notes: For created notes , first time update not happening | Done | Akhila Gattu | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2249 | IIRM-4738 | Task | Display Policy List view | Done | meghana |  | IIRM-777 — SOW#50 - Policy Configurator
2250 | IIRM-4739 | Task | Single Policy View | Done | meghana |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2251 | IIRM-4740 | Task | Notifications Management | Done | meghana |  | IIRM-761 — SOW#34 - Notifications Management
2252 | IIRM-4741 | Task | Tasks and Meetings Drag and Drop | Done | meghana |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2253 | IIRM-4743 | Task | Opty Activity Scroll | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
2254 | IIRM-4744 | Story | User Management: Add, Edit, Delete | Done | meghana |  | IIRM-744 — SOW#17 - User Management
2255 | IIRM-4745 | Task | Role and ACL Map: Add edit del | Done | meghana |  | IIRM-18 — SOW#1 - ACL & RBAC Control
2256 | IIRM-4746 | Task | Previous TPA / Broker / Insurer Placement | Done | meghana |  | IIRM-742 — SOW#15 - Add/Manage TPA
2257 | IIRM-4747 | Task | Cover Data AI | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
2258 | IIRM-4748 | Task | Localization | Done | meghana |  | IIRM-764 — SOW#37 - Localisation
2259 | IIRM-4749 | Task | Add Contact, uncontrolled ACL | Done | meghana |  | IIRM-737 — SOW#10 - Add/Manage Contact
2260 | IIRM-4750 | Bug | Add Contact in Opty | Done | meghana |  | IIRM-737 — SOW#10 - Add/Manage Contact
2261 | IIRM-4752 | Task | Smart Adds: Company flow and Add Intelligent Data | Done | meghana |  | IIRM-754 — SOW#27 - AI - Smart Adds
2262 | IIRM-4753 | Bug | KDM Meeting - User has no option to complete the meeting | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2263 | IIRM-4754 | Bug | Make password reset guidelines in blue colour | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2264 | IIRM-4755 | Bug | add a floater scroll down in the login page | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2265 | IIRM-4756 | Task | New iWork: Source code + tech doc + Architecture (Infra + source code), presentation next week | Done | meghana |  | IIRM-3817 — Data Migration
2266 | IIRM-4757 | Task | To give template for data migration for policies | Done | meghana |  | IIRM-3817 — Data Migration
2267 | IIRM-4758 | Task | Write a script for data mig, make it automated (csv) | Done | meghana |  | IIRM-3817 — Data Migration
2268 | IIRM-4759 | Task | Group Company: All Individual companies | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2269 | IIRM-4760 | Bug | alphabets should not enter in Annual premium field | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2270 | IIRM-4761 | Bug | IIRM: Opty creation progress: 5% completion shown on BD Planning | Done | Prabhakar Mantripragada |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2271 | IIRM-4762 | Bug | IIRM: Unauthorised Access: User able to view company but unable to complete Data Validation stage | Done | Prabhakar Mantripragada |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2272 | IIRM-4763 | Bug | Without Validating the Opty details, able to submit the activity "Data Validation" | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2273 | IIRM-4764 | Bug | IIRM: SO: Server is down for Opportunity page. | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2274 | IIRM-4765 | Bug | IIRM: Opty Stages: Mandate Details Entry: Compensation Type has additional value | Done | Prabhakar Mantripragada |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2275 | IIRM-4766 | Task | Check tool for generating CSAT Survey + Course and assessment | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2276 | IIRM-4767 | Task | IIRM: To give LoVs for meeting feedback | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2277 | IIRM-4768 | Bug | Mandate Details Entry - Date fields validation to be changed | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2278 | IIRM-4770 | Sub-task | Smart Action Panel should show Contact sensitivity in search | Draft | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2279 | IIRM-4772 | Task | Check application and change the navigation breadcrumb behaviour | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2280 | IIRM-4773 | Bug | Quote 2 is not getting added | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2281 | IIRM-4774 | Bug | Covers List is missing in Policy hard Copy receipt | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2282 | IIRM-4775 | Task | Broking slip download in Excel | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2283 | IIRM-4776 | Bug | In Quote comparison: Under Premium comparison, similar table should come | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2284 | IIRM-4777 | Bug | The numbers of activities should be circled and BD stages to have 1 colour and ISG to have one colour | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2285 | IIRM-4778 | Task | Using AI: Policy to Quote | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2286 | IIRM-4779 | Task | Using AI: Policy to Create Opportunity | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2287 | IIRM-4780 | Bug | IIRM: Opportunity Stages: Doc Upload Issues | Done | Prabhakar Mantripragada |  | IIRM-760 — SOW#33 - Document Generation
2288 | IIRM-4781 | Bug | opty planning for activity meeting final negotiation can't submit because TPA id pop-up | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2289 | IIRM-4782 | Bug | No quotes are reflecting for comparision | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2290 | IIRM-4783 | Bug | Enter quote process is very confusing. After versions are displyayed we have toadd quote and the details arent synced from the version. Also the 'compare' is not working as well as 'submit for approval' | Done | Prajakta Vijay Kadam |  | IIRM-756 — SOW#29 - Manage ISG Stages
2291 | IIRM-4784 | Bug | submit button is disable in brokering slip generation | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2292 | IIRM-4785 | Bug | IIRM: Opty stages: Duplicate stages shown in Activities for newly created SO | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2293 | IIRM-4786 | Bug | IIRM: UAT: After contact creation, navigation should get redirects to the contact portfolio on company overview page | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2294 | IIRM-4787 | Bug | IIRM: Opty stages: Participants not showing on stages | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2295 | IIRM-4788 | Bug | IIRM: Opty stages: Unauthorized access shown on validating company from data validation stage | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2296 | IIRM-4789 | Bug | IIRM: Opty stages: On Doc upload API response thrown 500 error | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2297 | IIRM-4790 | Bug | IIRM: Opty stages: Can't submit the KDM meeting stage | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2298 | IIRM-4791 | Story | Backlog: Assign Country to TPA, Insurers, Brokers | Done | Keerthi Polepalle |  | IIRM-742 — SOW#15 - Add/Manage TPA
2299 | IIRM-4792 | Bug | Data Validation - Have 2 buttons for validate - Validate Company, Validate SO | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2300 | IIRM-4793 | Bug | IIRM: Insurer: Unable to create insurer, error thrown: read ECONNRESET | Done | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
2301 | IIRM-4794 | Bug | IIRM: Opty stages: Cover details data missing in RFP Data collection stage | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2302 | IIRM-4795 | Bug | IIRM: Opty stages: QCR generation failed thrown error like "Required fields are missing in the request." | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2303 | IIRM-4797 | Bug | IIRM: Opty stages: Handover meet stage: cant submit : Error thrown "Meeting type with ID 7602 is not a Handover Meeting" | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2304 | IIRM-4798 | Bug | IIRM: OPty stages: Opportunity Lost stage: Cant submit error thrown "documents: property documents should not exist" | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2305 | IIRM-4799 | Bug | Add covers in policy hard copy and make it editable | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2306 | IIRM-4800 | Bug | Breadcrumb Navigation: verify that breadcrumb navigation is correctly implemented and consistent across all pages. | Ready for QA | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2307 | IIRM-4801 | Bug | Manager's approval in activities implementation | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2308 | IIRM-4802 | Bug | Form Fields & Button to be disabled post activity Completion | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2309 | IIRM-4803 | Bug | KDM Meeting: MoM required for submit | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2310 | IIRM-4804 | Task | Data validation: 2 buttons for validating company & SO | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2311 | IIRM-4805 | Bug | Data Validation: Enable submit only after SO is validated | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2312 | IIRM-4806 | Bug | IIRM: Companies: KPIs for my leads | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2313 | IIRM-4807 | Bug | Mandate details: Issues to be fixed | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2314 | IIRM-4808 | Bug | RFP Data Collection - crash | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2315 | IIRM-4809 | Bug | "Broking Slip: Brokerage % is accepting strings Should only accept positive decimals until 100" | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2316 | IIRM-4810 | Bug | Broking Slip: Policy From date, policy to date (not from date and to date) | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2317 | IIRM-4811 | Bug | "Broking Slip: Save Version should be a small button instead of long one A separator below the button" | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2318 | IIRM-4812 | Bug | RFP Data Collection: Date Picker Icon Allignment | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2319 | IIRM-4814 | Bug | RFP Details Entry Excluded TPA - Remove branch location and contact | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2320 | IIRM-4815 | Bug | RFP Details Entry Target QCR Date - should be before opty close date | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2321 | IIRM-4816 | Bug | ISG Planning ISG planning is also submitted along with BD planning - ISg planning should be open after RFP Details Entry | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2322 | IIRM-4817 | Bug | Broking Slip Generation Edit Version not available on hover | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2323 | IIRM-4818 | Bug | Broking Slip Generation Toast message when broking slip version is saved | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2324 | IIRM-4819 | Bug | Broking Slip Generation Save Version is working like submit and the activity goes to disabled state | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2325 | IIRM-4820 | Bug | Broking Slip Generation Insurers list is taking 3.6 mins to load | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2326 | IIRM-4821 | Bug | Broking Slip Generation Popup on deletion of broking slip version | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2327 | IIRM-4822 | Bug | Enter Quote Net Premium should be calculated (Basic Premium + Terrorism + Tax) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2328 | IIRM-4823 | Bug | Enter Quote Insurers's Remarks should be changed to "Insurer's Remarks" | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2329 | IIRM-4824 | Bug | Enter Quote Moving to next field is not keyboard enabled | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2330 | IIRM-4825 | Bug | Enter Quote Document error - Save Quote | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2331 | IIRM-4826 | Bug | Enter Quote Document Error - Submit Activity | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2332 | IIRM-4827 | Bug | Meeting for Final Negotiation If new meeting is selected, Select meeting should be disabled | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2333 | IIRM-4828 | Bug | Meeting for Final Negotiation MOM should be mandatory to submit | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2334 | IIRM-4829 | Bug | Meeting for Final Negotiation If multiple insurers is selected, Insurer share percentage should be removed or disabled | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2335 | IIRM-4830 | Bug | Meeting for Final Negotiation Single Insurer vs multiple insurer | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2336 | IIRM-4831 | Bug | Meeting for Final Negotiation If multiple insurers is selected, Insurer share percentage should be removed or disabled | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2337 | IIRM-4832 | Task | IIRM: UAT Bug fix verification and Regression testing on Opty stages | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2338 | IIRM-4833 | Task | IIRM: Execute Opportunity test cases and create a test cycle for Opportunity stages. | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2339 | IIRM-4834 | Task | IIRM; Bug fixes and Regression checking on Company , TPA/Insurer modules | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
2340 | IIRM-4835 | Task | IIRM: Regression testing on contact & Opty creation modules | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2341 | IIRM-4836 | Task | IIRM: Bug fixes and Regression testing on TPA/Broker/Insurer contact | Done | SaikumarMahanthi |  | IIRM-742 — SOW#15 - Add/Manage TPA
2342 | IIRM-4837 | Task | IIRM: Opportunites stages verification & Bug fixes | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2343 | IIRM-4838 | Task | IIRM: Verify the UAT builds and regression checking On opportunites stages | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2344 | IIRM-4839 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2345 | IIRM-4840 | Bug | Enter Quote - Insurer remarks is not marked mandatory but able to submit without entering insurer remarks | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2346 | IIRM-4841 | Bug | All Covers should be mandatory in Enter Quote | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2347 | IIRM-4842 | Bug | QCR - RFP and Broking slip are displayed after insurer details in the comparison report | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2348 | IIRM-4843 | Bug | QCR - Insurer not displayed in the report | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2349 | IIRM-4844 | Bug | QCR Generation - Placement Dynamics - Not optional on screen but not able to complete activity without entering data | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2350 | IIRM-4845 | Bug | Meeting for final negotiation: "Would you like to edit quote?" should be after covers | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2351 | IIRM-4846 | Bug | IIRM: TPA/Insurer/Broker UI issues | Done | SaikumarMahanthi | IBP | IIRM-740 — SOW#13 - Add/Manage Opportunity
2352 | IIRM-4847 | Bug | Meeting for final negotiation: By default New Meeting should be selected | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2353 | IIRM-4848 | Task | IIRM: ALL Number in Quote comparison should be comma seperated and Right aligned | Done | SaikumarMahanthi |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2354 | IIRM-4849 | Story | Save Activity - Proper Implementation | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2355 | IIRM-4850 | Bug | IIRM: Static data displayed on meeting feedback form | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2356 | IIRM-4851 | Bug | ISG Planning - all activities have single default date | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2357 | IIRM-4852 | Bug | Meeting for final negotiation: Versions are showed even if there are no quotes entered for the version | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2358 | IIRM-4853 | Task | Notifications UI Implementation | Done | Nikhil V |  | IIRM-761 — SOW#34 - Notifications Management
2359 | IIRM-4854 | Task | Opty Stages Bug fixes | Done | Nikhil V |  | IIRM-797 — SOW#69 - Manage Opportunities
2360 | IIRM-4855 | Task | Apply geo restriction for the application access | Done | joshuva |  | IIRM-749 — SOW#22 - Data Security (NFR)
2361 | IIRM-4856 | Task | WAF Rules implementation | Done | joshuva |  | IIRM-749 — SOW#22 - Data Security (NFR)
2362 | IIRM-4858 | Bug | IIRM: opportunity: "Cannot PUT /opportunity" Message is displayed | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2363 | IIRM-4859 | Task | Opportunity Lost activity should be open only when an opportunity is lost | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2364 | IIRM-4860 | Bug | Policy Confirmation Activity should be after policy hard copy receipt | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2365 | IIRM-4861 | Task | Sri Lanka Data Migration | WORK IN PROGRESS | meghana |  | IIRM-3817 — Data Migration
2366 | IIRM-4862 | Sub-task | Policy data structure | WORK IN PROGRESS | meghana |  | IIRM-4861 — Sri Lanka Data Migration
2367 | IIRM-4863 | Sub-task | Clean database + Lanka data | WORK IN PROGRESS | meghana |  | IIRM-4861 — Sri Lanka Data Migration
2368 | IIRM-4864 | Sub-task | Infrastructure | Done | meghana |  | IIRM-4861 — Sri Lanka Data Migration
2369 | IIRM-4865 | Sub-task | Docs and code review | WORK IN PROGRESS | meghana |  | IIRM-4861 — Sri Lanka Data Migration
2370 | IIRM-4866 | Bug | Participants not reflecting in activities | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2371 | IIRM-4868 | Bug | IIRM_OptyStages: Every activity is duplicated for existing opportunities | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2372 | IIRM-4869 | Bug | IIRM_Data Validation: Validate Company Details button issues | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2373 | IIRM-4870 | Bug | IIRM: Opty stages: Upload doc: Reupload and delete icons should not shown for already submitted activity. | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2374 | IIRM-4871 | Bug | IIRM: Opty stages: Cant proceed with RFP details entry on clicking submit for approval | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2375 | IIRM-4872 | Bug | Lost Opportunity is a showstopper for final step (Unable to create Policy) | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2376 | IIRM-4873 | Bug | IIRM_Placement Slip Generation: Error message is displayed when we click on the Approve button | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
2377 | IIRM-4874 | Bug | IIRM_Approvals: No notifications are displayed when a user sends an activity for approval/Rejects | Reopen | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2378 | IIRM-4875 | Bug | IIRM_Approvals: The activity to be approved should display by default on clicking on the Approval Request card from the Approvals tab | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
2379 | IIRM-4876 | Bug | IIRM_Approvals: Activities Enabled and Disable functionalities based on the Approval status are not working | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
2380 | IIRM-4877 | Task | User Management: Add, Edit | Done | meghana |  | IIRM-744 — SOW#17 - User Management
2381 | IIRM-4878 | Bug | IIRM: Opty stages: Final negotiation stage edit meeting issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2382 | IIRM-4879 | Task | Cover Data AI | Done | meghana |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2383 | IIRM-4880 | Bug | IIRM_Approvals: Correct the pop up messages when The activity sends for Approval/Approved/Rejected | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
2384 | IIRM-4881 | Bug | IIRM: Opty stages: Quote comparison report issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2385 | IIRM-4882 | Bug | IIRM_Approvals: Approve and Reject buttons should not display for the users who send the activity for approval(BD Executive) | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2386 | IIRM-4883 | Task | IIRM_Opportunity: The Percentage of the Opty activities should not include BD and ISG planning stages | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2387 | IIRM-4885 | Task | Approvals & Assignments | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
2388 | IIRM-4886 | Task | Export QCR to Excel and Mail | Done | meghana |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2389 | IIRM-4887 | Task | RO related business flow | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
2390 | IIRM-4888 | Task | Smart Adds: Company flow and Add Intelligent Data | Done | meghana |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2391 | IIRM-4889 | Bug | IIRM: Opty stages: Data validation activity workflow issues | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2392 | IIRM-4890 | Bug | "Installment dates are being marked as mandatory even when 'Installment' is set to 'No'. Please update the logic so that installment dates are only required when 'Installment' is set to 'Yes'." | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2393 | IIRM-4891 | Bug | Decimal is not allowed in brokerage % | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2394 | IIRM-4892 | Task | Role and ACL Map: Add edit delete | Done | meghana |  | IIRM-18 — SOW#1 - ACL & RBAC Control
2395 | IIRM-4893 | Bug | If fee is selected in installment no option to add installment details | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2396 | IIRM-4894 | Bug | IIRM: Opty stages: Enter Quote Activity: The timestamp should not display for the "Quote received on" | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2397 | IIRM-4895 | Bug | Mandate details showing blank after activity completion | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2398 | IIRM-4896 | Bug | In meeting final negotiation activity and rfp details entry Variation/issues from QCR 1 module and Insurer service level agreement 1 are missing | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2399 | IIRM-4897 | Bug | mandate details entry are disappear after submit | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2400 | IIRM-4898 | Bug | IIRM: Opty stages: Can't submit RFP details entry error thrown "remarks: nested property remarks must be either object or array" | Done | Akhila Gattu |  | IIRM-797 — SOW#69 - Manage Opportunities
2401 | IIRM-4899 | Bug | IIRM_All Feature: User is navigated to the Login screen | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2402 | IIRM-4900 | Bug | IIRM_Localization: City Dropdown LOVs Missing for Uva and Eastern States | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2403 | IIRM-4901 | Bug | IIRM_Localization: Pincode and Phone Number Fields Rejects Valid Format for Lanka | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2404 | IIRM-4902 | Bug | IIRM_Localization: VAT/ SVAT/ Business registration number field errors | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2405 | IIRM-4903 | Bug | IIRM_Company_UI: UI issues | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2406 | IIRM-4904 | Bug | IIRM_Localization: No option is displayed for adding Multiple VAT/SVAT details | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2407 | IIRM-4905 | Bug | IIRM_Localization: Indian Country code is displayed in view details page | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2408 | IIRM-4906 | Bug | Meeting feedback can't be submit after filling the data. | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2409 | IIRM-4908 | Bug | gst number field can't accept the format and issue appear. | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2410 | IIRM-4911 | Task | Meta Data should be in front end for Activities | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2411 | IIRM-4912 | Task | Save activity in activities: Front End | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2412 | IIRM-4913 | Task | Save activity in activities: Back End | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2413 | IIRM-4914 | Task | State Management for Opty Activities in Accordian | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2414 | IIRM-4915 | Bug | IIRM_Localization: Able to view the Indian employees and Companies in LOV's | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2415 | IIRM-4916 | Bug | IIRM_Localization_UI: Change the text from India to Sri Lanka | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2416 | IIRM-4917 | Bug | IIRM_Localization: Make the Country dropdown read-only | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2417 | IIRM-4918 | Bug | IIRM_Localization_UI: Service Tax field is highlighted in red colour | Done | Leela Pakalapati | iWork | IIRM-764 — SOW#37 - Localisation
2418 | IIRM-4919 | Bug | Unable upload document in create company | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2419 | IIRM-4920 | Bug | Lanka_Contact address shows India by default | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2420 | IIRM-4921 | Bug | IIRM_Placement Slip Generation: "Unable to retrieve hierarchy for the user" error message is displayed | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2421 | IIRM-4922 | Bug | IIRM: Employee Creation not working | Done | SaikumarMahanthi |  | IIRM-739 — SOW#12 - Manage Employees
2422 | IIRM-4923 | Bug | IIRM_Document: [object object] is displayed when we downloaded the uploaded document | Done | Leela Pakalapati | iWork | IIRM-760 — SOW#33 - Document Generation
2423 | IIRM-4924 | Bug | IIRM_Document: The uploaded document is not retrieved | Done | Leela Pakalapati | iWork | IIRM-760 — SOW#33 - Document Generation
2424 | IIRM-4925 | Bug | IIRM_Approvals: "Failed to approve opportunity activity: Opportunity activity with ID 3461 is not submitted." error message is dispalyed | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
2425 | IIRM-4926 | Bug | IIRM: In KDM& Mandate details Contact details are not retrived | Done | SaikumarMahanthi | iWork | IIRM-764 — SOW#37 - Localisation
2426 | IIRM-4927 | Bug | Victoria reflecting in location dropdown through out the app | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2427 | IIRM-4928 | Bug | Empty Tabs visiblein between activity stages | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2428 | IIRM-4929 | Bug | No option to approve activity details | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2429 | IIRM-4930 | Bug | Data not showing after submitting activity- RFP Details entry | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2430 | IIRM-4931 | Bug | IIRM: Incorrect Error Message Displayed on Clicking Policies Tab in Company Details Page | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2431 | IIRM-4932 | Bug | IIRM: Opty Lost: Incorrect % displayed | Done | Prabhakar Mantripragada |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2432 | IIRM-4933 | Bug | IIRM_Meeting For Final Negotiation: "request entity too large" message is displayed | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
2433 | IIRM-4934 | Bug | IIRM_Aprovals: Correct the "Activity Planned Date" displayed in the Approvals tab for the Approver (BD Manager) | Done | Leela Pakalapati |  | IIRM-781 — SOW#54 - CD Management
2434 | IIRM-4935 | Bug | insurer company type_Yes/No | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2435 | IIRM-4936 | Bug | IIRM_Approvals: Reject and Approve buttons are displayed even there is privilege for the role | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
2436 | IIRM-4937 | Bug | Lanka_Add insurer<add<country is freezed | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2437 | IIRM-4938 | Bug | IIRM: SO: ID displays for BD/CRM filter | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2438 | IIRM-4939 | Bug | Lanka_Account manager list is of India | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2439 | IIRM-4940 | Bug | IIRM: Company: Upload doc: Unable to create a company from Business card upload | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2440 | IIRM-4941 | Bug | IIRM: Company: AI Business card: Address details not fetching from card | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2441 | IIRM-4942 | Bug | IIRM: Company: No Error Message Displayed for Unaccepted Cards | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2442 | IIRM-4943 | Bug | Lanka_Add insurer_preprod_mobile and postal code validation wrong | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2443 | IIRM-4944 | Bug | IIRM: Contact: Typo issue on Contact type dropdown | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2444 | IIRM-4945 | Bug | for lanka users CURRENCY row visible as INR in manage company screen in demo | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2445 | IIRM-4946 | Bug | IIRM_Opportunity: B(Billion) is displayed in the "Sum insured" quick card | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2446 | IIRM-4947 | Sub-task | IIRM: Bugfixes verification and regression testing | Done | SaikumarMahanthi | iWork | IIRM-4950 — IIRM: Testing roles and Employess
2447 | IIRM-4948 | Sub-task | IIRM:Testing Opportunite stages blockers in Local environment | Done | SaikumarMahanthi | iWork | IIRM-4950 — IIRM: Testing roles and Employess
2448 | IIRM-4949 | Sub-task | IIRM: Approval flow and QA-Ready bugs Testing | Done | SaikumarMahanthi | iWork | IIRM-4826 — Enter Quote Document Error - Submit Activity
2449 | IIRM-4950 | Task | IIRM: Testing roles and Employess | Done | SaikumarMahanthi | iWork | IIRM-18 — SOW#1 - ACL & RBAC Control
2450 | IIRM-4952 | Task | The Manage company and manage contact flow needs to be redesigned | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2451 | IIRM-4953 | Task | Put a disclaimer: Different AI card types may be read and interpreted differently based on their structure and content. Please review each card carefully before use. Do you want to proceed with it or clear this | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2452 | IIRM-4954 | Bug | Remove all the decimals from the application | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2453 | IIRM-4955 | Bug | Srilanka amount to change to million from Lakhs | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
2454 | IIRM-4956 | Bug | IIRM_Company_DB Issues: "No Info" is displayed in the state dropdown in GST details section | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2455 | IIRM-4957 | Bug | IIRM: Opty stages: Cant submit Held Cover Note Activity | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2456 | IIRM-4958 | Bug | IIRM: Opty Stages: Cant submit the Final negotiation meeting with Document upload | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2457 | IIRM-4959 | Task | IIRM: Ready for QA Bugfixes verification and regression testing | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2458 | IIRM-4960 | Task | IIRM: Approval flow and Localization Testing | Done | SaikumarMahanthi | iWork | IIRM-764 — SOW#37 - Localisation
2459 | IIRM-4961 | Task | IIRM: Ready for QA bugs and UAT, Prepod Testing | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2460 | IIRM-4962 | Task | IIRM: Ready for QA Bugfixes verification and regression testing | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2461 | IIRM-4963 | Task | IIRM: Approvals, Localization Testing on latest | Done | SaikumarMahanthi | iWork | IIRM-764 — SOW#37 - Localisation
2462 | IIRM-4964 | Task | IIRM: Opportunites test cases updation with latest design changes | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2463 | IIRM-4965 | Task | VAT & SVAT Format: Kapil Sir to check and confirm. | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
2464 | IIRM-4966 | Task | Validation Removal: Remove validation for PAN, TAN, VAT, and SVAT fields | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
2465 | IIRM-4967 | Task | AI: Business Card Reader: Should override Manage Contacts (renamed to Manage Companies) — redesign this journey. | Draft | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2466 | IIRM-4968 | Task | AI Card Issues: Different company cards failed; model training required. | Done | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2467 | IIRM-4969 | Task | Disclaimer to Add: "Different AI card types may be read and interpreted differently based on their structure and content. Please review each card carefully before use." → Team to confirm if this should be implemented or cleared. | Done | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2468 | IIRM-4970 | Task | Decimal Cleanup: Remove all decimals from the app except in Percentage fields | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2469 | IIRM-4971 | Bug | Sri Lanka Currency: Change amount representation from Lakhs to Millions. | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
2470 | IIRM-4972 | Task | Policy view: Insurer Info: Display insurer name in header. | Done | Richa Bagchi Mazumdar |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2471 | IIRM-4973 | Story | Policy View: New Tab: Add “Policy Document” as an additional tab | Done | Richa Bagchi Mazumdar |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2472 | IIRM-4974 | Task | Lost Opportunities: Sales Order (SO) to be created for lost opportunities and NOT RO | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2473 | IIRM-4975 | Story | Instalment Reminders (Email): For Policy owners for each instalment | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2474 | IIRM-4976 | Task | Policy & CD Management: Policy Dates: Format for start and end dates needs correction. | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
2475 | IIRM-4977 | Task | CD Account – Opening Balance: Should reflect cheque amount. | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
2476 | IIRM-4978 | Task | Top-up in CD Management: Include a Transaction Type field. | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
2477 | IIRM-4979 | Story | Low Balance Alert: Notify CRM if CD balance is low. | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
2478 | IIRM-4980 | Task | CD Validation: Cheque amount must be ≥10% of premium. To be checked daily. | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
2479 | IIRM-4981 | Task | Assignments: BD Planning Assignment: Assignment functionality should also be available under BD Planning. Users should be able to reassign the activity to another BD user as long as the Opportunity (Opty) is active. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2480 | IIRM-4982 | Task | Ownership Update: The BD user to whom the activity is reassigned will become the new owner of that activity. User with assignment priviledge can assign it | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2481 | IIRM-4983 | Task | Navigation Panel 📐 Sub-Menu Indentation: Increase the indentation level for sub-menu items to improve visual hierarchy and clarity. | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2482 | IIRM-4984 | Task | Clarify whether the application should allow users to operate in the same browser across different tabs simultaneously. | Draft | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2483 | IIRM-4985 | Task | Session Management 🔒 Auto Logout on Browser Close: The user session should automatically log out when the browser is closed to enhance security. | Draft | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2484 | IIRM-4986 | Task | Masking the URL: After the fixed domain(https://newiwork.indiainsure.com), the rest of the url should be masked | Draft | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2485 | IIRM-4987 | Task | Add more logs based on the activities being done in the application | Draft | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2486 | IIRM-4989 | Task | SonarQube findings need to be addressed. | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2487 | IIRM-4990 | Story | Security Scan - Flyingduck Issues & Resolution | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2488 | IIRM-4991 | Bug | IIRM: SO: Duplicate SO got created | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2489 | IIRM-4992 | Bug | IIRM: Opty stages: GTL and GMC policy : AI Functionality Covers file upload dropdown field data not getting retrieved from upload file. | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2490 | IIRM-4993 | Bug | IIRM_RFP Data Collection: Covers upload functionalities issues | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2491 | IIRM-4994 | Task | Requirement from Kapil sir: Monthly email to go to Arindam about the list of opty Lost And also Monthly report of email: Opty Won | Draft | Richa Bagchi Mazumdar |  | IIRM-761 — SOW#34 - Notifications Management
2492 | IIRM-4995 | Task | The smart assistance should be made more noticeable add animation | Draft | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2493 | IIRM-4996 | Task | Opportunity approval hard refresh screens need to fix | Done | Rama K |  | IIRM-797 — SOW#69 - Manage Opportunities
2494 | IIRM-4998 | Bug | KYC details for Srilanka are giving wrong validation for format | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2495 | IIRM-4999 | Bug | Comma format for Srilanka is - 1,000,000,000 (after 3 digits) | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2496 | IIRM-5000 | Bug | INR can be seen in the list view for lanka: Company | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2497 | IIRM-5001 | Bug | Cannot add data in broking slip and ISG planning is freezed | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2498 | IIRM-5002 | Bug | IIMR: Company: Business Card: Company name should get reflected based on business card | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2499 | IIRM-5003 | Bug | IIRM: Company: Business Card: few fields were missing from business card while creating company | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2500 | IIRM-5004 | Bug | IIMR: Company: Business card: Previously fetched company name from business card not clearing when navigating to 'Manage Company' → 'Create Company | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2501 | IIRM-5005 | Bug | IIMR: Contact: Business card: Mobile number not getting fetch on contact create page | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2502 | IIRM-5006 | Bug | IIRM: Company: Business card: Address type not getting captured if business card have a Address type | Open | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2503 | IIRM-5007 | Bug | IIRM: Failed to create Opportunity on selecting previous TPA/Insurer/Broker | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2504 | IIRM-5008 | Bug | IIRM: Opty stages: few fields were not getting prefilled on cover file upload | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2505 | IIRM-5009 | Bug | IIRM: Opty stages: To approve RFP details entry ,Preferred TPA details not fetching for BD manager role | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2506 | IIRM-5010 | Bug | IIRM: Company List: Default order | Done | Prabhakar Mantripragada |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2507 | IIRM-5011 | Bug | IIRM: Opportunity: Risk Location: Address format | Done | Prabhakar Mantripragada |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2508 | IIRM-5012 | Bug | IIRM: Company : Invalid error thrown on KYC details page | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2509 | IIRM-5013 | Bug | IIRM: Company : Can't Proceed with TAN | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2510 | IIRM-5014 | Task | Renewal Opportunity (RO) Creation | Done | meghana |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2511 | IIRM-5015 | Task | Handling Lost Opportunities | Done | meghana |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2512 | IIRM-5016 | Bug | Tpa is not required for lanka users and it shouldn't be mandatory for lanka users | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2513 | IIRM-5017 | Bug | IIRM: Lanka and India user: Unable to create insurer/TPA/Broker | Done | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
2514 | IIRM-5018 | Bug | IIRM_Knowledge Central: Unable to upload document | Done | Leela Pakalapati | iWork | IIRM-768 — SOW#41 - Knowledge Central
2515 | IIRM-5019 | Task | Implement RO Visibility Logic with Custom Start Date and Filters | Done | Keerthi Polepalle |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2516 | IIRM-5020 | Task | Enhance Opportunity Creation with Start Date and Lost Opty Expiry Capture | Draft | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2517 | IIRM-5021 | Story | Infra-Prowler-Report | WORK IN PROGRESS | Anyarambhatla Nitish Bharadwaj |  | IIRM-749 — SOW#22 - Data Security (NFR)
2518 | IIRM-5022 | Sub-task | Disable Public Access to EBS Snapshots | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2519 | IIRM-5023 | Sub-task | Verify Default Root Object Across All CloudFront Distributions | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2520 | IIRM-5024 | Sub-task | Restrict Ingress from 0.0.0.0/0 to High-Risk Ports in Security Groups | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2521 | IIRM-5025 | Sub-task | Complete IAM Role Configuration for Cross-Service and Deputy Prevention | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2522 | IIRM-5026 | Sub-task | Enable MFA for the Users | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2523 | IIRM-5027 | Sub-task | Enforce the SSL in the RDS | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2524 | IIRM-5028 | Sub-task | Ensure All SNS Topics Are Encrypted | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2525 | IIRM-5029 | Sub-task | Check S3 Account Level Public Access Block. | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2526 | IIRM-5030 | Sub-task | Review and Restrict Cross-Account Access on All S3 Bucket Policies | Done | Anyarambhatla Nitish Bharadwaj |  | IIRM-5021 — Infra-Prowler-Report
2527 | IIRM-5031 | Bug | IIRM: Created Tasks are not displayed on Task Tab | Done | SaikumarMahanthi | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2528 | IIRM-5032 | Bug | IIRM: India: Lanka: TPA: BROKER: INSURER: Contacts: Country name not freezed | Done | Akhila Gattu | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
2529 | IIRM-5033 | Bug | IIRM: Srilanka: Insurer: Insurer name already exists shown | Done | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
2530 | IIRM-5034 | Bug | IIRM: Lanka: Country code not accepting | Done | Akhila Gattu | iWork | IIRM-741 — SOW#14 - Add/Manage Insurer
2531 | IIRM-5035 | Bug | IIRM: Opty stages: Data changes made before approval are not retained | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2532 | IIRM-5036 | Bug | IIRM_Company: "Something went wrong. Please try again." displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2533 | IIRM-5037 | Bug | IIRM_Meeting: The feedback data is not being retrieved | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2534 | IIRM-5041 | Bug | IIRM: Correct the error message through out the application | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2535 | IIRM-5042 | Bug | IIRM_Company: An error appears for some Industry filter selections in Smart Search | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2536 | IIRM-5043 | Bug | IIRM_Company: LOV's are missing for the City filter of smart search | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2537 | IIRM-5044 | Bug | IIRM_Company: Sort functionality is not working for few columns in company listing table | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2538 | IIRM-5045 | Bug | IIRM_Company: "Something went wrong. Please try again." message is displayed when we click on the Manage Company | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2539 | IIRM-5046 | Bug | IIRM_Contacts: Sort functionality is not working for a few columns in listing table | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2540 | IIRM-5047 | Bug | For fire policy getting max age of dependent field which related to gmc in placement slip generation activity | Done | Prajakta Vijay Kadam |  | IIRM-764 — SOW#37 - Localisation
2541 | IIRM-5048 | Bug | IIRM_Contacts: The status filter for inactive selection in the smart search is not working | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2542 | IIRM-5049 | Task | IIRM: UAT Sanity Testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2543 | IIRM-5050 | Task | IIRM: Opportinunity bugfixes and regression Testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2544 | IIRM-5051 | Task | IIRM: All Feature Ready for QA issues and Regression Testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2545 | IIRM-5052 | Task | IIRM: TPA/Insuer/Broker Bugfixes and Sanity testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2546 | IIRM-5053 | Task | IIRM: Company &Contact Bugfixes and Sanity Testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2547 | IIRM-5054 | Task | IIRM: UAT Sanity Testing & Bug fixes Verification | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2548 | IIRM-5055 | Task | IIRM: Opportinunity bugfixes and Sanity verification | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2549 | IIRM-5056 | Task | IIRM: UAT Sanity Testing & Preproduction Testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2550 | IIRM-5057 | Bug | IIRM: Data Issues in Location drop downs | Reopen | Prabhakar Mantripragada |  | IIRM-3817 — Data Migration
2551 | IIRM-5058 | Bug | IIRM: Opty Activities: Sri Lanka users are listed for assignment Opty activities in Indian user | Done | Prabhakar Mantripragada |  | IIRM-797 — SOW#69 - Manage Opportunities
2552 | IIRM-5059 | Bug | IIRM: Opty validation: Failed to create opportunity error when validating opty | Done - Not Reproducible | Prabhakar Mantripragada |  | IIRM-797 — SOW#69 - Manage Opportunities
2553 | IIRM-5060 | Bug | IIRM: File Uploads: Drag drop does not work | Done | Prabhakar Mantripragada |  | IIRM-797 — SOW#69 - Manage Opportunities
2554 | IIRM-5061 | Bug | IIRM: Notifications: Notification alert is not indicated near the bell icon | Done | Prabhakar Mantripragada |  | IIRM-761 — SOW#34 - Notifications Management
2555 | IIRM-5062 | Bug | IIRM: Installment Fee: Unable to provide installment fee option for multiple instalments scenario | Done | Prabhakar Mantripragada |  | IIRM-797 — SOW#69 - Manage Opportunities
2556 | IIRM-5063 | Bug | IIRM: Held Cover Note: Deviation fields to be made mandatory when Deviations are present | Done | Prabhakar Mantripragada |  | IIRM-797 — SOW#69 - Manage Opportunities
2557 | IIRM-5064 | Bug | IIRM: Compare button does not work | Done | Prabhakar Mantripragada |  | IIRM-797 — SOW#69 - Manage Opportunities
2558 | IIRM-5065 | Bug | IIRM: Contacts not listed for Company with Optys | Done | Prabhakar Mantripragada |  | IIRM-737 — SOW#10 - Add/Manage Contact
2559 | IIRM-5066 | Bug | IIRM: Company: Policies Tab: Something went wrong. Please try again. error shown when navigated to | Done | Prabhakar Mantripragada |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2560 | IIRM-5067 | Task | IIRM: Pre-production testing after data migration | Done | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
2561 | IIRM-5068 | Task | In held cover note hide the compare button | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2562 | IIRM-5069 | Task | IIRM - Deviations in the policy confirmation if Yes need to stop the activity | Done | VedaVyas |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2563 | IIRM-5070 | Task | IN RFP: Policy upload excel should also be allowed | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2564 | IIRM-5073 | Task | We need to get the release version information on the hidden route | Done | VedaVyas |  | IIRM-797 — SOW#69 - Manage Opportunities
2565 | IIRM-5074 | Task | We need to build a page where we need to show the application is unavailable (page is message configrable) | Done | VedaVyas |  | IIRM-797 — SOW#69 - Manage Opportunities
2566 | IIRM-5075 | Bug | IIRM: Opty stages: RFP details entry field validation not showing if char count exceeded | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2567 | IIRM-5076 | Bug | IIRM: Brokers not yet visible | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2568 | IIRM-5078 | Bug | IIRM: Installment Option to be corrected. If selected NO, mandatory installment dates to be filled | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2569 | IIRM-5079 | Bug | IIRM: Fee option in installment has no option for installment dates | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2570 | IIRM-5081 | Bug | IIRM: Led By details are not visible | Done | Akhila Gattu | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2571 | IIRM-5082 | QAlity Test | IIRM: Company: Edit: Verify the Edit Functionality of the company | Draft | Leela Pakalapati | iWork
2572 | IIRM-5083 | QAlity Test | IIRM: Company/Contact: Business Card: Verify the user can create a company/contact through document upload | Draft | Leela Pakalapati | iWork
2573 | IIRM-5084 | Task | User should be able to complete meeting even if the meeting is scheduled and the meeting time is not completed | Open | Keerthi Polepalle |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2574 | IIRM-5085 | Bug | IIRM: Meeting: Meeting issues | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2575 | IIRM-5087 | Bug | IIRM: Policy type SO throws an “Error loading activities | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2576 | IIRM-5088 | Task | IIRM: Data Migration – Renewal Opportunities (RO) Cron Job | Done | SaikumarMahanthi | iWork | IIRM-3817 — Data Migration
2577 | IIRM-5089 | Bug | Supperannuation SO Drill down is giving error | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2578 | IIRM-5090 | Bug | Opportunity Stage is showing, active in process | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2579 | IIRM-5091 | Bug | Creating Meetings attachments: Document Type | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2580 | IIRM-5092 | Bug | PDF only message in the covers data | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2581 | IIRM-5093 | Bug | comments box in close meetings | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2582 | IIRM-5094 | Story | Implement Activity Filter in Smart Filters of SO Screen | Done | Rama K
2583 | IIRM-5095 | Task | In Add contact: Contact Type: Lov has to be Finance, Accounts, Procurement, Purchase, Insurance, HR, SPOC | Done | Richa Bagchi Mazumdar |  | IIRM-737 — SOW#10 - Add/Manage Contact
2584 | IIRM-5096 | Bug | IIRM:Completed state not maintained in Data Validation stage for SO details verification | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2585 | IIRM-5097 | Story | Display Version label in the application | Done | Rama K
2586 | IIRM-5098 | Bug | IIRM: Data Validation: The fields are getting re-set after validating the company details | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2587 | IIRM-5099 | Bug | IIRM: Enter Quote: Enter Quote form is getting added when we refresh the screen every time | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2588 | IIRM-5100 | Bug | IIRM: Contact Address: Functional Issues in Address Step | Reopen | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
2589 | IIRM-5101 | Bug | IIRM: Few fields missing in Policies list and details view | Done | SaikumarMahanthi | iWork | IIRM-777 — SOW#50 - Policy Configurator
2590 | IIRM-5102 | Bug | IIRM: Company locations not retrieved in Policy details page → Add New TPA Contact form | Done | SaikumarMahanthi | IBP | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2591 | IIRM-5103 | Bug | IIRM: Policies: Policy status is Inactive by default | Done | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
2592 | IIRM-5104 | Bug | IIRM: TPA/Broker: Edit functionality is not working | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
2593 | IIRM-5105 | Bug | RO Creation through cron | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2594 | IIRM-5106 | Bug | IIRM: Broker/TPA/Insurer: Incorrect Error Message Shown When Mandatory Fields Are Missing in creation | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
2595 | IIRM-5107 | Bug | IIRM: Broker/Insurer/TPA Contacts: Broker Overview Section – Text Overflow | Done | Leela Pakalapati | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
2596 | IIRM-5108 | Task | Document for Dashboard + Quick Cards | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2597 | IIRM-5109 | Bug | IIRM: Company: Sri Lanka: Company already exists message is displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2598 | IIRM-5110 | Task | Manage Company Quick card logic | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2599 | IIRM-5111 | Task | Manage Contacts Quick card logic | Done | Richa Bagchi Mazumdar |  | IIRM-737 — SOW#10 - Add/Manage Contact
2600 | IIRM-5112 | Task | Manage SO - Update logic for KPI Counts in Manage SO screen | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2601 | IIRM-5113 | Bug | IIRM: KDM Metting: Not able to complete the activity with existing meeting details | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2602 | IIRM-5114 | Bug | IIRM: Approvals: The edited changes by the Approver is not reflecting | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2603 | IIRM-5115 | Bug | Basic covers section is freeezed in Held cover note activity before the compare button was removed it was editable | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2604 | IIRM-5116 | CR - Story | CR: For Bulk Assignment | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2605 | IIRM-5117 | Task | IIRM: Regression testing all Functionality & QA- Ready Bug fixes verification | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2606 | IIRM-5118 | Task | IIRM: Policy list and details page testing | Done | SaikumarMahanthi |  | IIRM-777 — SOW#50 - Policy Configurator
2607 | IIRM-5119 | Task | IIRM: Company test cases updation with latest changes | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2608 | IIRM-5120 | Task | IIRM:New -CR's Testing and regression testing on both QA& UAT | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2609 | IIRM-5121 | Task | IIRM: Verify the Policy configuration end -to end testing | Done | SaikumarMahanthi | IBP | IIRM-777 — SOW#50 - Policy Configurator
2610 | IIRM-5122 | Task | IIRM: Preapre test cases for Policy confiuration | Done | SaikumarMahanthi | IBP | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2611 | IIRM-5123 | Task | IIRM: Bugfixes verification on Ready for QA issues and regression testing | Done | SaikumarMahanthi | IBP | IIRM-797 — SOW#69 - Manage Opportunities
2612 | IIRM-5124 | Bug | Mandate details entry page "Compensation Payable" if we give 0 then it throws this error. Also it should accept decimal value | Done | Rama K |  | IIRM-797 — SOW#69 - Manage Opportunities
2613 | IIRM-5125 | QAlity Test | IIRM: Company: Verify the user can create multiple address and GST Details for a company | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2614 | IIRM-5126 | Task | Listing in RO and SO, Country need to consider | Done | Rama K |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2615 | IIRM-5127 | QAlity Test | IIRM: Company: View: Verify the company view details page | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2616 | IIRM-5128 | QAlity Test | IIRM: Appropriate validations messages are displayed for invalid data inputs and required input data is missing | Draft | Leela Pakalapati | iWork
2617 | IIRM-5129 | QAlity Test | IIRM: Manage Company: UX: Verify that page design matches approved Figma screens | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2618 | IIRM-5130 | QAlity Test | IIRM: Manage Company: Verify the Functionalities of the Quick Cards | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2619 | IIRM-5131 | QAlity Test | IIRM: Verify the Sorting, Pagination, and Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2620 | IIRM-5132 | Task | Sales activities Tasks should not be as per hierarchy | Done | Richa Bagchi Mazumdar |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2621 | IIRM-5133 | Story | Cross Imports from Micro-Services need to refractor | Done | Rama K
2622 | IIRM-5136 | Task | Add Organization & SBU when defining sales stages | Draft | Richa Bagchi Mazumdar |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2623 | IIRM-5137 | Task | Assignment - Add name and branch | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2624 | IIRM-5138 | Task | In Smart Assistant, when "Help me add a Company / Contact / Opportunity" | Done | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2625 | IIRM-5139 | Task | Bulk Assignment logic for SO, RO, Policy, Company. Provide Bulk Assignment function in the Manage pages of these entities and control by privileges | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2626 | IIRM-5140 | Task | Manage Company changes | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2627 | IIRM-5141 | Task | Company creation process | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2628 | IIRM-5142 | Task | Contact creation process | Done | Richa Bagchi Mazumdar |  | IIRM-737 — SOW#10 - Add/Manage Contact
2629 | IIRM-5143 | Task | Make these changes in SO creation (P0) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2630 | IIRM-5144 | Task | Flow Changes | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2631 | IIRM-5145 | Task | Following changes are required in the Meetings | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2632 | IIRM-5146 | Task | Meetings: Time control to be replaced with better control | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2633 | IIRM-5147 | Task | In all the data entry pages, all the mandatory fields should be together in the beginning | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2634 | IIRM-5148 | Sub-task | Business Done report generation | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-5477 — CR In IIRM
2635 | IIRM-5149 | Task | Policy upload functionality in the application | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2636 | IIRM-5150 | Task | HOLD: Provide one new menu option in the application top menu as "Telemetry". Put this as first option followed by Feedback and other options. This should be iFrame opening the lovable page in it. We will provide the Lovable page link | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2637 | IIRM-5151 | Task | iWork "Stage" field is missing in SO and RO. This needs to be added. Status - Open, WIP, won, lost; Stage - RFP/ Policy Issuance etc Sales Activity and Sales Stage should be maintained across application | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2638 | IIRM-5152 | Task | All the changes of SO to be validated in RO also and implemented as applicable | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2639 | IIRM-5153 | Task | In Contact drill-down, associated policy, SO & RO to be shown in different tabs. | Done | Richa Bagchi Mazumdar |  | IIRM-737 — SOW#10 - Add/Manage Contact
2640 | IIRM-5154 | Task | In company drill-down, associated policy, SO & RO to be shown in different tabs. "Policy" tab to be renames as "Our Portfolio" SO and RO - different tabs | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2641 | IIRM-5155 | Task | In Contact details, drill down on company name to be provided In the header of contact details page, company name should be clickable | Done | Richa Bagchi Mazumdar |  | IIRM-737 — SOW#10 - Add/Manage Contact
2642 | IIRM-5156 | Task | For all LOV fields, option to delete the selected value to be provided. | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2643 | IIRM-5157 | Task | AI to be enabled during manual company creation. It should fetch the data based on Industry | Done | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2644 | IIRM-5158 | Task | In KDM Meeting - field "MOM" to be renamed as "Agenda" | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2645 | IIRM-5159 | Task | In Company Drill Down Rename - Overview tab as More Info Rename - Profile tab as Overview Add new tab as Profile Company level Dashboard | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2646 | IIRM-5160 | Task | Sales activities tasks should not be with hierarchy | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2647 | IIRM-5163 | QAlity Test | IIRM: Smart Search: Verify the Functionalities of the Smart Search | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2648 | IIRM-5164 | Task | Refresh token and access token time needs to be reduced | Draft | Rama K |  | IIRM-749 — SOW#22 - Data Security (NFR)
2649 | IIRM-5165 | Task | Java script/CSS errors need to be addressed in console | Draft | Rama K |  | IIRM-2215 — Technical Debt
2650 | IIRM-5166 | Story | iWork: Mobile responsive | Draft | Rama K |  | IIRM-734 — SOW#7 - UI Design System
2651 | IIRM-5167 | Task | Implement Notification for service down | Done | Rama K |  | IIRM-761 — SOW#34 - Notifications Management
2652 | IIRM-5169 | Task | Left menu- Expanded Menu | Done | meghana |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2653 | IIRM-5170 | Task | Left menu- Under India Insure logo | Done | meghana |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2654 | IIRM-5171 | Task | Top Menu | Done | meghana |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2655 | IIRM-5172 | Task | Right side Smart Actions Tab - Pull Button | Done | meghana |  | IIRM-754 — SOW#27 - AI - Smart Adds
2656 | IIRM-5173 | Task | Right side Smart Actions Tab | Ready for QA | meghana |  | IIRM-754 — SOW#27 - AI - Smart Adds
2657 | IIRM-5174 | Task | Smart Assistant | Done | meghana |  | IIRM-754 — SOW#27 - AI - Smart Adds
2658 | IIRM-5175 | Task | Notifications Bell | Done | meghana |  | IIRM-761 — SOW#34 - Notifications Management
2659 | IIRM-5176 | Task | Login screen- Branding section | Done | meghana |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2660 | IIRM-5178 | Sub-task | Indentation of main menu and sub menu differentiation | Done | meghana |  | IIRM-5169 — Left menu- Expanded Menu
2661 | IIRM-5179 | Sub-task | Icons should be reworked | Done | meghana |  | IIRM-5169 — Left menu- Expanded Menu
2662 | IIRM-5180 | Sub-task | Icon repetition should be avoided | Done | meghana |  | IIRM-5169 — Left menu- Expanded Menu
2663 | IIRM-5181 | Sub-task | Move collapsable icon to top or middle | Done | meghana |  | IIRM-5169 — Left menu- Expanded Menu
2664 | IIRM-5182 | Sub-task | Change collapsible icon image | Pushed to Backlog | meghana |  | IIRM-5169 — Left menu- Expanded Menu
2665 | IIRM-5183 | Sub-task | Top menu background color should not be white | Done | meghana |  | IIRM-5171 — Top Menu
2666 | IIRM-5184 | Sub-task | Profile picture should be visible | Done | meghana |  | IIRM-5171 — Top Menu
2667 | IIRM-5185 | Sub-task | On click on profile name should also have an option for Profile Page link, then on mouse hover should change to actionable(Mouse icon). Arrow should become hand | Pushed to Backlog | meghana |  | IIRM-5171 — Top Menu
2668 | IIRM-5186 | Sub-task | Right pull button should be animated(to be more noticeable) | Done | meghana |  | IIRM-5172 — Right side Smart Actions Tab - Pull Button
2669 | IIRM-5187 | Sub-task | Remove Approvals and Assignments from the smart action tab | Done | meghana |  | IIRM-5172 — Right side Smart Actions Tab - Pull Button
2670 | IIRM-5188 | Sub-task | Smart action tab should relate to the center page, based on the opty those meetings, tasks, should come first | Done | meghana |  | IIRM-5172 — Right side Smart Actions Tab - Pull Button
2671 | IIRM-5189 | Sub-task | When smart actions tab is open, smart assistant should not disappear | Done | meghana |  | IIRM-5173 — Right side Smart Actions Tab
2672 | IIRM-5190 | Sub-task | Smart action row should have toggle for completion and closure action(for meetings) | PENDING PEER or LEAD REVIEW | meghana |  | IIRM-5173 — Right side Smart Actions Tab
2673 | IIRM-5191 | Sub-task | Red dot should disappear after viewing all | Pushed to Backlog | meghana |  | IIRM-5175 — Notifications Bell
2674 | IIRM-5192 | Sub-task | Notification Linking to be clarified | Pushed to Backlog | meghana |  | IIRM-5175 — Notifications Bell
2675 | IIRM-5194 | QAlity Test | IIRM: Contact: Add: Verify that the user who has create privilege can add a new contact | Draft | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2676 | IIRM-5195 | Task | Company Creation - Only Company name, Address Type, City is mandatory at the time of company creation. Rest all fields are non mandatory fields. | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2677 | IIRM-5196 | Task | Contact Creation - Only contact First Name, Last Name, Company Location, Department, Designation, Phone is mandatory. Rest all fields are non mandatory. | Done | Keerthi Polepalle |  | IIRM-737 — SOW#10 - Add/Manage Contact
2678 | IIRM-5197 | QAlity Test | IIRM: Contact: Edit: Verify the edit functionality of the create contact | Draft | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2679 | IIRM-5198 | QAlity Test | IIRM: Contact: View: Verify the company view details page | Draft | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2680 | IIRM-5199 | QAlity Test | IIRM: Contact: Verify the contact creation by adding multiple data | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2681 | IIRM-5200 | QAlity Test | IIRM: Manage Contacts: Verify the Functionalities of the Smart Search | Draft | Leela Pakalapati | iWork
2682 | IIRM-5201 | QAlity Test | IIRM: Manage Contacts: Verify the Functionalities of the Quick Cards | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2683 | IIRM-5202 | QAlity Test | Opportunity Lost : Verify that user is able to mark an Opportunity as lost | Draft | SaikumarMahanthi
2684 | IIRM-5217 | Task | Company Creation Wizard - changes | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2685 | IIRM-5218 | Task | Insurer Details in Placement Slip as per policy placed type | Done | Keerthi Polepalle |  | IIRM-741 — SOW#14 - Add/Manage Insurer
2686 | IIRM-5219 | Task | Create Admin Module Links in Side Navbar | Done | Rama K |  | IIRM-797 — SOW#69 - Manage Opportunities
2687 | IIRM-5220 | Bug | IIRM: Company: UI: Company view details page | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2688 | IIRM-5221 | Bug | ISG Assignment tasks need to assign to active users only | Done | Rama K |  | IIRM-756 — SOW#29 - Manage ISG Stages
2689 | IIRM-5222 | Bug | IIRM: Contacts: Contacts are missing in the create wizard | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2690 | IIRM-5223 | Bug | IIRM: Contacts: Company name not auto-populated when creating a contact from the Sales opportinities tab | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2691 | IIRM-5224 | Bug | IIRM: MY SO: Correct the LOV's for the status filter | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2692 | IIRM-5225 | Task | Front End - Lead tasks (Planning, Code Review, team Support) | WORK IN PROGRESS | meghana |  | IIRM-6276 — SOW-TBD
2693 | IIRM-5227 | QAlity Test | IIRM: Company: Verify that multiple contacts can be created for a company with all field data | Draft | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2694 | IIRM-5228 | QAlity Test | IIRM: Smart Search: Verify the Functionalities of the filters in Smart Search | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2695 | IIRM-5229 | Bug | IIRM: Smart Assistant: UI issues | Done | Leela Pakalapati | iWork | IIRM-754 — SOW#27 - AI - Smart Adds
2696 | IIRM-5230 | Bug | IIRM: Smart Assistant: Policy Status is set to 'Fresh' by default for opportunities created via Smart Assistant | Done | Leela Pakalapati | iWork | IIRM-754 — SOW#27 - AI - Smart Adds
2697 | IIRM-5231 | Task | Rename MOM at all places with Agenda/ MOM | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2698 | IIRM-5232 | QAlity Test | IIRM: Manage Company: Verify the details in Manage Company Page | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2699 | IIRM-5233 | Story | Fuzzy search (Create Company) | Done | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2700 | IIRM-5234 | Bug | IIRM: Opty stages: Cant approve RFP details entry activity | Done | Akhila Gattu | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2701 | IIRM-5235 | Task | Contact Creation - Designation and Department - Adding LOVs and if user types an option, add it to the LOV | Draft | Keerthi Polepalle |  | IIRM-737 — SOW#10 - Add/Manage Contact
2702 | IIRM-5236 | Bug | IIRM: Company: "Something went wrong" screen is displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2703 | IIRM-5237 | Task | Meetings change - participants as per meeting type; Meeting links and participants design rework | Done | Keerthi Polepalle |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2704 | IIRM-5238 | Task | From Business card reader to create quick company flow | Done | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
2705 | IIRM-5239 | Bug | IIRM: Company: Undefined screen is displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2706 | IIRM-5240 | Bug | Opportunity planning after opty creation through quick create is missing | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2707 | IIRM-5241 | Bug | IIRM: Policy Details: Insurer Contact Created from Contacts Portfolio Not Displayed in Contact Tab | Done | Akhila Gattu | iWork | IIRM-777 — SOW#50 - Policy Configurator
2708 | IIRM-5242 | Task | Srilanka users fetching in acknowledged by in held cover note | Done | Pampana Ravi Kiran |  | IIRM-797 — SOW#69 - Manage Opportunities
2709 | IIRM-5243 | Bug | IIRM: AI - Company Creation: Empty display name is displayed | Done | SaikumarMahanthi | IBP | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2710 | IIRM-5244 | Story | Google Address Lookup POC | Draft | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2711 | IIRM-5245 | Story | Multi select drop downs - checkboxes required for the selection | Done | Keerthi Polepalle
2712 | IIRM-5247 | Task | Multiple Insurers case handling in Placement Slip and Meeting for final negotiation | Ready for QA | Keerthi Polepalle |  | IIRM-741 — SOW#14 - Add/Manage Insurer
2713 | IIRM-5248 | Bug | IIRM: SO Edit not working Error(Estimated brokerage percentage must be a valid number) | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2714 | IIRM-5249 | Bug | IIRM: UAT:Created opportunities are not listed under the Opportunities tab on the Company Details page | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2715 | IIRM-5250 | Task | IIRM: UAT Bug fix verification and Regression testing | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2716 | IIRM-5251 | Task | IIRM: Update the all test artificates and test cases | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2717 | IIRM-5252 | Task | Company Wizard | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2718 | IIRM-5253 | Task | Meeting Date to be defaulted for today | Done | Keerthi Polepalle |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2719 | IIRM-5254 | Task | Meetings - If internal is selected, then client location should be defaulted to IIRM Office and disable | Done | Keerthi Polepalle |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2720 | IIRM-5255 | Task | Global Sort | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2721 | IIRM-5256 | Task | Count in Paranthesis in Manage Company | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2722 | IIRM-5257 | Task | Manage Company: Policy Premium to be added | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2723 | IIRM-5258 | Task | Company Details - Profile - Company Dashboard | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2724 | IIRM-5259 | Task | Company Details - SO, RO, Documents Tabs | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2725 | IIRM-5260 | Task | Company Details: Make Profile the first tab | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2726 | IIRM-5261 | Task | Company Details - SO & RO Tab - Active & Inactive SOs | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2727 | IIRM-5262 | Task | Manage Company - Drill down SO/ RO count | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2728 | IIRM-5263 | Task | Dashboard - Align Tasks & follow ups section (left side) bottom with the smart assistant section (on the right side) bottom | Done | Keerthi Polepalle |  | AR-45 — Metrics Dashboard
2729 | IIRM-5264 | Story | CR: Create Tasks - Self and Assign to others | Done | Keerthi Polepalle |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2730 | IIRM-5265 | Task | Assignments - ISG lead to executives | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2731 | IIRM-5266 | Task | Backlog - Capture Brokerage amount in placement slip | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2732 | IIRM-5267 | Task | Design: Button to open meetings bar to be redesigned | Done | Keerthi Polepalle | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2733 | IIRM-5268 | Task | Design: Self explanatory icons in the left navigation panel | Done | Keerthi Polepalle | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2734 | IIRM-5269 | CR - Story | Generic Policy Creation - API for Company Creation | Draft | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2735 | IIRM-5270 | CR - Story | Generic Policy Creation - API for Policy Creation | Draft | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2736 | IIRM-5271 | Task | IIRM: Company & Contact Test cases Updation | Done | SaikumarMahanthi |  | IIRM-737 — SOW#10 - Add/Manage Contact
2737 | IIRM-5272 | Task | IIRM: Ready for QA tickets verification and regression testing | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2738 | IIRM-5273 | Task | IIRM: New RO Creations and Stages verification | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2739 | IIRM-5275 | Task | Company Details Page - Rename the Tabs Sale Opportunity to SO , Renewal Opportunity to RO | Done | Rama K |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2740 | IIRM-5276 | Task | PO Tasks | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
2741 | IIRM-5277 | Bug | Company Creation: All Independent Companies are not Listed in the Parent Company Dropdown lLst. | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2742 | IIRM-5278 | Sub-task | Team Support | Done | meghana |  | IIRM-5276 — PO Tasks
2743 | IIRM-5279 | Sub-task | Meetings/KT | Done | meghana |  | IIRM-5276 — PO Tasks
2744 | IIRM-5280 | Task | The BD team did not complete several key tasks, such as entering Mandate, collecting RFP details, and progressing through the Entry stages in the application | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2745 | IIRM-5281 | Task | The system did not prevent BD users from submitting stages like Mandate without uploading the required documents. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2746 | IIRM-5282 | Task | The BD team did not complete several key tasks, such as entering Mandate, collecting RFP details, and progressing through the Entry stages in the application:RFP covers were not entered, as the application does not mark them as mandatory | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2747 | IIRM-5283 | Task | Policy coverage details have not been updated with the latest provided data | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2748 | IIRM-5284 | Task | The coverage items are out of sequence. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2749 | IIRM-5285 | Task | Mandatory covers have not been indicated. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2750 | IIRM-5286 | Task | Recent additions or deletions of covers are not reflected (Data Change) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2751 | IIRM-5287 | Task | Certain asset fields, based on the selected policy type in the application and the broking slip, are missing. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2752 | IIRM-5288 | Task | Broking slip activity: The Excel export option does not align with the expected template | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2753 | IIRM-5289 | Task | Broking Slip Activity: The Excel file lacks a logo, is poorly structured, and is missing key sections | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2754 | IIRM-5290 | Task | Broking Slip Activity: There is no header or footer information, and asset fields and covers are not properly organized (as per the template). | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2755 | IIRM-5291 | Task | Broking Slip Activity: The mandatory document upload section is not visible for the ISG user to upload the relevant documents. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2756 | IIRM-5292 | Story | Opportunity History details are unavailable for the end user to view. | Draft | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2757 | IIRM-5293 | Task | Approver details are not displayed, including the Approver's name and the approval date/time. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2758 | IIRM-5295 | Bug | IIRM: QCR Generation: UAT: The buttons are enable and able to complete the activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2759 | IIRM-5296 | Bug | IIRM: Created TPAs are not displayed in TPA contact creation dropdown | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2760 | IIRM-5297 | QAlity Test | SO: Create: Verify by creating one Opty of each type (using the Company details page SO tab) | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2761 | IIRM-5298 | Task | Manage Company - Add SO/RO/Policy indication colour in company list | Done | Rama K |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2762 | IIRM-5299 | Bug | IIRM: Contact: Inactive contacts are displayed | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2763 | IIRM-5300 | Sub-task | API Development for Add SO/RO/Policy indication colour in company list | Pushed to Backlog | Rama K |  | IIRM-5298 — Manage Company - Add SO/RO/Policy indication colour in company list
2764 | IIRM-5301 | Task | Multi Select - All the Multi select need to be shown with Checkbox | Done | Rama K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2765 | IIRM-5302 | Task | Companies having active policies - shown GREEN colour small dot in the beginning of company name column | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2766 | IIRM-5303 | Task | Companies without Active Policies, but with SOs --- Amber | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2767 | IIRM-5304 | Task | Companies without any SO & RO - shown RED colour small dot in the beginning of company name column | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2768 | IIRM-5305 | Task | The buttons required are - Cancel, Back, Next Step, Create Company. Let user decide the action that needs to be done. User should be allowed to enter data for all mandatory fields only and do Create Company without going to next steps. | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2769 | IIRM-5306 | Task | Contact Creation: The buttons required are - Cancel, Back, Next Step, Create Contact. Let user decide the action that needs to be done. User should be allowed to enter data for all mandatory fields only and do Create Contact without going to next steps. | Done | Richa Bagchi Mazumdar |  | IIRM-737 — SOW#10 - Add/Manage Contact
2770 | IIRM-5307 | Task | Policy Premium column to be added in Manage Companies List | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2771 | IIRM-5308 | Task | Backlog: Opportunity Status should have Won (In Progress) and Won (Completed) | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2772 | IIRM-5309 | Task | Add Risk Location and Service Level to Policy Entity | Done | Keerthi Polepalle |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2773 | IIRM-5310 | Task | Policy Details - Company name, show brokerage instead of sum insured | Done | Keerthi Polepalle |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2774 | IIRM-5311 | Task | Policy Details - Contact Drill Down | Done | Keerthi Polepalle |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2775 | IIRM-5312 | Task | Manage Policies - changes | Done | Keerthi Polepalle |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2776 | IIRM-5313 | Bug | Manage SO- Statuses - won should be Won, lost should be Lost, check spellings | Done | Keerthi Polepalle |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2777 | IIRM-5314 | Task | Design: Dashboard | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2778 | IIRM-5315 | Bug | Create Company- Company’s history name error | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2779 | IIRM-5316 | Task | User Activity Report Generation | Done | Rama K |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2780 | IIRM-5317 | Bug | Reports should be available for everyone and not just super user | Done | Keerthi Polepalle |  | IIRM-778 — SOW#51 - Admin Reports
2781 | IIRM-5318 | Task | Policy Attribute - Data Model is updated to take the new columns (SO/RO, Mined, Brokerage Amount) | Done | Keerthi Polepalle |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2782 | IIRM-5319 | Task | Manage Policies - Owner hierarchy should be in the filter | Done | Keerthi Polepalle |  | IIRM-777 — SOW#50 - Policy Configurator
2783 | IIRM-5320 | Sub-task | Smart assist Form (Company, contact, opportunity, meetings) | Done | meghana |  | IIRM-5174 — Smart Assistant
2784 | IIRM-5321 | Sub-task | AI integration with quick creation of company, contact, opportunity | Done | meghana |  | IIRM-5174 — Smart Assistant
2785 | IIRM-5322 | Sub-task | APIs for smart assist | Done | meghana |  | IIRM-5174 — Smart Assistant
2786 | IIRM-5323 | Sub-task | API integration of smart assist form | Done | meghana |  | IIRM-5174 — Smart Assistant
2787 | IIRM-5324 | Task | Dashboard - Business Performance | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2788 | IIRM-5325 | Task | Dashboard - Funnel | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2789 | IIRM-5326 | Bug | IIRM: Incorrect navigation when clicking on SO count in Manage List page | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2790 | IIRM-5327 | Task | Menu Icons Redesigns | Done | bala |  | IIRM-797 — SOW#69 - Manage Opportunities
2791 | IIRM-5328 | Task | Dashboard - Funnel graph and Speedometer graph designs and meeting | Done | bala |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2792 | IIRM-5329 | Task | Smart Actions Overlay design | Done | bala |  | IIRM-797 — SOW#69 - Manage Opportunities
2793 | IIRM-5330 | Task | Dashboard - Filters | Done | tharun |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2794 | IIRM-5331 | Task | Updated Business performance chart | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2795 | IIRM-5332 | Task | Brokerage column to be added in Manage Companies listing | Done | Keerthi Polepalle |  | IIRM-797 — SOW#69 - Manage Opportunities
2796 | IIRM-5333 | Bug | IIRM: RO: Change the text from SO to RO in Edit RO details flow | QA in Progress | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2797 | IIRM-5334 | Bug | IIRM: RO: Smart Search: Activity filter is disabled | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2798 | IIRM-5335 | Bug | IIRM: Manage Company: Green dot indicator missing and policy count not updating for companies with active policies | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2799 | IIRM-5336 | Bug | IIRM: Placement Slip Generation: Installment dates required when 'No' is selected for "Premium is Installment Based" | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2800 | IIRM-5337 | Bug | IIRM: Company: "Address update failed" while updating the address | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2801 | IIRM-5338 | Task | In UAT we are not able to select company while creating meeting | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2802 | IIRM-5339 | Task | Documents Tab to show documents in opty details | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2803 | IIRM-5340 | Task | A. Add following in the smart filter - Branch, Led By, SBU, Vertical | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2804 | IIRM-5341 | Task | The activity name of company pursuit --- Park for now, but need to discuss with Business for the value. (Not priority) | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2805 | IIRM-5342 | Task | Front End: Activities front end implementation gaps | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2806 | IIRM-5343 | Bug | IIRM: Opty Stages: The amounts should be display in currency format separated with comma's | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2807 | IIRM-5344 | Bug | IIRM: Contacts: Missing company name in Contact Details view under Professional Experience | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2808 | IIRM-5345 | Bug | IRM: Previous Placement Details Missing for SO Created After Opportunity is Lost | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2809 | IIRM-5346 | Bug | IIRM: SO: Claim Percentage Calculation Correction Based on Sum Insured | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2810 | IIRM-5347 | Task | IIRM: RO: Service Level and Policy Status are set to default values and read only | Done | Leela Pakalapati |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2811 | IIRM-5348 | Task | Task and meetings overlay design | Done | bala |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2812 | IIRM-5349 | Bug | IIRM: Approvals: Due date is not displayed correctly | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
2813 | IIRM-5350 | Task | Name Changes in Dashboard | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2814 | IIRM-5351 | Task | Dashboard: Business Performance - In speedometer control, show the target figure also. | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2815 | IIRM-5352 | Task | In Sales Funnel and Renewal Funnel, show the % from previous stage to next stage. | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2816 | IIRM-5353 | Task | Dashboard: Activate Filters | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2817 | IIRM-5354 | Task | Dashboard: Work on the right side sections in the dashboard | Done | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2818 | IIRM-5355 | Task | Stalled Companies Follow-up | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2819 | IIRM-5356 | Task | Inactive Key Accounts Alert | Done | Keerthi Polepalle |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2820 | IIRM-5357 | Task | Multiple Stakeholders, No Meetings | Pushed to Backlog | Keerthi Polepalle |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2821 | IIRM-5358 | Task | Dashboard: Scenarios for Smart Assistant Section of Dashboard | Pushed to Backlog | Keerthi Polepalle |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2822 | IIRM-5359 | Bug | IIRM: Manage Policies: The Company Name is not presented in the smart filters | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2823 | IIRM-5360 | Bug | IIRM: Manage Policies: Clickable Pointer is missing | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2824 | IIRM-5361 | Bug | Quick Contact Creation: Company Location not reflected in Contact Details | Done | Prabhakar Mantripragada |  | IIRM-737 — SOW#10 - Add/Manage Contact
2825 | IIRM-5362 | Bug | IIRM: Manage Company: Policy Premium(# Count) and Brokerage columns are missing | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2826 | IIRM-5363 | Task | Provide decimal entry in estimated brokerage amount | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2827 | IIRM-5364 | Bug | IIRM: Contacts: Unable to recognise the contact if it's created with the same name in the 'Reporting To' field | Done | Leela Pakalapati | IBP | IIRM-737 — SOW#10 - Add/Manage Contact
2828 | IIRM-5365 | Bug | IIRM: Right Side Menu: Arrow is not functioning correctly | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2829 | IIRM-5366 | Bug | IIRM: Manage Contacts: Correct the Typo | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2830 | IIRM-5367 | Bug | IIRM: Document Upload: Multiple toast messages are conveying the same information | Done | Leela Pakalapati | iWork | IIRM-760 — SOW#33 - Document Generation
2831 | IIRM-5368 | Task | Icons and feedback changes on menu | Done | bala |  | IIRM-797 — SOW#69 - Manage Opportunities
2832 | IIRM-5369 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on new CRS | Done | SaikumarMahanthi |  | IIRM-777 — SOW#50 - Policy Configurator
2833 | IIRM-5370 | Task | IIRM: Combine testing on UAT Environment with bugfixes | Done | SaikumarMahanthi |  | IIRM-777 — SOW#50 - Policy Configurator
2834 | IIRM-5371 | Task | IIRM: Opportunity stages verifications after bug fixes | Done | SaikumarMahanthi |  | IIRM-777 — SOW#50 - Policy Configurator
2835 | IIRM-5372 | Task | IIRM: Opportunity test cases updation with latest CRs | Done | SaikumarMahanthi |  | IIRM-777 — SOW#50 - Policy Configurator
2836 | IIRM-5373 | Task | IIRM: Ready for QA primary blocklog tickets verification | Done | SaikumarMahanthi |  | IIRM-777 — SOW#50 - Policy Configurator
2837 | IIRM-5374 | Task | IIRM: Oppoortunity Satges verifications with different typs of Policies | Done | SaikumarMahanthi | iWork | IIRM-777 — SOW#50 - Policy Configurator
2838 | IIRM-5375 | Bug | IIRM: Approval and Assessments tabs should not be displayed for Executive role | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2839 | IIRM-5376 | Bug | IIRM: Covers are disabled in Held Cover Note even though they are mandatory to submit the activity | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2840 | IIRM-5377 | Bug | IIRM: Dashboard: Dashboard filters are not functioning | Done | Leela Pakalapati | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2841 | IIRM-5378 | Bug | IIRM: Manage RO: In Smart Search add Vertical and BAU also. | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2842 | IIRM-5379 | Bug | IIRM: Smart Filters: The 'Owned By' dropdown is not resetting when the Reset button is clicked. | Done | Leela Pakalapati | iWork | IIRM-754 — SOW#27 - AI - Smart Adds
2843 | IIRM-5380 | Bug | IIRM: Planning: Additional participants dropdown should display with the checkboxes | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2844 | IIRM-5381 | Task | Display Assets at RFP Data Collection and need to appear into the next activities | Done | Rama K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2845 | IIRM-5382 | Task | Approvals - Only users with approval privilege should be able to see approvals | Done | Keerthi Polepalle |  | IIRM-18 — SOW#1 - ACL & RBAC Control
2846 | IIRM-5383 | Task | Validation in Meeting activities - if meeting time is in future, cannot complete activity | Open | Keerthi Polepalle |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2847 | IIRM-5384 | Bug | IRM: Delete (–) icon not working for multiple claim experience entries in Create SO page | Done | SaikumarMahanthi |  | IIRM-782 — SOW#55 - Claim Management
2848 | IIRM-5385 | Bug | IIRM: "Oops! Something went wrong" error displayed when user logs in with empty role | Done | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
2849 | IIRM-5386 | Task | IIRM: Dashboard: Funnel Visualization Fixes & Dashboard Enhancements | Done | Leela Pakalapati | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2850 | IIRM-5387 | Bug | RO list of records not matching with the actual ROs from excel | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2851 | IIRM-5389 | Task | RO/SO List - Grid feedback changes | Done | Rama K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2852 | IIRM-5390 | Task | Smart Filters - Feedback changes | Done | Rama K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2853 | IIRM-5391 | Task | SO / RO - KPI count feedback changes | Done | Rama K |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2854 | IIRM-5392 | Task | Endorsement flow screen Designs | Done | bala |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
2855 | IIRM-5393 | Task | Endorsement flow design changes | Done | bala |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
2856 | IIRM-5394 | Task | Include Lead_CRM field in Policy Table | Done | Rama K |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2857 | IIRM-5395 | Bug | Company Quick Card - My client data is not updated if Company have one policy, or so, Ro then counts should be updated | Done | Rama K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2858 | IIRM-5396 | Task | IIRM: Verify production backlog QA-Ready Issue | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2859 | IIRM-5397 | Task | IIRM; Regression on Testing on company & Contact , Opportunities Madules | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2860 | IIRM-5398 | Task | IIRM: Playwriight setup and Automation Test script for Company Madule | WORK IN PROGRESS | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2861 | IIRM-5399 | Task | IIRM: Verify the QA And UAT builds and regression checking | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2862 | IIRM-5400 | Task | IIRM: NEW CRs testing from primary backlog list | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2863 | IIRM-5401 | Bug | IIRM: SO Filter style showing different height | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2864 | IIRM-5402 | Bug | IIRM: All Features: Inactive contacts are displayed inside the company contacts dropdown | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2865 | IIRM-5403 | Bug | IIRM: SO/RO: Planning activity is missing in the Activity filter | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2866 | IIRM-5404 | Task | GMC top up covers are same as GMC, But Currently in application showing GPA covers | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2867 | IIRM-5405 | Task | Covers & Assests need to be in order as per the Policy sheet shared | Done | Richa Bagchi Mazumdar |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2868 | IIRM-5406 | Task | Where ever Enter Quote - At insurer Need to Show Insurer Name + Location | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2869 | IIRM-5407 | Task | In Broking Slip , Location is showing wrong- Person sitting in Pune, Bangalore location is capture | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
2870 | IIRM-5408 | Task | Some Covers and Assets are Repeated and some are not required | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2871 | IIRM-5409 | Task | Implement Dashboard Performance Outcomes | Done | Rama K |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2872 | IIRM-5410 | Sub-task | Bizdone report changes | Done | Richa Bagchi Mazumdar |  | IIRM-5477 — CR In IIRM
2873 | IIRM-5411 | Task | Bizdone: Create two new roles and need to assign permissions | Done | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
2874 | IIRM-5412 | Task | Need to update the policy creation fields in the database table | Done | Richa Bagchi Mazumdar |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2875 | IIRM-5413 | Bug | IIRM: Cover details are not displayed in RFP data collection stage | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2876 | IIRM-5414 | Task | After SO / RO Expiry, Need to provide privilege to manager so that expiry can be extended | Done | Rama K |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2877 | IIRM-5415 | Bug | IIRM: Communication details are not saved on the Contact Details page | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2878 | IIRM-5416 | Bug | IIRM: Only 10 companies are retrieved in the Parent Company dropdown/search | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-774 — SOW#47 - Company Plans
2879 | IIRM-5417 | Bug | IIRM: Inactive companies are displayed in the Parent Company dropdown list | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2880 | IIRM-5418 | Bug | IIRM: Admin side menu opens unexpectedly when creating Company, Contact, or SO | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2881 | IIRM-5419 | Bug | IIRM: Data not preserved when navigating back in Contact creation form | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2882 | IIRM-5420 | Bug | IIRM: Display Name validation error shown despite auto-population and no required field indication | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2883 | IIRM-5436 | Bug | IIRM: Incorrect access denied message displayed when non-owner tries to edit a contact | Done | SaikumarMahanthi | iWork | IIRM-783 — SOW#56 - Insurer / TPA integration
2884 | IIRM-5437 | Task | Design: Dashboard: Birthdays and Anniversaries | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2885 | IIRM-5438 | Task | IIRM: Sanity verifications on UAT Environment | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2886 | IIRM-5439 | Task | IIRM: Verify Ready for QA issues and Regression checking | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2887 | IIRM-5440 | Task | Enhancement User Activity Report | Done | Rama K |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2888 | IIRM-5441 | Story | Biz Done Reports | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
2889 | IIRM-5442 | Task | Executive and Manager Roles Issues | Done | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
2890 | IIRM-5459 | CR - Subtask | My Team Celebration Widget Implementation (FE+BE) | Done | Richa Bagchi Mazumdar |  | IIRM-5474 — CR: Birthday and Anniversary
2891 | IIRM-5460 | CR - Subtask | Organization Announcements Widget Implementation (FE+BE) | Done | Richa Bagchi Mazumdar |  | IIRM-5474 — CR: Birthday and Anniversary
2892 | IIRM-5461 | Bug | IIRM: Improve multi-select combo box usability — Show selected values at the top or allow clearing with delete icons | Open | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2893 | IIRM-5462 | QAlity Test | IIRM: Contact: Verify Data Preservation While Navigating Backward Direction | Draft | SaikumarMahanthi
2894 | IIRM-5463 | Task | IIRM: UAT Sanity Testing On QA-Ceritified issues | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2895 | IIRM-5464 | Task | IIRM: Performed regression testing on the Opportunity, Company, and Contact | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2896 | IIRM-5465 | Task | IIRM: Dashboard Funnel graphs verification | Done | SaikumarMahanthi |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2897 | IIRM-5466 | Bug | IIRM: TPA details blocking Final Negotiation submission despite not being mandatory | Done | SaikumarMahanthi |  | IIRM-783 — SOW#56 - Insurer / TPA integration
2898 | IIRM-5467 | Sub-task | UI Implementation of the Bizdone Screen | Done | Karan Agarwal |  | IIRM-5441 — Biz Done Reports
2899 | IIRM-5468 | Task | IIRM: Sanity Testing AI-card upload functionality | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2900 | IIRM-5469 | Bug | IIRM: Company not visible in search results after clearing all editable field data | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2901 | IIRM-5470 | Task | Others in Placement slip should be a amount field | Done | Keerthi Polepalle |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2902 | IIRM-5471 | Task | IIRM: Verify Ready for QA issues and Regression checking | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2903 | IIRM-5472 | Task | IIRM: UAT Bug fix verification and Regression testing on Opty stages | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
2904 | IIRM-5473 | QAlity Test | TPA Contact Validation | Draft | KOWTRAPU KAVYA SRI
2905 | IIRM-5474 | CR - Story | CR: Birthday and Anniversary | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2906 | IIRM-5475 | Bug | IIRM: UI issues on Contact Details – Text overlap and label casing inconsistencies | Done | SaikumarMahanthi |  | IIRM-783 — SOW#56 - Insurer / TPA integration
2907 | IIRM-5476 | Bug | IRM: Only First Name displayed in reporting fields instead of Display Name | Done | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2908 | IIRM-5477 | CR - Story | CR In IIRM | Draft | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2909 | IIRM-5478 | Bug | IIRM: Account Manager dropdown fails to return results when search contains spaces | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2910 | IIRM-5479 | Bug | IIRM: Order of data retrieved is different from the stored order in Contact/Profile Details page | Done - Not a Bug | SaikumarMahanthi | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2911 | IIRM-5480 | Bug | IIRM: MY SO: "Undefined" screen is displayed by clicking on the "Save & Exit and Next" button while creating SO | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2912 | IIRM-5481 | Task | [CR] - Stage Activity Template - Names should be different for SO and RO | Done | Gopal Gottumukkala | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2913 | IIRM-5482 | Task | Manage company: Document/Profile tab related to be made functional | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2914 | IIRM-5483 | Bug | Logo overlapping issues, Placement slip and Broking slip download file issues for ISG team | Done | Richa Bagchi Mazumdar |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2915 | IIRM-5484 | Story | No screen provided to configure the notifications/communications from front-end | Draft | Richa Bagchi Mazumdar |  | IIRM-761 — SOW#34 - Notifications Management
2916 | IIRM-5485 | Story | No screen provided to view the usage/Audits | Draft | Richa Bagchi Mazumdar |  | IIRM-748 — SOW#21 - Usage & Audit
2917 | IIRM-5486 | Task | Coverages entered in brokingslip generation stage are not depicting/populating in Enter quote stage and also same are not visible in QCR and finally in placementslip activity stage. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2918 | IIRM-5487 | Task | Remove mandatory requirement for Coverages, Brokerage %, and Brokerage Amount in Policy Hardcopy Receipt stage. | Done | Richa Bagchi Mazumdar |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2919 | IIRM-5488 | Task | When brokerage % & GST % are entered, it is not calculating brokerage amount & GST amount automatically. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2920 | IIRM-5489 | Task | GMC Top up Policy Issues | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2921 | IIRM-5490 | Task | Issue in completing SO / RO activities with Vippinc and Surya Account | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2922 | IIRM-5491 | Task | Business performance Outcomes implementation | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2923 | IIRM-5492 | Task | Updating Reporting Manager issue | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2924 | IIRM-5493 | Task | Sorting functionality implementation update | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2925 | IIRM-5494 | Task | Retail Policy & Company / user creation APIs | Open | Richa Bagchi Mazumdar |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2926 | IIRM-5495 | Bug | IIRM: Parent Company field appears empty when navigating back from the Submit page | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2927 | IIRM-5496 | QAlity Test | Insurer Contact: Edit: RBAC: Authorized users can edit all permitted fields of the Insurer Contact. | Draft | KOWTRAPU KAVYA SRI
2928 | IIRM-5497 | QAlity Test | Broker Contact: Edit: RBAC: Authorized users can edit all permitted fields of the Broker Contact. | Draft | KOWTRAPU KAVYA SRI
2929 | IIRM-5498 | QAlity Test | Insurer Contact: Add: Appropriate validations and errors are displayed when invalid data is input during Insurer Contact creation | Draft | KOWTRAPU KAVYA SRI
2930 | IIRM-5499 | QAlity Test | Broker Contact: Add: Appropriate validations and errors are displayed when invalid data is input during Broker Contact creation | Draft | KOWTRAPU KAVYA SRI
2931 | IIRM-5500 | Story | NFR-SEC-067: The platform must implement strong password policies including complexity and expiration rules. | Done | Richa Bagchi Mazumdar |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
2932 | IIRM-5502 | Bug | Internal meeting users are not populated | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2933 | IIRM-5503 | Sub-task | CR: In Tasks and meetings, we need option in Task to tag others | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2934 | IIRM-5504 | Task | Policy Dashboard design changes & status stepper design in table | Done | bala |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2935 | IIRM-5505 | Task | IIRM: Reverifying the issues | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
2936 | IIRM-5506 | Task | Change the following Menu items | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2937 | IIRM-5507 | Task | Hide other links (Reinsurance hub, personal lines, LIA consulting, Fin Ops, Manthan, Poppins) for all users. Links in the header, let them be as they are. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2938 | IIRM-5508 | Task | Display ownership guidance message in listing pages when ownership-driven data is unavailable. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2939 | IIRM-5509 | Task | Update card labels in SO/RO listing screen | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
2940 | IIRM-5510 | Task | SO and RO listing has performance issue, taking long time to load on each change and first load as well. Especially RO is taking way longer. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2941 | IIRM-5511 | Task | In policy details page Change Configure --> Configuration & View Configure to -> View Configuration | Done | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
2942 | IIRM-5512 | Task | Bring in SBU into Org -> Vertical hierarchy. It has to be Org -> SBU -> Vertical. T | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2943 | IIRM-5513 | Bug | IIRM: My SO: Not able to create an SO | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2944 | IIRM-5514 | QAlity Test | Company: Edit: Assign Owner: Verify that the manager can assign a new Lead CRM for a Company | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2945 | IIRM-5515 | Bug | IIRM: Opty Stages: All the activities set should be enabled for the user. Till the activities set are sent for approval/Approved | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
2946 | IIRM-5516 | Bug | IIRM:Permission issue encountered while logging out of the system | Done | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
2947 | IIRM-5517 | Task | Investigate and fix permission error encountered on logout in QA environment | Done | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
2948 | IIRM-5518 | Bug | IIRM: Task: Data issues for the Deviation tasks created from the activities | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2949 | IIRM-5519 | Task | Quick create: Meeting should have a text box | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
2950 | IIRM-5535 | Task | IIRM: Logout: "You don’t have the required permissions to access this resource" message displayed | Done | Leela Pakalapati | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
2951 | IIRM-5536 | Bug | IIRM: Manager role unable to associate another BD Exec as Lead CRM for a company | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2952 | IIRM-5537 | Task | Prototype for the policy flow | Done | bala |  | IIRM-797 — SOW#69 - Manage Opportunities
2953 | IIRM-5538 | Task | Demo on Approvals to IIRM team | Done | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
2954 | IIRM-5539 | Task | In the database, create "ISG Manager 2" role for VRK garu without the "Assignment" privilege | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2955 | IIRM-5540 | Task | Need to add SBU Item (get more details from Naveen & Rama) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2956 | IIRM-5541 | Task | in RO table, show the recent 3 months data. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2957 | IIRM-5542 | Task | List of records to have "My Records" and "My Team's records" | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2958 | IIRM-5543 | Task | Include filter on "Vertical" | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2959 | IIRM-5544 | Task | Disable 3 letter validation for Last name field (when adding employee) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2960 | IIRM-5545 | Task | Add "Consulting" and "Speciality Lines" to the list of SBU. When adding employees | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2961 | IIRM-5546 | Task | Ensure to match data from Bizdone reports vs dashboard (by considering Inactive user's count) | Open | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2962 | IIRM-5547 | Story | Policy Renewal notification to be sent to CRM users | Done | Richa Bagchi Mazumdar |  | IIRM-761 — SOW#34 - Notifications Management
2963 | IIRM-5548 | Task | All users of Sri Lanka, Maldives, Kenya & Safe Risk to be added. | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
2964 | IIRM-5549 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2965 | IIRM-5550 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2966 | IIRM-5551 | Task | Divami Bold: Figma Testing | Done | Leela Pakalapati |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2967 | IIRM-5552 | Bug | IIRM: Contacts: Inactive users are displayed in Reporting to field | Done | Leela Pakalapati | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
2968 | IIRM-5553 | Task | Dashboard Data Consistency | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2969 | IIRM-5554 | Task | Approval Issues – Pending approval-related problems need to be fixed. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2970 | IIRM-5555 | Task | State Model Functionality (BE + FE) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2971 | IIRM-5557 | Task | UAT Merge | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2972 | IIRM-5558 | Task | For lost RO/SO, please activate all of them till 25th October | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2973 | IIRM-5559 | Bug | IIRM: Duplicate phone numbers allowed while creating multiple TPA contacts | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
2974 | IIRM-5561 | Task | Dev - Lead Tasks | Done | meghana |  | IIRM-797 — SOW#69 - Manage Opportunities
2975 | IIRM-5562 | Task | Org and SBU also to be added in all tabs of Bizdone report | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
2976 | IIRM-5563 | Bug | IIRM: Close (×) icon is misaligned in all dropdown fields On Opty | Done | SaikumarMahanthi |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2977 | IIRM-5564 | Bug | IIRM: City name displayed with state name in IIRM (e.g., “Andhra Pradesh Nelluru” instead of “Nelluru”) | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2978 | IIRM-5565 | Task | Main Dashboard Changes_Priority | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
2979 | IIRM-5566 | Bug | IIRM: Company: Not able to view the created company in Create Company wizard | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2980 | IIRM-5567 | Bug | IIRM: Approve name not displayd | Done | SaikumarMahanthi |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2981 | IIRM-5568 | Bug | IIRM: Quote issues in broking slip | Done | SaikumarMahanthi |  | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
2982 | IIRM-5569 | Bug | IIRM: Manage Policies: Policy numbers are not displayed | Done - Not Reproducible | SaikumarMahanthi |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2983 | IIRM-5570 | Bug | IIRM: Company: Full name should be display in Lead CRM field while creating a company | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2984 | IIRM-5571 | Bug | IIRM: Quick Company: "Cancel" button is not displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
2985 | IIRM-5572 | Bug | IIMR:Invalid Date name Displayed for Policy From and To Dates | Done | SaikumarMahanthi |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
2986 | IIRM-5573 | Bug | IIRM: Search is not working on My SO list page | Done | SaikumarMahanthi |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
2987 | IIRM-5574 | Task | Claims Corner Page - UI Design | Done | bala | IBP | IIRM-787 — SOW#60 - Claims Corner
2988 | IIRM-5575 | Task | UX- Claims Corner | Done | meghana | IBP | IIRM-787 — SOW#60 - Claims Corner
2989 | IIRM-5576 | Story | Policy Template | Done | meghana | IBP | IIRM-777 — SOW#50 - Policy Configurator
2990 | IIRM-5577 | Story | Policy Configuration | Done | meghana | IBP | IIRM-777 — SOW#50 - Policy Configurator
2991 | IIRM-5578 | Story | Policy Creation | Open | meghana | IBP | IIRM-777 — SOW#50 - Policy Configurator
2992 | IIRM-5579 | Sub-task | Analyze and design database tables to store policy configuration data related to policies. | Done | meghana |  | IIRM-5577 — Policy Configuration
2993 | IIRM-5580 | Sub-task | Develop an API to create a policy configuration for a given policy. | Done | meghana |  | IIRM-5577 — Policy Configuration
2994 | IIRM-5581 | Sub-task | Implement APIs to update and retrieve the policy configuration for a policy. | Done | meghana |  | IIRM-5577 — Policy Configuration
2995 | IIRM-5582 | Sub-task | Create an API to approve or reject a policy configuration. | Done | meghana |  | IIRM-5577 — Policy Configuration
2996 | IIRM-5583 | Sub-task | UI: Policy Listing Page | PENDING PEER or LEAD REVIEW | Nikhil V |  | IIRM-5577 — Policy Configuration
2997 | IIRM-5584 | Sub-task | UI: Policy Configuration Stepper | Done | Nikhil V |  | IIRM-5577 — Policy Configuration
2998 | IIRM-5585 | Sub-task | UI: Policy Configuration API Integration | PENDING PEER or LEAD REVIEW | Nikhil V |  | IIRM-5577 — Policy Configuration
2999 | IIRM-5586 | Sub-task | UI: Policy Template Creation | Pushed to Backlog | Nikhil V |  | IIRM-5577 — Policy Configuration
3000 | IIRM-5587 | Sub-task | UI Tweaks for Configurator | Pushed to Backlog | meghana |  | IIRM-5577 — Policy Configuration
3001 | IIRM-5588 | Sub-task | Implement Validations for Policy configurator | Done | meghana |  | IIRM-5577 — Policy Configuration
3002 | IIRM-5589 | Sub-task | API to fetch Policy list | Done | meghana |  | IIRM-5577 — Policy Configuration
3003 | IIRM-5590 | Sub-task | API to Fetch Policy Details | Done | meghana |  | IIRM-5577 — Policy Configuration
3004 | IIRM-5591 | Sub-task | Policy details page | Pushed to Backlog | meghana |  | IIRM-5577 — Policy Configuration
3005 | IIRM-5592 | Sub-task | API to store the Policy Configuration (POST, UPDATE) | Done | meghana |  | IIRM-5577 — Policy Configuration
3006 | IIRM-5593 | Sub-task | Implement Filters at Policy Listing Page | Done | meghana |  | IIRM-5577 — Policy Configuration
3007 | IIRM-5594 | Sub-task | In My Ro listing page add 3 moths as default search value in period | Done | meghana |  | IIRM-5577 — Policy Configuration
3008 | IIRM-5595 | Sub-task | Quick Links Card in the Policy dashboard | Done | meghana |  | IIRM-5577 — Policy Configuration
3009 | IIRM-5596 | Sub-task | Design and create policy-related tables | Done | meghana |  | IIRM-5578 — Policy Creation
3010 | IIRM-5597 | Sub-task | Analyze and create entities, relationships and Dto's | Done | meghana |  | IIRM-5578 — Policy Creation
3011 | IIRM-5598 | Sub-task | Analyse existing opportunity details relevant to policy creation | Done | meghana |  | IIRM-5578 — Policy Creation
3012 | IIRM-5599 | Sub-task | Implement logic to insert or associate opportunity data with policy creation in their respective sections | Done | meghana |  | IIRM-5578 — Policy Creation
3013 | IIRM-5600 | Sub-task | API to create policy tempate | Pushed to Backlog | meghana |  | IIRM-5576 — Policy Template
3014 | IIRM-5601 | Sub-task | UI to Download / Upload Policy Template | Done | meghana |  | IIRM-5576 — Policy Template
3015 | IIRM-5602 | Task | UI for Policy overview, components, relationships, parameters, template, choices and constraints and final review | Done | meghana |  | IIRM-777 — SOW#50 - Policy Configurator
3016 | IIRM-5603 | Task | User stories and acceptance criteria for Policy Configurator | Done | meghana |  | IIRM-777 — SOW#50 - Policy Configurator
3017 | IIRM-5623 | Story | Upload of Corporate Employee Data | Open | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3018 | IIRM-5624 | Story | Provide Excel template based on Policy configuration | Open | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3019 | IIRM-5625 | Story | Design- Landing Page | Done | meghana | IBP | IIRM-771 — SOW#44 - IBP Landing Page (Design)
3020 | IIRM-5626 | Story | TPA Processing: BE+FE | Done | Richa Bagchi Mazumdar | IBP | IIRM-783 — SOW#56 - Insurer / TPA integration
3021 | IIRM-5627 | Story | CD Management | Done | Richa Bagchi Mazumdar | IBP | IIRM-781 — SOW#54 - CD Management
3022 | IIRM-5628 | Story | IBP - TPA | Done | meghana | IBP | IIRM-783 — SOW#56 - Insurer / TPA integration
3023 | IIRM-5629 | Story | Claim Data Ingestion | Done | meghana | IBP | IIRM-782 — SOW#55 - Claim Management
3024 | IIRM-5630 | Story | Policy Enrollment | WORK IN PROGRESS | meghana | IBP | IIRM-773 — SOW#46 - Enrolment Portal
3025 | IIRM-5631 | Story | IBP: UI: Login page implementation | Done | Nikhil V | IBP | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
3026 | IIRM-5632 | Story | UI: API Integration in the dahboard page | Done | Nikhil V | IBP
3027 | IIRM-5633 | Story | UI: Implement relationship enrollment flow static | Done | Nikhil V | IBP
3028 | IIRM-5634 | Story | Design - Policy Enrolment | Draft | meghana | IBP | IIRM-773 — SOW#46 - Enrolment Portal
3029 | IIRM-5635 | Sub-task | Backend - Upload of Corporate Employee Data | Done | meghana | IBP | IIRM-5623 — Upload of Corporate Employee Data
3030 | IIRM-5636 | Sub-task | UI - Upload of Corporate Employee Data | Done | meghana | IBP | IIRM-5623 — Upload of Corporate Employee Data
3031 | IIRM-5637 | Sub-task | Backend - Provide Excel template based on Policy configuration | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5624 — Provide Excel template based on Policy configuration
3032 | IIRM-5638 | Sub-task | UI - Provide Excel template based on Policy configuration | Done | meghana | IBP | IIRM-5624 — Provide Excel template based on Policy configuration
3033 | IIRM-5639 | Sub-task | BE:Analyze DB Schema for CD management | Done | Richa Bagchi Mazumdar | IBP | IIRM-5627 — CD Management
3034 | IIRM-5640 | Sub-task | BE:API for Creating CD Account Based on Company and Policy | Done | Richa Bagchi Mazumdar | IBP | IIRM-5627 — CD Management
3035 | IIRM-5641 | Sub-task | BE:API for updating the CD Premium amount and maintaing the transactions | Done | Richa Bagchi Mazumdar | IBP | IIRM-5627 — CD Management
3036 | IIRM-5642 | Sub-task | BE:API For fetching the List of CD account Transactions | Done | Richa Bagchi Mazumdar | IBP | IIRM-5627 — CD Management
3037 | IIRM-5643 | Sub-task | UI - For Adding Premium amount into CD account | Done | Richa Bagchi Mazumdar | IBP | IIRM-5627 — CD Management
3038 | IIRM-5644 | Sub-task | UI - Displaying the CD account Transactions | Done | Richa Bagchi Mazumdar | IBP | IIRM-5627 — CD Management
3039 | IIRM-5645 | Sub-task | Analysis of the database schema for mapping tpa ids against employees & dependents | Done | meghana | IBP | IIRM-5628 — IBP - TPA
3040 | IIRM-5646 | Sub-task | Backend processing to add the TPA ids against employees and dependents | Done | meghana | IBP | IIRM-5628 — IBP - TPA
3041 | IIRM-5647 | Sub-task | Fetch TPA ids mapped to the employees and dependents | Done | meghana | IBP | IIRM-5628 — IBP - TPA
3042 | IIRM-5648 | Sub-task | UI for TPA processing screens | Done | meghana | IBP | IIRM-5628 — IBP - TPA
3043 | IIRM-5649 | Sub-task | Integrate API to capture TPA processing screens | Done | meghana | IBP | IIRM-5628 — IBP - TPA
3044 | IIRM-5650 | Sub-task | UX- Policy Enrollment | Done | meghana | IBP | IIRM-5634 — Design - Policy Enrolment
3045 | IIRM-5651 | Sub-task | UI- Policy Enrollement | Done | meghana | IBP | IIRM-5634 — Design - Policy Enrolment
3046 | IIRM-5652 | Sub-task | UX-Feedback changes | Done | gowtham | IBP | IIRM-5634 — Design - Policy Enrolment
3047 | IIRM-5653 | Sub-task | BE:Update the template with mock data while downloading | Done | Richa Bagchi Mazumdar | IBP | IIRM-5626 — TPA Processing: BE+FE
3048 | IIRM-5654 | Sub-task | BE:Analysis of the database schema for mapping tpa ids against employees & dependents | Done | Richa Bagchi Mazumdar | IBP | IIRM-5626 — TPA Processing: BE+FE
3049 | IIRM-5655 | Sub-task | BE:Backend processing to add the TPA ids against employees and dependents | Done | Richa Bagchi Mazumdar | IBP | IIRM-5626 — TPA Processing: BE+FE
3050 | IIRM-5656 | Sub-task | BE:Fetch TPA ids mapped to the employees and dependents | Done | Richa Bagchi Mazumdar | IBP | IIRM-5626 — TPA Processing: BE+FE
3051 | IIRM-5657 | Sub-task | UI for TPA processing screens - Tweaks for the endorsement table and add the TPA upload functionality | Done | Richa Bagchi Mazumdar | IBP | IIRM-5626 — TPA Processing: BE+FE
3052 | IIRM-5658 | Sub-task | Analyse the Database schema for saving the claims report received from the TPA | Done | meghana | IBP | IIRM-5629 — Claim Data Ingestion
3053 | IIRM-5659 | Sub-task | "API for mapping the claims data received from the TPA and mapping that against the policy of the employees, CD balance updation and balance sum insured for the users" | Done | meghana | IBP | IIRM-5629 — Claim Data Ingestion
3054 | IIRM-5660 | Sub-task | API for fetching the claims data specific to policy / employee | Done | meghana | IBP | IIRM-5629 — Claim Data Ingestion
3055 | IIRM-5661 | Sub-task | UI for Claim Data Ingestion processing screens | Pushed to Backlog | meghana | IBP | IIRM-5629 — Claim Data Ingestion
3056 | IIRM-5662 | Sub-task | Integrate API to capture Claim Data Ingestion processing screens | Done | meghana | IBP | IIRM-5629 — Claim Data Ingestion
3057 | IIRM-5663 | Sub-task | Landing section | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3058 | IIRM-5664 | Sub-task | wellness section | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3059 | IIRM-5665 | Sub-task | KPI's/values | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3060 | IIRM-5666 | Sub-task | Numbers | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3061 | IIRM-5667 | Sub-task | commitment section | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3062 | IIRM-5668 | Sub-task | Why IWH ? section | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3063 | IIRM-5669 | Sub-task | collaborating companies | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3064 | IIRM-5670 | Sub-task | Need help page | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3065 | IIRM-5671 | Sub-task | footer | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3066 | IIRM-5672 | Sub-task | Login Page- login section | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5625 — Design- Landing Page
3067 | IIRM-5673 | Sub-task | UI: Implement Policy Enrollment flow static | PENDING PEER or LEAD REVIEW | Nikhil V | IBP | IIRM-5630 — Policy Enrollment
3068 | IIRM-5674 | Sub-task | UI: API integration for the policy enrollment flow | PENDING PEER or LEAD REVIEW | Nikhil V | IBP | IIRM-5630 — Policy Enrollment
3069 | IIRM-5675 | Sub-task | UI: API Integration for the Relationship flow | WORK IN PROGRESS | Nikhil V | IBP | IIRM-5630 — Policy Enrollment
3070 | IIRM-5676 | Sub-task | UI: Implementing common component for the enrollment flow | PENDING PEER or LEAD REVIEW | Nikhil V | IBP | IIRM-5630 — Policy Enrollment
3071 | IIRM-5677 | Sub-task | Create user Login based on Uploaded Data | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5630 — Policy Enrollment
3072 | IIRM-5678 | Sub-task | Dashboard Banner Section design with Static data | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5630 — Policy Enrollment
3073 | IIRM-5679 | Sub-task | Dashboard Details section design with Static data | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5630 — Policy Enrollment
3074 | IIRM-5680 | Sub-task | Animations for Banner section | Pushed to Backlog | meghana | IBP | IIRM-5630 — Policy Enrollment
3075 | IIRM-5681 | Sub-task | Animations for Details section | Pushed to Backlog | meghana | IBP | IIRM-5630 — Policy Enrollment
3076 | IIRM-5682 | Sub-task | API to fetch the Policies available based on company and Logged in User | Done | meghana | IBP | IIRM-5630 — Policy Enrollment
3077 | IIRM-5683 | Sub-task | API to get user details for a logged in user | Done | meghana | IBP | IIRM-5630 — Policy Enrollment
3078 | IIRM-5684 | Sub-task | API to Update user details for a logged in user | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5630 — Policy Enrollment
3079 | IIRM-5685 | Sub-task | API to get Policy Configured details for logged in user | Done | meghana | IBP | IIRM-5630 — Policy Enrollment
3080 | IIRM-5686 | Sub-task | API to save the data for policy configuration submitted by the user | Done | meghana | IBP | IIRM-5630 — Policy Enrollment
3081 | IIRM-5687 | Sub-task | API to save the draft data | Done | meghana | IBP | IIRM-5630 — Policy Enrollment
3082 | IIRM-5688 | Sub-task | Integrations for Policy selction by the logged in user (7 screens ) | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5630 — Policy Enrollment
3083 | IIRM-5689 | Sub-task | API to Implement Enrollment Management when Employees not using IBP - Directly form HR | Done | meghana | IBP | IIRM-5630 — Policy Enrollment
3084 | IIRM-5690 | Sub-task | UI Screen implementation for Enrollment Management when Employees not using IBP - Directly form HR | Pushed to Backlog | meghana | IBP | IIRM-5630 — Policy Enrollment
3085 | IIRM-5691 | Sub-task | UI Integration for Enrollment Management when Employees not using IBP - Directly form HR | Pushed to Backlog | meghana | IBP | IIRM-5630 — Policy Enrollment
3086 | IIRM-5692 | Task | Design- Endorsements | Done | meghana | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
3087 | IIRM-5693 | Task | Evaluate the integration of Excel enrollment data into database tables | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3088 | IIRM-5694 | Task | Analyse the data intake process for enrollment data | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3089 | IIRM-5695 | Task | Review and refine the template structure for adding employee intake data | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3090 | IIRM-5696 | Task | My Documents - UI Designs | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3091 | IIRM-5697 | Task | Claim history page UI design | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3092 | IIRM-5698 | Task | If there is no error, the error file should be disabled | Done | Richa Bagchi Mazumdar | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3093 | IIRM-5699 | Task | The error message should be specific | Done | Richa Bagchi Mazumdar | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3094 | IIRM-5700 | Task | Modify the cron job to include employee enrollment data | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3095 | IIRM-5701 | Task | Design - Portal Configuration | Done | meghana | IBP | IIRM-794 — SOW#67 - Portal Configuration
3096 | IIRM-5702 | Task | My insurance and login page design review and Client meeting | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3097 | IIRM-5703 | Task | My Insurance Page UI Design - card designs | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3098 | IIRM-5704 | Task | Policy Dashboard UI Design | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3099 | IIRM-5705 | Task | Update insurer acknowledgement file label change. | Done | Richa Bagchi Mazumdar | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3100 | IIRM-5706 | Task | Dashboard redesign & Login Page | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3101 | IIRM-5707 | Task | My Insurance Page UI Design - Accordion design | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3102 | IIRM-5708 | Task | Outside development time test, we need to create a screen to check whether the configuration is correct or not. | Done | Richa Bagchi Mazumdar | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3103 | IIRM-5709 | Task | ''the file is created it will take few mins to process the file" | Done | Richa Bagchi Mazumdar | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3104 | IIRM-5710 | Task | send email to the owner of the policies | Done | Richa Bagchi Mazumdar | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3105 | IIRM-5711 | Task | All the primary columns need to be aligned(columns need to be aligned). | Done | Richa Bagchi Mazumdar | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3106 | IIRM-5712 | Task | Claims corner Page Feedback changes | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3107 | IIRM-5713 | Task | Icon design review | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3108 | IIRM-5714 | Task | summarization of the company needs to be their | Done | Richa Bagchi Mazumdar | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3109 | IIRM-5715 | Task | Backend - Enrollment readiness for Corporate Employees - Auth, etc. | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3110 | IIRM-5716 | Task | Backend- Create Users & Logins based on Uploaded Data | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3111 | IIRM-5717 | Task | Backend- Process Uploaded Data and DB Storage | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3112 | IIRM-5718 | Task | IBP: Verified endorsement build and bugs raising | Done | Akhila Gattu | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
3113 | IIRM-5719 | Task | IBP: Endorsement: Verifying QA Ready bugs and endorsement functionality | Done | Akhila Gattu | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
3114 | IIRM-5720 | Task | IBP: Employee data build verified and raised bugs onit | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3115 | IIRM-5721 | Task | IBP: Endorsement: Verifying QA Ready bugs and verifying Endorsement and raising bugs | Done | Akhila Gattu | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
3116 | IIRM-5722 | Task | IBP: Employee data build received verifying sanity and Preparing testdata of employee data | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3117 | IIRM-5723 | Task | IBP: Endorsement: Verifying QA Ready bugs, validating endorsement feature and testcases updating | Done | Akhila Gattu | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
3118 | IIRM-5724 | Task | IBP- Verifying data intake build | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3119 | IIRM-5725 | Task | IBP: Endorsement: Verifying functionality and raising bugs | Done | Akhila Gattu | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
3120 | IIRM-5726 | Task | IBP: Prepared testdata for employee and verified build on policy configure | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3121 | IIRM-5727 | Task | IBP: Updating testcases | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3122 | IIRM-5728 | Task | Analyse the template for the data intake for enrollment | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3123 | IIRM-5729 | Task | .Create a template for the enrollment through Excel | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3124 | IIRM-5730 | Task | Excel template should have the same choices | Done | Richa Bagchi Mazumdar | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3125 | IIRM-5731 | Task | User journey: For clients who don't have portal access still IIRM have to do it in a structured format as of they have access to the portal | Done | Richa Bagchi Mazumdar | IBP | IIRM-773 — SOW#46 - Enrolment Portal
3126 | IIRM-5733 | Task | Review testcases ,updated testplan, test stretagy Verifying QA Ready bugs on latest build Prepared RTM for policyconfigure" | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3127 | IIRM-5734 | Task | "Testcycle created for policy configure ZAP report generated" | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3128 | IIRM-5735 | Task | Worked on policy configure QA build, Test execution report send | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3129 | IIRM-5736 | Task | Preparing testcases for employee data and review | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3130 | IIRM-5737 | Task | IBP - build on employee data verifying | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3131 | IIRM-5738 | Task | User stories and Acceptance Criteria for CD Management | Done | meghana | IBP | IIRM-774 — SOW#47 - Company Plans
3132 | IIRM-5739 | Task | User stories and Acceptance Criteria for MIR Entry Management | Done | meghana | IBP | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
3133 | IIRM-5740 | Task | User stories and Acceptance Criteria for Enrollment Portal | Done | meghana | IBP | IIRM-773 — SOW#46 - Enrolment Portal
3134 | IIRM-5741 | Task | User stories and Acceptance Criteria for Endorsements | Done | meghana | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
3135 | IIRM-5742 | Task | Style Establishment | Done | meghana | IBP | IIRM-771 — SOW#44 - IBP Landing Page (Design)
3136 | IIRM-5743 | Task | UX- My Insurance Page for Client employee | Done | meghana | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3137 | IIRM-5744 | Task | Dashboard animation and Overlay animation | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3138 | IIRM-5745 | Task | Design- Landing page for Client employee | Done | meghana | IBP | IIRM-771 — SOW#44 - IBP Landing Page (Design)
3139 | IIRM-5746 | Task | Insurance cards design | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3140 | IIRM-5747 | Task | wellness Benefits section design | Done | bala | IBP | IIRM-784 — SOW#57 - Basic Wellness Hub
3141 | IIRM-5748 | Task | Dashboard redesigns with new sections UI design | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3142 | IIRM-5749 | Task | Enrollment design changes with new sections addons | Done | bala | IBP | IIRM-773 — SOW#46 - Enrolment Portal
3143 | IIRM-5750 | Task | IBP Initial Setup of Code into Repo | Done | meghana | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3144 | IIRM-5752 | Task | Endorsements | Done | meghana | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
3145 | IIRM-5753 | Task | Details Page Fixes | Done | meghana | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3146 | IIRM-5754 | Task | Hospital Network | Done | meghana | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3147 | IIRM-5755 | Task | API Gateway concept in enrollment portal | Done | Richa Bagchi Mazumdar | IBP | IIRM-773 — SOW#46 - Enrolment Portal
3148 | IIRM-5756 | Task | HR Corner UI Designs | Done | bala | IBP | IIRM-776 — SOW#49 - HR Portal View
3149 | IIRM-5757 | Task | Enrolment page - Policy Cards Designs | Done | bala | IBP | IIRM-773 — SOW#46 - Enrolment Portal
3150 | IIRM-5758 | Task | Experience design Brainstorming with internal team | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3151 | IIRM-5759 | Task | API to Upload the Employee data of the Policy to S3 | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3152 | IIRM-5760 | Task | Enrolment flow - Changes and feedback | Done | bala | IBP | IIRM-773 — SOW#46 - Enrolment Portal
3153 | IIRM-5761 | Task | UI to Display the List of Processed data details | Done | meghana | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3154 | IIRM-5762 | Task | Animation landing page and illustration | Done | bala | IBP | IIRM-771 — SOW#44 - IBP Landing Page (Design)
3155 | IIRM-5763 | Task | Futuristic Page with car and flight insurance and personal insurance banner design | Done | bala | IBP | IIRM-771 — SOW#44 - IBP Landing Page (Design)
3156 | IIRM-5764 | Task | Dataabase schema analysis for processing the employee data | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3157 | IIRM-5765 | Task | API to Fetch the list of Processed data details | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3158 | IIRM-5766 | Task | Crone to Process employee records from S3 Uploaded file to Database | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3159 | IIRM-5767 | Task | Experience design dashboard design and internal feedback changes | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3160 | IIRM-5768 | Task | FAQ page - UI Design | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3161 | IIRM-5769 | Task | API Business logic for Processing the data into Success and Failure records | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3162 | IIRM-5770 | Task | Update the Depenedents List for the processed Employee record | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3163 | IIRM-5771 | Task | Implement the Validations of Employee data at API for the uploaded data | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3164 | IIRM-5772 | Task | Create user Login based on Uploaded Data | Done | meghana | IBP | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
3165 | IIRM-5773 | Task | IBP: Hospital Network Page Redesign - UI | Done | bala | IBP | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
3166 | IIRM-5774 | Task | Dashboard illustration Animation | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3167 | IIRM-5775 | Task | Dashboard illustration tracing | Done | bala | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3168 | IIRM-5776 | Task | UI Approach2 for Internal Wireframe | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3169 | IIRM-5777 | Task | IBP: Verification on Policy Configurator | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3170 | IIRM-5778 | Task | Claims corner edge cases design | Done | bala | IBP | IIRM-787 — SOW#60 - Claims Corner
3171 | IIRM-5779 | Task | Review and Design changes | Done | bala | IBP | IIRM-797 — SOW#69 - Manage Opportunities
3172 | IIRM-5780 | Task | Design - IBP Portal | Done | meghana | IBP | IIRM-771 — SOW#44 - IBP Landing Page (Design)
3173 | IIRM-5781 | Task | IBP: Policy Configure: Preparing testcases | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3174 | IIRM-5782 | Task | UX- HR Corner (Future Scope) | Done | meghana | IBP | IIRM-776 — SOW#49 - HR Portal View
3175 | IIRM-5783 | Task | IBP: PolicyConfigure: Preparing testcases | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3176 | IIRM-5784 | Task | IBP: PolicyConfigure: Preparing flowchart of configurator process | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3177 | IIRM-5785 | Task | IBP: PolicyConfigure: Verifying Configure API's | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3178 | IIRM-5786 | Task | IBP: PolicyConfigure: Modifying testcases | Done | Akhila Gattu | IBP | IIRM-777 — SOW#50 - Policy Configurator
3179 | IIRM-5787 | Sub-task | UX- Listing Page | Done | meghana | IBP | IIRM-5743 — UX- My Insurance Page for Client employee
3180 | IIRM-5788 | Sub-task | UX- Enrollment Details | Done | meghana | IBP | IIRM-5743 — UX- My Insurance Page for Client employee
3181 | IIRM-5789 | Sub-task | UX- Enrollment Summary | Done | meghana | IBP | IIRM-5743 — UX- My Insurance Page for Client employee
3182 | IIRM-5790 | Sub-task | UX- Landing Page for first time users | Done | meghana | IBP | IIRM-5745 — Design- Landing page for Client employee
3183 | IIRM-5791 | Sub-task | UX- Landing page for existing users | Done | meghana | IBP | IIRM-5745 — Design- Landing page for Client employee
3184 | IIRM-5792 | Sub-task | Feedback changes | Done | gowtham | IBP | IIRM-5745 — Design- Landing page for Client employee
3185 | IIRM-5793 | Sub-task | Policy details page | Done | gowtham | IBP | IIRM-5745 — Design- Landing page for Client employee
3186 | IIRM-5794 | Sub-task | Analyse and extract endorsement data into an Excel sheet for the insurer | Done | meghana | IBP | IIRM-5752 — Endorsements
3187 | IIRM-5795 | Sub-task | Analyse the Database schema for managing Endorsements | Done | meghana | IBP | IIRM-5752 — Endorsements
3188 | IIRM-5796 | Sub-task | Review the template creation process for endorsement data | Done | meghana | IBP | IIRM-5752 — Endorsements
3189 | IIRM-5797 | Sub-task | API to fetch endorsement data for insurer | Done | meghana | IBP | IIRM-5752 — Endorsements
3190 | IIRM-5798 | Sub-task | UI to Display the endorsement stats and upload /download template | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5752 — Endorsements
3191 | IIRM-5799 | Sub-task | Integrate API to display the endorsement stats and download template | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5752 — Endorsements
3192 | IIRM-5800 | Sub-task | Analyse the Database schema for saving the acknowledgement of endorsements from insurer | Done | meghana | IBP | IIRM-5752 — Endorsements
3193 | IIRM-5801 | Sub-task | API to fetch / add endorsement acknowledgments | Done | meghana | IBP | IIRM-5752 — Endorsements
3194 | IIRM-5802 | Sub-task | Tweaks for the database schema based on the overall analysis of the Endorsement UI form to capture the endorsement acknowledgments | Done | meghana | IBP | IIRM-5752 — Endorsements
3195 | IIRM-5803 | Sub-task | Integrate API to capture the endorsement acknowledgments | PENDING PEER or LEAD REVIEW | meghana | IBP | IIRM-5752 — Endorsements
3196 | IIRM-5804 | Sub-task | API to get the stats of the endorsement specific to a policy | Done | meghana | IBP | IIRM-5752 — Endorsements
3197 | IIRM-5805 | Sub-task | Endorsement listing page | Done | meghana | IBP | IIRM-5752 — Endorsements
3198 | IIRM-5806 | Sub-task | Hospital List | Done | meghana | IBP | IIRM-5754 — Hospital Network
3199 | IIRM-5807 | Sub-task | Hospital Details | Done | meghana | IBP | IIRM-5754 — Hospital Network
3200 | IIRM-5808 | Sub-task | UX- Details page Fixes | Done | meghana | IBP | IIRM-5753 — Details Page Fixes
3201 | IIRM-5809 | Sub-task | UI- Details page fixes | Done | meghana | IBP | IIRM-5753 — Details Page Fixes
3202 | IIRM-5810 | Sub-task | Approach and research experiential design | Done | bala | IBP | IIRM-5742 — Style Establishment
3203 | IIRM-5811 | Sub-task | Approach 1 with existing client wireframe | Done | bala | IBP | IIRM-5742 — Style Establishment
3204 | IIRM-5812 | Sub-task | login page design and animation | Done | bala | IBP | IIRM-5742 — Style Establishment
3205 | IIRM-5813 | Sub-task | wireframe for the dashboard | Done | bala | IBP | IIRM-5742 — Style Establishment
3206 | IIRM-5814 | Sub-task | experiential design approach for the internal wireframe | Done | bala | IBP | IIRM-5742 — Style Establishment
3207 | IIRM-5815 | Sub-task | Defining use case | Done | meghana | IBP | IIRM-5692 — Design- Endorsements
3208 | IIRM-5816 | Sub-task | Drafting Design (iteration 1) | Done | meghana | IBP | IIRM-5692 — Design- Endorsements
3209 | IIRM-5817 | Sub-task | Policy dashboard | Done | gowtham | IBP | IIRM-5692 — Design- Endorsements
3210 | IIRM-5818 | Sub-task | Add employee/Del endorsement workflow | Done | gowtham | IBP | IIRM-5692 — Design- Endorsements
3211 | IIRM-5819 | Sub-task | Create endoresement workflow | Done | gowtham | IBP | IIRM-5692 — Design- Endorsements
3212 | IIRM-5820 | Sub-task | UX- My Documents page | Done | meghana | IBP | IIRM-5780 — Design - IBP Portal
3213 | IIRM-5821 | Sub-task | UX- History Page | Done | meghana | IBP | IIRM-5780 — Design - IBP Portal
3214 | IIRM-5822 | Sub-task | UX- Life events flow | Done | meghana | IBP | IIRM-5780 — Design - IBP Portal
3215 | IIRM-5823 | Sub-task | Logo management | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3216 | IIRM-5824 | Sub-task | Policy Linking | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3217 | IIRM-5825 | Sub-task | Policy Feature | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3218 | IIRM-5826 | Sub-task | FAQ Management | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3219 | IIRM-5827 | Sub-task | Utility Management | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3220 | IIRM-5828 | Sub-task | Claim Process Management | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3221 | IIRM-5829 | Sub-task | Contact Detail Management | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3222 | IIRM-5830 | Sub-task | Communication management | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3223 | IIRM-5831 | Sub-task | Enrollment Window Management | Done | meghana | IBP | IIRM-5701 — Design - Portal Configuration
3224 | IIRM-5832 | Sub-task | User stories and Acceptance Criteria for Enrollment Portal (Client Employee) | Done | meghana | IBP | IIRM-5740 — User stories and Acceptance Criteria for Enrollment Portal
3225 | IIRM-5833 | Sub-task | User stories and Acceptance Criteria for Enrollment Portal (Insurance Broker) | Done | meghana | IBP | IIRM-5740 — User stories and Acceptance Criteria for Enrollment Portal
3226 | IIRM-5834 | Process Sub Task | In endorsement page convert all the drawers into modal views | RELEASED | Richa Bagchi Mazumdar |  | IIRM-5752 — Endorsements
3227 | IIRM-5835 | Bug | IBP: Endorsement: ‘Ready for Endorsement’ Count Incorrect for Large File Uploads (20,000 Records) | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3228 | IIRM-5836 | Bug | IBP: PolicyConfiguration: UI : Alignments were incorrect | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3229 | IIRM-5837 | Bug | IBP: Endorsement : Invalid effective date shown on error file | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3230 | IIRM-5838 | Bug | IBP: Endorsement: marital status parameter functionality not working | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3231 | IIRM-5839 | Bug | IBP: Manage endorsement : Search functionality not working | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3232 | IIRM-5840 | Bug | IBP- PolicyConfigure: Min age validation missing | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3233 | IIRM-5841 | Bug | IBP: Endorsement: Endorsement functionality not working | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3234 | IIRM-5842 | Bug | IBP: Enrollment: Dependencies can be restrict with designation and CTC | Done | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
3235 | IIRM-5843 | Bug | IBP: Endorsement: Uploaded file not able to view on dashboard | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3236 | IIRM-5844 | Bug | IBP: Endorsement: Fake data template shown invalid data for relationship parameter | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3237 | IIRM-5845 | Bug | IBP: Employeedata: Enrollment template upload functionality not working | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3238 | IIRM-5846 | Bug | IBP: TPA : Once endorsement file got successful, track endorsement is not getting updated. | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3239 | IIRM-5847 | Bug | IBP: CD: CD balance empty showing on policy header | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3240 | IIRM-5848 | Bug | IBP: PolicyConfigure: Custom range field restricts input to 3 digits, preventing entry of larger values | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3241 | IIRM-5849 | Bug | IBP: File upload: Only Excel Files should accept — Non-Excel Formats gets Restricted | Done | Akhila Gattu |  | IIRM-783 — SOW#56 - Insurer / TPA integration
3242 | IIRM-5850 | Bug | IBP Endorsement: ‘Ready for Endorsement’ Count Underreports on 1000-Record Upload | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3243 | IIRM-5851 | Bug | IBP: TPA: TPA Data count should get updated after TPA file upload | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3244 | IIRM-5852 | Bug | IBP: PolicyConfigure: Provided years on constraints stage not maintains after approval | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3245 | IIRM-5853 | Bug | IBP: employeeData: For dependencies CTC error should not shown | Done - Not Reproducible | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3246 | IIRM-5854 | Bug | IBP: EmployeeData: More than one same relation type cant be accept | Done | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
3247 | IIRM-5855 | Bug | IBP: EmployeeData: Invalid Error file shown on employee data upload | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3248 | IIRM-5856 | Bug | IBP: PolicyConfigure: Policy status is not updating to Active, on configure status is live. | Open | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3249 | IIRM-5857 | Bug | IBP: Endorsement: 2 records were getting triggered on error file for same dependency | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3250 | IIRM-5858 | Bug | IBP: Endorsement: File Upload: Unexpected Double Pop‑Up Appears Post‑Upload | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3251 | IIRM-5859 | Bug | IBP: EmployeeData: Valid Date of Birth (DOB) triggers incorrect validation error message | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3252 | IIRM-5860 | Bug | IBP: Track Endorsement: Ack received date, uploaded by, Endorsement type not getting updated on track endorsement | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3253 | IIRM-5861 | Bug | IBP: Endorsement: Grade Parameter: Endorsement functionality not working | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3254 | IIRM-5862 | Bug | IBP: Insurerack & TPA upload: Drag and drop functionality not working | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3255 | IIRM-5863 | Bug | IBP: Endorsement: Remove Serial no column on downloaded endorsement file | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3256 | IIRM-5864 | Bug | IBP: Insurer ack & TPA : Multiple files were getting uploaded , file is not getting replaced on file re-upload process | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3257 | IIRM-5865 | Bug | IBP: CD: NEFT, RTGS should be in upper case | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3258 | IIRM-5866 | Bug | IBP: Endorsement: Disable the future dates, if future dates were restricted | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3259 | IIRM-5867 | Bug | IBP: Endorsement: Designation Parameter: File Upload Count Remains ‘Not Started’ Instead of Transitioning to ‘Ready for Endorsement’” | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3260 | IIRM-5868 | Bug | IBP: DOJ is getting empty on endorsement file | Done | Akhila Gattu |  | IIRM-783 — SOW#56 - Insurer / TPA integration
3261 | IIRM-5869 | Bug | IBP: Endorsement: MaritualStatus Parameter: File Upload Count Remains ‘Not Started’ Instead of Transitioning to ‘Ready for Endorsement’” | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3262 | IIRM-5870 | Bug | IBP: Endorsement: RelationShip Parameter: File Upload Count Remains ‘Not Started’ Instead of Transitioning to ‘Ready for Endorsement’” | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3263 | IIRM-5871 | Bug | IBP: PolicyConfigure: Validation error should show when 'Parental Policy' is selected and user clicks Next | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3264 | IIRM-5872 | Bug | IBP: Endorsement : Instead of Employee Number , Employee ID should be shown | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3265 | IIRM-5873 | Bug | IBP: Policy: Policy is not reflecting on manage policies Error thrown : Socket hangup | Done | Akhila Gattu |  | IIRM-755 — SOW#28 - Manage BD 2 Stages & Policy Creation
3266 | IIRM-5875 | Bug | IBP: TPA: Yet to receive TPA count not getting updated on " Need your attention " card | Done | Akhila Gattu |  | IIRM-742 — SOW#15 - Add/Manage TPA
3267 | IIRM-5876 | Bug | IBP: Endorsement: Added dependents not showing on endorsement file | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3268 | IIRM-5877 | Bug | IBP: Enrollment: Uploaded data not reflecting on UI | Done | Akhila Gattu |  | IIRM-756 — SOW#29 - Manage ISG Stages
3269 | IIRM-5878 | Bug | IBP: Endorsement: CustomRange Parameter: Proper remarks should shown on error file | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3270 | IIRM-5879 | Bug | IBP: Endorsement: Dependency deletion functionality not working | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3271 | IIRM-5880 | Bug | IBP: PolicyConfigure: Field error message should not get change | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3272 | IIRM-5881 | Bug | IBP: CD: Empty field shown on Placement slip generation for existing account if opening balance is 0 | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3273 | IIRM-5882 | Bug | IBP: CD: Empty transaction details showing on Debit process(CD details) | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3274 | IIRM-5883 | Bug | IBP:CD: Reference type dropdown not matching with spec | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3275 | IIRM-5884 | Bug | IBP: CD : CD balance not updating after adding via 'Add CD Balance' option | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3276 | IIRM-5885 | Bug | IBP: PolicyConfigure: "-" Value Not Removing Field and Should Be Hidden When only one Field is available | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3277 | IIRM-5886 | Bug | IBP: PolicyConfigure: "0" Value Should Not Be Accepted or Saved in SI Fields | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3278 | IIRM-5887 | Bug | IBP: PolicyConfigure: Mandatory Field Validation Message Not Displayed Below the Field | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3279 | IIRM-5888 | Bug | IBP: API: PolicyConfigure: PUT API Response Successful but Data Not Reflected on UI | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3280 | IIRM-5889 | Bug | IBP: API: PolicyConfig: Get By Policy ID API Returns 400 Bad Request | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3281 | IIRM-5890 | Bug | IBP: API: PolicyConfigure: Get By PolicyConfigurator ID API Returns 404 not found | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3282 | IIRM-5891 | Bug | IBP: PolicyConfigure: Empty details shown on CD details page | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3283 | IIRM-5892 | Bug | IBP: CD Account: Endorsement: Unable to download endorsement file | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3284 | IIRM-5893 | Bug | IBP: Policy Dashboard: Duplicate endorsement track record is getting added on file download fail | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3285 | IIRM-5894 | Bug | IBP: DataInTake: Employee data template not triggered after policy configuration is activated | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3286 | IIRM-5895 | Bug | IBP: Policy Configure: Saved Breadcrumb Data Displayed Incorrectly on Reopening Policy – Not Navigating to Unsaved/Next Stage | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3287 | IIRM-5896 | Bug | IBP: Policy configure: Policy components: Invalid SI Values Accepted – Missing Min/Max Validation | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3288 | IIRM-5897 | Bug | IBP: Policy configure: Policy components: Mandatory Symbol Missing for Required Fields | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3289 | IIRM-5898 | Bug | IBP: Policy Configure: Policy components: Commas Not Auto-Applying While Typing | QA in Progress | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3290 | IIRM-5899 | Bug | IBP: Policy configure: Policy Template: Sequence column not properly aligned | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3291 | IIRM-5900 | Bug | IBP: Policy Configure: Policy relationships: Validation Missing for Spouse/Partner Type – Multiple Checkboxes Allowed | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3292 | IIRM-5901 | Bug | IBP: Policy configure: Policy relationships: Max Number Field Not Reset to default state on Checkbox Deselect | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3293 | IIRM-5902 | Bug | IBP: Policy Configure: Policy choices: UI is not user friendly | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3294 | IIRM-5903 | Bug | IBP: Policy configure: Policy choices: Remove shortcut words on policy choices stage | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3295 | IIRM-5904 | Bug | IBP: Policy configure: Constraints &Final Review: Age limit not restricted | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3296 | IIRM-5905 | Bug | IBP: EnrollmentTemplate: File upload is getting rejected with valid data | Done | Akhila Gattu |  | IIRM-756 — SOW#29 - Manage ISG Stages
3297 | IIRM-5906 | Bug | IBP: EnrollmentTemplate: Failed status file not displayed after enrollment file upload | Done | Akhila Gattu |  | IIRM-756 — SOW#29 - Manage ISG Stages
3298 | IIRM-5907 | Bug | IBP: Policy configure: Policy list: Rejected Status Still Displayed on Configuration Status After Policy Approval | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3299 | IIRM-5908 | Bug | IBP: EmployeeData: Invalid DOB shown on error file and DOB validation missing | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3300 | IIRM-5909 | Bug | IBP: EmployeeData: 400 thrown on Employee data | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3301 | IIRM-5910 | Bug | IBP: EmployeeData: File upload not returns as success status with valid data | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3302 | IIRM-5911 | Bug | IBP: API: PolicyConfigure: API Response Successful but Data Not Reflected on UI | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3303 | IIRM-5912 | Bug | IBP:API: PolicyConfigure: Duplicate API Request with Same Payload Incorrectly Returns 'Created Successfully' | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3304 | IIRM-5913 | Bug | IBP: PolicyConfigure: Error message 'Oops! Something went wrong' displayed on navigating from View Configure to Policy Components | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3305 | IIRM-5914 | Bug | IBP: Policy: empty policy number shown on UI | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3306 | IIRM-5915 | Bug | IBP: EmployeeData: Employee data is getting ingesting with empty intake type | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3307 | IIRM-5916 | Bug | IBP: EmployeeData: Employee data is getting ingested with empty name type | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3308 | IIRM-5917 | Bug | IBP: EmployeeData: Employee data is getting ingested with empty gender type dependency | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3309 | IIRM-5918 | Bug | IBP: EmployeeData: Employee data is getting ingested with empty mobile number type | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3310 | IIRM-5919 | Bug | IBP: EmployeeData: Data is getting uploaded with empty CTC , error not thrown | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3311 | IIRM-5920 | Bug | IBP: Employeedata: File upload takes excessive time to reflect on UI and lacks delay message | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3312 | IIRM-5921 | Bug | IBP: PolicyConfigure: Age validations missing on PolicyRelationships , Policy Parameters, | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3313 | IIRM-5922 | Bug | IBP: EmployeeData: For empty data row upload error thrown | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3314 | IIRM-5923 | Bug | IBP: Employeedata: Database error encountered during upload of 1000-event data file | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3315 | IIRM-5924 | Bug | IBP: EmployeeData: Invalid Date text shown in Date column | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3316 | IIRM-5925 | Bug | IBP: EmployeeData: Dependencies data upload fails when using separate file – error thrown | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3317 | IIRM-5926 | Bug | IBP: PolicyConfigure: Typo error on "PolicyDefinition" text and duplicate tabs | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3318 | IIRM-5927 | Bug | IBP: EmployeeData: Incorrect no.of records shown on UI | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3319 | IIRM-5928 | Bug | IBP: Endorsement: Relationship parameter policy endorsement functionality not working error thrown "Invalid choices are mapped to this employee for this policy. Please verify." | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3320 | IIRM-5929 | Bug | IBP: PolicyConfigure: Previous Partner Age Values Displayed by Default When "Another Relationship" Checkbox is Selected | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3321 | IIRM-5930 | Bug | IBP: TPA: Upload TPA IDs: File Is Ingested Without Required ‘TPA ID’ Column | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3322 | IIRM-5931 | Bug | IBP: Endorsement: Error thrown "Invalid choices are mapped to this employee for this policy. Please verify "on endorsement file upload | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3323 | IIRM-5932 | Bug | IBP: Endorsement : Empty Topup sum insured column showing on endorsement file | Done - Not a Bug | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3324 | IIRM-5933 | Bug | IBP: Endorsement: Download failed error thrown for 4000 employees | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3325 | IIRM-5934 | Bug | IBP: endorsement: Error on file upload with Age parameter | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3326 | IIRM-5935 | Bug | IBP: EmployeeData: Duplicate employee data tab shown on policy details | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3327 | IIRM-5936 | Bug | IBP: Endorsement: Invalid remarks shown for invalid data | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3328 | IIRM-5937 | Bug | IBP- Endorsement: Invalid DOB shown on Error file | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3329 | IIRM-5938 | Bug | IBP: Endorsement: Gender parameter policy endorsement fucntionality not working | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3330 | IIRM-5939 | Bug | IBP: EmployeeData: Validation should trigger for current year | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3331 | IIRM-5940 | Bug | IBP: Endorsement: Endorsement file upload fails when 2 parents are provided and 1 is deleted in the same file, despite only single parent being allowed | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3332 | IIRM-5941 | Bug | IBP: EmployeeData: Template API is getting failed, even if data is not present | Done | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3333 | IIRM-5942 | Bug | IBP: Endorsement: file upload validation message should get change | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3334 | IIRM-5943 | QAlity Test | IBP: PolicyConfigure: Verify Owner of the policy is able to update the policy configuration. | Draft | Akhila Gattu
3335 | IIRM-5944 | QAlity Test | IBP: SanityLevel: PolicyTemplate: Verify Policy Template screen loads correctly. | Draft | Akhila Gattu
3336 | IIRM-5945 | QAlity Test | IBP: PolicyConfigure: Verify Policy Configurator is disabled for inactive policies, for policies where current user is not the owner and submitted policies | Draft | Akhila Gattu
3337 | IIRM-5946 | QAlity Test | IBP: PolicyConfigure: verify validations for each of the types covering only the default options | Draft | Akhila Gattu
3338 | IIRM-5947 | QAlity Test | IBP: PolicyConfigure: Verify Configure policies of all supported types | Draft | Akhila Gattu
3339 | IIRM-5948 | QAlity Test | IBP: PolicyConfigure: Verify Configure policies of all supported types and validations for each of the types covering age bands | Draft | Akhila Gattu
3340 | IIRM-5949 | QAlity Test | IBP: PolicyConfigure: Verify Configure policies of all supported types and validations for each of the relationship types | Draft | Akhila Gattu
3341 | IIRM-5950 | QAlity Test | IBP: PolicyConfigure: verify Configure set of complex policies with combinations of all supported parameters | Draft | Akhila Gattu
3342 | IIRM-5951 | QAlity Test | IBP: PolicyConfigure: verify validations for each of the types covering multiple sum insured options - SI, CTC, etc. using non-default options | Draft | Akhila Gattu
3343 | IIRM-5952 | QAlity Test | IBP: SanityLevel: PolicyTemplate: Validate Policy Template Screen Loading, Field Inputs, Radio Button Functionality, and Navigation Buttons | Draft | Akhila Gattu
3344 | IIRM-5953 | QAlity Test | IBP:SanityLevel: PolicyRelationship: Verify Policy Relationships screen loads correctly. | Draft | Akhila Gattu
3345 | IIRM-5954 | QAlity Test | IBP: SanityLevel: PolicyRelationship: Validate Policy Relationships Screen Defaults, Field Inputs, Checkbox Functionality, and Navigation Buttons | Draft | Akhila Gattu
3346 | IIRM-5955 | QAlity Test | IBP: SanityLevel: PolicyParameter: Verify Policy Parameters screen loads correctly. | Draft | Akhila Gattu
3347 | IIRM-5960 | QAlity Test | IBP: SanityLevel: PolicyParameter: Validate Policy Parameters Screen: Parameter Addition, Saving, and Navigation | Draft | Akhila Gattu
3348 | IIRM-5961 | QAlity Test | IBP: SanityLevel: PolicyChoices: Verify Policy Choices screen loads correctly. | Draft | Akhila Gattu
3349 | IIRM-5962 | QAlity Test | IBP: SanityLevel: PolicyChoices: Validate Policy Choices Screen: Component Selection, Checkboxes, Saving, and Navigation | Draft | Akhila Gattu
3350 | IIRM-5963 | QAlity Test | IBP: SanityLevel: Constraints: Verify "Constraints & Final Review" screen loads correctly. | Draft | Akhila Gattu
3351 | IIRM-5964 | QAlity Test | IBP: SanityLevel: Constraints: Validate Constraints & Final Review Screen: Field Inputs, Radio Buttons, Saving, and Navigation | To Do | Akhila Gattu
3352 | IIRM-5965 | QAlity Test | IBP:UIValidation: PoliyComponent: Validate "Sequence (Seq)" Field: Required, Numeric, Positive Integer, and Uniqueness Rules | Draft | Akhila Gattu
3353 | IIRM-5966 | QAlity Test | IBP: UIValidation: PolicyComponent: Verify default selection for Yes/No radio buttons on screen load. | Draft | Akhila Gattu
3354 | IIRM-5967 | QAlity Test | IBP: UIvalidation: PolicyComponent: Verify add-on component checkboxes can be checked/unchecked. | Draft | Akhila Gattu
3355 | IIRM-5968 | QAlity Test | IBP: UIValidation: PolicyComponent: Verify 'Display Label' respects maximum character limit. | Draft | Akhila Gattu
3356 | IIRM-5969 | QAlity Test | IBP: UIvalidation: PolicyComponent: Verify all applicable validation rules are enforced upon clicking 'Save'. | Draft | Akhila Gattu
3357 | IIRM-5972 | QAlity Test | IBP: EmployeeData: Verify Error validation file should generate , if dependencies were added without self | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3358 | IIRM-5973 | QAlity Test | IBP: EmployeeData: Verify bulk employees data can upload with their dependencies | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3359 | IIRM-5974 | QAlity Test | IBP: EmployeeData: Verify Download functionality for rejected data | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3360 | IIRM-5975 | QAlity Test | IBP: EmployeeData: Verify DOB should not contain present day | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3361 | IIRM-5976 | QAlity Test | IBP: EmployeeData: Verify validation on data file contains more than one same relation type | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3362 | IIRM-5977 | QAlity Test | IBP: EmployeeData: Verify validations on employee data file upload for DOB, Gender, Email, Phno. | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3363 | IIRM-5978 | QAlity Test | IBP: EmployeeData: Verify proper remarks should be shown on error file | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3364 | IIRM-5979 | QAlity Test | IBP: EmployeeData: Verify null intake on file upload should get rejected | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3365 | IIRM-5980 | QAlity Test | IBP: EmployeeData: Verify on error file, all columns data should get match with uploaded data | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3366 | IIRM-5981 | QAlity Test | IBP: EmployeeData: Verify all columns data on employee data page, should get properly generated after file upload | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3367 | IIRM-5982 | QAlity Test | IBP: EmployeeData: Verify Employee data should get rejected, if already existing data is getting uploaded with proper remarks | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3368 | IIRM-5984 | QAlity Test | IBP: CD: Verify CD amount for new account in policy dashboard | Draft | Akhila Gattu
3369 | IIRM-5985 | QAlity Test | IBP: CD: Verify CD balance credited on endorsement file uploaded with deletion of employees/Dependencies | Draft | Akhila Gattu
3370 | IIRM-5986 | QAlity Test | IBP: CD: Verify CD amount for existing account in policy dashboard | Draft | Akhila Gattu
3371 | IIRM-5990 | QAlity Test | IBP: CD: Verify endorsement without sufficient CD balance | Draft | Akhila Gattu
3372 | IIRM-5991 | QAlity Test | IBP: CD: Verify validation on policy dashboard, CD amount is less than premium amount | Draft | Akhila Gattu
3373 | IIRM-5992 | QAlity Test | IBP: CD: Verify Credit and Debit actions were getting reflect on CD details tab | Draft | Akhila Gattu
3374 | IIRM-5993 | QAlity Test | IBP: CD: Verify CD amount reduced on Endorsement file upload with Ingestion/Addition of employees | Draft | Akhila Gattu
3375 | IIRM-5994 | QAlity Test | IBP: CD: Verify CD amount is equal to premium amount | Draft | Akhila Gattu
3376 | IIRM-5995 | QAlity Test | IBP: CD: Verify CD amount less than premium amount | Draft | Akhila Gattu
3377 | IIRM-5996 | QAlity Test | IBP: PolicyConfigure: BasePolicy: Verify SI Amount Field Functionality for Flat Sum Insured Model | Draft | Akhila Gattu
3378 | IIRM-5997 | QAlity Test | IBP: Policyconfigure: BasePolicy: Verify Premium Calculation Behavior When 'Per Family' Option is Selected | Draft | Akhila Gattu
3379 | IIRM-6000 | QAlity Test | IBP: PolicyConfigure: BasePolicy: Verify Mid-Year Enrollment Toggle, Default State and SI Visibility Toggles Behavior for Base Policy | Draft | Akhila Gattu
3380 | IIRM-6001 | QAlity Test | IBP: PolicyConfigure: BasePolicy: Verify Max Number Field Accepts Valid Input for Each Relationship Type in Base Policy | Draft | Akhila Gattu
3381 | IIRM-6002 | QAlity Test | IBP: PolicyConfigure: BasePolicy: Verify Min and Max Age Limit for Permitted Relations Configured Under Base Policy | Draft | Akhila Gattu
3382 | IIRM-6003 | QAlity Test | IBP: PolicyConfigure: BasePolicy: Verify Dropdown List Displays All Available Policy Parameters for Base Policy | Draft | Akhila Gattu
3383 | IIRM-6004 | QAlity Test | IBP: PolicyConfigure: BasePolicy: Verify Range Display and Min/Max Fields Functionality Upon Selecting a Policy Parameter | Draft | Akhila Gattu
3384 | IIRM-6005 | QAlity Test | IBP: PolicyConfigure: BasePolicy: Verify Configuration of Base Policy with Sum Insured, Availability, Default Selection, and Contributions | Draft | Akhila Gattu
3385 | IIRM-6006 | QAlity Test | IBP: PolicyConfigure: BasePolicy: Verify Final Review Constraints in Base Policy for GPA, GTL, GMC | Draft | Akhila Gattu
3386 | IIRM-6007 | QAlity Test | IBP: CD: Verify CD balance is getting updated on CD details and CD balance card after adding via 'Add CD Balance' option | Draft | Akhila Gattu
3387 | IIRM-6008 | QAlity Test | IBP: Policy Configure: Verify Policy configure for Base +Optional policy | Draft | Akhila Gattu
3388 | IIRM-6009 | QAlity Test | IBP: Policy Configure: Verify Policy configure for Base +Parental+Optional policy | Draft | Akhila Gattu
3389 | IIRM-6010 | QAlity Test | IBP: Policy Configure: Verify policy configure for Base +parental policy | Draft | Akhila Gattu
3390 | IIRM-6011 | QAlity Test | IBP: Policy Configure: Verify policy configure for Base policy | Draft | Akhila Gattu
3391 | IIRM-6012 | QAlity Test | IBP: Policy Configure: Verify policy configure for other policy types | Draft | Akhila Gattu
3392 | IIRM-6014 | QAlity Test | IBP: PolicyConfigure: Verify Configure policy to be paid in installments | Draft | Akhila Gattu
3393 | IIRM-6015 | QAlity Test | IBP: PolicyConfigure: Verify policy using GST flag and verify that relevant messages are displayed. | Draft | Akhila Gattu
3394 | IIRM-6016 | QAlity Test | IBP: PolicyConfigure: Verify policy configuration validations from admin side | Draft | Akhila Gattu
3395 | IIRM-6017 | QAlity Test | IBP: PolicyConfigure: Verify Reconfigure existing policy to update ages and see its impact on the premium logic | Draft | Akhila Gattu
3396 | IIRM-6018 | QAlity Test | IBP: PolicyConfigure: Verify Enable re-enrollment in the mid year for life events | Draft | Akhila Gattu
3397 | IIRM-6019 | QAlity Test | IBP: PolicyConfigure: Verify policy linking with other active policies | Draft | Akhila Gattu
3398 | IIRM-6020 | QAlity Test | IBP: PolicyConfigure: Verify activate button for inactive / expired policies | Draft | Akhila Gattu
3399 | IIRM-6021 | QAlity Test | IBP: PolicyConfigure: Verify active button for configured policies | Draft | Akhila Gattu
3400 | IIRM-6022 | QAlity Test | IBP: PolicyConfigure: Verify UI for all stages before submit and after submit | Draft | Akhila Gattu
3401 | IIRM-6023 | QAlity Test | IBP: PolicyConfigure: Verify commas for all numeric fields | Draft | Akhila Gattu
3402 | IIRM-6024 | QAlity Test | IBP: EmployeeData: Verify employee data can be uploaded for GMC, GTL, GPA | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3403 | IIRM-6025 | QAlity Test | IBP: EmployeeData: Verify employee data template can be upload policy types( apart of GPA,GMC, GTL) | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3404 | IIRM-6026 | QAlity Test | IBP: EmployeeData: Verify generated error file can be uploaded by removing remarks column | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3405 | IIRM-6027 | QAlity Test | IBP: Endorsement: Verify Functionality of Ins ACK and Upload TPA's should get work from Manage service | Draft | Akhila Gattu
3406 | IIRM-6028 | QAlity Test | IBP: Endorsement: Verify list of endorsements were displayed under manage service | Draft | Akhila Gattu
3407 | IIRM-6029 | QAlity Test | IBP: HLT: PolicyConfigure: Verify that the system allows selecting an active policy and correctly associates all configuration changes with it. | Draft | Akhila Gattu
3408 | IIRM-6030 | QAlity Test | IBP: HLT: PolicyConfigure: Verify that the system ensures only a single policy type can be selected and that this selection is accurately reflected and saved. | Draft | Akhila Gattu
3409 | IIRM-6031 | QAlity Test | IBP:HTL: Policy Configure: Verify that the system allows for the creation, modification, and deletion of custom age bands while enforcing non-overlapping ranges. | Draft | Akhila Gattu
3410 | IIRM-6032 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system correctly restricts the relationships applicable in a policy to only those selected from a master list. | Draft | Akhila Gattu
3411 | IIRM-6033 | QAlity Test | IBP: UIvalidation: PolicyTemplate:Validate "Sum Insured Model" Radio Buttons Rendering, Initial State, Selection Behavior, and Event Handling | Draft | Akhila Gattu
3412 | IIRM-6034 | QAlity Test | IBP: UIValidation: PolicyRelationship: Validate "Show Company Contribution" Checkbox Rendering, Initial State, Toggling, and Event Handling | Draft | Akhila Gattu
3413 | IIRM-6035 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows defining minimum and maximum age limits for selected relationships and enforces valid age ranges. | Draft | Akhila Gattu
3414 | IIRM-6036 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows setting and enforcing limits for people per relationship and the total family size. | Draft | Akhila Gattu
3415 | IIRM-6037 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system supports the creation of multiple relationship groups and the association of selected relationships within these groups. | Draft | Akhila Gattu
3416 | IIRM-6038 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows the definition of multiple unique sum insured options and makes these available for selection during enrollment. | Draft | Akhila Gattu
3417 | IIRM-6039 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows defining and storing unique employee grades for use in policy mapping. | Draft | Akhila Gattu
3418 | IIRM-6040 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system enables linking employee grades, relationship groups, and sum insured options, preventing incomplete mappings. | Draft | Akhila Gattu
3419 | IIRM-6041 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system supports various premium calculation logics (e.g., Flat, Age Band) and dynamically adjusts the input interface accordingly. | Draft | Akhila Gattu
3420 | IIRM-6042 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system provides functionality to define and enter premiums for complex combinations such as grade, relationship, and gender. | Draft | Akhila Gattu
3421 | IIRM-6043 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows defining employer and employee premium sharing percentages and validates that their sum equals 100%. | Draft | Akhila Gattu
3422 | IIRM-6044 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system provides mutually exclusive options for defining whether the sum insured is fixed or floater. | Draft | Akhila Gattu
3423 | IIRM-6045 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system provides mutually exclusive options for defining whether the premium is calculated per life, per family, or not applicable. | Draft | Akhila Gattu
3424 | IIRM-6046 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows administrators to configure the visibility of employee and employer premium shares to employees. | Draft | Akhila Gattu
3425 | IIRM-6047 | QAlity Test | IBP: UIValidation: PolicyParameter: Validate "Max No." and "Min/Max Age" Fields: Required, Numeric, Positive Integer, Range, and Min-Max Constraints | Draft | Akhila Gattu
3426 | IIRM-6048 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows defining and enforcing cross-parent selection rules during the enrollment process. | Draft | Akhila Gattu
3427 | IIRM-6049 | QAlity Test | IBP: HLT: PolicyConfigure: Verify that the system allows configuring and enforcing twin allowance for the second child. | Draft | Akhila Gattu
3428 | IIRM-6050 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows configuring and displaying GST and enrollment confirmation messages. | Draft | Akhila Gattu
3429 | IIRM-6051 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows configuring installment payment options and generates a corresponding payment schedule. | Draft | Akhila Gattu
3430 | IIRM-6052 | QAlity Test | IBP:UIValidation: PolicyChoices: Validate "Co. Contrib", "Emp. Contrib" Fields, Default/Available Checkbox Interactions, and Form-Level Validations | Draft | Akhila Gattu
3431 | IIRM-6053 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows configuring and applying employee age calculation methods for premiums. | Draft | Akhila Gattu
3432 | IIRM-6054 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system provides comprehensive controls for defining various detailed policy behavior rules, including visibility, parent selection logic, age restrictions, and eligibility. | Draft | Akhila Gattu
3433 | IIRM-6055 | QAlity Test | IBP: UIValidation: Constraints: Validate Complete Policy Configuration Workflow: Screen Navigation, Core Field Validations, Component Configuration, and Final Submission | Draft | Akhila Gattu
3434 | IIRM-6056 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows linking the policy to other active policies belonging to the same client. | Draft | Akhila Gattu
3435 | IIRM-6057 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows defining and applying sum insured relationship logic with linked policies. | Draft | Akhila Gattu
3436 | IIRM-6058 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system allows administrators to select predefined life events that trigger mid-year policy changes and re-enrollment functionality. | Draft | Akhila Gattu
3437 | IIRM-6059 | QAlity Test | IBP: HLT: Policy Configure: Verify that the system controls policy activation based on mandatory fields and subsequently locks settings while enabling enrollment upon activation. | Draft | Akhila Gattu
3438 | IIRM-6060 | QAlity Test | IBP: API: PolicyConfigure: GET: Retrieve Policy Template configuration. | Draft | Akhila Gattu
3439 | IIRM-6061 | QAlity Test | IBP: PolicyConfigure: Validate Boolean fields accept only true/false. | Draft | Akhila Gattu
3440 | IIRM-6062 | QAlity Test | IBP: PolicyConfigure: Verify Unauthorized access attempt. | Draft | Akhila Gattu
3441 | IIRM-6063 | QAlity Test | IBP: PolicyConfigure: Verify Forbidden access attempt (if user lacks permission). | Draft | Akhila Gattu
3442 | IIRM-6064 | QAlity Test | IBP: EnrollmentTemplate: Verify when the policy ID is not a number | Draft | Akhila Gattu
3443 | IIRM-6065 | QAlity Test | IBP: EnrollmentTemplate: Verify If this endpoint requires a token or API key in the headers, it's missing or invalid. | Draft | Akhila Gattu
3444 | IIRM-6066 | QAlity Test | IBP: EnrollmentTemplate: Verify If a policy exists but for some reason, an enrollment template is not associated with it, | Draft | Akhila Gattu
3445 | IIRM-6068 | QAlity Test | IBP: Enrollment template: Verify enrollment template download with download API | Draft | Akhila Gattu
3446 | IIRM-6069 | QAlity Test | IBP: EnrollmentTemplate: Verify policy ID that does not exist in the system is provided. | Draft | Akhila Gattu
3447 | IIRM-6071 | QAlity Test | IBP: PolicyConfiguration: Verify payload updating an existing configuration. | Draft | Akhila Gattu
3448 | IIRM-6072 | QAlity Test | IBP: PolicyConfiguration: Verify put call on existing payload | Draft | Akhila Gattu
3449 | IIRM-6073 | QAlity Test | IBP: PolicyConfiguration: Verify PUT API with single and multiple policy step | Draft | Akhila Gattu
3450 | IIRM-6074 | QAlity Test | IBP: SanityLevel: PolicyConfigure: Verify policy got generated after placementslip generation approved | Draft | Akhila Gattu
3451 | IIRM-6075 | QAlity Test | IBP: EnrollmentTemplate: Verify template is uploaded with only mandatary fields | Draft | Akhila Gattu
3452 | IIRM-6076 | QAlity Test | IBP: SanityLevel: PolicyConfigure: Policy Component: Validate Display Label Text Field Rendering, Input Functionality, and Constraints | Draft | Akhila Gattu
3453 | IIRM-6077 | QAlity Test | IBP: EmployeeData: Verify Employeedata file uploaded with mandatary fields | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3454 | IIRM-6078 | QAlity Test | IBP: EnrollmentTemplate: Verify enrollment data is uploaded for per family policy | Draft | Akhila Gattu
3455 | IIRM-6079 | QAlity Test | IBP: Enrollment Template: Verify enrollment data is uploaded with empty file | Draft | Akhila Gattu
3456 | IIRM-6080 | QAlity Test | IBP: EnrollmentTemplate: Verify enrollment data is uploaded with data type mismatch | Draft | Akhila Gattu
3457 | IIRM-6081 | QAlity Test | IBP: EnrollmentTemplate : Verify enrollment data is uplaoded only with non-mandatary fields. | Draft | Akhila Gattu
3458 | IIRM-6082 | QAlity Test | IBP: EnrollmentTemplate: Verify Enrollment data is uploaded with single record | Draft | Akhila Gattu
3459 | IIRM-6083 | QAlity Test | IBP: EnrollmentTemplate: Verify enrollment data is uploaded with 100 records. | Draft | Akhila Gattu
3460 | IIRM-6084 | QAlity Test | IBP: EnrollmentTemplate: Verify Enrollment data is uploaded with 10,000 events | Draft | Akhila Gattu
3461 | IIRM-6085 | QAlity Test | IBP: EnrollmentTemplate: Verify Enrollment template data is uploaded for per life policy | Draft | Akhila Gattu
3462 | IIRM-6086 | QAlity Test | IBP: SanityLevel: PolicyConfigure: PolicyComponents: Validate "Sum Insured Model" Radio Buttons Rendering, Initial State, Selection Behavior, and Event Handling | Draft | Akhila Gattu
3463 | IIRM-6087 | QAlity Test | IBP: SanityLevel: PolicyConfigure: Policy Component: Validate "SI Amount" Field Rendering, Input Type, Increment/Decrement Functionality, Value Limits, and Formatting | Draft | Akhila Gattu
3464 | IIRM-6089 | QAlity Test | IBP: SanityLevel: policyComponent: Validate "Show Company Contribution" Checkbox Rendering, Initial State, Toggling, and Event Handling | Draft | Akhila Gattu
3465 | IIRM-6094 | QAlity Test | IBP: EmployeeData: Verify employee data is uploaded with 100 records | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3466 | IIRM-6095 | QAlity Test | IBP: EmployeeData: verify employee data can be uploaded with 10000 records | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3467 | IIRM-6098 | QAlity Test | IBP: enployeeData: EmployeeData is uplaoded with non mandatary fields | Draft | Akhila Gattu |  | IIRM-739 — SOW#12 - Manage Employees
3468 | IIRM-6099 | QAlity Test | IBP: SanityLevel: policyComponent: Validate "Premium Calculation" Radio Buttons Rendering, Initial State, Selection Behavior, and Event Handling | Draft | Akhila Gattu
3469 | IIRM-6100 | QAlity Test | IBP: SanityLevel: PolicyComponent: Validate Rendering and Click Functionality of "Save", "Save & Exit", and "Next" Buttons | Draft | Akhila Gattu
3470 | IIRM-6111 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3471 | IIRM-6112 | Task | IIRM: NEW CRs testing from primary backlog list | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3472 | IIRM-6113 | Task | IIRM: No Maximum Character Validation for Company and Contact Fields | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3473 | IIRM-6114 | Bug | IIRM: KDM Meeting: Inconsistency in displaying the city name in the Employee Participants field | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
3474 | IIRM-6115 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3475 | IIRM-6116 | Task | IIRM: Approval flow and Opportunity stages verification | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3476 | IIRM-6117 | Task | IIRM: Primary backlogs and Regression Testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3477 | IIRM-6118 | Bug | IBP: Policy details card: Commas should be shown for CD balance and for updated premium | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3478 | IIRM-6119 | Bug | IIRM: Insurer/TPA Name Missing in RFP Details on Approval | Done | SaikumarMahanthi | iWork | IIRM-783 — SOW#56 - Insurer / TPA integration
3479 | IIRM-6120 | Bug | IIRM: Invalid Name (ISG Assigned Name) Displayed as BD Planning Assignee | Done | SaikumarMahanthi | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
3480 | IIRM-6121 | Bug | IIRM: Opty. - No Notification on Activity Rejection by Approver | QA in Progress | SaikumarMahanthi | iWork | IIRM-761 — SOW#34 - Notifications Management
3481 | IIRM-6122 | Task | Add new indicators in the My Business Performance section to display Total Premium, Premium Collected, and Uncollected Premium | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
3482 | IIRM-6123 | Task | Implement a clear indication message when no activities are available, instead of showing a blank screen. | Done | Jadhav Sai Prasad |  | IIRM-797 — SOW#69 - Manage Opportunities
3483 | IIRM-6124 | Task | Implement Smart Search functionality across the application | Open | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3484 | IIRM-6125 | Task | Manage Company Screen Enhancements | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3485 | IIRM-6126 | QAlity Test | IIRM: Update Expiry Date for WIP/Lost Sales and Renewal Opportunities and Validate Reflection | Draft | SaikumarMahanthi | iWork
3486 | IIRM-6127 | Bug | Dashboard Discrepancy – Sales Funnel | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3487 | IIRM-6128 | Bug | IBP: Endorsement: CTA not working on Need your attention card | Open | Akhila Gattu | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
3488 | IIRM-6129 | Task | When we click on my portfolio, by default My RO should come, don't change the sequence | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3489 | IIRM-6130 | Task | Remove brokerage amount from opty form | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
3490 | IIRM-6131 | Task | Data Allignment changes in RO and SO Premium in list of records in company | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3491 | IIRM-6132 | QAlity Test | IBP: CD: Verify multiple policies with single CD account | Draft | Akhila Gattu
3492 | IIRM-6133 | QAlity Test | IBP: CD: Verify policy with multiple CD accounts | Draft | Akhila Gattu | None
3493 | IIRM-6134 | QAlity Test | IBP: CD: Verify validations on Add CD balance | Draft | Akhila Gattu | None
3494 | IIRM-6135 | Bug | Manager Insurer: Page Unresponsive | Done | Richa Bagchi Mazumdar |  | IIRM-741 — SOW#14 - Add/Manage Insurer
3495 | IIRM-6136 | Bug | IBP: CD: Validation missing for CD reference type as Cheque | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3496 | IIRM-6137 | Bug | IBP: CD: Error validations showing background to the popup | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3497 | IIRM-6138 | Bug | IBP: Endorsement: Invalid status shown on uploaded employee data | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3498 | IIRM-6139 | Story | Sales Dashboard, my business performance and Renewal Funnel | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3499 | IIRM-6140 | Sub-task | In sales dashboard, after My Business Performance | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-6139 — Sales Dashboard, my business performance and Renewal Funnel
3500 | IIRM-6141 | Sub-task | In My Business Performance | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-6139 — Sales Dashboard, my business performance and Renewal Funnel
3501 | IIRM-6142 | Sub-task | Create a new section after My Renewal Funnel section | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-6139 — Sales Dashboard, my business performance and Renewal Funnel
3502 | IIRM-6143 | Sub-task | Create a new section after Brokerage to Collect section – My Follow-up | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-6139 — Sales Dashboard, my business performance and Renewal Funnel
3503 | IIRM-6144 | Sub-task | Every policy record should have the following fields | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-6139 — Sales Dashboard, my business performance and Renewal Funnel
3504 | IIRM-6145 | Bug | IBP: Endorsement: Employee data reflecting in not started state. | Done - Not Reproducible | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3505 | IIRM-6146 | Task | Industry Insight & Potential Opportunity Sections | Done | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
3506 | IIRM-6147 | Task | Sales Pitch Tab in SO & RO | Done | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
3507 | IIRM-6148 | Bug | IIRM: Employee Update Fails – Loading Screen Persists on Create/Update | Done | SaikumarMahanthi |  | IIRM-739 — SOW#12 - Manage Employees
3508 | IIRM-6149 | Task | Default column Sequence for company, contact, SO, RO, Policy | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3509 | IIRM-6150 | Task | Filter Persistence: Filters applied by a user should remain active upon navigating away from and returning to the same page | Open | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3510 | IIRM-6151 | Bug | Brokerage Amount should not be applied on gross, it should be on net/base premium | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3511 | IIRM-6152 | Task | IIRM: Ready for QA Bugfixes verification and regression testing | Done | SaikumarMahanthi
3512 | IIRM-6153 | Task | IIRM: Verify bizdone report | Done | SaikumarMahanthi |  | IIRM-778 — SOW#51 - Admin Reports
3513 | IIRM-6154 | Task | IIRM: Dashboard data verification | Done | SaikumarMahanthi |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3514 | IIRM-6155 | Task | IIRM: Ready for QA Bugfixes verification in Sprint the current srpint | Done | SaikumarMahanthi
3515 | IIRM-6156 | Task | IIRM: Bizdone Report Fails to Load – “Something Went Wrong” Error | Done | SaikumarMahanthi |  | IIRM-778 — SOW#51 - Admin Reports
3516 | IIRM-6157 | Task | Include endorsement data into business performances | Done | Rama K |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3517 | IIRM-6158 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi
3518 | IIRM-6159 | Task | IIRM: Bizdone , Dashboard Funnel, Opportunity Changes verifcations | Done | SaikumarMahanthi |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3519 | IIRM-6160 | Bug | IIRM: Quick Create / Company Creation Fails – “Invalid Input Syntax for Type Integer” | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3520 | IIRM-6161 | Bug | ISG process: Deviation process, upon manager approval, the respective stage/activity should enable for the ISG user to modify the data. Screen should be editable for all the fields. | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
3521 | IIRM-6162 | Task | IIRM: Drilldown functionality from dashboards | Done | Leela Pakalapati | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3522 | IIRM-6163 | Bug | Policy Type Covers should be updated as per Neeraj sheet and also I shared another sheet to Gopal garu to delete and re-map with the correct policy types and renaming the active records. | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
3523 | IIRM-6164 | Bug | Endorsements premiums, brokerage amount reflecting in the application dashboards, bizdone, RO/SO/Policies | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3524 | IIRM-6166 | Bug | IIRM: API: Incorrect Error Message Displayed on Company Creation Failure | Open | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3525 | IIRM-6167 | Bug | IIRM: Incorrect Status code displayed for Access denied request(401 instead of 403) | Done | SaikumarMahanthi |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3526 | IIRM-6168 | Task | Bizdone Report with Endorsement data | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
3527 | IIRM-6169 | Task | Contact mapping to Opportunity | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3528 | IIRM-6170 | QAlity Test | IIRM: Manage Company: Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3529 | IIRM-6171 | QAlity Test | IIRM: RO: Verify the RO creation when a policy meets eligibility criteria | Draft | Leela Pakalapati
3530 | IIRM-6172 | QAlity Test | IIRM: RO: BD activities and ISG Activities for newly created RO | Draft | Leela Pakalapati
3531 | IIRM-6173 | Bug | IIRM: CreateCompany: Loading takes more time on create company | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3532 | IIRM-6174 | Task | IIRM: API:Employee Creation API Fails – 504 Gateway Timeout | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3533 | IIRM-6175 | Bug | IIRM: CompanyCreate: Validation shown on clicking next from KYC | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3534 | IIRM-6176 | Bug | IIRM:QuickCreate: Proper validation error not showing for meeting invalid time slot | Done | Akhila Gattu | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3535 | IIRM-6177 | Bug | IIRM: Meeting: Count should not be show for Opportunity type | Done | Akhila Gattu | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
3536 | IIRM-6178 | Bug | IIRM: Incorrect Snackbar Message Shown When Searching Non-Existing Employee | Done | SaikumarMahanthi | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3537 | IIRM-6179 | Task | Dynamic Form Input Fields Refactoring | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3538 | IIRM-6180 | Task | Auto-calculate Service Tax and Total Premium in Placement Slip (BE+FE) | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3539 | IIRM-6181 | Task | Wherever the word Commission is used, Change it to Brokerage, including Bizdone report | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3540 | IIRM-6182 | Bug | IIRM:InsurerContact: Unable to create insurer contact invalid validation thrown | Done | Akhila Gattu | iWork | IIRM-737 — SOW#10 - Add/Manage Contact
3541 | IIRM-6183 | Bug | IIRM: API :API Returns Incorrect Message for Long Text Input and Duplicate Entry | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3542 | IIRM-6184 | Task | IIRM: Opportunity Contacts Filter: Fails on Multiple Contacts | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
3543 | IIRM-6185 | Task | RO Screen cosmetic changes: rename Total Commision Amount to Total Expected Brokerage Amount and rename Total Premium Amount to Total Expected Premium Amount | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3544 | IIRM-6186 | Bug | IIRM: Assigned Opportunities Not Displayed in SO Tab | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
3545 | IIRM-6187 | Sub-task | Add collected amount related columns to Policy Entity | Pushed to Backlog | Rama K |  | IIRM-6139 — Sales Dashboard, my business performance and Renewal Funnel
3546 | IIRM-6188 | Sub-task | Update the Bizdone Report with brokerage_collected and premium_collected columns | Pushed to Backlog | Rama K |  | IIRM-5441 — Biz Done Reports
3547 | IIRM-6189 | Task | Manage Company Quick Cards | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3548 | IIRM-6190 | Bug | IIRM: Duplicate Options Displayed in Dropdowns | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3549 | IIRM-6191 | Bug | IIRM: Total Companies list Not Displayed When Owner Unchecked | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3550 | IIRM-6192 | Story | Inception / Endorsement request received / Data upload | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3551 | IIRM-6193 | Story | Open Enrolment Portal | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3552 | IIRM-6194 | Story | Send Inception/ Endorsement to Insurer | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3553 | IIRM-6195 | Story | Insurer Acknowledgement | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3554 | IIRM-6196 | Story | Client Confirmation | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3555 | IIRM-6197 | Story | TPA ID Upload | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3556 | IIRM-6199 | Story | Data Reconciliation & Closure | Draft | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3557 | IIRM-6201 | Story | Manage Endorsement Screen | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3558 | IIRM-6202 | Sub-task | For Companies with Enrollment Portal, A two-step endorsement flow will be followed | Done | Richa Bagchi Mazumdar |  | IIRM-6192 — Inception / Endorsement request received / Data upload
3559 | IIRM-6205 | Sub-task | The system must allow the user to enter and capture the Insurer Communication Date, Endorsement Document, and Communication Details before sending | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6194 — Send Inception/ Endorsement to Insurer
3560 | IIRM-6206 | Sub-task | The screen must display a summary of the endorsement batch including | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6194 — Send Inception/ Endorsement to Insurer
3561 | IIRM-6207 | Sub-task | If CD Balance is insufficient, the system should prevent submission and display an alert. | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6194 — Send Inception/ Endorsement to Insurer
3562 | IIRM-6213 | Sub-task | 1. The system must allow the user to input Acknowledgement Details, Acknowledgement Reference, and upload an Acknowledgement Document. | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6195 — Insurer Acknowledgement
3563 | IIRM-6214 | Sub-task | The system must provide fields to capture Client Confirmation Date, Client Confirmation Method (e.g., phone, email, meeting), and Client Response. | Done | Richa Bagchi Mazumdar |  | IIRM-6196 — Client Confirmation
3564 | IIRM-6215 | Sub-task | The system must allow the user to upload a TPA ID file, enter the TPA ID upload date, and provide remarks. | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-6197 — TPA ID Upload
3565 | IIRM-6217 | Sub-task | The system must allow users to enter a Reconciliation Date, Closure Date, and Final Remarks. | Draft | Richa Bagchi Mazumdar |  | IIRM-6199 — Data Reconciliation & Closure
3566 | IIRM-6218 | Sub-task | The system must display additional three quick links on the policy page a. Insurer Acknowledgement | Done | Richa Bagchi Mazumdar |  | IIRM-6201 — Manage Endorsement Screen
3567 | IIRM-6219 | Sub-task | On clicking quick links / Cards: | Done | Richa Bagchi Mazumdar |  | IIRM-6201 — Manage Endorsement Screen
3568 | IIRM-6221 | Bug | IIRM: White Screen Appears Immediately After Login/Reload | Done | SaikumarMahanthi |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3569 | IIRM-6227 | Task | Once clicked SO Funnel, it should navigate to Sales Opty and if KDM is clicked automatically filter should be applied on that | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3570 | IIRM-6232 | QAlity Test | IIRM: Manage Contacts: Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3571 | IIRM-6238 | QAlity Test | IIRM: Manage TPA : Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3572 | IIRM-6240 | QAlity Test | IIRM: Manage Insurer : Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3573 | IIRM-6241 | QAlity Test | IIRM: Manage Broker: Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3574 | IIRM-6243 | QAlity Test | IIRM: TPA Contacts: Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3575 | IIRM-6244 | QAlity Test | IIRM: Insurer Contacts : Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3576 | IIRM-6246 | QAlity Test | IIRM: Broker Contacts: Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3577 | IIRM-6247 | QAlity Test | IIRM:SO : Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3578 | IIRM-6248 | QAlity Test | IIRM: RO : Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3579 | IIRM-6267 | Bug | IIRM: Meeting Agenda/MoM Not Reflected in Meeting Tab from Activities | Open | SaikumarMahanthi |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
3580 | IIRM-6268 | Task | Multitexting variant in Covers | Open | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3581 | IIRM-6272 | Task | Unable to complete Placement slip generation for - Systopic Laboratories ¦ GMC ¦ Opp Nos 931633, 931640, and 931641 | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3582 | IIRM-6273 | QAlity Test | Endorsement: Verify create endorsement filtered with companyname and policy type | Draft | Akhila Gattu
3583 | IIRM-6275 | Sub-task | Add Widget with graph to show the metrics about Brokerage Collected in My Business Performance | Pushed to Backlog | Rama K |  | IIRM-6139 — Sales Dashboard, my business performance and Renewal Funnel
3584 | IIRM-6276 | Epic | SOW-TBD | Draft | Richa Bagchi Mazumdar
3585 | IIRM-6277 | Story | Default Portfolio View | Done | Richa Bagchi Mazumdar |  | IIRM-6276 — SOW-TBD
3586 | IIRM-6278 | Sub-task | Default screen must show | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-6277 — Default Portfolio View
3587 | IIRM-6279 | Story | Drilldown to Company Details | Done | Richa Bagchi Mazumdar |  | IIRM-6276 — SOW-TBD
3588 | IIRM-6280 | Sub-task | On clicking View, two drilldown tables must appear | Done | Richa Bagchi Mazumdar |  | IIRM-6279 — Drilldown to Company Details
3589 | IIRM-6281 | Story | Policy Details Table | Done | Richa Bagchi Mazumdar |  | IIRM-6276 — SOW-TBD
3590 | IIRM-6282 | Story | Service Score Table | QA Failed | Richa Bagchi Mazumdar |  | IIRM-770 — SOW#43 - SLA mgmt (Including Service Score)
3591 | IIRM-6283 | Story | Service Score Detail Drilldown | Done | Richa Bagchi Mazumdar |  | IIRM-6276 — SOW-TBD
3592 | IIRM-6284 | Sub-task | Policy Details Table must show columns: Policy Number, Company Name, Contact, Policy Type, Status, Sum Assured, Premium, Policy From, Policy To, Account Manager | Done | Richa Bagchi Mazumdar |  | IIRM-6281 — Policy Details Table
3593 | IIRM-6285 | Sub-task | On clicking any row/column, navigate to Manage Policy screen of that policy | Done | Richa Bagchi Mazumdar |  | IIRM-6281 — Policy Details Table
3594 | IIRM-6286 | Sub-task | Service Score Table must show columns: Month, Marks Scored, Total Marks, Scored %, Indicator, Action (View Details) | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-6282 — Service Score Table
3595 | IIRM-6287 | Sub-task | Logic for populating service score is to be defined later | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-6282 — Service Score Table
3596 | IIRM-6288 | Sub-task | On clicking 'View Details', open drilldown Service Score Detail table | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-6282 — Service Score Table
3597 | IIRM-6289 | Sub-task | Service Score Detail Table must show columns: Service Name, Number of Policies, <7 Days, <10 Days, <21 Days, <30 Days, <45 Days, >45 Days, Scored, WTG | Done | Richa Bagchi Mazumdar |  | IIRM-6283 — Service Score Detail Drilldown
3598 | IIRM-6290 | Sub-task | Data must correspond to company + month selected | Done | Richa Bagchi Mazumdar |  | IIRM-6283 — Service Score Detail Drilldown
3599 | IIRM-6291 | Task | Wrote Product Spec for Client Portfolio | Done | Richa Bagchi Mazumdar |  | IIRM-6276 — SOW-TBD
3600 | IIRM-6296 | Story | Claims Overview Card | Done | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3601 | IIRM-6297 | Story | Additional Widget: Endorsement TAT Card | Done | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3602 | IIRM-6298 | Story | Additional Widgets - Claims TAT Card | Done | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3603 | IIRM-6299 | Story | Additonal: Widget Policy Type Distribution Card | Done | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3604 | IIRM-6300 | Story | Additional Widget : My Client Testimonials | Draft | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3605 | IIRM-6301 | Story | Additional Widget: Policy Expiry Timeline Card | Done | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3606 | IIRM-6303 | Story | User Role-based Actions | Done | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3607 | IIRM-6309 | Sub-task | Show Total Claims Amount (all reported claims irrespective of settlement/rejection) | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6296 — Claims Overview Card
3608 | IIRM-6310 | Sub-task | Show Customer Count for Claim Amount | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6296 — Claims Overview Card
3609 | IIRM-6311 | Sub-task | Show Policy Count for Claim Amount | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6296 — Claims Overview Card
3610 | IIRM-6312 | Sub-task | Show Claims Count for Total Claim Amount | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6296 — Claims Overview Card
3611 | IIRM-6313 | Sub-task | Provide CTA: 'Manage Claims' → Redirect to Manage Claims screen | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6296 — Claims Overview Card
3612 | IIRM-6314 | Sub-task | Show Open >10 days → count of endorsements open >10 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6297 — Additional Widget: Endorsement TAT Card
3613 | IIRM-6315 | Sub-task | Show Open <10 days → count of endorsements open <10 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6297 — Additional Widget: Endorsement TAT Card
3614 | IIRM-6316 | Sub-task | Show Closed <10 days → count of endorsements acknowledged within 10 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6297 — Additional Widget: Endorsement TAT Card
3615 | IIRM-6317 | Sub-task | Show Closed 10–20 days → count of endorsements acknowledged within 10–20 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6297 — Additional Widget: Endorsement TAT Card
3616 | IIRM-6318 | Sub-task | Show Closed >20 days → count of endorsements acknowledged in more than 20 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6297 — Additional Widget: Endorsement TAT Card
3617 | IIRM-6319 | Sub-task | On clicking any value, navigate to Manage Endorsement screen with corresponding filter pre-applied | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6297 — Additional Widget: Endorsement TAT Card
3618 | IIRM-6320 | Sub-task | Show Open >15 days → claims open more than 15 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6298 — Additional Widgets - Claims TAT Card
3619 | IIRM-6321 | Sub-task | Show Open <15 days → claims open less than 15 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6298 — Additional Widgets - Claims TAT Card
3620 | IIRM-6322 | Sub-task | Show Closed <15 days → claims settled within 15 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6298 — Additional Widgets - Claims TAT Card
3621 | IIRM-6323 | Sub-task | Show Closed 15–30 days → claims settled in 15–30 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6298 — Additional Widgets - Claims TAT Card
3622 | IIRM-6324 | Sub-task | Show Closed >30 days → claims settled in more than 30 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6298 — Additional Widgets - Claims TAT Card
3623 | IIRM-6325 | Sub-task | On clicking any value, navigate to Manage Claims screen with corresponding filter pre-applied | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6298 — Additional Widgets - Claims TAT Card
3624 | IIRM-6326 | Sub-task | Display a pie chart showing distribution of Policy Count, Premium Amount, and Brokerage Amount | Done | Jadhav Sai Prasad |  | IIRM-6299 — Additonal: Widget Policy Type Distribution Card
3625 | IIRM-6327 | Sub-task | Provide CTA: 'View Portfolio' → Redirect to My Portfolio screen | Done | Jadhav Sai Prasad |  | IIRM-6299 — Additonal: Widget Policy Type Distribution Card
3626 | IIRM-6328 | Sub-task | Table/Chart must be generated by system after servicing | Draft | Jadhav Sai Prasad |  | IIRM-6300 — Additional Widget : My Client Testimonials
3627 | IIRM-6330 | Sub-task | Show count of policies expiring in next 30 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6301 — Additional Widget: Policy Expiry Timeline Card
3628 | IIRM-6331 | Sub-task | Show count of policies expiring in next 60 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6301 — Additional Widget: Policy Expiry Timeline Card
3629 | IIRM-6332 | Sub-task | Show count of policies expiring in next 90 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6301 — Additional Widget: Policy Expiry Timeline Card
3630 | IIRM-6333 | Sub-task | Show count of policies expiring beyond 90 days | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6301 — Additional Widget: Policy Expiry Timeline Card
3631 | IIRM-6334 | Sub-task | On clicking any value, navigate to Manage Policy screen with filter pre-applied | PENDING PEER or LEAD REVIEW | Jadhav Sai Prasad |  | IIRM-6301 — Additional Widget: Policy Expiry Timeline Card
3632 | IIRM-6336 | Sub-task | Users with Sales activity only → Show existing dashboard widgets | Done | Jadhav Sai Prasad |  | IIRM-6303 — User Role-based Actions
3633 | IIRM-6337 | Sub-task | Users with Service activity only → Show new Service Dashboard widgets | Done | Jadhav Sai Prasad |  | IIRM-6303 — User Role-based Actions
3634 | IIRM-6338 | Sub-task | Users with both Sales and Service activity → Show both old + new widgets | Done | Jadhav Sai Prasad |  | IIRM-6303 — User Role-based Actions
3635 | IIRM-6339 | Sub-task | Business Overview section should follow new widget design for combined users | Done | Jadhav Sai Prasad |  | IIRM-6303 — User Role-based Actions
3636 | IIRM-6340 | QAlity Test | IIRM: Manage Policies : Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3637 | IIRM-6341 | Bug | IIRM: TPA/Insurer Company Name Not Displayed in TPA/Insurer Contact Edit | Ready for QA | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
3638 | IIRM-6342 | Bug | IIRM: SO: Can't proceed with meeting for final negotiation , error thrown on Insurer location ID | Done | Akhila Gattu | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
3639 | IIRM-6343 | Bug | IIRM: Sorting Fails with Error in Brokerage & Follow Up Tables | Done | SaikumarMahanthi | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3640 | IIRM-6344 | Bug | IIRM: “Something Went Wrong” Screen Displayed on Dashboard | Done | SaikumarMahanthi |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3641 | IIRM-6345 | Bug | IIMR: Filters data not fetching properly | Done | Akhila Gattu | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3642 | IIRM-6346 | Bug | IIRM: My sales funnel and My renewal funnel count mismatch on drilldown | Done - Not Reproducible | Akhila Gattu | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3643 | IIRM-6347 | QAlity Test | IIRM: Manage Endorsement : Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3644 | IIRM-6348 | QAlity Test | IIRM: Manage Employees : Verify the Table Settings Functionality | Draft | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3645 | IIRM-6349 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi
3646 | IIRM-6350 | Task | Bizdone report link need to be out of Admin module | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
3647 | IIRM-6351 | Task | Bizdone: Need to visble based on previllage (Downloadd is only for Chairman and System Admin) | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
3648 | IIRM-6352 | Task | Bizdone Report grid - Drill downs need to be enabled | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
3649 | IIRM-6353 | Task | Business Performances | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3650 | IIRM-6354 | Task | Brokerage Collected Dial graph | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3651 | IIRM-6355 | Task | Bizdone report Changes | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
3652 | IIRM-6356 | QAlity Test | IBP: ClientPortfolio: Login as CRM and open My Client Portfolio. | Draft | Akhila Gattu
3653 | IIRM-6357 | QAlity Test | IBP: ClientPortfolio: Verify four KPI cards render on initial load. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3654 | IIRM-6358 | QAlity Test | IBP: ClientPortfolio: Check number/currency formatting for Premium and Brokerage on KPI cards. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3655 | IIRM-6359 | QAlity Test | IBP: ClientPortfolio: Validate columns in Company Overview table. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3656 | IIRM-6360 | QAlity Test | IBP: ClientPortfolio: Click 'View' under Action column for a company. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3657 | IIRM-6361 | QAlity Test | IBP: ClientPortfolio: Verify Policy Details table columns and order. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3658 | IIRM-6362 | QAlity Test | IBP: ClientPortfolio: Click a Policy Number link in Policy Details. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3659 | IIRM-6363 | QAlity Test | IBP: ClientPortfolio: Validate Service Score table columns. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3660 | IIRM-6364 | QAlity Test | IBP: ClientPortfolio: Click 'View details' in Service Score row to open the detailed scorecard table. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3661 | IIRM-6365 | QAlity Test | IBP: ClientPortfolio: Create a new policy for a company (pre-seeded) and refresh dashboard. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3662 | IIRM-6366 | QAlity Test | IBP: ClientPortfolio: Check High/Medium/Low priority badges in Company Overview. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3663 | IIRM-6367 | QAlity Test | IBP: ClientPortfolio: Validate Claim Amount displays in correct unit (Lakhs). | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3664 | IIRM-6368 | QAlity Test | IBP: ClientPortfolio: Open 'View' for two different companies sequentially. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3665 | IIRM-6369 | QAlity Test | IBP: ClientPortfolio: Verify Smart Filter panel shows all filters. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3666 | IIRM-6370 | QAlity Test | IBP: ClientPortfolio: Set multiple filters and click Apply. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3667 | IIRM-6371 | QAlity Test | IBP: ClientPortfolio: After applying filters, click Clear Filters. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3668 | IIRM-6372 | QAlity Test | IBP: ClientPortfolio: Type a partial company name and apply filter. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3669 | IIRM-6373 | QAlity Test | IBP: ClientPortfolio: Enter From and To dates and apply. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3670 | IIRM-6374 | QAlity Test | IBP: ClientPortfolio: Toggle Period between Monthly, Quarterly, Yearly. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3671 | IIRM-6375 | QAlity Test | IBP: ClientPortfolio: Open a company drilldown and filter Policy Details by Policy Type. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3672 | IIRM-6376 | QAlity Test | IBP: ClientPortfolio: Open Portfolio with no accessible company data. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3673 | IIRM-6377 | QAlity Test | IBP: ClientPortfolio: Open Service Score for a company with no service scores. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3674 | IIRM-6378 | QAlity Test | IBP: ClientPortfolio: Click a Policy Number that no longer exists (deleted). | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3675 | IIRM-6379 | QAlity Test | IBP: ClientPortfolio: Load >1000 companies and interact with table. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3676 | IIRM-6380 | QAlity Test | IBP: ClientPortfolio: Open drilldown for a company with >500 policies. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3677 | IIRM-6381 | QAlity Test | IBP: ClientPortfolio: Verify Indicator around threshold boundaries (e.g., 0%, boundary %, 100%). | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3678 | IIRM-6382 | QAlity Test | IBP: ClientPortfolio: Open Service Score details and verify bucket counts and totals. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3679 | IIRM-6383 | QAlity Test | IBP: ClientPortfolio: Open Policy Details and Service Score, then collapse the parent company row. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3680 | IIRM-6384 | QAlity Test | IBP: ClientPortfolio: Apply filters → open a drilldown → use browser back. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3681 | IIRM-6385 | QAlity Test | IBP: ClientPortfolio: Simulate backend data update; refresh Portfolio. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3682 | IIRM-6386 | QAlity Test | IBP: ClientPortfolio: Open Portfolio as a user without CRM access. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3683 | IIRM-6387 | QAlity Test | IBP: ClientPortfolio: Simulate API failure while loading Company Overview. | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3684 | IIRM-6388 | Task | In all stages, if entered deviation was yes then activity should be editable | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3685 | IIRM-6389 | Bug | IIRM: CreateCompany: For new company , error thrown company already exists | Done | Akhila Gattu |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3686 | IIRM-6390 | Task | My Companies: Header | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3687 | IIRM-6391 | Task | Sys Admin is not able to see the data in SOs, ROs, Policies pages. Screen is blank. This user should see all the pages. | Draft | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
3688 | IIRM-6392 | Bug | In my policies Financial year search does not work correctly in Manage Policies | Open | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3689 | IIRM-6393 | Bug | IIRM: Error “Something Went Wrong” on Clicking Policy Link in Bizdone Report | Done | SaikumarMahanthi |  | IIRM-778 — SOW#51 - Admin Reports
3690 | IIRM-6394 | Bug | IIRM: Knowledge Central Page:Remove training material section from Knowledge central and put it under iLearn | Reopen | Munganti Sravani | iWork | IIRM-768 — SOW#41 - Knowledge Central
3691 | IIRM-6395 | Bug | In Manage Policy: Please refer to screenshot and remove the links | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3692 | IIRM-6396 | Bug | At the time of company creation in the application, error is coming, check screenshot | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3693 | IIRM-6397 | Task | IIRM: UAT Bug fix verification and Regression testing on Opty stages | Done | SaikumarMahanthi
3694 | IIRM-6398 | Task | IIRM: NEW Change requests testing Dashboard functionality | Done | SaikumarMahanthi
3695 | IIRM-6399 | Task | Manage Company Screen Enhancement (2) | Done | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3696 | IIRM-6400 | Task | Insurer Details Refactor_Placement slip Generation Activity | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3697 | IIRM-6401 | QAlity Test | Endorsement: Validate inception data upload allowed only once before policy effective date | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3698 | IIRM-6402 | QAlity Test | Endorsement: Verify endorsement data upload handles additions, deletions, and corrections | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3699 | IIRM-6403 | QAlity Test | Endorsement: Ensure OS Ticket ID, endorsement type, and receive date are mandatory for each batch | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3700 | IIRM-6404 | QAlity Test | Endorsement: Validate insurer communication captures date, document, details, and computed premium fields | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3701 | IIRM-6405 | QAlity Test | Endorsement: Verify acknowledgement from insurer must include reference and document | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3702 | IIRM-6406 | QAlity Test | Endorsement: Validate client confirmation allows only supported methods (phone/email/portal) | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3703 | IIRM-6407 | QAlity Test | Endorsement: Verify TPA ID upload supports only allowed file formats and size | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3704 | IIRM-6408 | QAlity Test | Endorsement: Verify e-card generation captures date, delivery method, and remarks | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3705 | IIRM-6409 | QAlity Test | Endorsement: Validate reconciliation and closure requires all mandatory fields completed | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3706 | IIRM-6410 | QAlity Test | Endorsement: POST /endorsements should create new endorsement with OS Ticket and policy number | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3707 | IIRM-6411 | QAlity Test | Endorsement: Manage Policy CTA - Create Endorsement flow from global CTA | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3708 | IIRM-6412 | QAlity Test | Endorsement: Manage Policy CTA - Edit existing endorsement | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3709 | IIRM-6413 | QAlity Test | Endorsement: Quick Cards - Visibility and counts on Policy page | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3710 | IIRM-6414 | QAlity Test | Endorsement: Smart Filters - Presence of all filter controls | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3711 | IIRM-6415 | QAlity Test | Endorsement: Smart Filters - Apply multiple filters together | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3712 | IIRM-6416 | QAlity Test | Endorsement: Smart Filters - Clear filters resets to default view | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3713 | IIRM-6417 | QAlity Test | Endorsement: Smart Filters - Invalid date range | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3714 | IIRM-6418 | QAlity Test | Endorsement: Smart Filters - Period aggregation changes metrics | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3715 | IIRM-6419 | QAlity Test | Endorsement: Smart Filters - Owned By (workflow) filter | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3716 | IIRM-6420 | QAlity Test | Endorsement: Smart Filters - Large dataset performance | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3717 | IIRM-6421 | QAlity Test | Endorsement: GET /endorsements with filter params | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3718 | IIRM-6422 | QAlity Test | Endorsement: GET /policies/{id}/quick-cards aggregates counts by stage | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3719 | IIRM-6423 | QAlity Test | Endorsement: Smart Filters - Unsupported values rejected | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3720 | IIRM-6424 | QAlity Test | Endorsement: Filters + Drilldown persistence across navigation | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3721 | IIRM-6425 | Task | Single Insurer and Multiple Insurer level data points | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3722 | IIRM-6426 | Task | Payment Type by Cheque/CD level issues | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3723 | IIRM-6427 | Bug | ClientPortfolio: Error message on View CTA: Oops, something went wrong’ when company has policy | Done | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3724 | IIRM-6428 | Bug | ClientPortfolio: Navigations were not properly implemented | Done | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3725 | IIRM-6431 | Bug | Clientportfolio: Spacing after company table, policy table, service score table alignments are not properly aligned. | Done | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3726 | IIRM-6432 | Bug | ClientPortfolio: Space b/w company table and pagination not matching with policy table and servicescore table | Done - Not Reproducible | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3727 | IIRM-6433 | Bug | ClientPortfolio: Filters were not valid on client portfolio page | Done | Akhila Gattu |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3728 | IIRM-6434 | Bug | Brokerage Collected Dial graph | Done | Leela Pakalapati |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3729 | IIRM-6435 | Story | P0_Restructure: Side Menu bar Sequence | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3730 | IIRM-6436 | Story | P1_Service score table ( dynamic) | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3731 | IIRM-6437 | Story | P2_Service score table breakdown (Logic) | Done | Richa Bagchi Mazumdar |  | IIRM-770 — SOW#43 - SLA mgmt (Including Service Score)
3732 | IIRM-6438 | Story | Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3733 | IIRM-6439 | Bug | IIRM: Company Details: UI: UI issues | Done | Leela Pakalapati |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3734 | IIRM-6440 | Bug | ClientPortfolio: Lovable few columns were missing on portal | Ready for QA | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3735 | IIRM-6441 | Bug | ClientPortfolio: Validation thrown: Something went wrong, Please try again shown on navigating to policy number | Done - Not Reproducible | Akhila Gattu | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3736 | IIRM-6442 | Bug | ClientPortfolio: Company empty page should not be shown while navigating from policy details | Done | Akhila Gattu | IBP | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3737 | IIRM-6443 | Story | P3: CD Management list | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
3738 | IIRM-6444 | Story | P4: CD Management Details | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
3739 | IIRM-6445 | Story | <Place Holder> | Draft | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
3740 | IIRM-6446 | Story | P6: Manage claims list | Done | Richa Bagchi Mazumdar |  | IIRM-782 — SOW#55 - Claim Management
3741 | IIRM-6447 | Story | P7: Create CD Account | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
3742 | IIRM-6448 | Task | For informational items displayed on the platform, an "informational CTA icon" should be available to guide users to further details or related actions | Draft | Richa Bagchi Mazumdar |  | IIRM-750 — SOW#23 - Document Management - CMS
3743 | IIRM-6449 | Task | My Business Performance" Implementation - Need to introduce a Indicators for total collected , total non collected premium in ( for lanka ) highlight non collected premium | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3744 | IIRM-6450 | Task | For users within the IIRM Holdings group, the system should by default display relevant "commercial line" information for a specified "period." This should align with user privilege and data visibility requirements, as well as role-based access control | Draft | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
3745 | IIRM-6451 | Task | For companies and contacts, the default listing display should present those owned by the user and their team and do not enforce time period | Draft | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3746 | IIRM-6452 | Task | Ensure that criteria available in filters can also be applied and reflected in table settings | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3747 | IIRM-6453 | Task | Certain users like (Chairman ) must see data across all teams and departments based on their privilege or designation, even if they are not part of the standard reporting hierarchy to facilitate testing and data visibility | Open | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3748 | IIRM-6454 | Task | AI agent to analyze email tones and sentiments, identifying annoyance or other negative emotions that could impact business opportunities | Draft | Richa Bagchi Mazumdar |  | IIRM-754 — SOW#27 - AI - Smart Adds
3749 | IIRM-6455 | Task | For Endorsements & Claims, provide navigate to manage endorsements and manage claims pages respectively. | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3750 | IIRM-6456 | QAlity Test | CDManagment: Verify CD account listing displays all required columns with hyperlinks | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3751 | IIRM-6457 | QAlity Test | CDManagment: Verify Replenish/Top-up CTA adds CD amount | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3752 | IIRM-6458 | QAlity Test | CDManagment: Validate CD Account detail page shows account details and linked policies | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3753 | IIRM-6459 | QAlity Test | CDManagment: Verify transaction history shows correct debit/credit with constraints | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3754 | IIRM-6460 | QAlity Test | CDManagment: Export functionality from transaction history | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3755 | IIRM-6461 | QAlity Test | CDManagment: Filter capability for transaction history | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3756 | IIRM-6462 | QAlity Test | CDManagment: Create CD Account without opening balance | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3757 | IIRM-6463 | QAlity Test | CDManagment: Create CD Account with opening balance | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3758 | IIRM-6464 | QAlity Test | CDManagment: Attempt to create CD Account linking policies with different insurers | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3759 | IIRM-6465 | QAlity Test | CDManagment: Navigation from Policy Detail to Add CD Amount page | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3760 | IIRM-6466 | QAlity Test | CDManagment: Navigation from CD Summary card on Policy Detail to CD Account Detail page | Completed | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3761 | IIRM-6467 | Story | My service follow up Widget | Blocked | Jadhav Sai Prasad |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3762 | IIRM-6468 | Task | For any unauthorized portion of the screen, you should not display as "Unauthorised access". Instead that place holder should be invisible and next portions should automatically adjust. | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3763 | IIRM-6470 | Bug | IIRM: Filters: Owner dropdown is not auto-selected with current user name when “View By” is applied | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3764 | IIRM-6471 | Bug | IIRM: Unable to Resubmit Held Cover Note Activity After Manager Rejection | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
3765 | IIRM-6472 | Bug | IIRM: SO/RO – Managers list not displayed when filtering by current user and Manager | Open | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
3766 | IIRM-6473 | Epic | Production Issues | Draft | Richa Bagchi Mazumdar
3767 | IIRM-6474 | Task | Biz done: Whenever I changing the owner, Manager+Team is getting unselected. | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
3768 | IIRM-6475 | Task | Other than IIRM India, no one is getting the following. If you have made this card specific to Country, just populate the same for them too. | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3769 | IIRM-6476 | Task | Selected Deepali, who heads Speciality Lines should not get ROs not related to her. Whole filters started working differently. | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3770 | IIRM-6477 | Task | My SO page is talking too much time to load. | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3771 | IIRM-6478 | Task | Maintain two decimals only: Stage Conversion | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3772 | IIRM-6479 | Task | some thing went wrong" appearing if data is not available on applied filters. | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3773 | IIRM-6480 | Task | Even thou 'deviation addressed' marked No we can submit activity for approval | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3774 | IIRM-6481 | Task | revised held cover selected as NO stll we were able to submit the activity | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3775 | IIRM-6482 | Task | post submission from ISG exec it shows waiting for approval(freezed), however in ISG managers bucket it shows submit for approval(Unfreezed). | Draft | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
3776 | IIRM-6483 | Task | IIRM: Dashboard Changes Testing on QA Environment | Done | SaikumarMahanthi
3777 | IIRM-6484 | Task | IIRM: Verify Ready for QA issues and Regression checking | Done | SaikumarMahanthi
3778 | IIRM-6485 | Task | IIRM: Opportunity changes(Held cover note) verification | Done | SaikumarMahanthi
3779 | IIRM-6486 | Task | IIRM: Dashboard Changes verification on QA Environment | Done | SaikumarMahanthi
3780 | IIRM-6487 | Task | In policy section, the policy record should the link to the related RO. On click, navigate user to manage RO page. | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
3781 | IIRM-6488 | Task | Back End - Lead tasks (Planning, Code Review, team Support) | Draft | meghana |  | IIRM-6276 — SOW-TBD
3782 | IIRM-6489 | Task | Project Lead tasks (Planning, Code Review, team Support) | Draft | meghana |  | IIRM-6276 — SOW-TBD
3783 | IIRM-6490 | Bug | Endorsement: Search functionality not working, Error thrown "Something went wrong" | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3784 | IIRM-6491 | Bug | Endorsement list – Count resets to 0 on page refresh with new data | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3785 | IIRM-6492 | Story | Pending fixes & enhancements after feedback - Manage Endorsement | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3786 | IIRM-6493 | Sub-task | Endorsement ID / upload | Done | Jadhav Sai Prasad |  | IIRM-6492 — Pending fixes & enhancements after feedback - Manage Endorsement
3787 | IIRM-6494 | Sub-task | Defaults & calculations | Done | Jadhav Sai Prasad |  | IIRM-6492 — Pending fixes & enhancements after feedback - Manage Endorsement
3788 | IIRM-6495 | Sub-task | Tracking & reporting | Done | Jadhav Sai Prasad |  | IIRM-6492 — Pending fixes & enhancements after feedback - Manage Endorsement
3789 | IIRM-6496 | Sub-task | Emails, toasts & confirmations | Done | Jadhav Sai Prasad |  | IIRM-6492 — Pending fixes & enhancements after feedback - Manage Endorsement
3790 | IIRM-6497 | Story | CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements | Done | Jadhav Sai Prasad |  | IIRM-781 — SOW#54 - CD Management
3791 | IIRM-6498 | Sub-task | Add Claims date in claims table in policy dashboard | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3792 | IIRM-6499 | Sub-task | In Client Portfolio, Service score should show latest month | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3793 | IIRM-6500 | Sub-task | Adjust the table number rows to 10 ( Where ever tables are there) | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3794 | IIRM-6501 | Sub-task | Remove view button border | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3795 | IIRM-6502 | Sub-task | Remove all borders on all clicks | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3796 | IIRM-6503 | Sub-task | Add cross icon to close information popup on claims | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3797 | IIRM-6504 | Sub-task | TAT days may have 3 more buckets ( 15 - 30, 30 - 45, 45+) TBD | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3798 | IIRM-6505 | Sub-task | Change Status Label in CD management | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3799 | IIRM-6506 | Sub-task | CD Management List - change Amount to Balance | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3800 | IIRM-6507 | Sub-task | Add + Icon before (Add CD Balance) | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3801 | IIRM-6508 | Sub-task | Add CD Balance - Transaction Type might be Credit and Adjust (TBD) | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3802 | IIRM-6509 | Sub-task | Change the column name “Transactions / Checkid date” | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3803 | IIRM-6510 | Sub-task | Change the sub title CD management list page - Cash deposit to caution deposit | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3804 | IIRM-6511 | Sub-task | Alert in CD management list - If minimum balance is less than 7.5% ( of gross premium) | Done | Jadhav Sai Prasad |  | IIRM-6497 — CD Management ¦ My Client Portfolio ¦ Claims listing demo feedback quick fixes and enhancements
3805 | IIRM-6512 | Bug | IIRM: Manage Company: “Something went wrong. Please try again.” message displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3806 | IIRM-6513 | Task | IIRM: Permission Error Thrown for Specific User (ISG Executive) | Draft | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
3807 | IIRM-6514 | Bug | Endorsement: Uploaded records is not getting stored and not visible on track | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3808 | IIRM-6515 | Bug | Endorsement: Field input retains leading zero instead of trimming | Done | Akhila Gattu | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
3809 | IIRM-6516 | Bug | Endorsement: Glitch appears on process steps | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3810 | IIRM-6517 | Bug | Myclientportfolio: Instead of Policynumber, policy type showing in policy number column | Done | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3811 | IIRM-6518 | Bug | CD: Policytype should not be shown twice | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3812 | IIRM-6519 | Story | Implement last-mile clickability for all relevant tables in the application. | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3813 | IIRM-6520 | Bug | IIRM: Planning Stage: Fields remain editable before activity assignment | Done | Leela Pakalapati | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
3814 | IIRM-6521 | Task | Policy Update & Activation | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3815 | IIRM-6522 | Task | IIRM: AI Services Failing to Process Business Card | Done | SaikumarMahanthi | iWork | IIRM-754 — SOW#27 - AI - Smart Adds
3816 | IIRM-6523 | Bug | CD: Back naviagtion missing for CD management transaction page | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3817 | IIRM-6524 | Bug | CD: Back navigation missing for add CD balance page | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3818 | IIRM-6525 | Bug | CD: Cd account details: Empty displayed in alert column and Percentage level not shown in min balance column | On Hold | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3819 | IIRM-6526 | Bug | CD: In create CD account page, Cd account number field should not get down and if policy linked to company "No policy message should be shown on UI" | Ready for QA | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3820 | IIRM-6527 | Bug | CD: Created CD account not reflecting in CD account details | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3821 | IIRM-6528 | Bug | CD: Add a search default text as "Search by company name or CD account number" | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3822 | IIRM-6529 | Bug | Claims: Filters not matching when compared to lovable filters | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
3823 | IIRM-6530 | Bug | IIRM: Policy Hard Copy Receipt: Basic Amount not updating when changes are made in previous activities | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
3824 | IIRM-6531 | Story | Client Service Score | Done | Jadhav Sai Prasad |  | IIRM-770 — SOW#43 - SLA mgmt (Including Service Score)
3825 | IIRM-6532 | Story | Service Contribution | Done | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
3826 | IIRM-6533 | Story | TAT Buckets | Done | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
3827 | IIRM-6534 | Story | Service Period and Reporting Logic | Done | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
3828 | IIRM-6535 | Story | Service-Level Score Calculation | Done | Jadhav Sai Prasad |  | IIRM-770 — SOW#43 - SLA mgmt (Including Service Score)
3829 | IIRM-6536 | Story | Weighted Score Calculation | Done | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
3830 | IIRM-6537 | Story | Exception Handling for Services | Done | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
3831 | IIRM-6538 | Bug | IIRM: Policy Hard Copy Receipt: Error message displayed when setting “Any Deviation = No” and completing the activity | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
3832 | IIRM-6539 | Bug | IIRM: Policy Docket: Submit for Approval button unresponsive when mandate details are not entered | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
3833 | IIRM-6540 | Bug | IIRM: Policy Hard Copy Receipt and Policy Confirmation: UI issues | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
3834 | IIRM-6541 | QAlity Test | ServiceScore: One service score per client per month is generated and stored | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3835 | IIRM-6542 | QAlity Test | ServiceScore: Per-service Achieved vs Total counts follow TAT rule and configured weights | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3836 | IIRM-6543 | QAlity Test | ServiceScore: Weighted Score = (Achieved / Total) × service weightage | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3837 | IIRM-6544 | QAlity Test | ServiceScore: Overall client score equals sum of applicable services' weighted scores | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3838 | IIRM-6545 | QAlity Test | ServiceScore: Exclude non-applicable services from calculation (Exception Service Weightage) | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3839 | IIRM-6546 | QAlity Test | ServiceScore: Exclude services applicable but not availed in a month | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3840 | IIRM-6547 | QAlity Test | ServiceScore: Zero Total transactions for a service (divide-by-zero handling) | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3841 | IIRM-6548 | QAlity Test | ServiceScore: All transactions breach TAT (no compliant buckets) | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3842 | IIRM-6549 | QAlity Test | ServiceScore: All transactions compliant (perfect TAT) | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3843 | IIRM-6550 | QAlity Test | ServiceScore: TAT bucket mapping uses configured ranges per service | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3844 | IIRM-6551 | QAlity Test | ServiceScore: Previous month service period calculation window logic | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3845 | IIRM-6552 | QAlity Test | ServiceScore: Current month service period calculation window logic (reporting mid-month) | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3846 | IIRM-6553 | QAlity Test | ServiceScore: UI: Aging and TAT views are separate but read from same backend table | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3847 | IIRM-6554 | QAlity Test | ServiceScore: Recompute after late data changes updates monthly score | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3848 | IIRM-6555 | QAlity Test | ServiceScore: Idempotency: Running scoring with same data yields same results | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3849 | IIRM-6556 | QAlity Test | ServiceScore: Per-service detail drilldown: bucket counts and Achieved/Total | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3850 | IIRM-6557 | QAlity Test | ServiceScore: Export of monthly scores matches on-screen values | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3851 | IIRM-6558 | QAlity Test | ServiceScore: Very large dataset computes within SLA | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3852 | IIRM-6559 | QAlity Test | ServiceScore: Role-based access: Only authorized roles can recompute or change config | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3853 | IIRM-6560 | QAlity Test | ServiceScore: Indicator color (Green/Amber/Red) based on Scored% thresholds | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3854 | IIRM-6561 | QAlity Test | ServiceScore: Per-service totals reconcile: sum of bucket counts equals Total; compliant bucket contributes Achieved | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3855 | IIRM-6562 | QAlity Test | ServiceScore: Filter by client and month updates all widgets consistently | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3856 | IIRM-6563 | QAlity Test | ServiceScore: Missing service weightage for applicable service triggers validation | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3857 | IIRM-6564 | QAlity Test | ServiceScore: Missing TAT configuration prevents scoring for that service | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3858 | IIRM-6565 | QAlity Test | ServiceScore: GET /service-scores?client&month returns overall and per-service metrics | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3859 | IIRM-6566 | QAlity Test | ServiceScore: POST /service-scores/recompute recomputes score and persists | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3860 | IIRM-6567 | QAlity Test | ServiceScore: GET /service-scores without required params returns 400 | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3861 | IIRM-6568 | QAlity Test | ServiceScore: GET /service-scores/details returns Aging and TAT blocks from same source | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3862 | IIRM-6569 | QAlity Test | ServiceScore: Rounding/precision uniform across UI and API for weighted and overall score | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3863 | IIRM-6570 | QAlity Test | ServiceScore: Locking/finalization: monthly score snapshots become immutable when locked | Draft | Akhila Gattu |  | IIRM-6276 — SOW-TBD
3864 | IIRM-6571 | Bug | IIRM: Manage Policy: Cover details not updating | Done | Leela Pakalapati | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
3865 | IIRM-6572 | Bug | Endorsement: File upload is getting failed for Self+dependent | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3866 | IIRM-6573 | Bug | Endorsment: Typo on insurer button | Reopen | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3867 | IIRM-6574 | Bug | Endorsment: Negative values should not be shown on insurer akc | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3868 | IIRM-6575 | Bug | Endorsement: Track endorsement columns data not getting triggered | Done | Akhila Gattu | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
3869 | IIRM-6576 | Story | Manage Endorsement Non GMC ¦ Capture Endorsement Request / Inception Data | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3870 | IIRM-6577 | Story | Manage Endorsement Non GMC ¦ Manage Premium Handling for Non-GMC | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3871 | IIRM-6578 | Story | Manage Endorsement Non GMC ¦ Manage Covers and Sub-Covers | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3872 | IIRM-6579 | Story | Manage Endorsement Non GMC ¦ Handle Standardized Templates | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3873 | IIRM-6580 | Story | Manage Endorsement Non GMC ¦ Process Flow Alignment with GMC | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3874 | IIRM-6581 | Bug | CD Management: Unable to select policies | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
3875 | IIRM-6582 | Task | Generate Placement Slip PDF based on Policy & Download | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
3876 | IIRM-6584 | Task | In the filter we have made the manager+team as default selection | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3877 | IIRM-6585 | Task | In the financial year filter we are currently considering the fiscal year starting to till date changed it to fiscal year starting to fiscal year end | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3878 | IIRM-6586 | Task | In the dashboard, Total drill down count mismatch issue | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3879 | IIRM-6587 | Task | Addressed the Deviations related Issues in Held Cover Note Policy Hard Copy Receipt Policy Confirmation | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3880 | IIRM-6588 | Task | Smart Filter - Fixed the issues with Period Filter | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3881 | IIRM-6589 | Task | When a user selects a From Date and To Date in the filter, the system should display data only for that selected period. The user should not be allowed to select a predefined period (e.g., 3 months, 6 months) and then further customize the date range. | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3882 | IIRM-6590 | Task | Addressed Dashboard Counts mismatch issue | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
3883 | IIRM-6591 | Task | RO / SO owner need to check and if the owner is from ISG team then need to check and change it to BD team member. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
3884 | IIRM-6592 | Task | Assets need to add for the policies which has the default covers | Open | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
3885 | IIRM-6593 | Task | Dashboard count mismatch issue. | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3886 | IIRM-6594 | Bug | IIRM: Dashboard: Incorrect data reflected in Business Overview, Claims Overview, and Policy Type Distribution KPIs | Done | Leela Pakalapati |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3887 | IIRM-6595 | Bug | IIRM: Dashboard: View Portfolio button in Policy Type Distribution KPI navigates user to My Client Portfolio instead of Manage Policies | Done | Leela Pakalapati |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3888 | IIRM-6596 | Bug | IIRM: Dashboard: Filters not set to correct values when navigating from KPI widgets | Open | Leela Pakalapati | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3889 | IIRM-6597 | Epic | UAT Bugs | Draft | Richa Bagchi Mazumdar
3890 | IIRM-6598 | Bug | Unable to download endorsement template today.( yesterday we could download and proceed) | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3891 | IIRM-6599 | Bug | Inception data field- yet to be deployed. Currently we are processing from Create endorsement tab for inception data as well. | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3892 | IIRM-6600 | Bug | Template for Non financial is same as financial | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3893 | IIRM-6601 | Bug | In Transaction history for CD- policy no, endt no, endt type is blank (list view) | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3894 | IIRM-6602 | Bug | Cannot continue the endt process if we pause in between eg. if step 2 is done today and we try to continue step 3 next day we are unable to proceed. | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3895 | IIRM-6603 | Bug | Unable to create CD account | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3896 | IIRM-6604 | Bug | Endorsement: Intake type should be inception for inception download file. | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3897 | IIRM-6605 | Bug | IIRM: Mismatch in Filter Results Between Month and Start–End Date in Period Filter | Done | SaikumarMahanthi | iWork | IIRM-2215 — Technical Debt
3898 | IIRM-6606 | Bug | Inception: Failed to create inception | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3899 | IIRM-6607 | Bug | Inception: Step saved successfully is not user friendly toast message at final step. | Open | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3900 | IIRM-6608 | Task | IIRM: Blank Screen Displayed on Save Action in Company List Page | Done | SaikumarMahanthi | iWork | IIRM-774 — SOW#47 - Company Plans
3901 | IIRM-6609 | Bug | Filters: From and to dates were not matching based on the financial year | Done | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3902 | IIRM-6610 | Bug | Breadcrumb: Dashboard breadcrumb missing for business overview , manage claims , view portfolio and policy expiry timeline | Reopen | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3903 | IIRM-6611 | Task | Rectify Funnel Stage Labels & Reorder Tabs | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
3904 | IIRM-6612 | Bug | Filters: Owner field defaults to “Jom” instead of latest saved filter view when filters are Reset | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
3905 | IIRM-6613 | Bug | Inception: Instead of step saved successfully show relative step message | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
3906 | IIRM-6614 | Story | Create Claims - Group policies | Done | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
3907 | IIRM-6615 | Bug | Claims: Oops something went wrong shown on upload claim data file | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
3908 | IIRM-6616 | QAlity Test | IIRM:Complete Filter and Settings Persistence Across Navigation and Sessions | Draft | SaikumarMahanthi | iWork
3909 | IIRM-6617 | QAlity Test | IIRM: Default Configuration Update and Override | Draft | SaikumarMahanthi | iWork
3910 | IIRM-6618 | QAlity Test | IIRM: Maximum Configuration Load in all filter and table settings | Draft | SaikumarMahanthi | iWork
3911 | IIRM-6619 | QAlity Test | IIRM: Financial Year and Period Selection with Field Interdependencies | Draft | SaikumarMahanthi | iWork
3912 | IIRM-6620 | QAlity Test | IIRM: Month Selection and Manual FromDate with Complex Field Logic | Draft | SaikumarMahanthi | iWork
3913 | IIRM-6621 | Bug | Manager is not able to see CD ac details created by executive and himself | Done | Prajakta Vijay Kadam |  | IIRM-782 — SOW#55 - Claim Management
3914 | IIRM-6622 | Bug | Manager is not able to see CD ac details created by executive and himself | Done | Prajakta Vijay Kadam |  | IIRM-781 — SOW#54 - CD Management
3915 | IIRM-6623 | Bug | In my client portfolio screen policy count sorting is not working | Done | Prajakta Vijay Kadam |  | IIRM-777 — SOW#50 - Policy Configurator
3916 | IIRM-6624 | Story | Claims (Non-GMC): Create & Manage | Done | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
3917 | IIRM-6625 | Bug | Search by company is disabled in Manage endorsements | Done | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
3918 | IIRM-6626 | Bug | IIRM: SO Records Count Mismatch Between Yearly and Monthly Filters | Not - Reproducible | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
3919 | IIRM-6627 | Bug | CD balance not reflecting after add cd balance - eg Company name "Royals' | Done | Prajakta Vijay Kadam |  | IIRM-781 — SOW#54 - CD Management
3920 | IIRM-6628 | Bug | Endorsement issues | Done | Prajakta Vijay Kadam |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3921 | IIRM-6629 | Bug | IIRM: City Filter in Contact List Showing Results Based on Company City Instead of Contact City | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3922 | IIRM-6630 | Bug | Inception/ ENdorsement: NEFT , RTGS should be in capital | Reopen | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3923 | IIRM-6631 | Bug | TAT widgets are placed above Team celebrations and announcements | Done - Not Reproducible | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
3924 | IIRM-6632 | Bug | Dollar sign in my portfolio and manage claims | Done | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
3925 | IIRM-6633 | Bug | Business View My Portfolio filter drilldown and count mismatch | Open | Prajakta Vijay Kadam |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3926 | IIRM-6634 | Bug | Inception: For inception process, endorsement should not show in download endorsement file | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3927 | IIRM-6635 | Task | IIRM:Dashboard Filter and new Widgets verification | Done | SaikumarMahanthi | iWork
3928 | IIRM-6636 | Task | IIRM: Filter persistance and Breadcrumb Navigation on QA Environment | Done | SaikumarMahanthi | iWork
3929 | IIRM-6637 | Task | IIRM: Ready for QA tickets verification and regression on related module testing | Done | SaikumarMahanthi | iWork
3930 | IIRM-6638 | Bug | Claim: Unable to get uploaded claim count on settled and pending | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
3931 | IIRM-6639 | Bug | Claims: claim batch Sorting is not matching through out the application | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
3932 | IIRM-6640 | Bug | Claims: Processing message is not getting updated | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
3933 | IIRM-6641 | Bug | Finalised Quotes are not getting displayed in Meeting for Final Negotiation | Done | SaiBhargavi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
3934 | IIRM-6642 | Bug | IIRM: Navigation Steps Not Displayed Properly (N+2 Issue) | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
3935 | IIRM-6643 | Bug | If a configuration is first rejected and then approved, the approved update is not applied, and the process cannot move forward | Done | Prajakta Vijay Kadam |  | IIRM-762 — SOW#35 - Configuration Management
3936 | IIRM-6644 | Bug | In the Manage Endorsement screen, no data is displayed, and an error message “Something went wrong” appears every time. | Done | Prajakta Vijay Kadam |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3937 | IIRM-6645 | Bug | In the CD Management screen, the filter module is missing. | Done | Prajakta Vijay Kadam |  | IIRM-781 — SOW#54 - CD Management
3938 | IIRM-6646 | Bug | IIRM: Dashboard: Filters selected in Dashboard are not applied in the Manage Policy Screen navigated through Policy Expiry Timelines section | Done | Prajakta Vijay Kadam |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3939 | IIRM-6647 | Bug | Policy premium doesnt match in all screens | Done | Prajakta Vijay Kadam |  | IIRM-777 — SOW#50 - Policy Configurator
3940 | IIRM-6648 | Bug | Claims: On policy dashboard claims summary count not matching | Open | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
3941 | IIRM-6649 | Bug | Claims: For self + dependent claim data upload is getting fail | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
3942 | IIRM-6650 | Story | ISG Executive Policy Ownership Requirement | Draft | Jadhav Sai Prasad |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
3943 | IIRM-6651 | Bug | If a configuration is first rejected and then approved, the approved update is not applied, and the process cannot move forward. | Done | Richa Bagchi Mazumdar |  | IIRM-762 — SOW#35 - Configuration Management
3944 | IIRM-6652 | Bug | In the inception stage, while uploading a file, a pop-up appears and prevents the file from being uploaded. | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3945 | IIRM-6653 | Bug | In the Manage Endorsement screen, no data is displayed, and an error message “Something went wrong” appears every time. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3946 | IIRM-6654 | Bug | In the CD Management screen, the filter module is missing. | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3947 | IIRM-6655 | Bug | When the user navigates from the Policy Expiry Timeline, the filters selected there are not applied in the Manage Policy screen. | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3948 | IIRM-6656 | Bug | bread crumbs &drill down are not working (new widgets) | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3949 | IIRM-6657 | Bug | count doesn't match at drill down at policy expiry timeline widget. | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
3950 | IIRM-6658 | Bug | Filter are not applicable when going through Policy expiry timeline widget to manage policy screen. | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3951 | IIRM-6659 | Bug | For all users in UAT by default owner is selected as Surya Mohan. | Done | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
3952 | IIRM-6660 | Bug | policy type distribution count are not matching with manage policy count. | On Hold | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
3953 | IIRM-6661 | Bug | In manage endorsement filters and search button is freezed. | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3954 | IIRM-6662 | Bug | My client portfolio search button is not working and drill down count is not matching. | Done | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
3955 | IIRM-6663 | Bug | Remove the dollar $ sign in dash board(claims overview business overview). | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3956 | IIRM-6664 | Bug | Dashboard Issue: The color coding need to be adjusted for better visibility in Endorsement TAT and Claims TAT widgets. | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
3957 | IIRM-6665 | Bug | Manage Endorsement Screen – Filter Issue: The filters on the Manage Endorsement screen are frozen and not functioning as expected. | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3958 | IIRM-6666 | Bug | Navigation Error: Clicking on any policy in the Manage Endorsement screen redirects to the | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3959 | IIRM-6667 | Bug | Manage Policy screen, but results in a "Something went wrong" error. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3960 | IIRM-6668 | Bug | Title Correction: The title "Employee Dependent Status" should be updated to "Employee and Dependent Status" for clarity. | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
3961 | IIRM-6669 | Bug | CD Balance Clarification: Users should be informed of the exact amount to be added to the CD balance based on the gross premium value., | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
3962 | IIRM-6670 | Story | CD Balance Tracking: All three types of CD balances—IIRM, Client, and Insurer should be tracked and displayed clearly in the system. | Draft | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
3963 | IIRM-6671 | Bug | Add * mark in ADD CD balance screen which are mandatory and for endorsement flow. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3964 | IIRM-6672 | Story | CD Management: Implement Filter | Ready for QA | Jadhav Sai Prasad |  | IIRM-781 — SOW#54 - CD Management
3965 | IIRM-6673 | Bug | Claims: Claim ID not getting triggered in track claims table | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
3966 | IIRM-6675 | Sub-task | Navigate to Create a Claim for a Non-GMC Policy | Done | Richa Bagchi Mazumdar |  | IIRM-6624 — Claims (Non-GMC): Create & Manage
3967 | IIRM-6676 | Sub-task | Scenario-2: Save a Claim as Draft | Done | Richa Bagchi Mazumdar |  | IIRM-6624 — Claims (Non-GMC): Create & Manage
3968 | IIRM-6677 | Sub-task | Scenario-3: Create a Claim ID in both scenario either as Draft or Next CTA in the “Claim Informed“ | Done | Richa Bagchi Mazumdar |  | IIRM-6624 — Claims (Non-GMC): Create & Manage
3969 | IIRM-6678 | Sub-task | Scenario-4: Validate data, Save it and Move to next step | Done | Richa Bagchi Mazumdar |  | IIRM-6624 — Claims (Non-GMC): Create & Manage
3970 | IIRM-6679 | QAlity Test | IIRM: Verify Policy Type Distribution Card Functionality | Draft | SaikumarMahanthi
3971 | IIRM-6680 | Sub-task | Scenario-5: Auto-save and replace document during claim process with validations and error handling | Done | Richa Bagchi Mazumdar |  | IIRM-6624 — Claims (Non-GMC): Create & Manage
3972 | IIRM-6681 | Sub-task | Claim initiation and stepwise process tracking | Done | Richa Bagchi Mazumdar |  | IIRM-6624 — Claims (Non-GMC): Create & Manage
3973 | IIRM-6682 | Sub-task | Action Buttons: Save Draft, Next CTA, Document Upload | Done | Richa Bagchi Mazumdar |  | IIRM-6624 — Claims (Non-GMC): Create & Manage
3974 | IIRM-6683 | QAlity Test | IIRM: Verify Policy Distribution Edge Cases and Error Handling | Draft | SaikumarMahanthi
3975 | IIRM-6684 | QAlity Test | IIRM: Dashboard: Verify Smart Search Section Display and Basic Search Functionality | Draft | Leela Pakalapati
3976 | IIRM-6685 | QAlity Test | IIRM: Dashboard: Verify Applied Filters Display and Filter Management | Draft | Leela Pakalapati
3977 | IIRM-6686 | QAlity Test | IIRM: Dashboard: Verify Save Filter View Functionality | Draft | Leela Pakalapati
3978 | IIRM-6687 | QAlity Test | IIRM: Dashboard: Verify Reset Filters and Latest Saved View Restoration | Draft | Leela Pakalapati
3979 | IIRM-6688 | QAlity Test | IIRM Dashboard: Verify My Business Performance Section Display with All Metric Categories | Draft | Leela Pakalapati
3980 | IIRM-6689 | QAlity Test | IIRM: Dashboard: Verify New Business Metrics Calculation Accuracy and Filter Responsiveness | Draft | Leela Pakalapati
3981 | IIRM-6690 | QAlity Test | IIRM: Dashboard: Verify Retention (Renewals) Metrics Calculation and Business Logic | Draft | Leela Pakalapati
3982 | IIRM-6691 | QAlity Test | IIRM: Dashboard: Verify Mined Business Metrics Calculation for Flagged Opportunities | Draft | Leela Pakalapati
3983 | IIRM-6692 | QAlity Test | IIRM: Dashboard: Verify Total Business Metrics as Mathematical Sum of All Categories | Draft | Leela Pakalapati
3984 | IIRM-6693 | QAlity Test | IIRM: Dashboard: Verify Premium Amount Calculation Across All Opportunity Types | Draft | Leela Pakalapati
3985 | IIRM-6694 | QAlity Test | IIRM: Dashboard: Verify Brokerage Amount Calculation and Commission Revenue Tracking | Draft | Leela Pakalapati
3986 | IIRM-6695 | QAlity Test | IIRM: Dashboard: Verify My Business Performance Quarterly View Accuracy and Consistency | Draft | Leela Pakalapati
3987 | IIRM-6696 | QAlity Test | Display Total Claims Amount | Draft | SaikumarMahanthi
3988 | IIRM-6697 | Bug | Non-GMC: Template helper not matching with Asset template | Done - Not Reproducible | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3989 | IIRM-6698 | Bug | NON- GMC: File is getting failed on asset inception | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3990 | IIRM-6699 | Bug | NON- GMC: Unable to enable next button from step 2 | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3991 | IIRM-6700 | Bug | NON- GMC: Cover code should be same for asset and sub asset on Inception/Create asset endorsement | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3992 | IIRM-6701 | Bug | NON-GMC: Deletion functionality not working for sub asset | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3993 | IIRM-6702 | Bug | NON-GMC: For inception process , inception type should not be in disable state | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3994 | IIRM-6703 | Bug | NON-GMC: Inception file should get upload only with Inception type = Inception | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3995 | IIRM-6704 | Bug | NON-GMC: Alert we are not showing if CD< Premium amount | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3996 | IIRM-6705 | Bug | NON-GMC: Count not getting updated on asset and sub asset card | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
3997 | IIRM-6706 | Bug | IIRM: AI Chatbot and Version Info Overlapping on Side Menu Expansion | Done | SaikumarMahanthi | iWork | IIRM-754 — SOW#27 - AI - Smart Adds
3998 | IIRM-6707 | Bug | IIRM: Planning Stage Not Disabled After Activity Submission | Done | SaikumarMahanthi | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
3999 | IIRM-6708 | Bug | IIRM: Compensation Type Field Accepting Incorrect Format in Mandate Details | Done | SaikumarMahanthi | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
4000 | IIRM-6709 | Bug | IIRM: Broking Slip: Insurer details are not reflected correctly in the exported file | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4001 | IIRM-6710 | Bug | IRM: Broking Slip: Able to submit the activity for approval without providing data in the "Other Risk Mitigation Features" field (mandatory field) | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4002 | IIRM-6711 | QAlity Test | Non-GMC: Step-1 Form Defaults & Mandatory Validation | Draft | Akhila Gattu
4003 | IIRM-6712 | QAlity Test | Non-GMC: Auto-populate & Read-only: Sum Insured and Basic Premium | Draft | Akhila Gattu
4004 | IIRM-6713 | QAlity Test | Non-GMC: Downloadable Templates: Asset & Sub-Asset | Draft | Akhila Gattu
4005 | IIRM-6714 | QAlity Test | Non-GMC: Asset Upload - Valid Data Happy Path | Draft | Akhila Gattu
4006 | IIRM-6715 | QAlity Test | Non-GMC: Asset Upload - Template Validation (missing/extra/duplicate) | Draft | Akhila Gattu
4007 | IIRM-6716 | QAlity Test | Non-GMC: Sub-Asset Upload - Valid Data & Parent Linkage | Draft | Akhila Gattu
4008 | IIRM-6717 | QAlity Test | Non-GMC: Sub-Asset Upload - Orphan Prevention | Draft | Akhila Gattu
4009 | IIRM-6718 | QAlity Test | Non-GMC: Financial Logic: No Auto Premium Calc + CD Balance Adjustments | Draft | Akhila Gattu
4010 | IIRM-6719 | QAlity Test | Non-GMC: Non-GMC UI Deltas & Step Availability | Draft | Akhila Gattu
4011 | IIRM-6720 | QAlity Test | Non-GMC: Covers & Sub-Covers Link Presence and Navigation | Draft | Akhila Gattu
4012 | IIRM-6721 | QAlity Test | Non-GMC: E2E Non-Financial Happy Path | Draft | Akhila Gattu
4013 | IIRM-6722 | QAlity Test | Non-GMC: E2E Financial Happy Path with CD Balance | Draft | Akhila Gattu
4014 | IIRM-6723 | QAlity Test | Non-GMC: Edit After Upload (Asset & Sub-Asset) | Draft | Akhila Gattu
4015 | IIRM-6724 | QAlity Test | Non- GMC: Date Validations | Draft | Akhila Gattu
4016 | IIRM-6725 | QAlity Test | Non-GMC: Authorization & Performance Essentials | Draft | Akhila Gattu
4017 | IIRM-6726 | Bug | NON-GMC: Self asset should't get uploaded , if sub asset got failed on file upload process | Done - Not a Bug | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4018 | IIRM-6727 | Bug | Invalid format showing on downlaoded template | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4019 | IIRM-6728 | Bug | PolicyConfigure: Template not matching for configured policy | Reopen | Akhila Gattu |  | IIRM-762 — SOW#35 - Configuration Management
4020 | IIRM-6729 | Story | Inception/Endorsement - File Processing Error Remarks - Update the messages | Done | Akhila Gattu |  | IIRM-762 — SOW#35 - Configuration Management
4021 | IIRM-6730 | Bug | PolicyConfigure: Age limit not matching for son with provided constraints. | Open | Akhila Gattu |  | IIRM-762 — SOW#35 - Configuration Management
4022 | IIRM-6731 | Bug | PolicyConfigure: Gender validation missing on endorsement file upload | On Hold | Akhila Gattu |  | IIRM-762 — SOW#35 - Configuration Management
4023 | IIRM-6732 | Bug | PolicyConfigure: Empty error file downloaded for configured policy | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4024 | IIRM-6733 | Bug | PolicyConfigure: For dependent claim ID file upload not working error thrown "Employee not found for provided policy and TPA ID" | Done | Akhila Gattu |  | IIRM-762 — SOW#35 - Configuration Management
4025 | IIRM-6735 | Task | IIRM:Breadcrumb navigation & Dasboard chnages verifcation | Done | SaikumarMahanthi | iWork
4026 | IIRM-6736 | Task | IIRM: Filter Persistance verifiaction in all screens | Done | SaikumarMahanthi | iWork
4027 | IIRM-6737 | Task | IIRM: Verify the Ready for QA Issues and Regression Testing | Done | SaikumarMahanthi | iWork | IIRM-6597 — UAT Bugs
4028 | IIRM-6738 | Task | IIRM: Policy Configuration flows verifications | Done | SaikumarMahanthi
4029 | IIRM-6739 | Bug | IIRM: Filters: Policies List filters issues | Open | SaikumarMahanthi | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4030 | IIRM-6740 | Bug | PolicyConfig: File should't get success , if children has same DOB | Done - Not Reproducible | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4031 | IIRM-6741 | Bug | IRM: Created Date Missing in Company, Contact, and My Client Portfolio Lists | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4032 | IIRM-6742 | QAlity Test | Cross Selection of Parents Allowed? — Config: No — father + mother-in-law not allowed, father-in-law+mother not allowed | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4033 | IIRM-6743 | QAlity Test | Cross Selection of Parents Allowed? — Config: Yes — Employee adds Father + Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4034 | IIRM-6744 | QAlity Test | Second Child as Twins Allowed? — Config: No — Two children with same DOB (twins) listed; second child flagged as twin | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4035 | IIRM-6745 | QAlity Test | Second Child as Twins Allowed? — Config: Yes — Two children with same DOB (twins) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4036 | IIRM-6746 | QAlity Test | Allow male employees to cover their parents-in-law? — Config: No — Male employee adds Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4037 | IIRM-6747 | QAlity Test | Allow male employees to cover their parents-in-law? — Config: Yes — Male employee adds Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4038 | IIRM-6748 | QAlity Test | Allow coverage for same-gender parent & parent-in-law? — Config: No — Employee adds Mother + Mother-in-law together | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4039 | IIRM-6749 | QAlity Test | Allow coverage for same-gender parent & parent-in-law? — Config: Yes — Employee adds Father + Father-in-law together | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4040 | IIRM-6750 | QAlity Test | Allow male employees to cover their own parents? — Config: No — Male employee adds Mother | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4041 | IIRM-6751 | QAlity Test | Allow male employees to cover their own parents? — Config: Yes — Male employee adds Father | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4042 | IIRM-6752 | QAlity Test | Allow female employees to cover their parents-in-law? — Config: No — Female employee adds Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4043 | IIRM-6753 | QAlity Test | Allow female employees to cover their parents-in-law? — Config: Yes — Female employee adds Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4044 | IIRM-6754 | QAlity Test | Allow female employees to cover their own parents? — Config: No — Female employee adds Mother | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4045 | IIRM-6755 | QAlity Test | Allow female employees to cover their own parents? — Config: Yes — Female employee adds Father | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4046 | IIRM-6756 | QAlity Test | Studying Son Age Limit Extension (years) — Config: No (Base limit 21) — Son age 22 marked as 'Studying' | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4047 | IIRM-6757 | QAlity Test | Studying Son Age Limit Extension (years) — Config: Yes (+2 years; Base 21 → 23) — Son age 22 marked as 'Studying' | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4048 | IIRM-6758 | QAlity Test | Unmarried Daughter Age Limit Extension (years) — Config: No (Base limit 25) — Unmarried daughter age 26 | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4049 | IIRM-6759 | QAlity Test | Unmarried Daughter Age Limit Extension (years) — Config: Yes (+3 years; Base 25 → 28) — Unmarried daughter age 26 | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4050 | IIRM-6760 | QAlity Test | Minimum required age gap between employee and their parent (years, parent older) — Config: Yes (Min gap 18) — Employee 40; Mother 55 (gap 15) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4051 | IIRM-6761 | QAlity Test | Minimum required age gap between employee and their parent (years, parent older) — Config: Yes (Min gap 18) — Employee 30; Father 50 (gap 20) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4052 | IIRM-6762 | QAlity Test | Minimum required age gap between employee and their parent (years, parent older) — Config: No — Employee 40; Mother 55 (gap 15) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4053 | IIRM-6763 | QAlity Test | Minimum required age gap between employee and their child (years) — Config: Yes (Min gap 18) — Employee 35; Son 20 (gap 15) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4054 | IIRM-6764 | QAlity Test | Minimum required age gap between employee and their child (years) — Config: Yes (Min gap 18) — Employee 32; Daughter 10 (gap 22) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4055 | IIRM-6765 | QAlity Test | Minimum required age gap between employee and their child (years) — Config: No — Employee 35; Son 20 (gap 15) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4056 | IIRM-6766 | QAlity Test | Combined: Cross-Selection=No & Same-Gender=No — Config: CrossSel=No; SameGender=No — Mother + Mother-in-law together | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4057 | IIRM-6767 | QAlity Test | Combined: Male Parents-in-law=No & Own Parents=Yes — Config: Male->In-law=No; Male->Own=Yes — Male adds Father + Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4058 | IIRM-6768 | QAlity Test | Combined: Female Own Parents=No & In-laws=Yes — Config: Female->Own=No; Female->In-law=Yes — Female adds Mother + Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4059 | IIRM-6769 | QAlity Test | Cross-Selection=No with Parent Age Gap=Yes (meets gap) — Config: C01 + C20 — Male employee adds Mother + Mother-in-law; EmpAge=30, Parent ages 55 & 60 (gap 25 & 30) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4060 | IIRM-6770 | QAlity Test | Cross-Selection=No with Parent Age Gap=Yes (violates gap) — Config: C01 + C19 — Male employee adds Mother + Mother-in-law; EmpAge=40, ages 55 & 54 (gap 15 & 14) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4061 | IIRM-6771 | QAlity Test | Cross-Selection=Yes with Parent Age Gap=Yes (meets gap) — Config: C02 + C20 — Female employee adds Father + Father-in-law; EmpAge=28, ages 50 & 52 (gap 22 & 24) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4062 | IIRM-6772 | QAlity Test | Cross-Selection=Yes with Parent Age Gap=Yes (violates gap) — Config: C02 + C19 — Female employee adds Father + Father-in-law; EmpAge=38, ages 50 & 52 (gap 12 & 14) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4063 | IIRM-6773 | QAlity Test | Male In-Laws=No vs Male Own Parents=Yes — Config: C05 + C10 — Male adds Father (own) + Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4064 | IIRM-6774 | QAlity Test | Female In-Laws=No vs Female Own Parents=Yes — Config: C11 + C14 — Female adds Father (own) + Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4065 | IIRM-6775 | QAlity Test | Same-Gender Parent+In-law=No with Cross-Selection=No — Config: C07 + C01 — Employee adds Mother + Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4066 | IIRM-6776 | QAlity Test | Same-Gender Parent+In-law=Yes with Cross-Selection=Yes — Config: C08 + C02 — Employee adds Father + Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4067 | IIRM-6777 | QAlity Test | Twins=No with Child Age Gap=Yes (violates both) — Config: C03 + C22 — EmpAge=35; 2 children twins age 20 (gap 15) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4068 | IIRM-6778 | QAlity Test | Twins=Yes with Child Age Gap=Yes (meets gap) — Config: C04 + C23 — EmpAge=36; twins age 12 (gap 24) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4069 | IIRM-6779 | QAlity Test | Studying Son Extension=Yes with Child Age Gap=Yes (violates gap) — Config: C16 + C22 — EmpAge=35; son age 22 (studying) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4070 | IIRM-6780 | QAlity Test | Studying Son Extension=Yes with Child Age Gap=No — Config: C16 + C24 — EmpAge=35; son age 22 (studying) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4071 | IIRM-6781 | QAlity Test | Unmarried Daughter Extension=Yes with Female Own Parents=Yes — Config: C18 + C14 — Female employee adds unmarried daughter age 26 & Father | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4072 | IIRM-6782 | QAlity Test | Unmarried Daughter Extension=No with Female Own Parents=Yes — Config: C17 + C14 — Female employee adds unmarried daughter age 26 & Father | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4073 | IIRM-6783 | QAlity Test | Female In-Laws=No with Cross-Selection=No — Config: C11 + C01 — Female adds Mother + Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4074 | IIRM-6784 | QAlity Test | Male In-Laws=Yes with Cross-Selection=Yes — Config: C06 + C02 — Male adds Mother + Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4075 | IIRM-6785 | QAlity Test | Male Own Parents=No & Male In-Laws=No — Config: C09 + C05 — Male adds Mother + Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4076 | IIRM-6786 | QAlity Test | Female Own Parents=No & Female In-Laws=Yes — Config: C13 + C12 — Female adds Mother + Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4077 | IIRM-6787 | QAlity Test | Cross-Selection=No vs Female In-Laws=Yes — Config: C01 + C12 — Female adds Mother + Mother-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4078 | IIRM-6788 | QAlity Test | Cross-Selection=Yes vs Female In-Laws=No — Config: C02 + C11 — Female adds Father + Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4079 | IIRM-6789 | QAlity Test | Unmarried Daughter Extension=Yes with Child Age Gap=Yes (violates gap) — Config: C18 + C22 — EmpAge=32; unmarried daughter age 26 (gap 6) | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4080 | IIRM-6790 | QAlity Test | Twins=No with Child Age Gap=No — Config: C03 + C24 — EmpAge=35; twins age 10 | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4081 | IIRM-6791 | QAlity Test | Parent Age Gap=Yes with Female In-Laws=Yes — Config: C20 + C12 — Female adds Mother-in-law (age gap met) + Father-in-law | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4082 | IIRM-6792 | QAlity Test | Twins=Yes with Unmarried Daughter Extension=Yes — Config: C04 + C18 — Twins age 12; unmarried daughter age 26 | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4083 | IIRM-6793 | QAlity Test | Male/Female -in-laws = yes, Own parents =No — Config: — | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4084 | IIRM-6794 | QAlity Test | Studying Son Extension=Yes + Unmarried Daughter Extension=Yes (within limits) — Config: EmpAge=40; Son=22 (Studying, within 23); Daughter=26 (Unmarried, within 28) — C16: PASS; C18: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4085 | IIRM-6795 | QAlity Test | Studying Son Extension=No + Unmarried Daughter Extension=Yes — Config: EmpAge=40; Son=22 (Studying, over base 21); Daughter=26 (Unmarried, within 28) — C15: FAIL; C18: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4086 | IIRM-6796 | QAlity Test | Studying Son Extension=Yes + Unmarried Daughter Extension=No — Config: EmpAge=40; Son=22 (Studying, within 23); Daughter=26 (Unmarried, base 25 exceeded) — C16: PASS; C17: FAIL | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4087 | IIRM-6797 | QAlity Test | Studying Son Extension=Yes + Parent Age Gap=Enforced (meets) — Config: EmpAge=30; Father=50 (gap 20); Son=22 (Studying within 23) — C16: PASS; C20: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4088 | IIRM-6798 | QAlity Test | Studying Son Extension=Yes + Parent Age Gap=Enforced (violates) — Config: EmpAge=40; Mother=55 (gap 15<18); Son=22 (Studying within 23) — C16: PASS; C19: FAIL | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4089 | IIRM-6799 | QAlity Test | Studying Son Extension=No + Parent Age Gap=Not Enforced — Config: EmpAge=40; Parent=55 (gap 15 not enforced); Son=22 (Studying over base 21) — C15: FAIL; C21: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4090 | IIRM-6800 | QAlity Test | Studying Son Extension=Yes + Child Age Gap=Enforced (meets) — Config: EmpAge=45; Son=22 (Studying within 23) → gap 23 — C16: PASS; C23: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4091 | IIRM-6801 | QAlity Test | Studying Son Extension=Yes + Child Age Gap=Enforced (violates) — Config: EmpAge=35; Son=22 (Studying within 23) → gap 13 — C16: PASS; C22: FAIL | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4092 | IIRM-6802 | QAlity Test | Studying Son Extension=No + Child Age Gap=Not Enforced — Config: EmpAge=35; Son=22 (Studying) — C15: FAIL; C24: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4093 | IIRM-6803 | QAlity Test | Unmarried Daughter Extension=Yes + Parent Age Gap=Enforced (meets) — Config: EmpAge=30; Mother=50 (gap 20); Daughter=26 (Unmarried within 28) — C18: PASS; C20: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4094 | IIRM-6804 | QAlity Test | Unmarried Daughter Extension=Yes + Parent Age Gap=Enforced (violates) — Config: EmpAge=40; Mother=55 (gap 15<18); Daughter=26 (Unmarried within 28) — C18: PASS; C19: FAIL | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4095 | IIRM-6805 | QAlity Test | Unmarried Daughter Extension=No + Parent Age Gap=Not Enforced — Config: EmpAge=40; Parent=55 (gap 15 not enforced); Daughter=26 (Unmarried over base 25) — C17: FAIL; C21: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4096 | IIRM-6806 | QAlity Test | Unmarried Daughter Extension=Yes + Child Age Gap=Enforced (meets) — Config: EmpAge=45; Daughter=26 (Unmarried within 28) → gap 19 — C18: PASS; C23: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4097 | IIRM-6807 | QAlity Test | Unmarried Daughter Extension=Yes + Child Age Gap=Enforced (violates) — Config: EmpAge=41; Daughter=26 → gap 15 — C18: PASS; C22: FAIL | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4098 | IIRM-6808 | QAlity Test | Unmarried Daughter Extension=No + Child Age Gap=Not Enforced — Config: EmpAge=38; Daughter=26 (Unmarried) — C17: FAIL; C24: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4099 | IIRM-6809 | QAlity Test | Parent Age Gap Enforced (meets) + Child Age Gap Enforced (meets) — Config: EmpAge=32; Father=52 (gap 20); Son=10 (gap 22) — C20: PASS; C23: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4100 | IIRM-6810 | QAlity Test | Parent Age Gap Enforced (violates) + Child Age Gap Enforced (violates) — Config: EmpAge=35; Mother=50 (gap 15); Son=20 (gap 15) — C19: FAIL; C22: FAIL | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4101 | IIRM-6811 | QAlity Test | Parent Age Gap Not Enforced + Child Age Gap Not Enforced — Config: EmpAge=35; Mother=50 (gap 15); Son=20 (gap 15) — C21: PASS; C24: PASS | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4102 | IIRM-6812 | QAlity Test | Studying Son Extension=Yes — Config: — | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4103 | IIRM-6813 | QAlity Test | First child DOB = 2017-06-01, Second and thrid child DOB = 2018-06-01, TwinFlag = No — Config: — | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4104 | IIRM-6814 | QAlity Test | First child DOB = 2018-06-01, Second child DOB = 2018-06-01, TwinFlag = No — Config: — | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4105 | IIRM-6815 | QAlity Test | First child DOB = 2018-06-01, Second child DOB = 2018-06-01, TwinFlag = Yes — Config: — Second kid twins allowed - Passed | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4106 | IIRM-6816 | QAlity Test | First child DOB = 2018-06-01, Second child DOB = 2019-05-10, TwinFlag = No — Config: — | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4107 | IIRM-6817 | QAlity Test | More than two children, with two marked as twins (DOB same) and one separate child — Config: — | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4108 | IIRM-6818 | QAlity Test | Twins with DOB same but Age Gap Rule also applied (e.g., employee too young to have children that old) — Config: — | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4109 | IIRM-6819 | QAlity Test | Twins scenario combined with Studying Son Extension (twin sons over age limit) — Config: — | Draft | Akhila Gattu |  | PT8-701 — Policy Configurator
4110 | IIRM-6820 | Bug | IIRM: Filter My client Portfolio issues | Open | SaikumarMahanthi | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4111 | IIRM-6821 | Bug | IIRM: Claim List Page Filter and Table Settings Issues | Done | SaikumarMahanthi | iWork | IIRM-777 — SOW#50 - Policy Configurator
4112 | IIRM-6822 | Bug | IIRM: Organization-Based Filter Not Displaying Records | Done | SaikumarMahanthi | iWork | IIRM-18 — SOW#1 - ACL & RBAC Control
4113 | IIRM-6823 | Bug | IIRM: Company Creation Fails for Maldives Account | Open | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4114 | IIRM-6824 | Bug | ManageEndorsement: Remove symbol of tilde(~) for policy number | Done - Not a Bug | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4115 | IIRM-6825 | Bug | IIRM: Dashboard: "Something went wrong" message is displayed when navigating from the My Renewal funnel graph with more records | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4116 | IIRM-6826 | Bug | IIRM: Dashboard: Data is not displayed in Manage Claims when navigated using the Manage Claims button from the dashboard | Done | Leela Pakalapati | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4117 | IIRM-6827 | Epic | Manage Policy | Draft | Jadhav Sai Prasad
4118 | IIRM-6828 | Story | Policy Activation | Done | Jadhav Sai Prasad |  | IIRM-6827 — Manage Policy
4119 | IIRM-6829 | QAlity Test | IIRM: Roles: Verify Restricted Access for Chairman, Vice Chairman, MD, HOD | Draft | SaikumarMahanthi | iWork
4120 | IIRM-6830 | QAlity Test | IIRM: City Dropdown Not Populated for Kenya During Company Creation | Draft | SaikumarMahanthi | iWork
4121 | IIRM-6831 | Bug | IIRM: Dashboard: User is navigated to the Manage Policies screen by clicking on the My Portfolio button | Done | Leela Pakalapati | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4122 | IIRM-6832 | Bug | IIRM: Manage Company: Total Premium Amount and Total Brokerage Amount displayed as 0 | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4123 | IIRM-6833 | Bug | PolicyDashboard: Need your attention card UI not matching with other cards | Done - Not Reproducible | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4124 | IIRM-6834 | Bug | Manage policies: Drilldown process not working as expected | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4125 | IIRM-6835 | Bug | Policy Expiry Timeline-Issue in count and logic for 30 and beyond 90 days | Open | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
4126 | IIRM-6836 | Bug | In endorsement TAT count showing as 0 even records are available | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4127 | IIRM-6837 | Bug | My portfolio when CTA goes to manage policies in Placement instead of client portfolio. Also no back button | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4128 | IIRM-6838 | Bug | Brokerage to collect- Data not populating for some filters. Eg we can see for Ramakrishna but no data for DeepaliRao. Total Count doesnt match for Satyushas login | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4129 | IIRM-6839 | Bug | Premium and policy count doesnt match in Business Service Overview. Drilldown shows a constant list of policies - 1336 In the Policy Type Distribution graph, the displayed count does not match the My Portfolio count. | Done | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
4130 | IIRM-6840 | Bug | Widget - Claims Overview -Not showing count even when manage claims widegt is showing some count | Open | Richa Bagchi Mazumdar |  | IIRM-782 — SOW#55 - Claim Management
4131 | IIRM-6841 | Bug | when filter are applied showing wrong data (eg.Login with any user having data → change the Owner → then navigate to Manage Claims and verify the data after changing the Owner | Done | Richa Bagchi Mazumdar |  | IIRM-782 — SOW#55 - Claim Management
4132 | IIRM-6842 | Task | For vipinc login manage endorsment menu is missing and manage TPA also | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4133 | IIRM-6843 | Bug | if we add any meeting or any activity in service score details is not reflecting | Open | Richa Bagchi Mazumdar |  | IIRM-6276 — SOW-TBD
4134 | IIRM-6844 | Bug | In Manage Policies, after activating a policy, two endorsement icons appear. But none of them navigates to the Endorsement screen | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4135 | IIRM-6845 | Task | Service Score details- if we add any meeting or any activity in service score details is not reflecting | Draft | Richa Bagchi Mazumdar |  | IIRM-6276 — SOW-TBD
4136 | IIRM-6846 | Bug | In SO screen Total Premium Amount Total Brokerage Amount are showing as 0 | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4137 | IIRM-6847 | Bug | Claim settled amount showing wrong in Claims upload data screen | Done | Richa Bagchi Mazumdar |  | IIRM-782 — SOW#55 - Claim Management
4138 | IIRM-6848 | Bug | Manage RO from Funnel drilldown - Not loading | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4139 | IIRM-6849 | Story | Edit Policy Configuration until Policy is activated. | Done | Jadhav Sai Prasad |  | IIRM-6827 — Manage Policy
4140 | IIRM-6850 | Bug | Dashboard: Correct the navigation to My Client Portfolio by clicking on the My Portfolio button | Done | Leela Pakalapati |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4141 | IIRM-6851 | Task | IIRM: New Dashboard Widgets Verification — Business, Claim, and Policy Distribution Widgets | Done | Leela Pakalapati | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4142 | IIRM-6852 | Task | IIRM: Ready-for-QA Bugs and Regression Testing related madules | Done | SaikumarMahanthi | iWork
4143 | IIRM-6853 | Task | IIRM: UAT Functional Testing | Done | SaikumarMahanthi | iWork
4144 | IIRM-6854 | Task | File Processing using Queue | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4145 | IIRM-6855 | Story | Additional Widgets - My Client Testimonials | Draft | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4146 | IIRM-6856 | Story | Additional Widget - My Delivery Performance / Service Score | Draft | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4147 | IIRM-6857 | Story | Additional Widget - Smart Actions | Draft | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4148 | IIRM-6861 | Story | Manage Broker | Draft | Jadhav Sai Prasad |  | IIRM-741 — SOW#14 - Add/Manage Insurer
4149 | IIRM-6862 | Story | Manage TPA | Draft | Jadhav Sai Prasad |  | IIRM-741 — SOW#14 - Add/Manage Insurer
4150 | IIRM-6863 | Story | Manage Insurer | Draft | Jadhav Sai Prasad |  | IIRM-741 — SOW#14 - Add/Manage Insurer
4151 | IIRM-6864 | Story | Quick Cards implementation | Draft | Jadhav Sai Prasad |  | IIRM-797 — SOW#69 - Manage Opportunities
4152 | IIRM-6866 | Story | <Place Holder> | Draft | Jadhav Sai Prasad |  | IIRM-781 — SOW#54 - CD Management
4153 | IIRM-6869 | Story | Send email notification to insurer for ( Inception - Send to Insurer & Endorsement - Send to Insurer) | Draft | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4154 | IIRM-6870 | Story | Email Notifications - Claims - Send to Insurer | Draft | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
4155 | IIRM-6871 | Bug | IIRM: Opportunity Editing Fails with “Property 'id' Not Found” Error | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
4156 | IIRM-6872 | QAlity Test | IIR: Insurer Contact – Creation and Verification in Overview page,List page and Edit page . | Draft | SaikumarMahanthi | iWork
4157 | IIRM-6873 | QAlity Test | Broker Contact – Creation and Verification in Overview page,List page and Edit page | Draft | SaikumarMahanthi | iWork
4158 | IIRM-6874 | QAlity Test | TPA Contact : Add: Appropriate error messages displayed when required inputs are missing during TPA Contact creation | Draft | SaikumarMahanthi | iWork
4159 | IIRM-6875 | QAlity Test | Insurer :Add: Appropriate error messages displayed when required inputs are missing during Insurer creation | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4160 | IIRM-6876 | QAlity Test | Broker : Only authorized user can create a new Broker with all fields. | Draft | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4161 | IIRM-6877 | QAlity Test | Insurer: Edit: Edit all permitted fields of the Insurer | Draft | SaikumarMahanthi | iWork
4162 | IIRM-6878 | QAlity Test | Broker: Edit: Edit all permitted fields of the Broker | Draft | SaikumarMahanthi | iWork
4163 | IIRM-6879 | QAlity Test | Insurer contact: Edit all permitted fields of Insurer contact | Draft | SaikumarMahanthi | iWork
4164 | IIRM-6880 | QAlity Test | Broker contact : Edit all permitted fields of Broker contact | Draft | SaikumarMahanthi | iWork
4165 | IIRM-6881 | QAlity Test | TPA Contact: Only authorized user can create a new TPA Contact with only mandatory fields. | Draft | SaikumarMahanthi | iWork
4166 | IIRM-6882 | Bug | Policydashboard: Empty hyphen should not be shown in policy card | Done | Akhila Gattu | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4167 | IIRM-6883 | Bug | Claim: Claim date format mismatch , when comparing to upload file and manage claims data on UI | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4168 | IIRM-6884 | QAlity Test | IIRM:Insurer Contact: Only authorized user can create a new Insurer Contact with only mandatory fields. | Draft | SaikumarMahanthi | iWork
4169 | IIRM-6885 | QAlity Test | IIRM: Broker Contact : Only authorized user can create a new Broker Contact with only mandatory fields. | Draft | SaikumarMahanthi | iWork
4170 | IIRM-6886 | QAlity Test | IIRM: TPA Contact: Only authorized user can create a new TPA contact with all fields. | Draft | SaikumarMahanthi | iWork
4171 | IIRM-6887 | QAlity Test | IIRM: Insurer Contact: Only authorized user can create a new Insurer contact with all fields. | Draft | SaikumarMahanthi
4172 | IIRM-6888 | QAlity Test | IIRM: Broker Contact : Only authorized user can create a new Broker contact with all fields. | Draft | SaikumarMahanthi | iWork
4173 | IIRM-6889 | QAlity Test | IIRM:Broker :Add: Appropriate error messages displayed when invalid data is input during Broker creation | Draft | SaikumarMahanthi | iWork
4174 | IIRM-6890 | QAlity Test | Placement Slip Generation: Verify the View PDF button visibility and functionality post approval | Draft | Leela Pakalapati | iWork
4175 | IIRM-6891 | QAlity Test | Placement Slip Generation: Verify PDF content and data accuracy | Draft | Leela Pakalapati | iWork
4176 | IIRM-6892 | QAlity Test | Placement Slip Generation: Verify PDF generation with maximum characters in fields | Draft | Leela Pakalapati | iWork
4177 | IIRM-6916 | QAlity Test | Placement Slip Generation: Verify multiple downloads at a time | Draft | Leela Pakalapati | iWork
4178 | IIRM-6917 | QAlity Test | Placement Slip Generation: Print PDF functionality | Draft | Leela Pakalapati | iWork
4179 | IIRM-6919 | QAlity Test | Placement Slip Generation: Verify access and permission validation | Draft | Leela Pakalapati | iWork
4180 | IIRM-6921 | Bug | IIRM: Placement Slip Generation: Cannot view or download the PDF in the Placement Slip generation activity | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4181 | IIRM-6927 | Bug | Endorsement TAT: TAT count displays 0 | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4182 | IIRM-6928 | QAlity Test | NON-GMC: Verify claim should not get uploaded without asset or sub-asset | Draft | Akhila Gattu
4183 | IIRM-6929 | QAlity Test | NON-GMC: Verify track claims should gets updated for every steps | Draft | Akhila Gattu
4184 | IIRM-6930 | QAlity Test | Launch Create Claim (Non-GMC) | Draft | Akhila Gattu
4185 | IIRM-6931 | QAlity Test | Save as Draft (new) shows in Manage Claims | Draft | Akhila Gattu
4186 | IIRM-6932 | QAlity Test | Claim ID generated on Save | Draft | Akhila Gattu
4187 | IIRM-6933 | QAlity Test | Claim ID generated on Next | Draft | Akhila Gattu
4188 | IIRM-6934 | QAlity Test | Next with valid data proceeds to next step | Draft | Akhila Gattu
4189 | IIRM-6935 | QAlity Test | Auto-save on valid doc upload | Draft | Akhila Gattu
4190 | IIRM-6936 | QAlity Test | Replace existing document (success) | Draft | Akhila Gattu
4191 | IIRM-6937 | QAlity Test | Status chip reflects current stage on Save | Draft | Akhila Gattu
4192 | IIRM-6938 | QAlity Test | Field names/order/rules match Excel | Draft | Akhila Gattu
4193 | IIRM-6939 | QAlity Test | Navigation aligns with prototype | Draft | Akhila Gattu
4194 | IIRM-6940 | QAlity Test | CTA visible only for Non-GMC | Draft | Akhila Gattu
4195 | IIRM-6941 | QAlity Test | Draft update moves to top | Draft | Akhila Gattu
4196 | IIRM-6942 | QAlity Test | Re-enter via status tag resumes same stage | Draft | Akhila Gattu
4197 | IIRM-6943 | QAlity Test | Claim ID persists across steps and refresh | Draft | Akhila Gattu
4198 | IIRM-6944 | QAlity Test | Claim ID uniqueness across claims | Draft | Akhila Gattu
4199 | IIRM-6945 | QAlity Test | Next with server-side validation failure | Draft | Akhila Gattu
4200 | IIRM-6946 | QAlity Test | Back navigation retains saved data | Draft | Akhila Gattu
4201 | IIRM-6947 | QAlity Test | Invalid doc type blocked | Draft | Akhila Gattu
4202 | IIRM-6948 | QAlity Test | Oversized doc blocked | Draft | Akhila Gattu
4203 | IIRM-6949 | QAlity Test | Corrupted doc blocked | Draft | Akhila Gattu
4204 | IIRM-6950 | QAlity Test | Auto-save failure on first upload | Draft | Akhila Gattu
4205 | IIRM-6951 | QAlity Test | Replace failure retains previous | Draft | Akhila Gattu
4206 | IIRM-6952 | QAlity Test | Document History & Audit capture events | Draft | Akhila Gattu
4207 | IIRM-6953 | QAlity Test | No Save/Upload → previous stage status persists | Draft | Akhila Gattu
4208 | IIRM-6954 | QAlity Test | Next CTA saves and navigates | Draft | Akhila Gattu
4209 | IIRM-6955 | QAlity Test | Manage Claims search by Claim ID | Draft | Akhila Gattu
4210 | IIRM-6956 | QAlity Test | Manage Claims filter by status | Draft | Akhila Gattu
4211 | IIRM-6957 | QAlity Test | Pagination / infinite scroll works | Draft | Akhila Gattu
4212 | IIRM-6958 | QAlity Test | Access: Create Claim restricted per role | Draft | Akhila Gattu
4213 | IIRM-6959 | QAlity Test | Access: Manage Claims visibility per role | Draft | Akhila Gattu
4214 | IIRM-6960 | QAlity Test | Network timeout on Save | Draft | Akhila Gattu
4215 | IIRM-6961 | QAlity Test | Network timeout on Next | Draft | Akhila Gattu
4216 | IIRM-6962 | QAlity Test | Idempotent retry after Save failure | Draft | Akhila Gattu
4217 | IIRM-6963 | QAlity Test | Duplicate uploads when only one allowed | Draft | Akhila Gattu
4218 | IIRM-6964 | QAlity Test | Unsupported MIME with valid extension | Draft | Akhila Gattu
4219 | IIRM-6965 | QAlity Test | Rapid successive Replace clicks (debounce) | Draft | Akhila Gattu
4220 | IIRM-6966 | QAlity Test | Session expiry mid-flow | Draft | Akhila Gattu
4221 | IIRM-6967 | QAlity Test | Invalid characters/length in text fields | Draft | Akhila Gattu
4222 | IIRM-6968 | QAlity Test | Max attachments reached | Draft | Akhila Gattu
4223 | IIRM-6969 | QAlity Test | Draft cleanup not losing data | Draft | Akhila Gattu
4224 | IIRM-6970 | QAlity Test | Verify file format gets downlaodable | Draft | Akhila Gattu
4225 | IIRM-6971 | Bug | Claim: NON-GMC: Default time is not getting captured , when we open create claim. | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4226 | IIRM-6972 | Bug | Claims:Non-GMC: Step 1: Glitch occurs on clicking on save draft | Done | Akhila Gattu | IBP | IIRM-782 — SOW#55 - Claim Management
4227 | IIRM-6973 | Bug | Claims: NON_GMC: Remove the previous button in step 1 | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4228 | IIRM-6974 | Bug | Claims:NON-GMC: Loss location should be shown as company location | Done | Akhila Gattu | iWork | IIRM-782 — SOW#55 - Claim Management
4229 | IIRM-6975 | Bug | Claims:NON-GMC: Claims is getting created with out asset functionality | Done - Not Reproducible | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4230 | IIRM-6976 | Bug | Claims:NON-GMC: Non-standard templates are being uploaded — system should restrict uploads to only standard templates | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4231 | IIRM-6977 | Bug | Claims: NON-GMC: Unable to proceed from step2 with default date and time | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4232 | IIRM-6978 | Bug | Claims:NON-GMC: No where showing completed claim step name in track claims records | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4233 | IIRM-6979 | Bug | Claims:NON-GMC: Proper step navigation not happening while navigating through claim ID from track claim | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4234 | IIRM-6980 | Bug | Claims: NON-GMC: Uploaded file not showing on navigating to previous step | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4235 | IIRM-6981 | QAlity Test | Claims:NON-GMC: Verify claim count is getting updating in dashboard | Internal Review Pending | Akhila Gattu
4236 | IIRM-6982 | Bug | Claims: NON-GMC – Existing Claim IDs incorrectly mapped to New Policy Claim Track when claims share the same company | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4237 | IIRM-6983 | Bug | Claims:NON-GMC: Description of loss allows > 500 chars | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4238 | IIRM-6984 | Bug | Claims:NON-GMC: File uploaded track details not getting after file upload | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4239 | IIRM-6985 | Bug | Claims: NON-GMC: Default supported files text needs to be changed | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4240 | IIRM-6986 | Bug | Claims:NON-GMC: Prepopulating insurer/company name not happening with Adjuster Assigned By field | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4241 | IIRM-6987 | Bug | Claims:NON-GMC: property should not be shown in validation error | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4242 | IIRM-6988 | Bug | Claims:NON-GMC: Char count validation missing for Adjuster Name | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4243 | IIRM-6989 | Bug | IIRM: Placement Slip Generation: Correct the file name format for the generated Placement Slip PDF | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4244 | IIRM-6990 | Bug | IIRM: Placement Slip Generation: Correct the data for accuracy in the generated PDF file | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4245 | IIRM-6991 | Bug | Claims:NON-GMC: step 4: When no file is uploaded then, No data should be shown | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4246 | IIRM-6992 | QAlity Test | IIRM: Sri Lanka Users Are Getting Access to TPA Module | Draft | SaikumarMahanthi | iWork
4247 | IIRM-6993 | Bug | Claims:NON-GMC: Surveyor Name, Findings Summary fields char validation missing | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4248 | IIRM-6994 | Bug | Claims:NON-GMC: Other doc name field not showing | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4249 | IIRM-6995 | Bug | Claims:NON-GMC: Calendar is getting overlapped in documents collected step | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4250 | IIRM-6996 | Bug | IIRM: Placement Slip Generation: The footer section is breaking when generating the PDF with more data | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4251 | IIRM-6997 | Bug | Claims:NON-GMC: Inspected by field char validation missing | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4252 | IIRM-6998 | Bug | Claims:NON-GMC: Design not matching for Join inception report stage. | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4253 | IIRM-6999 | Bug | Claims:NON-GMC: Joint inception report: Inception finding field char validation and uploaded file report validation missing | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4254 | IIRM-7000 | Bug | Claims: NON-GMC: property showing in validation message | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4255 | IIRM-7001 | Bug | Claim:NON-GMC: LOR Copy: File upload and table view requirements not matching. | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4256 | IIRM-7002 | Bug | Claims:NON-GMC: Track document submission requirement missing | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4257 | IIRM-7003 | Bug | Claims: NON-GMC: Property showing in track document submission step | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4258 | IIRM-7004 | Bug | Claims:NON-GMC: Assessment report requirement not matching | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4259 | IIRM-7005 | Bug | Claims:NON-GMC: Approved by char count not matching to the requirement | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4260 | IIRM-7006 | Bug | Claims: NON-GMC: Discharge voucher gen file upload requirement missing | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4261 | IIRM-7007 | Bug | Claims: NON-GMC: no validation is showing on clicking submit, if file not uploaded | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4262 | IIRM-7008 | Bug | Claims: NON-GMC: Customer agreement remarks requirement not matching | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4263 | IIRM-7009 | Bug | Claim: NON-GMC: After claim steps completed , auto redirect not happening to policy dashboard | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4264 | IIRM-7010 | Bug | Claims: NON-GMC: Claim TAT count is not getting displayed | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4265 | IIRM-7011 | Bug | Claims: NON-GMC: Manage claims count not getting updated after claim has submitted | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4266 | IIRM-7012 | Sub-task | Editable Section with form fields including the buttons (Based on the design) | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4267 | IIRM-7013 | Sub-task | API integration for the Policy Details Section | Done | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4268 | IIRM-7014 | Sub-task | Field level validations in the form for policy Details | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4269 | IIRM-7015 | Sub-task | Covers Editable section (Based on the design) | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4270 | IIRM-7016 | Sub-task | API integration for the Covers Section | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4271 | IIRM-7017 | Sub-task | CD details Editable Section | Done | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4272 | IIRM-7018 | Sub-task | API integration for the CD details section | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4273 | IIRM-7019 | Sub-task | Show the approval button based on the permission and cases | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4274 | IIRM-7020 | Sub-task | Changes in the policy configuration | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4275 | IIRM-7021 | Sub-task | Show the Activate Policy button based on the approval | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4276 | IIRM-7022 | Sub-task | Create an API to update policy details . | Done | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4277 | IIRM-7023 | Sub-task | Create an API to update existing covers for a policy. | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4278 | IIRM-7024 | Sub-task | Modify the existing “Get Policy by ID” API according to the new requirements. | Done | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4279 | IIRM-7025 | Sub-task | Update the existing Configuration Approval API. | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4280 | IIRM-7026 | Sub-task | Create an API for policy activation. | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4281 | IIRM-7027 | Sub-task | Create an API to update CD details. | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4282 | IIRM-7028 | Sub-task | Implement role-based approval in policy activation | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-6828 — Policy Activation
4283 | IIRM-7029 | Bug | Insurer contact details are not getting populated | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
4284 | IIRM-7030 | Bug | IIRM:TPA Contact, Insurer Contact, Broker Contacts are accepting white spaces data without validation | Done | SaikumarMahanthi | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
4285 | IIRM-7031 | Bug | IIRM: Placement Slip Generation: Nature of Business field is displayed with HTML tags in the Placement Slip generation PDF | Done | Leela Pakalapati |  | IIRM-756 — SOW#29 - Manage ISG Stages
4286 | IIRM-7032 | Bug | Claims: NON-GMC: Claims track ID is not getting started from 1 | Done - Not Reproducible | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4287 | IIRM-7033 | Bug | IRM: All Cover Details Not Populated in Placement PDF (GMC Cover) | Done | SaikumarMahanthi | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
4288 | IIRM-7034 | Bug | Claims: NON-GMC: Error still remains even after saving the step | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4289 | IIRM-7035 | Bug | Claims: NON-GMC: Wrong validation message shown , if fields exceed with char count | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4290 | IIRM-7036 | Bug | IIRM: Placement Slip Generation: The layout and design of the generated Placement Slip is not as per the reference PDF | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4291 | IIRM-7037 | Bug | Claims: NON-GMC: Error thrown on claim settlement step | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4292 | IIRM-7038 | Bug | Claims: NON-GMC: TAT aging count is not getting display | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4293 | IIRM-7039 | Bug | IIRM: Permission Issue Occurs in Placement Slip When Selecting Existing CD Account | Done | SaikumarMahanthi | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4294 | IIRM-7040 | Bug | Claims: NON-GMC: Space should get reduce in need your attention card | Done - Not Reproducible | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4295 | IIRM-7041 | Bug | Claims: NON-GMC: While adding document name from others,, text field was showing | Done | Akhila Gattu | iWork | IIRM-782 — SOW#55 - Claim Management
4296 | IIRM-7042 | Story | Sync Policy fields to SO/RO Stages | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4297 | IIRM-7043 | Task | Policy Visibility: Link ISG and AM to the Opportunities they are currently handling or have previously worked on | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4298 | IIRM-7044 | Story | IBP: Login (Email Only) to IBP Application and Navigate to Enrolment Process | Blocked | Richa Bagchi Mazumdar |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4299 | IIRM-7045 | Task | IBP: Landing Page | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4300 | IIRM-7046 | Story | IBP: Dashboard (Release-1) | Done | Richa Bagchi Mazumdar |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4301 | IIRM-7047 | Task | Scoping: Organization Hierarchy | Done | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
4302 | IIRM-7048 | Task | Scoping: Special Priviledges | Done | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
4303 | IIRM-7049 | Task | Policy Visibility: Add participants along with policy owners (AM, DB & ISG) | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
4304 | IIRM-7050 | Bug | Claims: Claim ID field is missing in step 1 | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4305 | IIRM-7051 | Bug | Claims: NON-GMC: Sent By field missing in step 2 | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4306 | IIRM-7052 | Bug | Claims: NON-GMC: Document received date, pending documents and file upload fields were missing in step 5 | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4307 | IIRM-7053 | Bug | Claims: NON-GMC: Surveyor filed is not available in Joint Inspection Report | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4308 | IIRM-7054 | Bug | Claims: NON-GMC: In Track Document Submission step status dropdown missing. | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4309 | IIRM-7055 | Bug | Claims: NON-GMC: Once file is saved into system, then show details in "Uploaded Survey Copy" section | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4310 | IIRM-7056 | Bug | IIRM: Placement Slip Data Not Retrieved Automatically After Approval | Done | SaikumarMahanthi |  | IIRM-756 — SOW#29 - Manage ISG Stages
4311 | IIRM-7096 | QAlity Test | Verify access to Policy Details screen from Manage Policy | Completed | Akhila Gattu
4312 | IIRM-7097 | QAlity Test | Verify Policy Details sections are displayed | Completed | Akhila Gattu
4313 | IIRM-7098 | QAlity Test | Verify Edit functionality for policy sections | Completed | Akhila Gattu
4314 | IIRM-7099 | QAlity Test | Verify Submit for Approval workflow | Completed | Akhila Gattu
4315 | IIRM-7100 | QAlity Test | Verify Manager can approve Policy Details | Completed | Akhila Gattu
4316 | IIRM-7101 | QAlity Test | Verify Cover Details display and edit | Completed | Akhila Gattu
4317 | IIRM-7102 | QAlity Test | Verify Cover Details approval workflow | Draft | Akhila Gattu
4318 | IIRM-7103 | QAlity Test | Verify successful policy activation | Draft | Akhila Gattu
4319 | IIRM-7104 | QAlity Test | Verify post-activation CTA state changes | Draft | Akhila Gattu
4320 | IIRM-7105 | QAlity Test | Verify policy visible in client portal | Draft | Akhila Gattu
4321 | IIRM-7106 | QAlity Test | Verify rejection workflow with mandatory comment | Draft | Akhila Gattu
4322 | IIRM-7107 | QAlity Test | Verify Edit disabled after approval | Draft | Akhila Gattu
4323 | IIRM-7108 | QAlity Test | Verify audit log captures activation details | Draft | Akhila Gattu
4324 | IIRM-7109 | QAlity Test | Verify notification on approval submission | Draft | Akhila Gattu
4325 | IIRM-7110 | QAlity Test | Verify notification on Manager rejection | Draft | Akhila Gattu
4326 | IIRM-7111 | QAlity Test | Verify notification on Manager approval | Draft | Akhila Gattu
4327 | IIRM-7112 | QAlity Test | Verify Endorsement and Claims icons enabled post-activation | Draft | Akhila Gattu
4328 | IIRM-7113 | QAlity Test | Verify backend reflects approved details before activation | Draft | Akhila Gattu
4329 | IIRM-7114 | QAlity Test | Verify approved configuration can be edited before activation | Draft | Akhila Gattu
4330 | IIRM-7115 | QAlity Test | Verify 'Approve Updated Configuration' creates audit log | Draft | Akhila Gattu
4331 | IIRM-7116 | QAlity Test | Verify edit option only for Account Number | Draft | Akhila Gattu
4332 | IIRM-7117 | QAlity Test | Verify Transaction table display | Draft | Akhila Gattu
4333 | IIRM-7118 | QAlity Test | Verify activity tagged with Policy ID and approval type | Draft | Akhila Gattu
4334 | IIRM-7119 | QAlity Test | Verify approved/rejected activity in Executive's assignment bucket | Draft | Akhila Gattu
4335 | IIRM-7120 | QAlity Test | Verify 'Basic Details' renamed to 'Policy Details' | Draft | Akhila Gattu
4336 | IIRM-7121 | QAlity Test | Verify multiple sections can be edited before submission | Draft | Akhila Gattu
4337 | IIRM-7122 | QAlity Test | Verify saved state persists across navigation | Draft | Akhila Gattu
4338 | IIRM-7123 | QAlity Test | Verify all covers edited together in single edit form | Draft | Akhila Gattu
4339 | IIRM-7124 | QAlity Test | Verify sequential approval of Policy Details then Cover Details | Draft | Akhila Gattu
4340 | IIRM-7125 | QAlity Test | Verify re-submission after rejection | Draft | Akhila Gattu
4341 | IIRM-7126 | QAlity Test | Verify activation flow for Individual Policy (no configuration required) | Draft | Akhila Gattu
4342 | IIRM-7127 | QAlity Test | Verify activation flow for Group Policy with configuration | Draft | Akhila Gattu
4343 | IIRM-7128 | QAlity Test | Verify configuration update prompt after editing approved details | Draft | Akhila Gattu
4344 | IIRM-7129 | QAlity Test | Verify auto-population of fields from Sales/Renewal data | Draft | Akhila Gattu
4345 | IIRM-7130 | QAlity Test | Verify mandatory field validation in edit form | Draft | Akhila Gattu
4346 | IIRM-7131 | QAlity Test | Verify Save button enabled only when all fields filled | Draft | Akhila Gattu
4347 | IIRM-7132 | QAlity Test | Verify Manager cannot approve without reviewing details | Draft | Akhila Gattu
4348 | IIRM-7133 | QAlity Test | Verify Account Number edit and save | Draft | Akhila Gattu
4349 | IIRM-7134 | QAlity Test | Verify navigation between Policy Details, Covers, and CD Account tabs | Draft | Akhila Gattu
4350 | IIRM-7135 | QAlity Test | Verify success message and redirection after activation | Draft | Akhila Gattu
4351 | IIRM-7136 | QAlity Test | Verify behavior when no source data available for fields | In Progress | Akhila Gattu
4352 | IIRM-7137 | QAlity Test | Verify handling when Manager and Executive are same user | Draft | Akhila Gattu
4353 | IIRM-7138 | QAlity Test | Verify behavior with single cover vs multiple covers | Draft | Akhila Gattu
4354 | IIRM-7139 | QAlity Test | Verify activation when approval pending for long duration | Draft | Akhila Gattu
4355 | IIRM-7140 | QAlity Test | Verify configuration changes saved but not approved before activation | Draft | Akhila Gattu
4356 | IIRM-7141 | QAlity Test | Verify behavior when user edits form but doesn't save before closing | Draft | Akhila Gattu
4357 | IIRM-7142 | QAlity Test | Verify multiple rejection and re-submission cycles | Draft | Akhila Gattu
4358 | IIRM-7143 | QAlity Test | Verify notification delivery when user is offline | Draft | Akhila Gattu
4359 | IIRM-7144 | QAlity Test | Verify activation attempt with partial approvals (only Policy Details approved) | Draft | Akhila Gattu
4360 | IIRM-7145 | QAlity Test | Verify behavior when no transactions exist in CD Account | Draft | Akhila Gattu
4361 | IIRM-7146 | QAlity Test | Verify backend sync when multiple users edit simultaneously | Draft | Akhila Gattu
4362 | IIRM-7147 | QAlity Test | Verify behavior with extremely long field values | Draft | Akhila Gattu
4363 | IIRM-7148 | QAlity Test | Verify activation blocked without Policy Details approval | Draft | Akhila Gattu
4364 | IIRM-7149 | QAlity Test | Verify activation blocked without Cover Details approval | Draft | Akhila Gattu
4365 | IIRM-7150 | QAlity Test | Verify Group Policy activation blocked without configuration | Draft | Akhila Gattu
4366 | IIRM-7151 | QAlity Test | Verify Save blocked with empty mandatory fields | Draft | Akhila Gattu
4367 | IIRM-7152 | QAlity Test | Verify Manager cannot reject without entering comment | Draft | Akhila Gattu
4368 | IIRM-7153 | QAlity Test | Verify Edit blocked after approval | Draft | Akhila Gattu
4369 | IIRM-7154 | QAlity Test | Verify Cover edit blocked after approval | Draft | Akhila Gattu
4370 | IIRM-7155 | QAlity Test | Verify activation blocked before Policy Confirmation step | Draft | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4371 | IIRM-7156 | QAlity Test | Verify invalid data format rejection in edit fields | Draft | Akhila Gattu
4372 | IIRM-7157 | QAlity Test | Verify activation blocked with unapproved configuration changes | Draft | Akhila Gattu
4373 | IIRM-7158 | QAlity Test | Verify unauthorized user cannot access Policy Details screen | Draft | Akhila Gattu
4374 | IIRM-7159 | QAlity Test | Verify invalid Account Number format rejected | Draft | Akhila Gattu
4375 | IIRM-7160 | QAlity Test | Verify already activated policy cannot be re-activated | Draft | Akhila Gattu
4376 | IIRM-7161 | QAlity Test | Verify submission blocked with unsaved changes | Draft | Akhila Gattu
4377 | IIRM-7162 | QAlity Test | Verify system handles network failure during save operation | Draft | Akhila Gattu
4378 | IIRM-7163 | QAlity Test | Verify special characters validation in text fields | Draft | Akhila Gattu
4379 | IIRM-7164 | QAlity Test | Verify negative values rejected in Premium/Sum Insured fields | Draft | Akhila Gattu
4380 | IIRM-7165 | QAlity Test | Verify Executive cannot approve their own submission | Draft | Akhila Gattu
4381 | IIRM-7166 | QAlity Test | Verify activation fails with expired policy dates | Draft | Akhila Gattu
4382 | IIRM-7167 | QAlity Test | Verify date field validation (future/past date restrictions) | Draft | Akhila Gattu
4383 | IIRM-7168 | QAlity Test | Endorsement: Verify once endorsement is created, Check dashboard count on endorsement TAT | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4384 | IIRM-7169 | QAlity Test | Endorsement: Verify claim process for uploaded endorsement employee ID's | Draft | Akhila Gattu
4385 | IIRM-7170 | QAlity Test | Endorsement: Verify claim TAT on dashboard for pending claims | Draft | Akhila Gattu
4386 | IIRM-7171 | QAlity Test | Endorsement: Verify once claims is settled, count on Claims TAT and manage claims dashboard | Draft | Akhila Gattu
4387 | IIRM-7172 | QAlity Test | Endorsement: Verify pending endorsement can be submit by using track endorsement ID's | Draft | Akhila Gattu
4388 | IIRM-7173 | QAlity Test | Inception: Verify inception can only be done for newly created policy. | Draft | Akhila Gattu
4389 | IIRM-7174 | QAlity Test | Inception: Verify inception process for already endorsement created policy | Draft | Akhila Gattu
4390 | IIRM-7175 | QAlity Test | Inception: Verify endorsement track ID should not get for inception processed users | Draft | Akhila Gattu
4391 | IIRM-7176 | QAlity Test | Inception: Verify endorsement TAT and claim TAT for inception processed users | Draft | Akhila Gattu
4392 | IIRM-7177 | QAlity Test | CD: Verify for already CD account exists company can't be added CD balance. | Draft | Akhila Gattu
4393 | IIRM-7178 | QAlity Test | CD: Verify added CD balance should get reflect in CD management, Policies | Draft | Akhila Gattu
4394 | IIRM-7179 | QAlity Test | CD: Verify CD< Premium amount , endorsement process can be done | Draft | Akhila Gattu
4395 | IIRM-7180 | Task | Removal of the mandatory email and mobile number during the enrollment file processing section | Done | Jagadeesh |  | IIRM-773 — SOW#46 - Enrolment Portal
4396 | IIRM-7181 | Task | Extraction of the policy enrollment file logic into common function with the new processing rules | Open | Jagadeesh |  | IIRM-762 — SOW#35 - Configuration Management
4397 | IIRM-7182 | Task | Creation of new Endpoint in the ibp service for handling the enrollment file handling | Done | Jagadeesh
4398 | IIRM-7183 | Epic | PO Tasks | Draft | Richa Bagchi Mazumdar
4399 | IIRM-7184 | Task | IIRM: Test cases authering for Placement Slip download functionality | Done | SaikumarMahanthi
4400 | IIRM-7185 | Task | IIRM: Test cases Execution for Placementslip download functionality | Done | SaikumarMahanthi
4401 | IIRM-7186 | Task | IIRM: Verify Ready for QA issues and Regression checking | Done | SaikumarMahanthi | iWork
4402 | IIRM-7187 | Task | IIRM: API Test data preparation for Company & Contact | Done | SaikumarMahanthi | iWork
4403 | IIRM-7188 | Bug | Opening Balance Issue in CD Account | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
4404 | IIRM-7189 | Task | IIRM: Automation test scripts refactor | Done | SaikumarMahanthi | iWork | IIRM-777 — SOW#50 - Policy Configurator
4405 | IIRM-7190 | Bug | NON- GMC : Claims: On download icon hover , object -ob ject showing | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4406 | IIRM-7191 | Bug | NON-GMC: claims: Commas were not showing for success and failure count | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4407 | IIRM-7192 | Bug | NON-GMC: Claims: Pending state not showing for step 2 | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4408 | IIRM-7193 | Bug | Claims: NON-GMC: Lead insurer details not fetching | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4409 | IIRM-7194 | Bug | Policy Expiry Timeline section should display below Claims TAT section | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4410 | IIRM-7195 | Bug | Clicking on any link in Endorsement TAT section does not match endorsement count, and the Run/Reset buttons are also disabled. | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4411 | IIRM-7196 | Bug | Clicking on any link in Claim TAT section is not showing matching Claims count. | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4412 | IIRM-7197 | Bug | The policy count displayed in the graph in Policy Type Distribution section does not match the count in the Business Service Overview section. | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4413 | IIRM-7198 | Bug | Individual sections should not be visible to the person who is not authorized to see it.(RBAC) | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4414 | IIRM-7200 | Bug | Total Policies quick card value is not matching with applied default filter search result. Also, Manager+Team filter is not default. | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-6827 — Manage Policy
4415 | IIRM-7202 | Bug | Remove Sum Insured column from Policy details section. | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
4416 | IIRM-7203 | Bug | Display month name instead of 01, 02 in Service score section. | Done | Richa Bagchi Mazumdar |  | IIRM-781 — SOW#54 - CD Management
4417 | IIRM-7204 | Task | The TAT title (e.g., ">7 Days") should be displayed in the header section in brackets of the "Service score details" section. | Open | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4418 | IIRM-7205 | Bug | PROD: During TPA upload (Step #6), if 100 records are uploaded and 30 fail, the system should allow uploading the remaining 30 records. Once all records are successfully uploaded, further uploads should be restricted. | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4419 | IIRM-7206 | Bug | During the Inception process, the system displays a message related to Endorsement and also in download excel, even though Inception data is being uploaded. | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4420 | IIRM-7207 | Bug | When uploading non-GMC data it is not considering sub assets. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4421 | IIRM-7208 | Bug | The two labels on the Claim Upload page are not identical but seem to serve the same function, so clarification is needed, or the labels should be updated to better reflect their distinct purposes | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4422 | IIRM-7209 | Bug | Email configuration is still not set up; for testing purposes, the emails should be directed to a designated recipient. | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4423 | IIRM-7210 | Bug | Template helper is not in sync with the relationship configuration eg parent -in -laws are not available in template. | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4424 | IIRM-7211 | Bug | Any date format must be accepted in template | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4425 | IIRM-7212 | Bug | Success records must be visible | Done - Not a Bug | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4426 | IIRM-7213 | Bug | Deletion Endorsement not working. | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4427 | IIRM-7214 | Bug | Version number at the bottom of left menu is not updating | Done - Not a Bug | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4428 | IIRM-7215 | Bug | PolicyActivate: Company type is disabled, cant update the basic details | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4429 | IIRM-7216 | Bug | ActivatePolicy: Commas missing for premium&Brokerage details | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4430 | IIRM-7217 | Bug | ActivatePolicy: Pending for approval needs to be shown for policy details, Once policy details got approved. | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4431 | IIRM-7218 | Bug | ActivatePolicy: For approve comment also mandatary should be there | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4432 | IIRM-7219 | Bug | ActivatePolicy: Submit for approval button glitch shown on UI | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4433 | IIRM-7220 | Bug | ActivatePolicy: Approved and Rejected buttons not showing for BD manager | Reopen | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4434 | IIRM-7221 | Bug | Claims: NON-GMC: Pending and in progress count not getting trigger | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4435 | IIRM-7222 | Bug | IRM: Placement Slip Generation: Unable to enter values in the Service Tax Percentage field and unable to complete the activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4436 | IIRM-7223 | Bug | IIRM: KDM Meeting: Able to access the Employee Participants dropdown after the activity is completed | Reopen | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4437 | IIRM-7224 | Bug | ActivatePolicy: Manage policy navigation missing. | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4438 | IIRM-7225 | Bug | ActivatePolicy: Activate button not getting redirected to policy dashboard page | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4439 | IIRM-7226 | Bug | ActivatePolicy: Premium, Deductible, and Status details not showing in Cover details | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4440 | IIRM-7227 | Bug | IIRM: Policy Activation: Few fields are missing | Done | Leela Pakalapati | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
4441 | IIRM-7228 | Bug | ActivatePolicy: Instead of update , save button should be available | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4442 | IIRM-7229 | Bug | IIRM: Policy Activation: Edit functionality is missing for a few fields | Done | Leela Pakalapati | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
4443 | IIRM-7230 | Bug | ActivatePolicy: Approve all covers button not available | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4444 | IIRM-7231 | Bug | IIRM: TPA/Insurer/Broker: Search is not working for Phone and Email is not displayed on row data while search with same | Done | KOWTRAPU KAVYA SRI |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4445 | IIRM-7232 | Bug | ActivatePolicy: Updated data on covers not maintains on switching tabs. | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4446 | IIRM-7233 | Bug | ActivatePolicy: Unable to approve policy config and activate policy | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4447 | IIRM-7234 | Story | SO Creation Fails After RO Rejection – Cross-Client Validation Required | Draft | Jadhav Sai Prasad |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4448 | IIRM-7235 | Bug | IIRM: Policy Activation: Amount and Percentage field issues | Done | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
4449 | IIRM-7236 | Story | Production Deployment of Email Communication | Draft | Jadhav Sai Prasad |  | IIRM-761 — SOW#34 - Notifications Management
4450 | IIRM-7237 | Story | Generic Option Standardization for Dependent Configurations | Draft | Jadhav Sai Prasad |  | IIRM-762 — SOW#35 - Configuration Management
4451 | IIRM-7238 | Story | Logical Grouping & Consolidation of Constraints | Draft | Jadhav Sai Prasad |  | IIRM-762 — SOW#35 - Configuration Management
4452 | IIRM-7239 | Bug | IIRM: Policy Activation – "Brokerage Amount as per Iwork" Value Not Mapping Correctly | Done | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
4453 | IIRM-7240 | Bug | IIRM: Manage Policy: Incorrect toast message displayed after successful update | Done | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
4454 | IIRM-7241 | Bug | ActivatePolicy: Recently updated tag not showing for policy details and for cover details as per design | Done - Not Reproducible | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4455 | IIRM-7242 | Task | IBP Scope and Timeline planning | Done | Jadhav Sai Prasad |  | IIRM-7183 — PO Tasks
4456 | IIRM-7243 | Task | Create tickets for raised issues in client discussions 4 tickets | Done | Jadhav Sai Prasad |  | IIRM-7183 — PO Tasks
4457 | IIRM-7244 | Task | KT on the Claims - Non GMC to the client | Done | Jadhav Sai Prasad |  | IIRM-7183 — PO Tasks
4458 | IIRM-7245 | Task | Review "Policy activation" module | Done | Jadhav Sai Prasad |  | IIRM-7183 — PO Tasks
4459 | IIRM-7246 | Task | Connect with the Front-end dev for the blockers | Done | Jadhav Sai Prasad |  | IIRM-7183 — PO Tasks
4460 | IIRM-7247 | Task | Call with Client regarding the ad-hock requirements | Done | Jadhav Sai Prasad |  | IIRM-7183 — PO Tasks
4461 | IIRM-7248 | Bug | Non-mandatory address fields show “required” validation errors during TPA Contact creation | Done - Not Reproducible | KOWTRAPU KAVYA SRI | iWork | IIRM-742 — SOW#15 - Add/Manage TPA
4462 | IIRM-7249 | Bug | IIRM: “Something Went Wrong” Error Displayed on Clicking Initiate Process in File Process | Done | SaikumarMahanthi | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
4463 | IIRM-7250 | Bug | IIRM: File Status Not Updated Automatically After Upload in File Process | Done | SaikumarMahanthi | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
4464 | IIRM-7251 | Sub-task | Welcome banner | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4465 | IIRM-7252 | Sub-task | Journey Cards | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4466 | IIRM-7253 | Sub-task | KPIs | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4467 | IIRM-7254 | Sub-task | Enrollment Banner | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4468 | IIRM-7255 | Sub-task | Policy Cards | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4469 | IIRM-7256 | Sub-task | Personal Insurance | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4470 | IIRM-7257 | Sub-task | Wellness Services Summary | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4471 | IIRM-7258 | Sub-task | Claim Summary | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4472 | IIRM-7259 | Sub-task | Explore wellness benefits | Done | Richa Bagchi Mazumdar |  | IIRM-7046 — IBP: Dashboard (Release-1)
4473 | IIRM-7260 | Sub-task | Login Form | Done | Richa Bagchi Mazumdar |  | IIRM-7044 — IBP: Login (Email Only) to IBP Application and Navigate to Enrolment Process
4474 | IIRM-7261 | Sub-task | Infographic | Done | Richa Bagchi Mazumdar |  | IIRM-7044 — IBP: Login (Email Only) to IBP Application and Navigate to Enrolment Process
4475 | IIRM-7262 | Sub-task | API integration | Done | Richa Bagchi Mazumdar |  | IIRM-7044 — IBP: Login (Email Only) to IBP Application and Navigate to Enrolment Process
4476 | IIRM-7263 | Story | IBP: Enrolment | Done | Richa Bagchi Mazumdar |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4477 | IIRM-7264 | Sub-task | Illustrations Image towards right | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4478 | IIRM-7265 | Sub-task | Common Edit section for employee details | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4479 | IIRM-7266 | Sub-task | UI-Add Dependent section | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4480 | IIRM-7267 | Sub-task | API: Add Dependent form | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4481 | IIRM-7268 | Sub-task | UI: Base health policy selection | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4482 | IIRM-7269 | Sub-task | Accordion | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4483 | IIRM-7270 | Sub-task | UI & API: sticky footer | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4484 | IIRM-7271 | Sub-task | API Integation & Logic Handling | Done | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4485 | IIRM-7272 | Sub-task | Summary Banner | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4486 | IIRM-7273 | Sub-task | GMC , SPA, GTL Key banner | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4487 | IIRM-7274 | Sub-task | API Integation & Logic Handling | Done | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4488 | IIRM-7275 | Sub-task | Success Policy cards | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4489 | IIRM-7276 | Sub-task | Success API Integation & Logic Handling | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4490 | IIRM-7277 | Sub-task | Sticky header | Done | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4491 | IIRM-7279 | Bug | IIRM: File Process Shows “Success” Without Self Employee Record in Uploaded Sheet | Reopen | SaikumarMahanthi | iWork | IIRM-777 — SOW#50 - Policy Configurator
4492 | IIRM-7280 | Bug | IIRM: File Process Takes Excessive Time to Process Files with 500 Records | Open | SaikumarMahanthi | iWork | IIRM-777 — SOW#50 - Policy Configurator
4493 | IIRM-7281 | Bug | IIRM: Policy Activation: "Policy Updated By" field is updated only after screen refresh | Done | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
4494 | IIRM-7282 | CR - Story | IIRM: Termiate actioin should be implement for file process | Draft | SaikumarMahanthi
4495 | IIRM-7283 | Bug | IIRM: UI Issues in Inception Data Upload Module | Done | SaikumarMahanthi | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
4496 | IIRM-7284 | Bug | IIRM: Unsupported File Types Accepted During File Upload (Only Excel Formats Should Be Allowed) | Done | SaikumarMahanthi | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
4497 | IIRM-7285 | Bug | ActivatePolicy: After approval invalid UI message should not be shown | Done | Akhila Gattu |  | IIRM-6827 — Manage Policy
4498 | IIRM-7286 | QAlity Test | IIRM: Verify concurrent file uploads and status updates | Draft | SaikumarMahanthi | iWork
4499 | IIRM-7287 | QAlity Test | IIRM: Verify uploading different file formats | Draft | SaikumarMahanthi | iWork
4500 | IIRM-7288 | QAlity Test | IIRM:Verify “Initiate File Process” changes the status to Processing | Draft | SaikumarMahanthi | iWork
4501 | IIRM-7289 | QAlity Test | IIRM: Verify Large Volume File Upload and Processing | Draft | SaikumarMahanthi | iWork
4502 | IIRM-7290 | QAlity Test | Organisation Hierarchy: Leadership Role – Full Permissions Verification | Draft | Leela Pakalapati
4503 | IIRM-7291 | QAlity Test | Organisations Hierarchy: Leadership Role – Organisation-specific Data Visibility | Draft | Leela Pakalapati
4504 | IIRM-7292 | QAlity Test | Organisation Hierarchy: Leadership Role – Approvals and Monitoring Across Modules | Draft | Leela Pakalapati
4505 | IIRM-7293 | Bug | ActivatePolicy: Commas missing for Terrorism amount and Brokerage amount as per ISG | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4506 | IIRM-7294 | Bug | ActivatePolicy: Cursor not working for back option( to erase data on gross premium amount and fee amount | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4507 | IIRM-7295 | Bug | ActivatePolicy: Ready for approval polices were not showing for ISG manager on approval tab. | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4508 | IIRM-7296 | Story | Asset and sub asset linking to the non group claims | Draft | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
4509 | IIRM-7297 | Bug | UAT: Replace "PANEL OF SURVEYORS" for GMC Policy Type to "SERVICE PROVIDER(TPA)"" | Done | NithinKrishna Sirigiri | iWork | IIRM-6597 — UAT Bugs
4510 | IIRM-7298 | CR - Subtask | UAT: Show Co-Insurer Premium based on Permium Percentage | Pushed to Backlog | NithinKrishna Sirigiri |  | IIRM-6582 — Generate Placement Slip PDF based on Policy & Download
4511 | IIRM-7299 | Story | IBP: <Placeholder Story - Re-use it> | Draft | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4512 | IIRM-7300 | Story | Lanka Localization | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
4513 | IIRM-7301 | Sub-task | DB Changes of Framework | Done | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4514 | IIRM-7302 | Sub-task | UI Forms of Sales | Done | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4515 | IIRM-7303 | Sub-task | UI Forms of policy | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4516 | IIRM-7304 | Sub-task | UI Forms of Service | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4517 | IIRM-7305 | Sub-task | Query Transformation | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4518 | IIRM-7306 | Sub-task | Field Propagation | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4519 | IIRM-7307 | Sub-task | Dynamic Formula | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4520 | IIRM-7308 | Sub-task | Stage Validation | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4521 | IIRM-7309 | Sub-task | API: Base health policy selection | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7263 — IBP: Enrolment
4522 | IIRM-7310 | Task | CR: Re-Performing Placement slip Activity | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4523 | IIRM-7311 | Task | CR: Policy Hard Copy Receipt Activity | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4524 | IIRM-7312 | Task | Policy Docket Activity | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4525 | IIRM-7313 | Task | Manage Policies | Open | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4526 | IIRM-7314 | Task | SO/RO: Documents Section | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4527 | IIRM-7315 | Task | Opty Filters missing Planning | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4528 | IIRM-7316 | Bug | CD Management: Wrong reference type(description) showing on transaction history | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
4529 | IIRM-7317 | Bug | KPI's: Look and fields of KPI's are inconsistance | Done - Not a Bug | Akhila Gattu |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4530 | IIRM-7318 | QAlity Test | IBP:Login: Verify successful login with valid credentials | Draft | Akhila Gattu
4531 | IIRM-7319 | QAlity Test | IBP:Login: Verify redirect to Dashboard for completed enrolment | Draft | Akhila Gattu
4532 | IIRM-7320 | QAlity Test | IBP:Login: Verify redirect to Enrolment for pending status | Draft | Akhila Gattu
4533 | IIRM-7321 | QAlity Test | IBP:Login: Verify company identification from policy | Draft | Akhila Gattu
4534 | IIRM-7322 | QAlity Test | IBP:Login: Verify Edit access for pending enrolment | Draft | Akhila Gattu
4535 | IIRM-7323 | QAlity Test | IBP:Login: Verify View-only access for completed enrolment | Draft | Akhila Gattu
4536 | IIRM-7324 | QAlity Test | IBP:Login: Verify secure session creation | Draft | Akhila Gattu
4537 | IIRM-7325 | QAlity Test | IBP:Login: Verify login activity in audit logs | Draft | Akhila Gattu
4538 | IIRM-7326 | QAlity Test | IBP:Login: Verify login fails with invalid email | Draft | Akhila Gattu
4539 | IIRM-7327 | QAlity Test | IBP:Login: Verify login fails with incorrect password | Draft | Akhila Gattu
4540 | IIRM-7328 | QAlity Test | IBP:Login: Verify generic error message (security) | Draft | Akhila Gattu
4541 | IIRM-7329 | QAlity Test | IBP:Login: Verify account lockout after 5 failed attempts | Draft | Akhila Gattu
4542 | IIRM-7330 | QAlity Test | IBP:Login: Verify account unlock after 15 minutes | Draft | Akhila Gattu
4543 | IIRM-7331 | QAlity Test | IBP:Login: Verify failed login audit log | Draft | Akhila Gattu
4544 | IIRM-7332 | QAlity Test | IBP:Login: Verify attempt counter increments | Draft | Akhila Gattu
4545 | IIRM-7333 | QAlity Test | IBP:Login: Verify login fails for inactive account | Draft | Akhila Gattu
4546 | IIRM-7334 | QAlity Test | IBP:Login: Verify login fails for expired account | Draft | Akhila Gattu
4547 | IIRM-7335 | QAlity Test | IBP:Login: Verify no access for inactive/expired accounts | Draft | Akhila Gattu
4548 | IIRM-7336 | QAlity Test | IBP:Login: Verify inactive/expired audit log | Draft | Akhila Gattu
4549 | IIRM-7337 | QAlity Test | IBP: Login: Verify user can navigate dashboard | Draft | Akhila Gattu
4550 | IIRM-7338 | QAlity Test | IBP:Login: Verify enrolment form functionality | Draft | Akhila Gattu
4551 | IIRM-7339 | QAlity Test | IBP:Login: Verify email case-insensitivity | Draft | Akhila Gattu
4552 | IIRM-7340 | QAlity Test | IBP:Login: Verify whitespace trimming | Draft | Akhila Gattu
4553 | IIRM-7341 | QAlity Test | IBP:Login: Verify special characters in password | Draft | Akhila Gattu
4554 | IIRM-7342 | QAlity Test | IBP:Login: Verify attempt counter with time gaps | Draft | Akhila Gattu
4555 | IIRM-7343 | QAlity Test | IBP:Login: Verify login after immediate deactivation | Draft | Akhila Gattu
4556 | IIRM-7346 | Bug | IIRM: Placement Slip Generation: Unable to approve or reject the activity due to missing mandatory data | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4557 | IIRM-7347 | QAlity Test | IIRM: India GST Categeroy Displayed for Sri Lanka User in Tax Details | Draft | SaikumarMahanthi
4558 | IIRM-7348 | QAlity Test | IIRM: Unable to Submit Held Cover Note – Error: “opportunity_held_cover_note_cover_detail does not exist” | Draft | SaikumarMahanthi | iWork
4559 | IIRM-7349 | Bug | Policy Name in placement slip file should be exactly as policy type in system. | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4560 | IIRM-7350 | Bug | Update Field Applicability for GMC, GPA, GTL, and WC Policies | Ready for QA | Jadhav Sai Prasad |  | IIRM-756 — SOW#29 - Manage ISG Stages
4561 | IIRM-7351 | QAlity Test | IBP:Login: Verify login functionality for deleted employee | Draft | Akhila Gattu
4562 | IIRM-7352 | QAlity Test | IBP:Login: Verify login functionality for employee, if email and phone number not provided on inception/endorsement process | Draft | Akhila Gattu
4563 | IIRM-7353 | Bug | IIRM: Placement Slip Generation: Able to select the same insurer details multiple times when “Policy Placed Type” is set to Multiple | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4564 | IIRM-7354 | QAlity Test | IBP:Enrollment: Verify Dashboard loads with Enroll Now button | Draft | Akhila Gattu
4565 | IIRM-7355 | QAlity Test | IBP:Enrollment: Enroll Now button navigates to Personal Details | Draft | Akhila Gattu
4566 | IIRM-7356 | QAlity Test | IBP:Enrollment: Personal details page loads with all fields and pre-populated data | Draft | Akhila Gattu
4567 | IIRM-7357 | QAlity Test | IBP:Enrollment: Edit and save personal details | Draft | Akhila Gattu
4568 | IIRM-7358 | QAlity Test | IBP:Enrollment: Validate mandatory fields (Name, Email, Phone) | Draft | Akhila Gattu
4569 | IIRM-7359 | QAlity Test | IBP:Enrollment: Validate field formats (Email, Phone, DOB) | Draft | Akhila Gattu
4570 | IIRM-7360 | QAlity Test | IBP:Enrollment: Handle special characters in name and maintain data integrity | Draft | Akhila Gattu
4571 | IIRM-7361 | QAlity Test | IBP:Enrollment: View, add, edit, and remove dependents with validation | Draft | Akhila Gattu
4572 | IIRM-7362 | QAlity Test | IBP:Enrollment: Enforce dependent age constraints (min 18, max 75) | Draft | Akhila Gattu
4573 | IIRM-7363 | QAlity Test | IBP:Enrollment: Enforce policy dependent limit and prevent duplicates | Draft | Akhila Gattu
4574 | IIRM-7364 | QAlity Test | IBP:Enrollment: Validate dependent relationships are from allowed list | Draft | Akhila Gattu
4575 | IIRM-7365 | QAlity Test | IBP:Enrollment: Dependent changes reflected in enrollment summary | Draft | Akhila Gattu
4576 | IIRM-7366 | QAlity Test | IBP:Enrollment: Display plans based on count: Single (auto-select), Dual (comparison), Multiple (carousel) | Draft | Akhila Gattu
4577 | IIRM-7367 | QAlity Test | IBP:Enrollment: Display plan details and selection with real-time summary | Draft | Akhila Gattu
4578 | IIRM-7368 | QAlity Test | IBP:Enrollment: Plan selection persists across navigation steps | Draft | Akhila Gattu
4579 | IIRM-7369 | QAlity Test | IBP:Enrollment: Verify responsive design on mobile, tablet, desktop | Draft | Akhila Gattu
4580 | IIRM-7370 | QAlity Test | IBP:Enrollment: Display complete summary with all enrollment data | Draft | Akhila Gattu
4581 | IIRM-7371 | QAlity Test | IBP:Enrollment: Edit each section from summary and verify changes reflected | Draft | Akhila Gattu
4582 | IIRM-7372 | QAlity Test | IBP:Enrollment: Verify dynamic data fetching and no stale data | Draft | Akhila Gattu
4583 | IIRM-7373 | QAlity Test | IBP:Enrollment: Navigate back and forward without data loss | Draft | Akhila Gattu
4584 | IIRM-7374 | QAlity Test | IBP:Enrollment: Save progress and resume enrollment later | Draft | Akhila Gattu
4585 | IIRM-7375 | QAlity Test | IBP:Enrollment: Submit enrollment and display success confirmation | Draft | Akhila Gattu
4586 | IIRM-7376 | QAlity Test | IBP:Enrollment: Verify enrollment data persisted in system | Draft | Akhila Gattu
4587 | IIRM-7377 | QAlity Test | IBP:Enrollment: Allow personal and dependent details without plan selection | Draft | Akhila Gattu
4588 | IIRM-7378 | QAlity Test | IBP:Enrollment: Send confirmation email with all enrollment details | Draft | Akhila Gattu
4589 | IIRM-7379 | QAlity Test | IBP:Enrollment: Send SMS notification for enrollment confirmation | Draft | Akhila Gattu
4590 | IIRM-7380 | QAlity Test | IBP:Enrollment: Complete end-to-end enrollment flow | Draft | Akhila Gattu
4591 | IIRM-7381 | QAlity Test | IBP:Enrollment: Handle session timeout gracefully | Draft | Akhila Gattu
4592 | IIRM-7382 | QAlity Test | IBP:Enrollment: Verify enrollment for all combiantions of constraints. | Draft | Akhila Gattu
4593 | IIRM-7383 | QAlity Test | IBP:Enrollement: Verify Policy Details page loads with all sections and data pre-populated | Draft | Akhila Gattu
4594 | IIRM-7384 | QAlity Test | IBP:Enrollement: Verify edit, save, and data persistence across sections | Draft | Akhila Gattu
4595 | IIRM-7385 | QAlity Test | IBP:Enrollement: Verify Submit for Approval locks details and changes status | Draft | Akhila Gattu
4596 | IIRM-7386 | QAlity Test | IBP:Enrollement: Verify Manager approval workflow: Approve/Reject with comment | Draft | Akhila Gattu
4597 | IIRM-7387 | QAlity Test | IBP:Enrollement: Verify Covers page displays all covers with edit and submit functionality | Draft | Akhila Gattu
4598 | IIRM-7388 | QAlity Test | IBP:Enrollement: Verify CD Account tab with Account Number edit and transaction table | Draft | Akhila Gattu
4599 | IIRM-7389 | QAlity Test | IBP:Enrollement: Verify successful policy activation when all prerequisites met | Draft | Akhila Gattu
4600 | IIRM-7390 | QAlity Test | IBP:Enrollement: Verify Active tag replaces Activate button and permissions enabled | Draft | Akhila Gattu
4601 | IIRM-7391 | QAlity Test | IBP:Enrollement: Verify re-submission after rejection: Edit, re-submit, approve | Draft | Akhila Gattu
4602 | IIRM-7392 | QAlity Test | IBP:Enrollement: Verify approved config editable before activation and audit logged | Draft | Akhila Gattu
4603 | IIRM-7393 | QAlity Test | IBP:Enrollement: Verify audit captures who activated, approved, timestamp, fields modified | Draft | Akhila Gattu
4604 | IIRM-7394 | QAlity Test | IBP:Enrollement: Verify notifications sent on submission, rejection, and approval | Draft | Akhila Gattu
4605 | IIRM-7395 | QAlity Test | IBP:Enrollement: Verify activity tagged with Policy ID and approval type in Manager bucket | Draft | Akhila Gattu
4606 | IIRM-7396 | QAlity Test | IBP:Enrollement: Verify approved/rejected activity appears in Executive's assignment bucket | Draft | Akhila Gattu
4607 | IIRM-7397 | QAlity Test | IBP:Enrollement: Verify backend reflects approved policy/cover details before activation | Draft | Akhila Gattu
4608 | IIRM-7398 | QAlity Test | IBP:Enrollement: Verify activated policy immediately visible in client portal | Draft | Akhila Gattu
4609 | IIRM-7399 | QAlity Test | IBP:Enrollement: Verify activation blocked without Policy Details approval | Draft | Akhila Gattu
4610 | IIRM-7400 | QAlity Test | IBP:Enrollement: Verify activation blocked without Cover Details approval | Draft | Akhila Gattu
4611 | IIRM-7401 | QAlity Test | IBP:Enrollement: Verify activation blocked for Group Policy without configuration | Draft | Akhila Gattu
4612 | IIRM-7402 | QAlity Test | IBP:Enrollement: Verify mandatory field validation and format validation | Draft | Akhila Gattu
4613 | IIRM-7403 | QAlity Test | IBP:Enrollement: Verify Manager cannot reject without mandatory comment | Draft | Akhila Gattu
4614 | IIRM-7404 | QAlity Test | IBP:Enrollement: Verify activation blocked before Policy Confirmation step completed | Draft | Akhila Gattu
4615 | IIRM-7405 | QAlity Test | IBP:Enrollement: Verify activation blocked with unapproved configuration changes | Draft | Akhila Gattu
4616 | IIRM-7406 | QAlity Test | IBP:Enrollement: Verify invalid amounts and date constraints rejected | Draft | Akhila Gattu
4617 | IIRM-7407 | QAlity Test | IBP:Enrollement: Verify already activated policy cannot be re-activated | Draft | Akhila Gattu
4618 | IIRM-7408 | QAlity Test | IBP:Enrollement: Verify CD Account: Invalid Account Number format rejected | Draft | Akhila Gattu
4619 | IIRM-7409 | QAlity Test | IBP:Enrollement: Verify special characters in text fields handled correctly | Draft | Akhila Gattu
4620 | IIRM-7410 | QAlity Test | IBP:Enrollement: Verify concurrent approval handling and session timeout | Draft | Akhila Gattu
4621 | IIRM-7411 | QAlity Test | IBP:Enrollement: Verify approval valid after long pending period (30+ days) | Draft | Akhila Gattu
4622 | IIRM-7412 | QAlity Test | IBP:Enrollement: Verify complete end-to-end: Edit > Submit > Approve > Activate > Visible | Draft | Akhila Gattu
4623 | IIRM-7413 | QAlity Test | IBP:Enrollement: Verify success message and redirect after activation | Draft | Akhila Gattu
4624 | IIRM-7414 | QAlity Test | IBP:Enrollement: Verify tab names, CTAs, and behaviors as per spec | Draft | Akhila Gattu
4625 | IIRM-7415 | QAlity Test | IBP:Login: Verify valid login in multiple machines at same time | Draft | Akhila Gattu
4626 | IIRM-7416 | QAlity Test | IBP:Login: Verify login using reactivated account. | Draft | Akhila Gattu
4627 | IIRM-7417 | QAlity Test | IBP:Login: Verify login with slow networks | Draft | Akhila Gattu
4628 | IIRM-7418 | QAlity Test | IBP:Login: Verify concurrent login with 50 accounts in 5 seconds | Draft | Akhila Gattu
4629 | IIRM-7419 | QAlity Test | IBP:Login: Verify login functionality with cross browsers | Draft | Akhila Gattu
4630 | IIRM-7420 | QAlity Test | IBP:Login: Verify mobile number login with other country codes. | Draft | Akhila Gattu
4631 | IIRM-7421 | QAlity Test | IBP:Login: Verify DB checks on login functionality | Draft | Akhila Gattu
4632 | IIRM-7422 | QAlity Test | IBP:Login:ForgotPassword: Verify complete forgot password flow: Link click to email input | Draft | Akhila Gattu
4633 | IIRM-7423 | QAlity Test | IBP:Login:ForgotPassword: Verify password reset link sent and received for valid email | Draft | Akhila Gattu
4634 | IIRM-7424 | QAlity Test | IBP:Login:ForgotPassword: Verify reset link redirects to password reset screen and password update works | Draft | Akhila Gattu
4635 | IIRM-7425 | QAlity Test | IBP:Login:ForgotPassword: Verify login with new password after reset | Draft | Akhila Gattu
4636 | IIRM-7426 | QAlity Test | IBP:Login:ForgotPassword: Verify email validation and reset link contains unique token with expiry | Draft | Akhila Gattu
4637 | IIRM-7427 | QAlity Test | IBP:Login:ForgotPassword: Verify password complexity validation and mismatch handling | Draft | Akhila Gattu
4638 | IIRM-7428 | QAlity Test | IBP:Login:ForgotPassword: Verify reset link is one-time use only | Draft | Akhila Gattu
4639 | IIRM-7429 | QAlity Test | IBP:Login:ForgotPassword: Verify multiple reset requests invalidate previous links | Draft | Akhila Gattu
4640 | IIRM-7430 | QAlity Test | IBP:Login:ForgotPassword: Verify email field validations: empty and invalid format | Draft | Akhila Gattu
4641 | IIRM-7431 | QAlity Test | IBP:Login:ForgotPassword: Verify unregistered email handling (security - no email disclosure) | Draft | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4642 | IIRM-7432 | QAlity Test | IBP:Login:ForgotPassword: Verify expired and invalid reset token handling | Draft | Akhila Gattu
4643 | IIRM-7433 | QAlity Test | IBP:Login:ForgotPassword: Verify password field validations: empty and weak passwords | Draft | Akhila Gattu
4644 | IIRM-7434 | QAlity Test | IBP:Login:ForgotPassword: Verify password and confirm password mismatch validation | Draft | Akhila Gattu
4645 | IIRM-7435 | QAlity Test | IBP:Login:ForgotPassword: Verify special characters in email and cross-browser compatibility | Draft | Akhila Gattu
4646 | IIRM-7436 | QAlity Test | IBP:Login:ForgotPassword: Verify new password same as old password handling | Draft | Akhila Gattu
4647 | IIRM-7437 | Bug | IBP:Enrollment: Dashboard static issues | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4648 | IIRM-7438 | Bug | IBP:Dashboard: Not enrolled static data not showing on UI | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4649 | IIRM-7439 | Bug | IBP: Dashboard: Enroll button navigation does not scroll to top — next screen loads mid-page | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4650 | IIRM-7440 | Bug | IBP: Dashboard: If fields were not updated , update button not working | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4651 | IIRM-7441 | Bug | IBP:Dashboard: Declaration and terms missing on view enrollment summary and according to figma remove save button | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4652 | IIRM-7442 | Bug | IBP:ResetPassword: With existing password, reset password functionality should not work | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4653 | IIRM-7443 | Bug | IBP:ForgotPassword: Show proper validation on forgot password screen | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4654 | IIRM-7444 | Bug | IIRM: Sri Lanka: Opportunity: TPA details should not be displayed | Done | Leela Pakalapati | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
4655 | IIRM-7445 | Bug | IIRM: Policies Not Created for Won Sales Opportunities | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-6827 — Manage Policy
4656 | IIRM-7446 | Bug | IIRM: Opportunity: Fields deviation from the reference sheet | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4657 | IIRM-7447 | Bug | IIRM: India: Meeting for Final Negotiation: Terrorism field is missing | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4658 | IIRM-7448 | Bug | IIRM: Sri Lanka: Meeting for Final Negotiation: Terrorism field is displayed instead of TC and Total Net Premium amount is calculated incorrectly | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4659 | IIRM-7449 | Story | IBP: Login (Other Options) to IBP Application and Navigate to Enrolment Process | Draft | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4660 | IIRM-7450 | Bug | IBP:Login: Dashboard is not getting view after successful login | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4661 | IIRM-7451 | Bug | IBP:Login: dummy email shown on password reset link screen | Done | Akhila Gattu | IBP | IIRM-18 — SOW#1 - ACL & RBAC Control
4662 | IIRM-7452 | Bug | IIRM: Documents: Uploaded Document Appears in Documents Tab Before Activity Completion | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4663 | IIRM-7453 | Bug | IBP:Login:Dashboard: Jerk observed on login process while navigating to dashboard. | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4664 | IIRM-7454 | Bug | IBP:Dashboard: Welcome text missing on welcome card | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4665 | IIRM-7455 | Bug | IBP: Dashboard: Enrollment card and company provided cards were missing | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4666 | IIRM-7456 | Bug | IBP:Login: Account lockout after 5 failed attempts | Done - Not Reproducible | Akhila Gattu |  | IIRM-18 — SOW#1 - ACL & RBAC Control
4667 | IIRM-7457 | Bug | IBP:Login: Reset link should be one-time use only | Done | Akhila Gattu |  | IIRM-6827 — Manage Policy
4668 | IIRM-7458 | Bug | IBP:Login: Week password should not get allowed | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4669 | IIRM-7459 | Bug | IBP:Login: New password same as old password should get handled. | Done | Akhila Gattu |  | IIRM-18 — SOW#1 - ACL & RBAC Control
4670 | IIRM-7460 | Bug | IBP:Login: Non-existing users are able to request for reset password link | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4671 | IIRM-7461 | Sub-task | Localization fields for policy details | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4672 | IIRM-7462 | Bug | IIRM: SO Filters: SO Activity filter is not working | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
4673 | IIRM-7463 | Story | IBP: Forgot, Reset, & Change Password | Draft | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4674 | IIRM-7464 | Bug | IIRM: Documents: Enter Quote: The file uploaded in the Enter Quote activity is not displayed in the Documents tab of that Opportunity | Done | Leela Pakalapati | iWork | IIRM-760 — SOW#33 - Document Generation
4675 | IIRM-7465 | Bug | IIRM: Documents: Opportunity: Incorrect file name is displayed | Open | Leela Pakalapati | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
4676 | IIRM-7466 | Bug | IIRM: Documents: Meeting for Final Negotiation: Document Overriding Issue | Done | Leela Pakalapati | iWork | IIRM-772 — SOW#45 - Document Management
4677 | IIRM-7467 | Bug | IIRM: Documents: Re-uploaded document not reflected in the Documents tab | Done | Leela Pakalapati | iWork | IIRM-772 — SOW#45 - Document Management
4678 | IIRM-7468 | Sub-task | For Srilankan companies change the owners | Done | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4679 | IIRM-7469 | Bug | IIRM: Opportunity: RFP Details Entry: Unable to update activity after rejection | Done | Leela Pakalapati | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
4680 | IIRM-7470 | Bug | Unable to complete Placement Slip Activity | Done | Richa Bagchi Mazumdar |  | IIRM-6473 — Production Issues
4681 | IIRM-7471 | Sub-task | Retest Srilanka Localization in QA Environment | Done | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4682 | IIRM-7472 | Sub-task | UI- Make the UI changes b adding the personal and non-personal toggle and owner fields | Done | VedaVyas |  | IIRM-5264 — CR: Create Tasks - Self and Assign to others
4683 | IIRM-7473 | Bug | IBP:ActivatePolicy: Once policy gets activated , active tag should be shown on policy dashboard page | Done - Not Reproducible | Akhila Gattu |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4684 | IIRM-7474 | Story | Implement Premium Calculation Logic for "SI Model - Multiple" | Open | Jadhav Sai Prasad |  | IIRM-777 — SOW#50 - Policy Configurator
4685 | IIRM-7475 | Story | Send Inception / Endorsement to Insurer | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4686 | IIRM-7476 | Story | Send Inception / Endorsement to Client | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4687 | IIRM-7477 | Bug | IIRM: Documents: Meeting for Final Negotiation: Uploaded file not reflecting in the Documents tab | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4688 | IIRM-7478 | Bug | IIRM: Tasks: "Task Association" and "Owner" fields are not retrieved during task update | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
4689 | IIRM-7479 | Bug | IIRM: Tasks: Updated task not displayed in the Task List | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
4690 | IIRM-7480 | Task | Error messages are not differentiated for different error types | Done | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4691 | IIRM-7481 | Task | Users need to view success records after uploading data in both Inception and Endorsement. | Open | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4692 | IIRM-7482 | Task | Employee is added in inception. Baby added in endorsement with employee id. but got rejected in endorsement | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4693 | IIRM-7483 | Task | The approval process for policy configuration is not functioning as expected | Done | Jadhav Sai Prasad |  | IIRM-777 — SOW#50 - Policy Configurator
4694 | IIRM-7484 | Bug | IIRM: Task: Incorrect data (0) displayed in the Opportunity field under “Link to Opportunity” section | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
4695 | IIRM-7485 | Bug | IIRM: Task: Task Close functionality | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
4696 | IIRM-7486 | QAlity Test | IIRM: Task: Verify Users can create and assign tasks to self or reporters within their hierarchy | Draft | Leela Pakalapati | iWork
4697 | IIRM-7487 | Task | IIRM: Verify Ready for QA issues and Regression testing on related madules | Done | SaikumarMahanthi
4698 | IIRM-7488 | QAlity Test | IIRM: Task: Verify functionality of “Personal” tasks | Draft | Leela Pakalapati | iWork
4699 | IIRM-7489 | QAlity Test | IIRM: Tasks: Verify Manager’s visibility for all non-personal tasks within their hierarchy | Draft | Leela Pakalapati | iWork
4700 | IIRM-7490 | Task | IIRM: Document upload functionaliy testing | Done | SaikumarMahanthi | iWork
4701 | IIRM-7491 | Task | IIRM: Policy docket and Planing activity new changes verification | Done | SaikumarMahanthi | iWork
4702 | IIRM-7492 | QAlity Test | IIRM: Task: Verify “Close task” CTA functionality to close tasks | Draft | Leela Pakalapati | iWork
4703 | IIRM-7495 | Task | Age as 0 in minimum configuration is not being accepted and the system is not calculating values correctly for age 0. | Open | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4704 | IIRM-7496 | Task | For some policy CD balance is showing as 0 in Policy Details page and when clicked on View CD Details it shows "Something went wrong" | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4705 | IIRM-7497 | Task | For some policy CD balance is showing as 0 in Policy Details page and when clicked on View CD Details it shows "Something went wrong" | Done | Jadhav Sai Prasad |  | IIRM-777 — SOW#50 - Policy Configurator
4706 | IIRM-7498 | Task | For some policy CD balance is showing as 0 in Policy Details page and when clicked on View CD Details it shows "Something went wrong" | Open | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4707 | IIRM-7499 | Task | cd balance showing wrong amount for existing records(migrated policy) | Draft | Jadhav Sai Prasad |  | IIRM-781 — SOW#54 - CD Management
4708 | IIRM-7500 | Task | Add/Del count is not showing in track endorsment for previous endorsment done.Earlier it was showing | Open | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4709 | IIRM-7501 | Task | When we download error file date formate changes for some records | Open | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4710 | IIRM-7502 | Bug | IIRM: Company Quick Create: The City field is disabled | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4711 | IIRM-7503 | Bug | Insurer location not visible in dropdown in Meetings | Ready for QA | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4712 | IIRM-7504 | Sub-task | Lanka Localization: Frontend - Update & Add Fields | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4713 | IIRM-7505 | Sub-task | Lanka Localization: Backend - Update & Add Fields | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4714 | IIRM-7506 | Task | In Receive Acknowledgement from Insurer step mandatory mark(*) was missing but going for next it was asking to upload the data file | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4715 | IIRM-7507 | Task | In endorsment CD balance for new account is showing open balance + cheque amount. | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4716 | IIRM-7508 | Task | There is no tracking available for inception, similar to Track Endorsement. | Open | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4717 | IIRM-7509 | Task | TPA ID Upload – No Confirmation Message and Uploaded File Not Visible | Open | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
4718 | IIRM-7510 | Bug | IIRM: Pre-Prod: Sri Lanka: Data Validation: Not able to complete the activity | Done | Leela Pakalapati | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
4719 | IIRM-7511 | Task | Implement - Table Sort on Policy Premium, SO Premium, RO Premium | Draft | Richa Bagchi Mazumdar |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4720 | IIRM-7512 | Bug | IIRM: Missing From and To Date Validation in Sales Opportunity Activities | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4721 | IIRM-7513 | Task | Clicking on Claim id in Track claim is resulting some java script validation error message | Done | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4722 | IIRM-7514 | Bug | No Mouse Hover in Claim Tracker for Claim ID field. | Ready for QA | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4723 | IIRM-7515 | QAlity Test | Localisation: Verify localised fields visibility for Sri Lanka organisation across ISG activities | Draft | Leela Pakalapati | iWork
4724 | IIRM-7516 | QAlity Test | Localisation: Verify localisation of Tax fields and dropdown values for Sri Lanka organisation | Draft | Leela Pakalapati | iWork
4725 | IIRM-7517 | QAlity Test | Localisation: Verify currency localisation and formatting for Sri Lanka organization | Draft | Leela Pakalapati | iWork
4726 | IIRM-7518 | QAlity Test | Localisation: Validate renamed field labels and new field additions for Sri Lanka | Draft | Leela Pakalapati | iWork
4727 | IIRM-7519 | QAlity Test | Localisation: Validate data validation for Sri Lanka localised numeric fields | Draft | Leela Pakalapati
4728 | IIRM-7520 | QAlity Test | Localisation: Validate end-to-end workflow across localized ISG activities | Draft | Leela Pakalapati | iWork
4729 | IIRM-7521 | Task | When uploading the sub-asset along with the asset which is already uploaded in a previous batch, it gives a validation error saying “Asset already mapped to this policy.”this for NON-GMC POLICY | Done | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4730 | IIRM-7522 | Bug | For First American one set of employee data is failing in endorsement. The error message says "One or more dependent records failed validation; employee enrollment rejected." Data seems to be fine but generalized message is not allowing to understand the | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4731 | IIRM-7523 | Task | For non-GMC, currently only one sub-asset can be attached with the main asset However, the system should allow attaching multiple sub-assets with the main asset during inception. | Done | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4732 | IIRM-7524 | Task | The claim uploaded data is not reflecting in the “Policy Claims Uploaded Data” section of the Manage Policy page. | Done | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4733 | IIRM-7525 | Bug | Before the policy is activated, the approval manager gets stuck on one screen. Even after navigating to other screens, the details from the previous (stuck) screen are still being reflected | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4734 | IIRM-7526 | Bug | IBP: PolicyParameters: RelationshipGroup: Family max total count not in disabled state | Done - Not Reproducible | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
4735 | IIRM-7527 | Bug | No confirmation or file visibility after TPA ID upload; shows “Socket hang up” and “Something went wrong” errors | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4736 | IIRM-7528 | Sub-task | Lanka Localization - Update & Add Fields_29-Oct-2025 | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-7300 — Lanka Localization
4737 | IIRM-7529 | Bug | Non-GMC policy allows inception before policy activation (validation missing) | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4738 | IIRM-7530 | Bug | Policy activation for non-GMC policy blocked by incorrect “Configure first” validation | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4739 | IIRM-7531 | Sub-task | Placement slip Download for Lanka | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4740 | IIRM-7532 | Bug | In the Inception process for GMC, when uploading only employee data, the system is not processing it correctly. The uploaded employee data is not moving forward to the next step, and the premium calculation is mismatched. | Done | Prajakta Vijay Kadam |  | IIRM-7604 — Production - Defects & Tasks
4741 | IIRM-7533 | Task | when downloading the template containing only employee data, the “Base Policy Sum Insured” column and its corresponding values are missing from the template | Done | Prajakta Vijay Kadam |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4742 | IIRM-7534 | Task | EMPLOYEE ID value is changed in "Endorsement Document" with actual employee ids in "Send Inception to Insurer" stage. This is there for inception and for endorsement as well | Done | Prajakta Vijay Kadam |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4743 | IIRM-7535 | Bug | IIRM: Placement Slip Submission Failed in prepod | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
4744 | IIRM-7536 | Bug | Field Values Not Auto-Populating from “Meeting for Final Negotiation” Stage to Policy Confirmation Stages | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4745 | IIRM-7537 | Bug | IIRM: Enter Quote Submission Failed – Invalid Property Error | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
4746 | IIRM-7538 | Bug | IIRM: Policy Dashboard Page Missing in Pre-PROD Environment | Done | SaikumarMahanthi | iWork | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4747 | IIRM-7539 | Story | Inception/Endorsement: "Only Employee Data" Process | Draft | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4748 | IIRM-7540 | Bug | IBP:PolicyConfigure: Parameters: Removed default values cannot be restored or re-added as default values | Done | Akhila Gattu |  | IIRM-762 — SOW#35 - Configuration Management
4749 | IIRM-7541 | Task | Premium & CD balance issue for addtion and deletion done together (Policyid - 555274) | Open | Prajakta Vijay Kadam |  | IIRM-7604 — Production - Defects & Tasks
4750 | IIRM-7542 | Task | Endorsement Summary values are changed after completion of endorsment. | Open | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4751 | IIRM-7543 | Task | Service org-service is Down - Intermittent issue occurred in application | Open | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4752 | IIRM-7544 | Bug | TPA upload: iterations on deleting file happening, if the file got replaced multiple times | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4753 | IIRM-7545 | Sub-task | Sri Lanka: Fields Sequence & Formulae | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7300 — Lanka Localization
4754 | IIRM-7546 | Bug | EMPLOYEE ID value is changed in "Endorsement Document" with actual employee ids in "Send Inception to Insurer" stage. This is there for inception and for endorsement as well | Done - Not Reproducible | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
4755 | IIRM-7547 | Bug | IIRM: Fields Not Auto-Populated in Subsequent Activities for Sri Lanka Users | Done | SaikumarMahanthi | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4756 | IIRM-7548 | Bug | City Doesnt populate while doing quick create | Ready for QA | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4757 | IIRM-7549 | Task | Getting error while clicking on complete asset inception in UAT | Open | Prajakta Vijay Kadam |  | IIRM-6597 — UAT Bugs
4758 | IIRM-7550 | Bug | IIRM: Lanka & India: Placement Slip Generation: The fields get prefilled only after selecting Policy From and To dates | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4759 | IIRM-7551 | Bug | Endorsement: Track endorsement count not getting reflected | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4760 | IIRM-7552 | Bug | IIRM: Placement Slip: GPA: The screen freezes when clicking on the Service Tax Percentage field | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4761 | IIRM-7553 | Bug | IIRM: Broking Slip: Correct the alignment of the logo in the downloaded Excel file | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4762 | IIRM-7554 | Bug | Lanka Issues By Client | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4763 | IIRM-7555 | Sub-task | Mandate: Brokerage Fee is expecting %value in compensation payable field. | Done | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4764 | IIRM-7556 | Sub-task | Final negotiation: Brokerage % should not be displayed | Done | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4765 | IIRM-7557 | Sub-task | Broking slip generation: Sum Insured to be autopopulated, brokerage percentage is not to be displayed, policy from and to auto populate, renewal date auto populate, preferred insurer details should be auto populated | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4766 | IIRM-7558 | Sub-task | ISG planning completion: After ISG executive assignment, assigned ISG user unable to view the task in the dashboard. Need to go to MySO | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4767 | IIRM-7559 | Sub-task | Enter quote: after saving quote, grid is not displaying brokerage amounts | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4768 | IIRM-7560 | Sub-task | QCR Parameters: RFP: variance showing blank, Last year showing blank, Total amount showing blank | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4769 | IIRM-7561 | Sub-task | QCR Parameters: Broking slip all values not displayed | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4770 | IIRM-7562 | Sub-task | QCR Parameters: Second insurer is not displayed | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4771 | IIRM-7563 | Sub-task | QCR Parameters: Insurer1 (Allianz) level few other fields are showing blank | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4772 | IIRM-7564 | Sub-task | QCR Parameters: Brokerage% should not be visible | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4773 | IIRM-7565 | Sub-task | QCR Parameters: Total amount is not relevant title. Is it premium? | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4774 | IIRM-7566 | Sub-task | Final negotiation: Insurer participant should not be mandatory | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4775 | IIRM-7567 | Sub-task | Premium calculation: Fields are not auto populated. Not moving further. Once I fixed, we will move next observations | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4776 | IIRM-7568 | Sub-task | Broking slip is downloaded in Excel format. But logo overlapping and email ID is displayed wrongly. | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4777 | IIRM-7569 | Sub-task | lanka cluster should be mapped with vertical | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4778 | IIRM-7570 | Sub-task | lead insurer section should be auto-populated with the value in case of single insurer level | Done | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4779 | IIRM-7571 | Sub-task | Final negotiation activity - insurer participant should not be mandatory | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4780 | IIRM-7572 | Sub-task | service owner field to be included in policy details page | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4781 | IIRM-7573 | Sub-task | Copy and Paste to be enabled. | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4782 | IIRM-7574 | Sub-task | policy docket screen - remove lable "placement slip details" and change field title to "policy issuance date" | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4783 | IIRM-7575 | Sub-task | admin charges percentage & cess percentage fields are not required and to be removed | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4784 | IIRM-7576 | Sub-task | Policy Renewal Date to be auto populated with the value entered in policy from date | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4785 | IIRM-7577 | Sub-task | Policy Renewal Date to be auto populated with the value entered in policy from date | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4786 | IIRM-7578 | Sub-task | "insurer policy number" is not showing the value in policy details page | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4787 | IIRM-7579 | Sub-task | "insurer invoice number" field to be displayed in policy details page | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4788 | IIRM-7580 | Sub-task | Rearrange all premium and brokerage related fields and bring them together. As of now all fields are spread across the application screen. | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4789 | IIRM-7581 | Sub-task | Cover values entered in Placement Slip should be carried forward to all susuquent activities with the option for user to change the values | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4790 | IIRM-7582 | Sub-task | "max age of dependents" field should be removed from commercial fire covers. | Done | Richa Bagchi Mazumdar |  | IIRM-7554 — Lanka Issues By Client
4791 | IIRM-7583 | Bug | IIRM: Service tax percentage calculation is incorrect in Placement Slip Generation. | Done | SaikumarMahanthi | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4792 | IIRM-7584 | Bug | IBP: InceptionProcess: Invalid grade is getting uploaded. | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4793 | IIRM-7585 | Bug | IIRM: Opty Activities: The Brokerage Amount fields are not auto-calculating based on the Brokerage Percentage fields | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4794 | IIRM-7586 | Bug | IIRM: Opty Activities: Not able to view the details after completing or approving the activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4795 | IIRM-7587 | Bug | IIRM: Pre-Prod: Lanka: Meeting for Final Negotiation: The details are not updated in the UI after completing the activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4796 | IIRM-7588 | Bug | PolicyEnroll: For expired policy edit enroll functionality should not work | Done | Akhila Gattu |  | IIRM-762 — SOW#35 - Configuration Management
4797 | IIRM-7589 | Story | IBP: Hospital Network Management | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
4798 | IIRM-7590 | Bug | PolicyEnroll: Premiums were not getting calculated for enrolled policies | Done | Akhila Gattu |  | IIRM-762 — SOW#35 - Configuration Management
4799 | IIRM-7591 | Story | IBP: FAQs Management (CMS) | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4800 | IIRM-7592 | Task | IIRM: Production Backlog verification and regression checking | Done | SaikumarMahanthi
4801 | IIRM-7593 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi
4802 | IIRM-7594 | Task | IIRM: Localization Testing for India and Srilanka | Done | SaikumarMahanthi | iWork
4803 | IIRM-7595 | Task | IIRM: Policy docekt changes verication | Done | SaikumarMahanthi
4804 | IIRM-7596 | Task | IIRM: Company APIs Testing | Done | SaikumarMahanthi
4805 | IIRM-7597 | Task | IIRM: Automation Test cases refactor | Done | SaikumarMahanthi
4806 | IIRM-7598 | Bug | QCR Premium Comparison – Missing Values and Sri Lanka Fields | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4807 | IIRM-7599 | Task | Carry forwarded for 3 fields for India - SI Insurer, Tax, Brokerage Amount | Open | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
4808 | IIRM-7600 | Task | Auto-populate “Sum Insured” | Done | Richa Bagchi Mazumdar |  | IIRM-6597 — UAT Bugs
4809 | IIRM-7601 | Bug | Broking Slip – Excel - Resize Logo | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4810 | IIRM-7602 | Bug | IIRM: Placement Slip Generation: The Open Balance field is not getting cleared | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4811 | IIRM-7603 | Bug | IIRM: My SO: The Activity name column is not correctly updated with the actual activity name of the SO in the listing table | Reopen | Leela Pakalapati | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
4812 | IIRM-7604 | Epic | Production - Defects & Tasks | WORK IN PROGRESS | NithinKrishna Sirigiri | iWork
4813 | IIRM-7605 | Bug | GMC Policy: Unable to complete "Policy Hard Copy Receipt" - Show error. Refer Description. | QA in Progress | NithinKrishna Sirigiri |  | IIRM-7604 — Production - Defects & Tasks
4814 | IIRM-7606 | Task | GMC Policy: Unable to perform inception - Unauthorised Access. Refer description | Done | NithinKrishna Sirigiri |  | IIRM-7604 — Production - Defects & Tasks
4815 | IIRM-7607 | Task | Placement Slips – PDF - Sri Lanka Fields and Currency Format | Done | NithinKrishna Sirigiri |  | IIRM-7604 — Production - Defects & Tasks
4816 | IIRM-7608 | Bug | IIRM: Placement Slip Generation: Not able to submit the Placement Slip activity for approval | Done | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4817 | IIRM-7609 | CR - Story | CR: For Bulk Deactivation | Draft | NithinKrishna Sirigiri |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4818 | IIRM-7610 | CR - Story | CR: For Bulk Reassignment | Draft | NithinKrishna Sirigiri |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4819 | IIRM-7611 | Bug | In Manage SO, if we select active in filters the status show is WIP it should be ISG planning. If we choose ISG planning the data shows zero | Open | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
4820 | IIRM-7612 | Bug | Service Flow: Inception/Endorsement: Tough the File Processing is failed status few records are stored and reflected in Policy Dashboard | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4821 | IIRM-7613 | Task | DB Update: Policy Status to "Generated" for Policies created in new iWork | Open | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4822 | IIRM-7614 | Bug | ISG Manager task is not displayed - Sri Lanka | On Hold | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
4823 | IIRM-7615 | Bug | IBP: Wrong validation thrown on self configured policy | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4824 | IIRM-7616 | Story | Auto-Populate: Record Insurer and Co-Insurer Details | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
4825 | IIRM-7618 | Bug | Create Company – Redirection from Contact Creation to SO Flow | Done | Richa Bagchi Mazumdar
4826 | IIRM-7619 | Bug | SO – Fields Sequence Missing | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4827 | IIRM-7620 | Bug | Service Flow – Unauthorized Access on Inception Data Upload | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4828 | IIRM-7621 | Bug | SO – Approval Flow and Policy Dashboard Missing (BD Manager Issue) | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4829 | IIRM-7622 | Bug | SO – Approvals for Sathyush’s ID | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4830 | IIRM-7623 | Bug | Policy Configuration – Missing Configuration Button | Done | Richa Bagchi Mazumdar
4831 | IIRM-7624 | Bug | Policy Activation – Incorrect Approval Routing | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4832 | IIRM-7625 | Bug | SO – “Enter Quote” Fields Not Populating | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4833 | IIRM-7626 | Bug | SO – Approval Failure: Value Too Long for Character Varying(255) | Done | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4834 | IIRM-7627 | Bug | Policy Details – Missing Policy Values | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4835 | IIRM-7628 | Bug | Policy Details – Missing Policy Dashboard | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4836 | IIRM-7629 | Bug | IBP: Premium calculations were not getting triggered according to the effective date | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4837 | IIRM-7630 | Bug | [Production] “Submit for Approval” button visible to Manager even after approval – Policy No. 329116 | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4838 | IIRM-7631 | Story | IBP: Claims Corner (Phase 1) - View Claims Details | Done | Jadhav Sai Prasad |  | IIRM-787 — SOW#60 - Claims Corner
4839 | IIRM-7632 | Bug | Manage Policy: Filters "Save view" is not working as expected | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4840 | IIRM-7633 | Story | Inception/Endorsement: Sent to client - Add a new file with Inception/Endorsement columns, Premium, Tax, Contributions | Draft | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4841 | IIRM-7634 | Bug | Inception/Endorsement: Employee count is getting captured from failed inception file | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4842 | IIRM-7635 | Bug | Endorsement: Database error thrown on remarks, if company data already exists. | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4843 | IIRM-7636 | Bug | Policy Details View – Header - Missing Field Values | Done - Not Reproducible | Richa Bagchi Mazumdar
4844 | IIRM-7637 | CR - Subtask | QCR Comparison - word wrap not reflecting | Pushed to Backlog | Richa Bagchi Mazumdar |  | IIRM-7604 — Production - Defects & Tasks
4845 | IIRM-7638 | Task | CR: Policy Renewal Date to be auto populated with the value entered in policy from date | Done | Richa Bagchi Mazumdar
4846 | IIRM-7639 | Story | Localization Frame Work (Pending Items) | Done | NithinKrishna Sirigiri |  | IIRM-764 — SOW#37 - Localisation
4847 | IIRM-7640 | QAlity Test | PolicyConfigure: Verify Policy creation through API | Draft | Akhila Gattu
4848 | IIRM-7641 | Task | Inception/Endorsement - Validate Effective From date within Policy From & To | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4849 | IIRM-7642 | Bug | IIRM: Lanka: Placement Slip Generation: Placement slip download issues | Reopen | Leela Pakalapati | iWork | IIRM-756 — SOW#29 - Manage ISG Stages
4850 | IIRM-7643 | Bug | IBP: Policy details: Wrong popup showing on CD, cover, policy details approvals | Done | Akhila Gattu |  | IIRM-781 — SOW#54 - CD Management
4851 | IIRM-7644 | Bug | IIRM: Contact Search Fails to Retrieve Data When Using Full Contact Name or Full Display Name | Done | Prathiphala Kandula |  | IIRM-737 — SOW#10 - Add/Manage Contact
4852 | IIRM-7645 | Bug | Inception: Unable to view inception process steps , if data got uploaded on step 1 | On Hold | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4853 | IIRM-7646 | Bug | Inception/Endorsement: Total records count mismatch from uploaded file | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4854 | IIRM-7647 | Bug | Inception/Endorsement: Duplicate serial no should not be shown on downloaded endorsement file | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4855 | IIRM-7648 | Sub-task | Set up core data models and DTOs in org-service | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4856 | IIRM-7649 | Sub-task | Implement bulk edit API endpoints in document-service | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4857 | IIRM-7650 | Sub-task | Create "Bulk Edit" privilege in database | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4858 | IIRM-7651 | Sub-task | Implement Company bulk update with validation in company.service.ts | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4859 | IIRM-7652 | Sub-task | Implement Opportunity bulk update with validation in opportunity.service.ts | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4860 | IIRM-7653 | Sub-task | Implement Policy bulk update with validation in policy.service.ts | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4861 | IIRM-7654 | Sub-task | Front End: Create JSON configuration for bulk editable fields | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4862 | IIRM-7655 | Sub-task | Implement bulk edit UI components | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4863 | IIRM-7656 | Sub-task | Integrate frontend with backend bulk edit APIs | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4864 | IIRM-7657 | Sub-task | Implement notification integration for ownership changes | Done | Richa Bagchi Mazumdar |  | IIRM-5116 — CR: For Bulk Assignment
4865 | IIRM-7660 | Bug | IIRM: Broking Slip Generation: Not able to Approve or Reject the activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4866 | IIRM-7661 | Bug | PROD: Premium: On total premium amount decimals were not getting calculated in step 2 | Done | Akhila Gattu |  | IIRM-777 — SOW#50 - Policy Configurator
4867 | IIRM-7662 | Bug | Claims: Uploaded with single record , but on track table showing multiple claim ID's | Done | Akhila Gattu |  | IIRM-782 — SOW#55 - Claim Management
4868 | IIRM-7663 | Bug | IBP: EmployeeDetails: For CTC commas missing | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4869 | IIRM-7664 | QAlity Test | IBP:Enrollment: Verify Enrollment Tracking Screen Display for Employee-Only Upload | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4870 | IIRM-7665 | QAlity Test | IBP:Enrollment: Verify 'Next' CTA is Disabled When Enrollment is In Progress | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4871 | IIRM-7666 | QAlity Test | IBP:Enrollment: Verify 'Next' CTA Enabled After Enrollment Closure Date | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4872 | IIRM-7667 | QAlity Test | IBP:Enrollment: Verify 'Next' CTA Enabled When All Employees Complete Enrollment Before Closure | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4873 | IIRM-7668 | QAlity Test | IBP:Enrollment: Verify Real-Time Enrollment Progress Update | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4874 | IIRM-7669 | QAlity Test | IBP:Enrollment: Verify Incomplete Enrollments Handled with Default Choices | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4875 | IIRM-7670 | QAlity Test | IBP:Enrollment: Verify Enrollment Portal Creates Login for Each Employee | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4876 | IIRM-7671 | QAlity Test | IBP:Enrollment: Verify Status Message Display for Inception | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4877 | IIRM-7672 | QAlity Test | IBP:Enrollment: Verify Status Message Display for Endorsement | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4878 | IIRM-7673 | QAlity Test | IBP:Enrollment: Verify Summary Table Metrics Display | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4879 | IIRM-7674 | QAlity Test | IBP:Enrollment: Verify Employee with Dependents Upload Flow Not Affected | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4880 | IIRM-7675 | QAlity Test | IBP:Enrollment: Verify Standard Inception Workflow After Enrollment Closure | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4881 | IIRM-7676 | QAlity Test | IBP:Enrollment: Verify Data Integrity of Enrollment Data | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4882 | IIRM-7677 | QAlity Test | IBP:Enrollment: Verify Multiple File Uploads in Same Case | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4883 | IIRM-7678 | QAlity Test | IBP:Enrollment: Verify Performance with Large Employee Dataset | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4884 | IIRM-7679 | QAlity Test | IBP:Enrollment: Verify Enrollment Window Extension | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4885 | IIRM-7680 | QAlity Test | IBP:Enrollment: Verify User Attempts Inception Before Closure with Incomplete Enrollments | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4886 | IIRM-7681 | QAlity Test | IBP:Enrollment: Verify Zero Employees Complete Enrollment by Closure | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4887 | IIRM-7682 | QAlity Test | IBP:Enrollment: Verify Concurrent Employee Enrollments Update | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4888 | IIRM-7683 | QAlity Test | IBP:Enrollment: Verify Integration Between CRM and Enrollment Portal | Draft | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4889 | IIRM-7684 | Task | Convert the amount number into decimals with 3 after dot, starting with Policy Configuration | Done | Richa Bagchi Mazumdar |  | IIRM-762 — SOW#35 - Configuration Management
4890 | IIRM-7685 | QAlity Test | ConstraintsCombinations: Verify employer contribution and custom declaration on Base policy enroll for PerFamily contribution | Draft | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4891 | IIRM-7686 | QAlity Test | ConstraintsCombinations: Verify employer contribution and custom declaration on Base policy enroll for PerLife contribution | Draft | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4892 | IIRM-7687 | QAlity Test | Constraints:Combinations: Verify employer contribution and custom declaration on Base policy enroll for Multiple CTC SI | Draft | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4893 | IIRM-7688 | Sub-task | Technical Notes | Done | Richa Bagchi Mazumdar |  | IIRM-7639 — Localization Frame Work (Pending Items)
4894 | IIRM-7689 | Sub-task | PROD Issue: Update the relative brokerage% to the actual brokerage% ¦ Opp No: 994930 ¦ Hamlai Industries Pvt Ltd ¦ Package (Post PROD Depolyment) | Done | NithinKrishna Sirigiri |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4895 | IIRM-7690 | Sub-task | Front End: Add the necessary fields in all the activities starting from Broking Slip Generation, wherever we have premium fields | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4896 | IIRM-7691 | Sub-task | Back End: Add the necessary fields in all the activities starting from Broking Slip Generation, wherever we have premium fields | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4897 | IIRM-7692 | Sub-task | Pre-populate the Preferred insurer details from RFP details entry to Broking Slip Generation activity | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4898 | IIRM-7693 | Sub-task | Pre-populate the insurer details from Broking Slip Generation to Meeting for Final Negotiation, Placement Slip Generation and deviation activities | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4899 | IIRM-7694 | Sub-task | Change the insurer dropdown so that the options contain only the preferred insurers from previous activities | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4900 | IIRM-7695 | Sub-task | Auto-calculation logic for the share amount and brokerage amount on their respective percentages and basic premium | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4901 | IIRM-7696 | Sub-task | Logic manipulation when the policy placed type changes from single to multiple and on Only Lead Insurer Pays Brokerage field | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4902 | IIRM-7697 | Sub-task | Backend: Implement the Preferred Insurers API based on the Opportunity ID. | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4903 | IIRM-7698 | Sub-task | Backend: Include preferred insurers in the deviation activities. | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4904 | IIRM-7699 | Sub-task | Backend: Update the policy with the preferred insurer details. | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4905 | IIRM-7700 | Bug | PROD Issue: File Processing & Counts Mis-matching | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4906 | IIRM-7701 | Bug | PROD Issue: Premium Mis-Matching | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4907 | IIRM-7702 | Bug | PROD Issue: User roles issues - Reported by Neeraj | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4908 | IIRM-7703 | Bug | PROD Issue: Policy Configurations - Available & Default options - Missing Mandatory | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4909 | IIRM-7704 | Sub-task | TASK-BE-B001: Employee hospital search API | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4910 | IIRM-7705 | Sub-task | TASK-BE-B002: Excel export functionality | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4911 | IIRM-7706 | Sub-task | TASK-BE-B003: Excel upload and validation service | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4912 | IIRM-7707 | Sub-task | TASK-BE-B004: Save validated hospitals and sync mechanism | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4913 | IIRM-7708 | Sub-task | TASK-BE-B005: Template download and transaction history APIs | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4914 | IIRM-7710 | Sub-task | TASK-BE-C002: Audit logging and monitoring | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4915 | IIRM-7712 | Sub-task | TASK-FE-E001: Hospital Network page with tabs | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4916 | IIRM-7713 | Sub-task | TASK-FE-E002: Hospital search filters component | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4917 | IIRM-7714 | Sub-task | TASK-FE-E003: Hospital table with pagination | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4918 | IIRM-7715 | Sub-task | TASK-FE-E004: Hospital search and export functionality | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4919 | IIRM-7716 | Sub-task | TASK-FE-F001: Portal Configuration page structure | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4920 | IIRM-7717 | Sub-task | TASK-FE-F002: Excel upload section with validation display | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4921 | IIRM-7718 | Sub-task | TASK-FE-F003: Transaction history and hospital list | Done | Richa Bagchi Mazumdar |  | IIRM-7589 — IBP: Hospital Network Management
4922 | IIRM-7722 | Task | Manage Policy Quick Cards | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4923 | IIRM-7723 | QAlity Test | IIRM: Validate Editable Fields for Company Entity in Bulk Edit | Draft | SaikumarMahanthi | iWork
4924 | IIRM-7724 | QAlity Test | IIRM: Verify filtering results update dynamically on the Company Listing Page | Draft | SaikumarMahanthi | iWork
4925 | IIRM-7725 | QAlity Test | IIRM: Verify multi-select user type filtering on Company listing | Draft | SaikumarMahanthi
4926 | IIRM-7726 | QAlity Test | IIRM: Validate Editable Fields for Opportunity Entity | Draft | SaikumarMahanthi | iWork
4927 | IIRM-7727 | QAlity Test | IIRM: Validate Editable Fields for Policy Entity in Bulk Edit | Draft | SaikumarMahanthi | iWork
4928 | IIRM-7728 | Sub-task | Test cases Documention | Done | SaikumarMahanthi |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4929 | IIRM-7729 | Sub-task | Test Cases Execution | Done | SaikumarMahanthi |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
4930 | IIRM-7730 | QAlity Test | IIRM: Auto-Populate: Verify that the user can provide Single/multiple preffered insurers in RFP Details Entry | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4931 | IIRM-7731 | Bug | IBP - Employee Login and Employee enrolment feedbacks from 07/11/25 | Open | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
4932 | IIRM-7732 | QAlity Test | IIRM: Auto-Populate: Verify user can Edit/Manually add new Preferred Insurers details in Broking Slip | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4933 | IIRM-7739 | QAlity Test | IIRM: Bulk Assignment Notifications When Source User Is Active | Draft | SaikumarMahanthi | iWork | IIRM-18 — SOW#1 - ACL & RBAC Control
4934 | IIRM-7740 | QAlity Test | IIRM: Auto-Population: Verify that editing insurer data in Broking Slip does not affect RFP Details | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4935 | IIRM-7741 | QAlity Test | IIRM: Bulk Assignment Notifications When Source User Is Inactive | Draft | SaikumarMahanthi | iWork
4936 | IIRM-7742 | QAlity Test | IIRM:Validate Notification Content for Bulk Assignment | Draft | SaikumarMahanthi | iWork
4937 | IIRM-7743 | QAlity Test | IIRM: Validate Privilege-Based Permission Enforcement for Bulk Edit | Draft | SaikumarMahanthi | iWork
4938 | IIRM-7744 | QAlity Test | IIRM: Validate Audit Logging for Bulk Edit Operations | Draft | SaikumarMahanthi
4939 | IIRM-7745 | QAlity Test | IIRM: Auto-Population: Verify mandatory field validations for insurer details | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4940 | IIRM-7746 | QAlity Test | IIRM: Privilege-Based Visibility of Multi-Select Checkboxes and Bulk Edit CTA | Draft | SaikumarMahanthi | iWork
4941 | IIRM-7747 | QAlity Test | IIRM: Validate Filtering and Record Selection for Bulk Edit | Draft | SaikumarMahanthi | iWork
4942 | IIRM-7748 | QAlity Test | IIRM: Validate Selection Persistence Across Pagination | Draft | SaikumarMahanthi | iWork
4943 | IIRM-7749 | QAlity Test | IIRM:Validate Bulk Ownership Transfer Across Multiple Records | Draft | SaikumarMahanthi | iWork
4944 | IIRM-7750 | QAlity Test | IIRM: Validate Bulk Updates for Status and Category Fields | Draft | SaikumarMahanthi | iWork
4945 | IIRM-7751 | QAlity Test | IIRM: Validate Bulk Date Field Updates with Confirmation | Draft | SaikumarMahanthi | iWork
4946 | IIRM-7752 | QAlity Test | IIRM: Auto-Population: Verify data flow of Preferred Insurers from Broking Slip to Meeting for Final Negotiation | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4947 | IIRM-7753 | Task | Enable Copy & Paste in the Opportunity flow | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
4948 | IIRM-7754 | Task | Sri Lanka: Allow BD Users to perform ISG Activities | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
4949 | IIRM-7755 | QAlity Test | IIRM: Auto-Population: Verify system behavior when Policy Placement Type set to Single | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4950 | IIRM-7756 | Task | Disable 100% validation check for Insurer Share - Brokerage Percentage | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
4951 | IIRM-7757 | QAlity Test | IIRM: Auto-Populated: Verify system behavior when Policy Placement Type is set to Multiple | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4952 | IIRM-7758 | Sub-task | TASK-A001: Create FAQ database entities and migrations | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4953 | IIRM-7759 | Sub-task | TASK-A002: Set up FAQ module structure in Policy Service | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4954 | IIRM-7760 | Sub-task | TASK-A003: Implement FAQ DTOs and validation | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4955 | IIRM-7761 | Sub-task | TASK-B001: Implement FAQ CRUD operations | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4956 | IIRM-7762 | Sub-task | TASK-B002: Implement Excel upload and processing | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4957 | IIRM-7763 | Sub-task | TASK-B003: Implement audit logging system | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4958 | IIRM-7764 | Sub-task | TASK-B004: Create FAQ template and download endpoints | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4959 | IIRM-7765 | Sub-task | FE TASK-C001: Create FAQ display components for Employee Portal | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4960 | IIRM-7766 | Sub-task | TASK-C002: Build FAQ management interface for CRM | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4961 | IIRM-7767 | Sub-task | TASK-C003: Implement FAQ API integration and state management | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4962 | IIRM-7768 | Sub-task | TASK-C004: Enhance existing FAQ page with category filtering | Done | Richa Bagchi Mazumdar |  | IIRM-7591 — IBP: FAQs Management (CMS)
4963 | IIRM-7769 | QAlity Test | IIRM: Auto-Population: Verify Share % and Brokerage % auto-calculation logic | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4964 | IIRM-7770 | QAlity Test | IIRM: Auto-Population: Verify insurer details auto-populate correctly from Meeting for Final Negotiation to subsequent activities | Draft | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
4965 | IIRM-7771 | Bug | IIRM: Expiry Date Fields Not Updated for Some Companies in Bulk Upload | Done | SaikumarMahanthi | iWork
4966 | IIRM-7772 | Bug | IIRM: Bulk Assign: Incorrect text displayed | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4967 | IIRM-7773 | Bug | IIRM: Inconsistent SO Status Handling During Bulk Upload | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4968 | IIRM-7774 | Sub-task | PROD Bug: TPA Upload failed when it has self & dependents in the backend process | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-6197 — TPA ID Upload
4969 | IIRM-7775 | Bug | IIRM: Incorrect Owner Name Mapping in Policy Bulk Upload | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4970 | IIRM-7776 | Bug | IIRM: ISG and Account Manager Details Not Updated in Bulk Edit | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4971 | IIRM-7777 | Task | CS Role - Executive & Manager MUST view Company, Opty & Policies. | Done | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
4972 | IIRM-7778 | Bug | IIRM: Bulk Assign: Edit option is not displayed for the assigned user as Lead CRM through Bulk Edit | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4973 | IIRM-7779 | Bug | IIRM: Bulk Assign: My SO: The past dates should be disabled in the Expiry Date calendar | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4974 | IIRM-7780 | Bug | IIRM: Bulk Assign: The Owners dropdown LOVs should display based on the organisation | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4975 | IIRM-7781 | Bug | IIRM: Bulk Assign: Notification issues | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
4976 | IIRM-7782 | Bug | IBP: Policy: Searched company resets on navigating from manage policy | Open | Akhila Gattu |  | IIRM-6827 — Manage Policy
4977 | IIRM-7783 | Bug | IBP:HospitalNetwork: TotalRecordsCount, Coverage and last updated details were missing | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4978 | IIRM-7784 | Bug | IBP: HospitalNetwork: File uploaded time mismatch on audit history view | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4979 | IIRM-7785 | Bug | IBP: HospitalNetwork: Search button color not matching to the design. | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4980 | IIRM-7786 | Bug | IBP: HospitalNetwork: Policy Breadcrumb missing from view hospital page | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4981 | IIRM-7787 | Task | CR: Create Tasks: Functionality and UI Changes | Done | Richa Bagchi Mazumdar |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
4982 | IIRM-7788 | Bug | IBP:HospitalNetwork: Auto refresh not happening if search string removed | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4983 | IIRM-7789 | Bug | IBP:HospitalNetwork: Validation error not matching with the spec for search results | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4984 | IIRM-7790 | Bug | IBP:HospitalNetwork: Invalid pincode validation not matching with spec | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4985 | IIRM-7791 | Bug | IBP: HospitalNetwork: Portal configuration tab not matches with spec | Done | Akhila Gattu | iWork | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4986 | IIRM-7792 | Task | My Follow up - Last Mile Clickability | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4987 | IIRM-7793 | Task | Brokerage To Collect - Last Mile Click-ability | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
4988 | IIRM-7794 | Bug | IBP: PolicyConfigure: On file inception error thrown as "Invalid choices are mapped to this employee for this policy. Please verify." with/ without parameters | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
4989 | IIRM-7795 | Sub-task | My Business Performance - Quarterly View - Last Mile Clickable | Done | Richa Bagchi Mazumdar |  | IIRM-6519 — Implement last-mile clickability for all relevant tables in the application.
4990 | IIRM-7796 | Sub-task | My Business Performance - Last Mile Clickable | Done | Richa Bagchi Mazumdar |  | IIRM-6519 — Implement last-mile clickability for all relevant tables in the application.
4991 | IIRM-7797 | Sub-task | Enable 3 Decimal Places in Policy Configuration Amount Fields | Done | NithinKrishna Sirigiri |  | IIRM-5577 — Policy Configuration
4992 | IIRM-7798 | Bug | IBP:HospitalNetwork: Search string count not matching with uploaded file | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4993 | IIRM-7799 | Bug | IBP:HospitalNetwork: First letter capital should get display on state and city | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4994 | IIRM-7800 | Bug | IBP:HospitalNetwork: On uploading bulk file, upload button CTA should get disabled until the file process should get completes | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4995 | IIRM-7801 | Bug | IBP:HospitalNetwork: On downloading source file message should be more clear | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4996 | IIRM-7802 | Bug | IBP: HospitalNetwork: Sorting functionality missing on view hospital page | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4997 | IIRM-7803 | Bug | Unable to update Policy Details - Showing internal server error | Done | Rama K |  | IIRM-6827 — Manage Policy
4998 | IIRM-7804 | Bug | IBP:HospitalNetwork: Records were not getting deleted and Replace error not showing if existing file got uploaded. | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
4999 | IIRM-7805 | Bug | IBP:HospitalNetwork: Search string is getting resets to default state on toggle change | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5000 | IIRM-7806 | Bug | IBP:FAQ: CTA not working on login page FAQ | On Hold | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5001 | IIRM-7807 | Bug | IBP:FAQ: Instead of PolicyID , Policy details needs to be shown in breadcrumb | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5002 | IIRM-7808 | Bug | IBP:FAQ: On bulk categories UI is not user friendly | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5003 | IIRM-7809 | Bug | IIRM: Tasks: “Assigned To” field should display all users in the organisation | Done | Leela Pakalapati | iWork
5004 | IIRM-7810 | Bug | IBP: FAQ: On category selection error thrown: property BILLING should not exist | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5005 | IIRM-7811 | Story | IIRM Holding - Users hierarchy | Done | NithinKrishna Sirigiri |  | IIRM-18 — SOW#1 - ACL & RBAC Control
5006 | IIRM-7812 | Bug | IBP:FAQ: On clicking All option , all category questions were not showing | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5007 | IIRM-7813 | Bug | IIRM: Tasks: Tasks created through Quick create bar are incorrectly displayed under Completed Tasks | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
5008 | IIRM-7814 | Bug | IBP:FAQ: First FAQ is getting expand and category change | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5009 | IIRM-7815 | Bug | IIRM: Task Update Not Working When Priority and Status Are Empty | Done | SaikumarMahanthi | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
5010 | IIRM-7816 | Bug | IBP:FAQ: Premium billing FAQ's were not fetching | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5011 | IIRM-7817 | Bug | IBP:FAQ: All FAQ's were not getting triggered in All tab | Done - Not Reproducible | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5012 | IIRM-7818 | Bug | IBP:HospitalNetwork: On clicking enter on search fields, Results were not getting fetch | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5013 | IIRM-7819 | Bug | IBP: PolicyConfigure: ContactsTab: Name is getting displayed instead of phonenumber | Done | Akhila Gattu |  | IIRM-6827 — Manage Policy
5014 | IIRM-7820 | Bug | IBP:FAQ: If same FAQ file got uploaded on group polices ( GPA, GMC, GTL), duplicate FAQ's showing | On Hold | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5015 | IIRM-7821 | Bug | IBP:FAQ: Auditlog missing on FAQ view all page | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5016 | IIRM-7822 | Bug | IIRM: Excluded Insurer Appearing Under Included Insurers on Brokering Slip | Done | SaikumarMahanthi | iWork
5017 | IIRM-7823 | Sub-task | Hide “Add to Existing” and “Replace All” Options When No Previous Uploads Exist (Hospital Network & FAQ) | Done | Jadhav Sai Prasad |  | IIRM-7591 — IBP: FAQs Management (CMS)
5018 | IIRM-7824 | Bug | IIRM: Inconsistency in My Follow-Up Drilldown Count | Ready for QA | SaikumarMahanthi | iWork
5019 | IIRM-7825 | Bug | IIRM: Bulk Edit Failing in Pre-Pod--> Internal server error during bulk edit execution | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
5020 | IIRM-7826 | Bug | IBP: HospitalNetwork: Complete address of the hospital needs to display in multiple lines | Done | Akhila Gattu | iWork | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5021 | IIRM-7827 | Bug | IBP:FAQ: Instead of showing popup, message should get display if FAQ's were not available | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5022 | IIRM-7828 | Bug | IIRM: Employees: Unable to update employee details | Done | Leela Pakalapati | iWork | IIRM-739 — SOW#12 - Manage Employees
5023 | IIRM-7829 | QAlity Test | IBP: ConstraintsCombinations: Verify employer contribution as off and custom declaration on Base policy enroll for PerFamily contribution | Draft | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5024 | IIRM-7830 | Bug | Issues in Approval Stage After Placement Slip Activity for Multi-Insurer / Co-Insurance Cases | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5025 | IIRM-7831 | Bug | coverage are not depicting in Marine Cargo Opportunity ¦ Opp. No.1175309 ¦ ¦ Apollo Coated Products. | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
5026 | IIRM-7832 | Bug | coverages are not available in CGL opportunity ¦ Opp. No.888435 ¦ Teamlease Services. | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
5027 | IIRM-7833 | Bug | GST Percentage Entered in Placement Slip Captured Incorrectly as Amount in Held Cover Note Stage | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
5028 | IIRM-7834 | Task | Localization field India GST should reflect in Service Tax field. | Done | Richa Bagchi Mazumdar |  | IIRM-764 — SOW#37 - Localisation
5029 | IIRM-7835 | Task | Placement Slip Generation: Make CD related field Required & Optional based on “Payment Type” | Done | Richa Bagchi Mazumdar |  | IIRM-756 — SOW#29 - Manage ISG Stages
5030 | IIRM-7836 | Bug | Service Tax field is populating with actual service tax value instead of % in policy details page | Reopen | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5031 | IIRM-7837 | Bug | While uploading inception data we observed Date format issue. In File the dates are as per provided template but during upload records are getting rejected | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5032 | IIRM-7838 | Bug | Amount fields like Gross Premium need to have decimals up to 2 digits only in inception/endorsement | Reopen | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5033 | IIRM-7839 | Bug | In Manage Policies screen, the system should allow searching by Policy Number/Insurer Policy Number. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5034 | IIRM-7840 | Bug | All premium fields across activities should support decimal up to 2 digits | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5035 | IIRM-7841 | Bug | After uploading TPA ID file, there is no summary of upload of TPA ID file | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5036 | IIRM-7842 | QAlity Test | IBP:HospitalNetwork: Verify that employee can access Hospital Network screen from dashboard | Draft | Akhila Gattu
5037 | IIRM-7843 | QAlity Test | IBP:HospitalNetwork: Verify that basic hospital search works with valid criteria | Draft | Akhila Gattu
5038 | IIRM-7844 | QAlity Test | IBP:HospitalNetwork: Verify admin can access Portal Configuration from Policy Details | Draft | Akhila Gattu
5039 | IIRM-7845 | QAlity Test | IBP:HospitalNetwork: Verify hospital search functionality using Pin Code filter | Draft | Akhila Gattu
5040 | IIRM-7846 | QAlity Test | IBP:HospitalNetwork: Verify keyword search filters hospital listing by name or address | Draft | Akhila Gattu
5041 | IIRM-7847 | QAlity Test | IBP:HospitalNetwork: Verify export functionality exports all search results to Excel | Draft | Akhila Gattu
5042 | IIRM-7848 | QAlity Test | IBP:HospitalNetwork: Verify navigation and functionality of Excluded Hospitals tab | Draft | Akhila Gattu
5043 | IIRM-7849 | QAlity Test | IBP:HospitalNetwork: Verify map navigation link opens hospital location in Google Maps | Draft | Akhila Gattu
5044 | IIRM-7850 | QAlity Test | IBP:HospitalNetwork: Verify admin can download hospital upload template | Draft | Akhila Gattu
5045 | IIRM-7851 | QAlity Test | IBP:HospitalNetwork: Verify successful upload of hospital data with valid template | Draft | Akhila Gattu
5046 | IIRM-7852 | QAlity Test | IBP:HospitalNetwork: Verify upload button behavior and configuration save functionality | Draft | Akhila Gattu
5047 | IIRM-7853 | QAlity Test | IBP:HospitalNetwork: Verify transaction history shows upload history and allows download | Draft | Akhila Gattu
5048 | IIRM-7854 | QAlity Test | IBP:HospitalNetwork: Verify delete functionality with option to add to excluded list | Draft | Akhila Gattu
5049 | IIRM-7855 | QAlity Test | IBP:HospitalNetwork: Verify system handles invalid pin code entries correctly | Draft | Akhila Gattu
5050 | IIRM-7856 | QAlity Test | IBP:HospitalNetwork: Verify appropriate message when no hospitals match search criteria | Draft | Akhila Gattu
5051 | IIRM-7857 | QAlity Test | IBP:HospitalNetwork: Verify system validates all mandatory fields during upload | Draft | Akhila Gattu
5052 | IIRM-7858 | QAlity Test | IBP:HospitalNetwork: Verify system prevents duplicate hospital entries | Draft | Akhila Gattu
5053 | IIRM-7859 | QAlity Test | IBP:HospitalNetwork: Verify system validates file format and template structure | Draft | Akhila Gattu
5054 | IIRM-7860 | QAlity Test | IBP:HospitalNetwork: Verify hospital data syncs from CRM to Employee Enrolment Portal after save | Draft | Akhila Gattu
5055 | IIRM-7861 | QAlity Test | IBP:HospitalNetwork: Verify updates and Replace all in CRM reflect correctly in Employee Portal | Draft | Akhila Gattu
5056 | IIRM-7862 | QAlity Test | IBP:HospitalNetwork: Verify all search functionality works correctly after system updates | Draft | Akhila Gattu
5057 | IIRM-7863 | QAlity Test | IBP:HospitalNetwork: Verify hospital data upload functionality works after system updates | Draft | Akhila Gattu
5058 | IIRM-7864 | Bug | IIRM: Bulk Assign: Incorrect notification behavior during ownership assignment | Done | Leela Pakalapati | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
5059 | IIRM-7865 | QAlity Test | IBP:FAQ: Validate that FAQ hyperlink is properly placed near Login CTA and opens FAQ screen correctly | Draft | Akhila Gattu
5060 | IIRM-7866 | QAlity Test | IBP:FAQ: Validate that FAQs are displayed category-wise in collapsible accordion layout | Draft | Akhila Gattu
5061 | IIRM-7867 | QAlity Test | IBP:FAQ: Validate that employee sees only FAQs associated with their specific policy | Draft | Akhila Gattu
5062 | IIRM-7868 | QAlity Test | IBP:FAQ: Validate appropriate message display when no FAQs are configured for employee's policy | Draft | Akhila Gattu
5063 | IIRM-7869 | QAlity Test | IBP:FAQ: Validate error message display when FAQ data cannot be loaded due to sync failure | Draft | Akhila Gattu
5064 | IIRM-7870 | QAlity Test | IBP:FAQ: Validate navigation to FAQ Upload tab from Policy Details screen | Draft | Akhila Gattu
5065 | IIRM-7871 | QAlity Test | IBP:FAQ: Validate download and structure of FAQ upload Excel template | Draft | Akhila Gattu
5066 | IIRM-7872 | QAlity Test | IBP:FAQ: Validate complete bulk upload process with valid FAQ data | Draft | Akhila Gattu
5067 | IIRM-7873 | QAlity Test | IBP:FAQ: Validate upload preview and error handling with partial invalid data | Draft | Akhila Gattu
5068 | IIRM-7874 | QAlity Test | IBP:FAQ: Validate system's ability to detect and handle duplicate FAQs | Draft | Akhila Gattu
5069 | IIRM-7875 | QAlity Test | IBP:FAQ: Validate manual FAQ addition functionality via Add FAQ button | Draft | Akhila Gattu
5070 | IIRM-7876 | QAlity Test | IBP:FAQ: Validate FAQ deletion process with proper confirmation and audit logging | Draft | Akhila Gattu
5071 | IIRM-7877 | QAlity Test | IBP:FAQ: Validate upload tracker section displays correct history and allows file downloads | Draft | Akhila Gattu
5072 | IIRM-7878 | QAlity Test | IBP:FAQ: Validate all mandatory field validation messages during upload | Draft | Akhila Gattu
5073 | IIRM-7879 | QAlity Test | IBP:FAQ: Validate file format restrictions and template structure requirements | Draft | Akhila Gattu
5074 | IIRM-7880 | QAlity Test | IBP:FAQ: Validate Policy ID format and existence in system | Draft | Akhila Gattu
5075 | IIRM-7881 | QAlity Test | IBP:FAQ: Validate that FAQ changes in CRM sync to Employee Portal correctly | Draft | Akhila Gattu
5076 | IIRM-7882 | QAlity Test | IBP:FAQ: Validate that deleted FAQs in CRM are removed from Employee Portal | Draft | Akhila Gattu
5077 | IIRM-7883 | QAlity Test | IBP:FAQ: Validate that bulk FAQ replacement in CRM replaces all FAQs in Employee Portal | Draft | Akhila Gattu
5078 | IIRM-7884 | QAlity Test | IBP:FAQ: Validate that only authorized CRM users can access FAQ management features | Draft | Akhila Gattu
5079 | IIRM-7885 | QAlity Test | IBP:FAQ: Validate system performance when handling large numbers of FAQs | Draft | Akhila Gattu
5080 | IIRM-7886 | QAlity Test | IBP:FAQ: Validate FAQ feature works correctly on mobile devices and tablets | Draft | Akhila Gattu
5081 | IIRM-7887 | QAlity Test | IBP:FAQ: Validate FAQ feature works consistently across major browsers | Draft | Akhila Gattu
5082 | IIRM-7888 | Bug | IBP: Inception: Date format validation missing in step 3 on inception/Endorsement process | Ready for QA | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5083 | IIRM-7889 | Task | IIRM: Verify Bulk Assgement Functionality | Done | SaikumarMahanthi | iWork
5084 | IIRM-7890 | Task | IIRM: Verify Ready for QA issues and Regression checking | Done | SaikumarMahanthi | iWork
5085 | IIRM-7891 | Task | IIRM: UAT and Pre-pod Sanity Checking | Done | SaikumarMahanthi | iWork
5086 | IIRM-7892 | Task | IIRM: NEW CRs testing and Regression testing | Done | SaikumarMahanthi | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
5087 | IIRM-7893 | Bug | IBP:HospitalNetwork: Text should get changed to HospitalNetwork. | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5088 | IIRM-7894 | Bug | IBP: FAQ: Questions count not showing after file upload | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5089 | IIRM-7895 | Bug | IBP: FAQ: Empty FAQ file upload should get restricted | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5090 | IIRM-7896 | Bug | IBP:FAQ: For empty file upload popup should be same as API failed status message. | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5091 | IIRM-7897 | Bug | IBP:HospitalNetwork: Error thrown on clicking pagination ellipses | QA in Progress | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5092 | IIRM-7898 | Bug | IIRM: Contacts:Filters: City filter is not appearing in the Applied Filters section on the My Contacts page | Done - Not Reproducible | PATIBANDLA VELANGINI RAJU | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
5093 | IIRM-7899 | Sub-task | Export Capability | Draft | Jadhav Sai Prasad |  | IIRM-7591 — IBP: FAQs Management (CMS)
5094 | IIRM-7900 | Bug | IIRM: Auto-Population – Preferred Insurer List Order Is Not Retained | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5095 | IIRM-7901 | Story | IIRM: Auto-Population: Preferred Insurer selection should be excluded from Insurers dropdown in Excluded Insurer section | Ready for QA | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5096 | IIRM-7902 | Bug | Service Tax Not Reflecting Post Upload for Policy Inception – GPA TeamLease Skills University (Policy ID: 527389) | Done | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
5097 | IIRM-7903 | Bug | IIRM: Auto-Population: Select Insurer Location field not auto-populated for the selected insurer | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5098 | IIRM-7904 | Bug | Deadlock issue in the service tat scheduler | Done | Richa Bagchi Mazumdar |  | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
5099 | IIRM-7905 | Bug | IIRM: Auto-Population: Brokerage Percentage and Amount field issues in Final Negotiation activity | Reopen | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5100 | IIRM-7906 | Bug | Selected Row Highlight Not Retained When Navigating Back to First Page | Ready for QA | Jadhav Sai Prasad |  | IIRM-6597 — UAT Bugs
5101 | IIRM-7907 | Bug | IIRM: Insurer details are not auto-populated for the selected Co-Insurer | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5102 | IIRM-7908 | Task | Update Toggle Placement and Styling for SO/RO Switch - "My Follow up Widget" | Done | Jadhav Sai Prasad |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
5103 | IIRM-7909 | Bug | Business performance - Breakup - Filter Persistance - Both Overall & Quaterly | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
5104 | IIRM-7910 | Bug | Brokerage collection and My Follow up - Back has to Navigate to respective table | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
5105 | IIRM-7911 | Bug | My Follow Up - Change Position and Style | Done | Richa Bagchi Mazumdar |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
5106 | IIRM-7912 | Bug | Biz Done Report - Add Insurer Filter | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
5107 | IIRM-7913 | Bug | Browser - Mozilla Firefox - Whole application compatibility | Done - Not Reproducible | Richa Bagchi Mazumdar |  | IIRM-64 — SOW#3 - Micro Service Framework
5108 | IIRM-7914 | Bug | If ASSIGNMENTS tab is only for ISG, let it appear only for those roles. NOT FOR ALL. | On Hold | Richa Bagchi Mazumdar |  | IIRM-18 — SOW#1 - ACL & RBAC Control
5109 | IIRM-7916 | Bug | Opportunities Not Visible in Approval Bucket & Unable to Approve from Held Cover Note Activity | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5110 | IIRM-7917 | Bug | Covers Not Available in Marine Sales Turnover Policy Opportunity in New iWork | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5111 | IIRM-7918 | Bug | Premium calculation Issue : Policy ID - POLICY ID 405351 | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5112 | IIRM-7919 | Bug | Error File Not Generated After Failed Inception Upload — Policy ID 526388 | Done | Jadhav Sai Prasad |  | IIRM-797 — SOW#69 - Manage Opportunities
5113 | IIRM-7920 | Bug | Policy Not Activating After Approval — Policy ID 521453 | Done | Jadhav Sai Prasad |  | IIRM-797 — SOW#69 - Manage Opportunities
5114 | IIRM-7921 | Bug | PROD: Incorrect Status Displayed for Error Records on Inception Upload — Policy ID 526819 | Done | Jadhav Sai Prasad |  | IIRM-797 — SOW#69 - Manage Opportunities
5115 | IIRM-7922 | Bug | Unable to Submit Held Cover Note — Error Prompt Despite All Details Filled (Opp. 1042886 & 1042888) | Done | Jadhav Sai Prasad |  | IIRM-797 — SOW#69 - Manage Opportunities
5116 | IIRM-7923 | Bug | Premium not updated on dashboard after member upload (4359 members) | Done | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5117 | IIRM-7924 | Bug | IIRM: Covers: Incorrect spellings are displayed across multiple covers | Open | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5118 | IIRM-7925 | Sub-task | Make all numeric values clickable in the "Business performance - Breakup" table except Percentages (%) | Done | NithinKrishna Sirigiri |  | IIRM-6519 — Implement last-mile clickability for all relevant tables in the application.
5119 | IIRM-7926 | Bug | IIRM: RFP Details Data Not Retrieved After Manager Rejects the Activity | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5120 | IIRM-7927 | Bug | IIRM: Auto-Population: Sri Lanka: Enter Quote: Screen becomes unresponsive when entering data in the Brokerage Percentage fields | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5121 | IIRM-7928 | Bug | Dual policy type names incorrectly clubbed under Opportunity No. 1175326 | Open | Jadhav Sai Prasad |  | IIRM-756 — SOW#29 - Manage ISG Stages
5122 | IIRM-7929 | Bug | Multiple Issues Identified Across Opportunities – Policy Types, Deviation Updates, Covers & Assignment | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5123 | IIRM-7930 | Bug | Incorrect activity ownership and team assignment for Won Opportunity – GTL (Opp. No. 1175351) | Done | Jadhav Sai Prasad |  | IIRM-756 — SOW#29 - Manage ISG Stages
5124 | IIRM-7931 | Story | IBP: My Documents - Policy feature | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5125 | IIRM-7932 | QAlity Test | IBP: Constraints: Verify combination of children and partner for base policy enroll | In Progress | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5126 | IIRM-7933 | Sub-task | Create new components for placement slip (Front END) | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
5127 | IIRM-7934 | Sub-task | For co-insurers LOV show list of all the active insureres | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
5128 | IIRM-7935 | Sub-task | Create new components for final negotiation (Front END) | Done | Richa Bagchi Mazumdar |  | IIRM-7616 — Auto-Populate: Record Insurer and Co-Insurer Details
5129 | IIRM-7936 | Task | Add a label to GST% and GST Amount in Manage Policy -> Policy Details tab | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
5130 | IIRM-7937 | Bug | IBP: PolicyConfigure: Error thrown for same employee Data on different GMC's of same company | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5131 | IIRM-7938 | Bug | IIRM: Preferred Insurer Not Updated Correctly in RFP Details Entry Activity | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5132 | IIRM-7939 | Bug | IIRM: Insurer Contact ID Displayed Instead of Insurer contact Name | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5133 | IIRM-7940 | Bug | IBP: Inception: Employee records got failed, even if valid data provided on bulk file upload | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5134 | IIRM-7941 | Bug | 337819-Application Error - Duplicate Employee-Mapping & GST Update | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5135 | IIRM-7942 | Bug | 405350 Application Error - 1763 uploaded but 4 records count is missing from the dashboard | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5136 | IIRM-7943 | Bug | 521453 Application Error - 2 records successfully uploaded and are missing in the dashboard stats employee count and premiums | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5137 | IIRM-7944 | Bug | 331354 Application Error - Approvals need to be rolled back | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5138 | IIRM-7945 | Bug | 526388 Application Error - Company employee already exists (duplicate id/email/phone) and some random email ids created by system for the blank email cells. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5139 | IIRM-7946 | Bug | 337820 Application Error - Duplicate employee-policy mapping and random email ids created by system | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5140 | IIRM-7947 | Bug | 337823 Application Error - Duplicate employee-policy mapping and random email ids created by system | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5141 | IIRM-7948 | Bug | 521451 Application Error - Duplicate employee-policy mapping and random email ids created by system | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5142 | IIRM-7949 | Bug | 548663 Application Error - Employee count and premiums are not matching | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5143 | IIRM-7950 | Bug | 332657 Application Error - Need confirmation on premium reflection post configuration amendment | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5144 | IIRM-7951 | Bug | 405351 Application Error - Premium is not reflecting correctly post configuration correction. - Data need to be deleted from backend | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5145 | IIRM-7952 | Bug | 329116 Errors escalated to IT 11/14/2025 Date format, Employee ID not found for dependents, Employee id mismatch | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5146 | IIRM-7953 | Bug | 337818 Application Error - Duplicate employee-policy mapping | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5147 | IIRM-7954 | Bug | IIRM: Opportunity page is fullly displayed after approal and rejected cases | Open | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5148 | IIRM-7955 | Bug | IIRM: Auto-Population: Share Percentage field is not accepting the value 100 in final negotiation activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5149 | IIRM-7956 | Bug | IIRM: Auto-Population: Lanka: Brokerage Percentage and Amount fields should not be displayed | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5150 | IIRM-7957 | Sub-task | BA: Write Product Specs | Done | NithinKrishna Sirigiri |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5151 | IIRM-7958 | Sub-task | QA: Write Test Cases | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5152 | IIRM-7959 | Sub-task | TL: Write Technical Specs | Done | NithinKrishna Sirigiri |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5153 | IIRM-7960 | Bug | IIRM: Saved Filters Not Working on Dashboard Screen | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
5154 | IIRM-7961 | Bug | IIRM: ISG Planning: Incorrect text displayed in ISG Planning screen | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5155 | IIRM-7962 | Bug | IRM: "Failed Brokerage Summary" Error When Changing Hierarchy in Dashboard Filter | Ready for QA | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5156 | IIRM-7963 | Bug | IIRM: Remove the empty links on Business performance - Breakup | Open | SaikumarMahanthi |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
5157 | IIRM-7964 | Bug | IIRM: Auto-Population: Issues in "Insurers share % and Brokerage % details" section in Placement Slip activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5158 | IIRM-7965 | Bug | IIRM: Auto-Population: "Insurers share % and Brokerage % details" functionality not working as expected after submitting activity for approval in Placement Slip Activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5159 | IIRM-7966 | Bug | IIRM: Auto-Population: Lead Insurer missing and fields not resetting when Policy Placed Type is changed from Multiple to Single | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5160 | IIRM-7967 | Bug | The number of records processed is having gap with total records uploaded | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5161 | IIRM-7968 | Bug | IIRM: RFP Details Entry: Unable to complete the activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5162 | IIRM-7969 | Bug | Premium Calculation issue: Vyyomik Innovations | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5163 | IIRM-7970 | Sub-task | TASK-A001: Database schema and migration setup | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5164 | IIRM-7971 | Sub-task | TASK-A002: Policy feature repository implementation | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5165 | IIRM-7972 | Sub-task | TASK-A003: Policy feature service layer and DTOs | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5166 | IIRM-7973 | Sub-task | TASK-A004: REST API endpoints and controller | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5167 | IIRM-7974 | Sub-task | TASK-A005: Module configuration and service integration | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5168 | IIRM-7975 | Sub-task | TASK-B001: Admin portal types and API service | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5169 | IIRM-7976 | Sub-task | TASK-B002: Upload policy features card component | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5170 | IIRM-7977 | Sub-task | TASK-B003: Policy feature document viewer component | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5171 | IIRM-7978 | Sub-task | TASK-B004: Portal configuration integration | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5172 | IIRM-7979 | Sub-task | TASK-C001: Employee portal types and API service | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5173 | IIRM-7980 | Sub-task | TASK-C002: Policy features dashboard button | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5174 | IIRM-7981 | Sub-task | TASK-C003: Documents screen with tabbed interface | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5175 | IIRM-7982 | Sub-task | TASK-C004: Multi-policy support and document loading | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5176 | IIRM-7983 | Sub-task | TASK-C005: Employee portal routing and integration | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5177 | IIRM-7984 | Sub-task | TASK-D001: Backend API comprehensive testing | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5178 | IIRM-7985 | Sub-task | TASK-D002: Frontend component testing | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5179 | IIRM-7986 | Sub-task | TASK-D003: Cross-service integration validation | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5180 | IIRM-7987 | Sub-task | TASK-D004: Performance testing and optimization | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5181 | IIRM-7988 | Sub-task | TASK-D005: Documentation and deployment preparation | Done | Richa Bagchi Mazumdar |  | IIRM-7931 — IBP: My Documents - Policy feature
5182 | IIRM-7989 | Story | Data Clean-up (PRODUCTION) | Draft | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
5183 | IIRM-7990 | Sub-task | PROD Task: Delete Test/Dummy Transaction (From Company to last trnx.) | Draft | NithinKrishna Sirigiri |  | IIRM-7989 — Data Clean-up (PRODUCTION)
5184 | IIRM-7991 | Bug | IIRM: Auto-Population: Sri Lanka: Unable to Complete the Placement Slip Generation Activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5185 | IIRM-7992 | Sub-task | BA: Write Product Specs | Done | NithinKrishna Sirigiri |  | IIRM-4849 — Save Activity - Proper Implementation
5186 | IIRM-7993 | Sub-task | BA: Write Product Specs | Done | NithinKrishna Sirigiri |  | IIRM-4973 — Policy View: New Tab: Add “Policy Document” as an additional tab
5187 | IIRM-7994 | Sub-task | BA: Write Product Specs | Done | NithinKrishna Sirigiri |  | IIRM-4975 — Instalment Reminders (Email): For Policy owners for each instalment
5188 | IIRM-7995 | Sub-task | BA: Write Product Specs | Draft | NithinKrishna Sirigiri |  | IIRM-5292 — Opportunity History details are unavailable for the end user to view.
5189 | IIRM-7996 | Sub-task | BA: Write Product Specs | Done | NithinKrishna Sirigiri |  | IIRM-7042 — Sync Policy fields to SO/RO Stages
5190 | IIRM-7997 | Sub-task | BA: Write Product Specs | Done | NithinKrishna Sirigiri |  | IIRM-7931 — IBP: My Documents - Policy feature
5191 | IIRM-7998 | Sub-task | Build the function to derive the form config based on the organisation | Done | Pampana Ravi Kiran |  | IIRM-7639 — Localization Frame Work (Pending Items)
5192 | IIRM-7999 | Sub-task | Build the config items that are removed, replaced and newly added to the existing configs | Done | Pampana Ravi Kiran |  | IIRM-7639 — Localization Frame Work (Pending Items)
5193 | IIRM-8000 | Sub-task | Adjsut the form config to each activity based on the organisation key | Done | Pampana Ravi Kiran |  | IIRM-7639 — Localization Frame Work (Pending Items)
5194 | IIRM-8001 | Bug | Inception - handle the Sub group matches from configurator while processing Inception | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5195 | IIRM-8002 | Bug | IIRM: Failed to Retrieve Opportunities Error When Clearing and Saving Active Filters | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5196 | IIRM-8003 | Bug | IRM: Page Becomes Unresponsive When Selecting Insurer Location in Meeting for Final Negotiation | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5197 | IIRM-8004 | Task | Enable Decimals in Amount Fields & Apply VAT% on All Components | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5198 | IIRM-8005 | Sub-task | BA: Write Product Specs | Done | NithinKrishna Sirigiri |  | IIRM-8006 — Create Task: Link to Opportunity - Show Company, Opportunity & Activities
5199 | IIRM-8006 | Story | Create Task: Link to Opportunity - Show Company, Opportunity & Activities | Done | NithinKrishna Sirigiri |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
5200 | IIRM-8007 | Bug | From now, the order of self first followed by dependent is not mandatory , dependent can come before the self in this updated flow | QA in Progress | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5201 | IIRM-8008 | Bug | During the endorsements, we can add dependent alone for employees (Self) who got already enrolled during the inception. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5202 | IIRM-8009 | Bug | IBP: Inception: Some thing went wrong screen shown on inception upload | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5203 | IIRM-8010 | Task | Change the status of Policies from Active to Generated so that policy can be activated | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5204 | IIRM-8011 | Sub-task | BA: Product Specs | Done | Jadhav Sai Prasad |  | IIRM-8004 — Enable Decimals in Amount Fields & Apply VAT% on All Components
5205 | IIRM-8012 | Task | Premiums change request - 529794 | Open | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5206 | IIRM-8013 | Bug | IIRM: Without reload aprove/reject buttons are not dispayed for approved | Done | SaikumarMahanthi | iWork | IIRM-752 — SOW#25 - Manage iWork Stages (BD)
5207 | IIRM-8015 | Story | Implement DPDP Act 2023 & DPDP Rules 2025 Compliance Framework | Draft | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
5208 | IIRM-8016 | Sub-task | India: Update new fields in the Biz Done report | Done | NithinKrishna Sirigiri |  | IIRM-5441 — Biz Done Reports
5209 | IIRM-8017 | Sub-task | Sri Lanka: Update new field in Biz Done report. Delete India fields | Done | NithinKrishna Sirigiri |  | IIRM-5441 — Biz Done Reports
5210 | IIRM-8018 | Bug | IIRM: Activity Not Loading or Updating Properly Without Page Reload | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5211 | IIRM-8019 | Bug | IIRM: Brokerage Percentage Decimals Rounding Mismatch Between Held Cover Note & Placement Slip | Done | SaikumarMahanthi | iWork
5212 | IIRM-8020 | Sub-task | API changes Save activity for the Data validation, Kdm Meeting, Mandate | Done | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5213 | IIRM-8021 | Sub-task | UI - implementation Save activity for the Data validation, Kdm Meeting, Mandate | Done | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5214 | IIRM-8022 | Sub-task | API changes Save activity for the Rfp cover, Rfp Details, QCR, premium Calculations | PENDING PEER or LEAD REVIEW | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5215 | IIRM-8023 | Sub-task | UI - implementation Save activity for the Rfp cover, Rfp Details, QCR, premium Calculations | Done | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5216 | IIRM-8024 | Sub-task | API changes Save activity for the Held Cover note, policy hard copy, policy confirmation, policy docket | Done | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5217 | IIRM-8025 | Sub-task | UI - implementation changes Save activity for the Held Cover note, policy hard copy, policy confirmation, policy docket | Done | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5218 | IIRM-8026 | Sub-task | API changes Save activity for the Broking Slip/ Quote Entry | PENDING PEER or LEAD REVIEW | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5219 | IIRM-8027 | Sub-task | UI - implementation changes Save activity for the Broking Slip/ Quote Entry | PENDING PEER or LEAD REVIEW | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5220 | IIRM-8028 | Sub-task | API changes Save activity for the Final negoatiation/placement slip | Done | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5221 | IIRM-8029 | Sub-task | UI -implementation changes Save activity for the Final negotiation/placement slip | PENDING PEER or LEAD REVIEW | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5222 | IIRM-8030 | Sub-task | API changes Save activity for the Hand over meet and bug fixes | PENDING PEER or LEAD REVIEW | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5223 | IIRM-8031 | Sub-task | UI - implementation changes Save activity for the Hand over meet and bug fixes | Done | VedaVyas |  | IIRM-4849 — Save Activity - Proper Implementation
5224 | IIRM-8032 | Bug | Premium calculation issue - 526387 | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5225 | IIRM-8033 | Sub-task | Front end for the change | PENDING PEER or LEAD REVIEW | Richa Bagchi Mazumdar |  | IIRM-7835 — Placement Slip Generation: Make CD related field Required & Optional based on “Payment Type”
5226 | IIRM-8034 | Sub-task | BA: Review Test Cases | Done | NithinKrishna Sirigiri |  | IIRM-7931 — IBP: My Documents - Policy feature
5227 | IIRM-8035 | Sub-task | QA: Executing Test Cases | Done | NithinKrishna Sirigiri |  | IIRM-7931 — IBP: My Documents - Policy feature
5228 | IIRM-8036 | Story | IBP: Contact Matrix | Draft | Richa Bagchi Mazumdar |  | IIRM-773 — SOW#46 - Enrolment Portal
5229 | IIRM-8037 | Sub-task | BA Write Product Specs | Done | Richa Bagchi Mazumdar |  | IIRM-8036 — IBP: Contact Matrix
5230 | IIRM-8038 | Bug | IIRM: “Something Went Wrong” Screen Appears When Resetting Filters in SO/RO Screens | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5231 | IIRM-8039 | Task | Approve and Activate the configuration update in DB brokerage as 7.5 | Done | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
5232 | IIRM-8040 | Bug | IBP: Endorsement: Duplicate error entries generated for a single uploaded record | QA in Progress | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5233 | IIRM-8041 | Task | Biz Done Report: Display Records for Both Lead and Co-Insurers in "Insurer" Filter | Done | Richa Bagchi Mazumdar |  | IIRM-778 — SOW#51 - Admin Reports
5234 | IIRM-8042 | Story | Build and Stabilize Core Framework Components Across IIRM and Other Generic Projects | Draft | Richa Bagchi Mazumdar |  | IIRM-775 — SOW#48 - Whitelabelling
5235 | IIRM-8043 | Sub-task | External API Access Management Framework | Draft | Richa Bagchi Mazumdar |  | IIRM-8042 — Build and Stabilize Core Framework Components Across IIRM and Other Generic Projects
5236 | IIRM-8044 | Sub-task | JWT Library Development | Draft | Richa Bagchi Mazumdar |  | IIRM-8042 — Build and Stabilize Core Framework Components Across IIRM and Other Generic Projects
5237 | IIRM-8045 | Sub-task | ACL (Access Control List) Library Development | Draft | Richa Bagchi Mazumdar |  | IIRM-8042 — Build and Stabilize Core Framework Components Across IIRM and Other Generic Projects
5238 | IIRM-8046 | Sub-task | Payment Gateway Integration Library | Draft | Richa Bagchi Mazumdar |  | IIRM-8042 — Build and Stabilize Core Framework Components Across IIRM and Other Generic Projects
5239 | IIRM-8047 | Sub-task | ORM-based Database Script Management (TypeORM Migrations) | Draft | Richa Bagchi Mazumdar |  | IIRM-8042 — Build and Stabilize Core Framework Components Across IIRM and Other Generic Projects
5240 | IIRM-8048 | Sub-task | Stabilization of IIRM Frameworks | Draft | Richa Bagchi Mazumdar |  | IIRM-8042 — Build and Stabilize Core Framework Components Across IIRM and Other Generic Projects
5241 | IIRM-8049 | Bug | PolicyFeature: Document uplaoded should be there instead of uploaded | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5242 | IIRM-8050 | Bug | PolicyFeature: "Policy features document replaced successfully" should be shown on document replace | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5243 | IIRM-8051 | Bug | PolicyFeature: On document download retrieved message should not be shown. | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5244 | IIRM-8052 | Bug | PolicyFeature: Document appears blurry in view state but downloads as clear PDF | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5245 | IIRM-8053 | Bug | PolicyFeature: Close button missing on my documents as per spec | On Hold | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5246 | IIRM-8054 | Bug | PolicyFeature: Instead of policy details, Policy dashboard should be shown on breadcrumb | Done - Not a Bug | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5247 | IIRM-8055 | Bug | PolicyFeature: Unable to view text from Uploaded PDF | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5248 | IIRM-8056 | Task | Label change from Share Percentage to Premium share percentage | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5249 | IIRM-8057 | Sub-task | DB: One time activity to update TPA contacts | Open | Richa Bagchi Mazumdar |  | IIRM-8036 — IBP: Contact Matrix
5250 | IIRM-8058 | Story | IBP: Portal Preferences - Company (Admin Module) | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-773 — SOW#46 - Enrolment Portal
5251 | IIRM-8059 | Story | IBP: Portal Configurator - Policy (Admin Module) | Draft | Richa Bagchi Mazumdar |  | IIRM-773 — SOW#46 - Enrolment Portal
5252 | IIRM-8060 | Bug | Iwork: SO Activities: RFD Details Entry "Submit for approval" error thrown. | Done | PATIBANDLA VELANGINI RAJU | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5253 | IIRM-8061 | Bug | PolicyFeature: While document is under upload process, Choose file option should be disabale state | Done | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5254 | IIRM-8062 | Bug | PolicyFeature: For 25MB file uplaod it is taking 27.83 sec , it should be less than 20 sec | On Hold | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5255 | IIRM-8063 | Story | <Place Holder> Use it. | Draft | NithinKrishna Sirigiri
5256 | IIRM-8064 | Story | Nudges & Insights (AI - iWork Productivity) | Done | NithinKrishna Sirigiri |  | IIRM-789 — SOW#62 - AI Chatbot
5257 | IIRM-8065 | Task | IIRM: Ready for QA issues Testing and Regression Checking | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5258 | IIRM-8066 | Story | AI Chatbot (Release-1) | Done | NithinKrishna Sirigiri |  | IIRM-789 — SOW#62 - AI Chatbot
5259 | IIRM-8067 | Task | IIRM: Auto Papulate Testing in UAT and Ready for QA issues verification | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5260 | IIRM-8068 | Task | IIRM: Production Bocklog and new CR Testing | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5261 | IIRM-8069 | Task | IIRM: Srillanka Locatiozaton testing on activites | Done | SaikumarMahanthi
5262 | IIRM-8070 | Bug | IIRM: SO Activities: Broking Slip Generation: Error - "Failed to Save Version" | Done | Prathiphala Kandula |  | IIRM-797 — SOW#69 - Manage Opportunities
5263 | IIRM-8071 | Bug | Discrepancy in Uploaded vs. Picked Records in Module | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5264 | IIRM-8072 | Story | <Place Holder> Please use it. | Draft | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5265 | IIRM-8073 | Bug | IBP: Dashboard Page – Policy expiry date not fetched in Enrollment Window card & in Compulsory Benefits card on My Insurance page | Open | PATIBANDLA VELANGINI RAJU | IBP | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5266 | IIRM-8074 | Task | Create New Policy Type: Marine cum Erection Policy (MCE) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5267 | IIRM-8075 | Sub-task | Create Task: Show Link to Opportunity section | Done | NithinKrishna Sirigiri |  | IIRM-8006 — Create Task: Link to Opportunity - Show Company, Opportunity & Activities
5268 | IIRM-8076 | Story | IBP: Support Request | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
5269 | IIRM-8077 | Story | IBP: Schedule Callback | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
5270 | IIRM-8078 | Story | IBP: Enrolment Status | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
5271 | IIRM-8079 | Sub-task | Write Story | Draft | Jadhav Sai Prasad |  | IIRM-8076 — IBP: Support Request
5272 | IIRM-8080 | Sub-task | Write Product Specs | Draft | Jadhav Sai Prasad |  | IIRM-8077 — IBP: Schedule Callback
5273 | IIRM-8081 | Sub-task | Write Product Specs | Draft | Jadhav Sai Prasad |  | IIRM-8078 — IBP: Enrolment Status
5274 | IIRM-8082 | Bug | The TPA ID Upload functionality requires improvements to handle file validation, error visibility, and product-specific field requirements. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5275 | IIRM-8083 | Bug | IBP: Inception/Endorsement: Next button should be in disable state if file status is in Complete state | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5276 | IIRM-8084 | Bug | IIRM: Save Activity: Incorrect Toast Message Displayed When Activity Is Saved | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5277 | IIRM-8085 | Bug | IIRM: Save Activity: Data Validation: Save Activity Button behaviour Not Working as Expected | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5278 | IIRM-8086 | Bug | IIRM: Save Activity: Uploaded Document Not Visible in Documents Tab | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5279 | IIRM-8087 | Bug | IIRM: Save Activity: Able to Save the Activity with Invalid Data | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5280 | IIRM-8088 | Task | IIRM: Verify Ready for QA issues and Regression Testing | Done | SaikumarMahanthi | iWork
5281 | IIRM-8089 | Task | IIRM: Auto Papulate Testing in UAT for Srilanka Localization | Done | SaikumarMahanthi
5282 | IIRM-8090 | Task | IIRM: NEW CRs testing and Production Backlog testing | Done | SaikumarMahanthi
5283 | IIRM-8091 | Task | IIRM: SO And RO Activites Regression Testing | Done | SaikumarMahanthi
5284 | IIRM-8092 | Task | CR: Update GPA/GTL Upload Rules & Enable Failed Record Visibility | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5285 | IIRM-8093 | Bug | IIRM: Save Activity: RFP Details Entry: Not able to Save the Activity without Mandate Details | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5286 | IIRM-8094 | Sub-task | TASK-A001: Setup Claims module structure in IBP service | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5287 | IIRM-8095 | Sub-task | TASK-A002: Create database views for claims aggregation | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5288 | IIRM-8096 | Sub-task | TASK-A003: Implement Claims Controller API endpoints | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5289 | IIRM-8097 | Sub-task | TASK-A004: Implement Claims Service business logic | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5290 | IIRM-8098 | Sub-task | TASK-B001: Enhance existing ClaimSummary component | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5291 | IIRM-8099 | Sub-task | TASK-B002: Add Claims Corner navigation and routing | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5292 | IIRM-8100 | Sub-task | TASK-B003: Create Claims Corner page component | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5293 | IIRM-8101 | Sub-task | TASK-C001: Implement API integration and data flow | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5294 | IIRM-8102 | QAlity Test | IBP:PolicyFeature: Upload Policy Feature Document (Happy Path) | Draft | Akhila Gattu
5295 | IIRM-8103 | QAlity Test | IBP:PolicyFeature: Upload Document - File Size Exceeds Limit | Draft | Akhila Gattu
5296 | IIRM-8104 | QAlity Test | IBP:PolicyFeature: Upload Document - Invalid File Format | Draft | Akhila Gattu
5297 | IIRM-8105 | QAlity Test | IBP:PolicyFeature: Upload Document - Filename with Special Characters | Draft | Akhila Gattu
5298 | IIRM-8106 | QAlity Test | IBP:PolicyFeature: View Upload Modal Elements | Draft | Akhila Gattu
5299 | IIRM-8107 | QAlity Test | IBP:PolicyFeature: Upload Document - Empty File | Draft | Akhila Gattu
5300 | IIRM-8108 | QAlity Test | IBP:PolicyFeature: Replace Existing Document (Happy Path) | Draft | Akhila Gattu
5301 | IIRM-8109 | QAlity Test | IBP:PolicyFeature: Replace Document - Cancel Confirmation | Draft | Akhila Gattu
5302 | IIRM-8110 | QAlity Test | IBP:PolicyFeature: Replace Document - Upload History Tracking | Draft | Akhila Gattu
5303 | IIRM-8111 | QAlity Test | IBP:PolicyFeature: Multiple Document Replacements | Draft | Akhila Gattu
5304 | IIRM-8112 | QAlity Test | IBP:PolicyFeature: View Uploaded Document | Draft | Akhila Gattu
5305 | IIRM-8113 | QAlity Test | IBP:PolicyFeature: View CTA Disabled State | Draft | Akhila Gattu
5306 | IIRM-8114 | QAlity Test | IBP:PolicyFeature: Download Document from Viewer | Draft | Akhila Gattu
5307 | IIRM-8115 | QAlity Test | IBP:PolicyFeature: Close Document Viewer | Draft | Akhila Gattu
5308 | IIRM-8116 | QAlity Test | IBP:PolicyFeature: PDF Rendering in Viewer | Draft | Akhila Gattu
5309 | IIRM-8117 | QAlity Test | IBP:PolicyFeature: View Upload History Panel | Draft | Akhila Gattu
5310 | IIRM-8118 | QAlity Test | IBP:PolicyFeature: Download Historical Document | Draft | Akhila Gattu
5311 | IIRM-8119 | QAlity Test | IBP:PolicyFeature: Upload History Ordering | Draft | Akhila Gattu
5312 | IIRM-8120 | QAlity Test | IBP:PolicyFeature: Upload History - Column Data Validation | Draft | Akhila Gattu
5313 | IIRM-8121 | QAlity Test | IBP:PolicyFeature: Close Upload History Panel | Draft | Akhila Gattu
5314 | IIRM-8122 | QAlity Test | IBP:PolicyFeature: Policy Features Button Visibility | Draft | Akhila Gattu
5315 | IIRM-8123 | QAlity Test | IBP:PolicyFeature: Click Policy Features Button | Draft | Akhila Gattu
5316 | IIRM-8124 | QAlity Test | IBP:PolicyFeature: Policy Features Button - No Enrollment | Draft | Akhila Gattu
5317 | IIRM-8125 | QAlity Test | IBP:PolicyFeature: View Document - Single Policy Enrollment | Draft | Akhila Gattu
5318 | IIRM-8126 | QAlity Test | IBP:PolicyFeature: Switch to TPA Card Tab - Single Policy | Draft | Akhila Gattu
5319 | IIRM-8127 | QAlity Test | IBP:PolicyFeature: No Document Available - Single Policy | Draft | Akhila Gattu
5320 | IIRM-8128 | QAlity Test | IBP:PolicyFeature: Download Document - Single Policy | Draft | Akhila Gattu
5321 | IIRM-8129 | QAlity Test | IBP:PolicyFeature: View Documents - Multiple Policy Enrollments | Draft | Akhila Gattu
5322 | IIRM-8130 | QAlity Test | IBP:PolicyFeature: Navigate Between Policy Sub-tabs | Draft | Akhila Gattu
5323 | IIRM-8131 | QAlity Test | IBP:PolicyFeature: Sub-tabs Persist Across Main Tab Switches | Draft | Akhila Gattu
5324 | IIRM-8132 | QAlity Test | IBP:PolicyFeature: Multiple Policies - One Missing Document | Draft | Akhila Gattu
5325 | IIRM-8133 | QAlity Test | IBP:PolicyFeature: Policy Sub-tab Labeling Format | Draft | Akhila Gattu
5326 | IIRM-8134 | QAlity Test | IBP:PolicyFeature: Multiple Policies - All Documents Available | Draft | Akhila Gattu
5327 | IIRM-8135 | QAlity Test | IBP:PolicyFeature: Multiple Policies - Tab Order | Draft | Akhila Gattu
5328 | IIRM-8136 | QAlity Test | IBP:PolicyFeature: PDF Viewer Controls | Draft | Akhila Gattu
5329 | IIRM-8137 | QAlity Test | IBP:PolicyFeature: Download Document - Employee | Draft | Akhila Gattu
5330 | IIRM-8138 | QAlity Test | IBP:PolicyFeature: Close Documents Screen | Draft | Akhila Gattu
5331 | IIRM-8139 | QAlity Test | IBP:PolicyFeature: Browser Back Button Behavior | Draft | Akhila Gattu
5332 | IIRM-8140 | QAlity Test | IBP:PolicyFeature: Multi-page PDF Navigation | Draft | Akhila Gattu
5333 | IIRM-8141 | QAlity Test | IBP:PolicyFeature: PDF Viewer - Mobile Responsiveness | Draft | Akhila Gattu
5334 | IIRM-8142 | QAlity Test | IBP:PolicyFeature: Document Update Reflection Time | Draft | Akhila Gattu
5335 | IIRM-8143 | QAlity Test | IBP:PolicyFeature: Concurrent Admin Uploads | Draft | Akhila Gattu
5336 | IIRM-8144 | QAlity Test | IBP:PolicyFeature: Multiple Policy Documents Isolation | Draft | Akhila Gattu
5337 | IIRM-8145 | QAlity Test | IBP:PolicyFeature: Permissions - Non-enrolled Employee Access | Draft | Akhila Gattu
5338 | IIRM-8146 | QAlity Test | IBP:PolicyFeature: Document Availability After Policy Enrollment | Draft | Akhila Gattu
5339 | IIRM-8147 | QAlity Test | IBP:PolicyFeature: Document Access After Policy Termination | Draft | Akhila Gattu
5340 | IIRM-8148 | QAlity Test | IBP:PolicyFeature: Large PDF Upload Performance | Draft | Akhila Gattu
5341 | IIRM-8149 | QAlity Test | IBP:PolicyFeature: Multiple Simultaneous Employee Views | Draft | Akhila Gattu
5342 | IIRM-8150 | QAlity Test | IBP:PolicyFeature: Upload History with Large Number of Replacements | Draft | Akhila Gattu
5343 | IIRM-8151 | QAlity Test | IBP:PolicyFeature: Document Viewer - Large PDF Performance | Draft | Akhila Gattu
5344 | IIRM-8152 | QAlity Test | IBP:PolicyFeature: Keyboard Navigation - Admin | Draft | Akhila Gattu
5345 | IIRM-8153 | QAlity Test | IBP:PolicyFeature: Screen Reader Compatibility - Employee | Draft | Akhila Gattu
5346 | IIRM-8154 | QAlity Test | IBP:PolicyFeature: Keyboard Navigation - Employee Documents Screen | Draft | Akhila Gattu
5347 | IIRM-8155 | QAlity Test | IBP:PolicyFeature: Color Contrast and Visual Accessibility | Draft | Akhila Gattu
5348 | IIRM-8156 | QAlity Test | IBP:PolicyFeature: Network Interruption During Upload | Draft | Akhila Gattu
5349 | IIRM-8157 | QAlity Test | IBP:PolicyFeature: Session Timeout During Upload | Draft | Akhila Gattu
5350 | IIRM-8158 | QAlity Test | IBP:PolicyFeature: Browser Refresh During Document View | Draft | Akhila Gattu
5351 | IIRM-8159 | QAlity Test | IBP:PolicyFeature: Corrupted PDF File Upload | Draft | Akhila Gattu
5352 | IIRM-8160 | QAlity Test | IBP:PolicyFeature: Document Deleted from Storage (Backend Issue) | Draft | Akhila Gattu
5353 | IIRM-8161 | QAlity Test | IBP:PolicyFeature: Duplicate Filename Upload | Draft | Akhila Gattu
5354 | IIRM-8162 | QAlity Test | IBP:PolicyFeature: Browser Compatibility | Draft | Akhila Gattu
5355 | IIRM-8163 | QAlity Test | IBP:PolicyFeature: Very Long Filename | Draft | Akhila Gattu
5356 | IIRM-8164 | QAlity Test | IBP:PolicyFeature: Special Characters in PDF Content | Draft | Akhila Gattu
5357 | IIRM-8165 | QAlity Test | IBP:PolicyFeature: Concurrent Document Views by Same Employee | Draft | Akhila Gattu
5358 | IIRM-8166 | QAlity Test | IBP:PolicyFeature: End-to-End Smoke Test - Admin Flow | Draft | Akhila Gattu
5359 | IIRM-8167 | QAlity Test | IBP:PolicyFeature: End-to-End Smoke Test - Employee Flow (Single Policy) | Draft | Akhila Gattu
5360 | IIRM-8168 | QAlity Test | IBP:PolicyFeature: End-to-End Smoke Test - Employee Flow (Multiple Policies) | Draft | Akhila Gattu
5361 | IIRM-8169 | QAlity Test | IBP:PolicyFeature: Portal Configuration - No Regression | Draft | Akhila Gattu
5362 | IIRM-8170 | QAlity Test | IBP:PolicyFeature: Employee Dashboard - No Regression | Draft | Akhila Gattu
5363 | IIRM-8171 | Task | Auto-Generate System Entry Reference Number for Every SO/RO Created | Open | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5364 | IIRM-8172 | Story | Make TPA upload step optional in Inception and Endorsement processes for GPA & GTL (Configurable at policy type) | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-777 — SOW#50 - Policy Configurator
5365 | IIRM-8174 | Sub-task | GPA / GTL Policies | Draft | Richa Bagchi Mazumdar |  | IIRM-8172 — Make TPA upload step optional in Inception and Endorsement processes for GPA & GTL (Configurable at policy type)
5366 | IIRM-8176 | Bug | IIRM: Pre-Prod: Tasks: Unable to Clear the Activity Dropdown Value | QA in Progress | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
5367 | IIRM-8177 | Bug | Search by Keywords field appears greyed out and needs UI enhancement | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5368 | IIRM-8178 | Story | Add Policy Header Sticker to All View Screens | Draft | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5369 | IIRM-8179 | Task | FAQ Ordering Not Configurable | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5370 | IIRM-8180 | Task | FAQ UI/UX Improvements | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5371 | IIRM-8181 | Task | Dashboard – Redirection of Static Icons and Tabs | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5372 | IIRM-8182 | Task | CR: Enroll Now card should not disappear after enrollment submission | Draft | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5373 | IIRM-8183 | Task | Enrolment Summary should display combined summary for multiple policies | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5374 | IIRM-8184 | Bug | IIRM: Bizdone Report: Incorrect Brokerage Percentage Displayed | Open | Leela Pakalapati | iWork | IIRM-778 — SOW#51 - Admin Reports
5375 | IIRM-8185 | Bug | 14 Parental Records Rejected for Policy 340646 – "Duplicate employee ID in file" | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5376 | IIRM-8186 | Bug | Premium did not match for addition and deletion endorsement for policy number 521452 | Done - Not a Bug | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5377 | IIRM-8187 | Bug | For policy number 521445(GMC) we saw below issues while doing the addition endorsements. | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5378 | IIRM-8188 | Bug | Records are rejected in inception#340646 | Done | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5379 | IIRM-8189 | Bug | IIRM: Documents: "Uploaded By" Not Updating on Re-Upload | Done | Leela Pakalapati | iWork | IIRM-772 — SOW#45 - Document Management
5380 | IIRM-8190 | Bug | IIRM: Save Activity: Unable to Save Updated Version & Quote Details | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5381 | IIRM-8191 | Bug | IIRM: Save Activity: Final Negotiation Activity: Unable to Save/Complete the activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5382 | IIRM-8192 | Bug | IIRM: Save Activity: Duplicate versions are getting added by clicking on the Save Activity button | Done | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5383 | IIRM-8193 | QAlity Test | IIRM: RO: Perform BD Opportunity Activties with privillaged user | Draft | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5384 | IIRM-8194 | Sub-task | Contract Matrix Front End | Done | Richa Bagchi Mazumdar |  | IIRM-8036 — IBP: Contact Matrix
5385 | IIRM-8195 | Sub-task | Contract Matrix Back End | Done | Richa Bagchi Mazumdar |  | IIRM-8036 — IBP: Contact Matrix
5386 | IIRM-8196 | Bug | Document in "Send Inception to Insurer" section has less records than the actual employees (Policy 405350) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5387 | IIRM-8197 | Bug | Document in "Send Inception to Insurer" section has less records than the actual employees (Policy 405350) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5388 | IIRM-8198 | Bug | Gross premium is showing 3 decimals (Policy 337814) | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5389 | IIRM-8199 | Bug | Provisional Endorsement Number/Insurer Endorsement number/Provisional Inception Number/Insurer Inception Number should be alphanumeric. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5390 | IIRM-8200 | Bug | Inception premium is not correct. Also, if more than one files are uploaded then file downloaded from "Send Inception to Insurer" section is not having all the records. it takes data from only 1 file. It should have all the data uploaded successfully. | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5391 | IIRM-8201 | Task | Enter Quote: Show all Insurer in "Select Insurer" drop-down | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5392 | IIRM-8202 | Bug | Unable to Create Additional Brokingslip Versions | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5393 | IIRM-8203 | Bug | If we have endorsement too then downloading the file from "Send Inception to Insurer" is downloading endorsement file. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5394 | IIRM-8204 | Bug | Error file shows different date format than the provided in the actual file. This is reported long back but no action. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5395 | IIRM-8205 | Bug | Should have the dates in the same format as the original file. (Policy 521445) | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5396 | IIRM-8206 | Bug | Currently system is supporting only 10 MB file size, it must support according to the file size. It should throw proper error message in case of file size exceeds defined limit. | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5397 | IIRM-8207 | Bug | Some records are missing to be processed during "TPA ID Upload". There is no way to know the failed records here. Policy ID: 574574 | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5398 | IIRM-8208 | Bug | One additional column is needed in Endorsement file to check the status of claims. This is needed for deletion. This will be confirmed by tomorrow morning. | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5399 | IIRM-8209 | Bug | In endorsement TPA deletion, records need to mention the TPA ID in the last column as confirmed by Nithin today. | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5400 | IIRM-8220 | Bug | IIRM: Auto-Population: Held Cover Note: Insurer details are missing when Policy Placed type is set to Multiple | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5401 | IIRM-8221 | Bug | IIRM: Placement Slip Generation: Lanka: Unable to Save or Complete the Activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5402 | IIRM-8222 | Story | Non-Financial Endorsements | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5403 | IIRM-8223 | Bug | IIRM: Save Activity: Not able to save partial data in the Final Negotiation activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5404 | IIRM-8224 | Sub-task | Push current version to PRODUCTION (ETA 2 days) | Done | NithinKrishna Sirigiri |  | IIRM-8066 — AI Chatbot (Release-1)
5405 | IIRM-8225 | Bug | IBP:HospitalNetwork: Pin point not showing on navigating to address details from HospitalNetwork page | Done - Not a Bug | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5406 | IIRM-8226 | Bug | IIRM: Save Activity: Policy Hard Copy: Data is not saved when clicking the Save button | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5407 | IIRM-8227 | Task | IIRM: Srilanka and india Opportunities activites Testing | Done | SaikumarMahanthi | iWork
5408 | IIRM-8228 | Task | Biz Done Report: Add Sri Lanka related fields and show them only for Sri Lanka report. | Done | NithinKrishna Sirigiri |  | IIRM-778 — SOW#51 - Admin Reports
5409 | IIRM-8229 | Task | Biz Done Report: DB Update: Share Amount, Share%, Brokerage Amount & Brokerage% from Opportunity to Policy | Open | NithinKrishna Sirigiri |  | IIRM-778 — SOW#51 - Admin Reports
5410 | IIRM-8230 | Bug | Endorsement Issues: Upload pending | Done - Not a Bug | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5411 | IIRM-8231 | Bug | Inception Premium Mismatch Issues | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5412 | IIRM-8232 | Task | Coverages Not Available ¦ Industrial All Risk ¦ Opp. No.1175419, 1175556 & 1175558 ¦ Inox Air Products | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5413 | IIRM-8233 | Task | IIRM: Localizatioin Testing on QA Environment | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5414 | IIRM-8234 | Task | IIRM: Save Activity testing and ready for QA issues verification | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5415 | IIRM-8235 | Task | IIRM: Backlog Ready for QA issues verification | Done | SaikumarMahanthi |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
5416 | IIRM-8236 | Task | IIRM: Sanity Verification on Pre-pod and production Environment | Done | SaikumarMahanthi |  | IIRM-7604 — Production - Defects & Tasks
5417 | IIRM-8237 | Bug | IBP:Document: Client confirmation data is not getting stored on documents tab. | Done | Akhila Gattu
5418 | IIRM-8238 | Bug | IBP: Document: OS number is getting overridden if 2 files got uplaoded in inception process | Done - Not a Bug | Akhila Gattu
5419 | IIRM-8239 | Bug | IBP:Document: FileName column to show not mentioned in spec | Done | Akhila Gattu
5420 | IIRM-8240 | Bug | IBP: Documents: Subactivity sequence missing on documents tab | Done | Akhila Gattu
5421 | IIRM-8241 | Bug | IBP: Policy: Document: Client confirmation subactivity record mapping not captured | Done - Not Reproducible | Akhila Gattu
5422 | IIRM-8242 | Story | Unified Enrollment Process for Employee Insurance Policies | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5423 | IIRM-8243 | Bug | IBP:Policy: Document: Send endorsement to insurer Mapping record appears on Step 2 instead of Step 3 | Done | Akhila Gattu
5424 | IIRM-8244 | Sub-task | SO/RO sync up with policy FE | Done | Pampana Ravi Kiran |  | IIRM-7042 — Sync Policy fields to SO/RO Stages
5425 | IIRM-8245 | Sub-task | SO/RO sync up of fields in BE | Done | Pampana Ravi Kiran |  | IIRM-7042 — Sync Policy fields to SO/RO Stages
5426 | IIRM-8246 | Bug | IBP: Policy: Document: Claims records were getting mapped in middle of the inception and endorsement mapped records | Done | Akhila Gattu
5427 | IIRM-8247 | Bug | IBP:Policy:Dashboard: 'From' and 'To' dates not working when same date is selected | Done | Akhila Gattu
5428 | IIRM-8248 | QAlity Test | PolicyDocument: Verify Documents Tab is Visible and Accessible | Draft | Akhila Gattu
5429 | IIRM-8249 | QAlity Test | PolicyDocument: Verify Documents Tab Does Not Display for Invalid Policy ID | Draft | Akhila Gattu
5430 | IIRM-8250 | QAlity Test | PolicyDocument: Verify Documents Tab Access with Insufficient Permissions | Draft | Akhila Gattu
5431 | IIRM-8251 | QAlity Test | PolicyDocument: Verify Documents Tab State Persistence During Navigation | Draft | Akhila Gattu
5432 | IIRM-8252 | QAlity Test | PolicyDocument: Verify Document Retrieval - All Inception Stages | Draft | Akhila Gattu
5433 | IIRM-8253 | QAlity Test | PolicyDocument: Verify Retrieval with Missing Inception Documents | Draft | Akhila Gattu
5434 | IIRM-8254 | QAlity Test | PolicyDocument: Verify Duplicate Document Uploads in Same Stage | Draft | Akhila Gattu
5435 | IIRM-8255 | QAlity Test | PolicyDocument: Verify TPA ID Document Type Mapping | Draft | Akhila Gattu
5436 | IIRM-8256 | QAlity Test | PolicyDocument: Verify Client Confirmation Stage Multiple Document Types | Draft | Akhila Gattu
5437 | IIRM-8257 | QAlity Test | PolicyDocument: Verify Document Retrieval - All Endorsement Stages | Draft | Akhila Gattu
5438 | IIRM-8258 | QAlity Test | PolicyDocument: Verify Combined Display of Inception and Endorsement Documents | Draft | Akhila Gattu
5439 | IIRM-8259 | QAlity Test | PolicyDocument: Verify Multiple Endorsements Document Retrieval | Draft | Akhila Gattu
5440 | IIRM-8260 | QAlity Test | PolicyDocument: Verify Endorsement Upload After Inception Document Deletion | Draft | Akhila Gattu
5441 | IIRM-8261 | QAlity Test | PolicyDocument: Verify Endorsement TPA ID Does Not Overwrite Inception TPA ID | Draft | Akhila Gattu
5442 | IIRM-8262 | QAlity Test | PolicyDocument: Verify Document Retrieval - TPA ID Upload Exclusion | Draft | Akhila Gattu
5443 | IIRM-8263 | QAlity Test | PolicyDocument: Verify Non-Group Policy Endorsement Document Retrieval | Draft | Akhila Gattu
5444 | IIRM-8264 | QAlity Test | PolicyDocument: Verify Policy Type Switch Document Handling | Draft | Akhila Gattu
5445 | IIRM-8265 | QAlity Test | PolicyDocument: Verify All Table Columns Are Rendered Correctly | Draft | Akhila Gattu
5446 | IIRM-8266 | QAlity Test | PolicyDocument: Verify OS Ticket Number Column Data Accuracy | Draft | Akhila Gattu
5447 | IIRM-8267 | QAlity Test | PolicyDocument: Verify File Name Column Displays Original Filename | Draft | Akhila Gattu
5448 | IIRM-8268 | QAlity Test | PolicyDocument: Verify Uploaded By Column Shows Correct User Information | Draft | Akhila Gattu
5449 | IIRM-8269 | QAlity Test | PolicyDocument: Verify Uploaded Date Column Format and Timezone | Draft | Akhila Gattu
5450 | IIRM-8270 | QAlity Test | PolicyDocument: Verify Download Column Icon Rendering and Accessibility | Draft | Akhila Gattu
5451 | IIRM-8271 | QAlity Test | PolicyDocument: Verify Single Document Download via Download Icon | Draft | Akhila Gattu
5452 | IIRM-8272 | QAlity Test | PolicyDocument: Verify Download of Large File (Over 10MB) | Draft | Akhila Gattu
5453 | IIRM-8273 | QAlity Test | PolicyDocument: Verify Download Failure Handling for Deleted Document | Draft | Akhila Gattu
5454 | IIRM-8274 | QAlity Test | PolicyDocument: Verify Concurrent Downloads of Multiple Documents | Draft | Akhila Gattu
5455 | IIRM-8275 | QAlity Test | PolicyDocument: Verify Download with Special Characters in Filename | Draft | Akhila Gattu
5456 | IIRM-8276 | QAlity Test | PolicyDocument: Verify Download Permission Enforcement | Draft | Akhila Gattu
5457 | IIRM-8277 | QAlity Test | PolicyDocument: Verify Download During Slow Network Connection | Draft | Akhila Gattu
5458 | IIRM-8278 | QAlity Test | PolicyDocument: Verify Activity Name Click Navigation to Inception Activity | Draft | Akhila Gattu
5459 | IIRM-8279 | QAlity Test | PolicyDocument: Verify Activity Name Navigation to Endorsement Activity | Draft | Akhila Gattu
5460 | IIRM-8280 | QAlity Test | PolicyDocument: Verify Activity Name Navigation for TPA ID Upload Stage | Draft | Akhila Gattu
5461 | IIRM-8281 | QAlity Test | PolicyDocument: Verify Activity Name Navigation with Insufficient Permission | Draft | Akhila Gattu
5462 | IIRM-8282 | QAlity Test | PolicyDocument: Verify Empty State Display When No Documents Exist | Draft | Akhila Gattu
5463 | IIRM-8283 | QAlity Test | PolicyDocument: Verify Empty State After All Documents Are Deleted | Draft | Akhila Gattu
5464 | IIRM-8284 | QAlity Test | PolicyDocument: Verify Empty State for New Policy Before Document Upload | Draft | Akhila Gattu
5465 | IIRM-8285 | QAlity Test | PolicyDocument: Verify Document Upload with Unsupported File Type | Draft | Akhila Gattu
5466 | IIRM-8286 | QAlity Test | PolicyDocument: Verify Document Upload File Size Boundary Validation | Draft | Akhila Gattu
5467 | IIRM-8287 | QAlity Test | PolicyDocument: Verify Document Upload with Corrupted File | Draft | Akhila Gattu
5468 | IIRM-8288 | QAlity Test | PolicyDocument: Verify File Format Spoofing Detection | Draft | Akhila Gattu
5469 | IIRM-8289 | QAlity Test | PolicyDocument: Verify Document Upload with Empty File | Draft | Akhila Gattu
5470 | IIRM-8290 | QAlity Test | Verify Dynamic Field Display Based on Country Selection | Draft | SaikumarMahanthi
5471 | IIRM-8291 | Sub-task | DB Changes: Localisation regulatory fields selection based upon different countries | Done | Rohit |  | IIRM-8228 — Biz Done Report: Add Sri Lanka related fields and show them only for Sri Lanka report.
5472 | IIRM-8292 | QAlity Test | TC-001: Verify Save Draft with Missing Mandatory Fields | Draft | SaikumarMahanthi
5473 | IIRM-8293 | QAlity Test | TC-002: Verify Save Draft Blocked on Format/Data Type/Range Validation Errors | Draft | SaikumarMahanthi
5474 | IIRM-8294 | QAlity Test | TC-003: Verify Cross-Field Validation During Save Draft | Draft | SaikumarMahanthi
5475 | IIRM-8295 | QAlity Test | TC-004: Verify Auto-populate Draft on Revisit and Overwrite Behavior | Draft | SaikumarMahanthi
5476 | IIRM-8296 | QAlity Test | TC-005: Verify Draft Deletion After Stage Completion | Draft | SaikumarMahanthi
5477 | IIRM-8297 | QAlity Test | TC-006: Verify Multiple Stages Maintain Independent Drafts | Draft | SaikumarMahanthi
5478 | IIRM-8298 | QAlity Test | TC-007: Verify Save Draft After Failed Completion Attempt | Draft | SaikumarMahanthi
5479 | IIRM-8299 | QAlity Test | TC-008: Verify Draft Persistence Across Sessions and Boundary Cases | Draft | SaikumarMahanthi
5480 | IIRM-8300 | QAlity Test | Verify Country-Specific Validation Rules and Financial Calculations | Draft | SaikumarMahanthi
5481 | IIRM-8301 | Bug | IBP: Document: Document mapping functionality not working for non-group policies | Done | Akhila Gattu
5482 | IIRM-8302 | Bug | Policy: Inception: In-law records mapped to Self record in dummy data | Open | Akhila Gattu
5483 | IIRM-8303 | Bug | Policy: Inception process: Invalid choices are mapped to this employee for this policy. Please verify, error thrown for valid records | Done - Not a Bug | Akhila Gattu
5484 | IIRM-8304 | Sub-task | Rework on Designs | Done | Richa Bagchi Mazumdar |  | IIRM-7631 — IBP: Claims Corner (Phase 1) - View Claims Details
5485 | IIRM-8305 | Bug | ServiceFlow: Claims: Without EMPLOYEE_ID claims upload functionality not working for GMC policy | Done | Akhila Gattu
5486 | IIRM-8306 | Bug | Claims: ServiceFlow: For failed claims , remarks were not showing on error download file | Open | Akhila Gattu
5487 | IIRM-8307 | Bug | Claims: ServiceFlow: IBP: IBP: Pending claims count not reflected on Claims Summary card after uploading file with pending claims | Done | Akhila Gattu
5488 | IIRM-8308 | Bug | Claims: ServiceFlow: File failed records also getting captured in step 2 | Open | Akhila Gattu
5489 | IIRM-8309 | Story | iLearn: Add, Edit and Show Training Materials ONLY | Done | NithinKrishna Sirigiri |  | IIRM-768 — SOW#41 - Knowledge Central
5490 | IIRM-8310 | Bug | IBP: Claims: Claims file upload failed, If inception/Endorsement process done with choices data type | Done | Akhila Gattu
5491 | IIRM-8311 | Sub-task | iLearn: Add, Edit and Show Training Materials ONLY | Done | Mallela Pushyami |  | IIRM-8309 — iLearn: Add, Edit and Show Training Materials ONLY
5492 | IIRM-8312 | Bug | IBP: Claims: Settled count not getting updated on IBP dashboard. | Done | Akhila Gattu | Framework
5493 | IIRM-8313 | Bug | IBP: Claims: Invalid policy number shown on UI | Done - Not a Bug | Akhila Gattu
5494 | IIRM-8314 | Bug | IBP: Claims: Claims reference number not showing on IBP dashboard | Reopen | Akhila Gattu
5495 | IIRM-8315 | QAlity Test | TC-ISG-001: Verify Sequential ISG Activities Execution by Privileged User | Draft | SaikumarMahanthi
5496 | IIRM-8316 | QAlity Test | TC-ISG-002: Verify Auto-Calculations, Multiple Versions, Multiple Insurers, and Deviations | Draft | SaikumarMahanthi
5497 | IIRM-8317 | Bug | IIRM: Hand Over Meet: Approval functionality inconsistency | Done | Prathiphala Kandula |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5498 | IIRM-8318 | Bug | IIRM: Existing Document Not Displayed on Document Edit Screen | Done | SaikumarMahanthi | iWork | IIRM-7604 — Production - Defects & Tasks
5499 | IIRM-8319 | Bug | IIRM: No confirmation popup displayed when deleting a document | Done | SaikumarMahanthi | iWork | IIRM-7604 — Production - Defects & Tasks
5500 | IIRM-8320 | Bug | RO Opportunity Nos 675403, 675422 & 675461 – Standard Chartered | QA in Progress | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5501 | IIRM-8321 | Sub-task | Changes the 2nd and 3rd setps processing in the inception and endorsment process | Done | VedaVyas |  | IIRM-7645 — Inception: Unable to view inception process steps , if data got uploaded on step 1
5502 | IIRM-8322 | Bug | In brokering slip generation basic premium and percentage is not appearing after save activity | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5503 | IIRM-8323 | Bug | In the broking slip activity preferred insurer issue | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5504 | IIRM-8324 | Bug | IBP: Claims: Settled amount shoud get allow > claim amount for the same CLAIM_INS_ID | Open | Akhila Gattu
5505 | IIRM-8325 | Bug | IIRM: Save Activity: Missing pop-up warning when saving the activity without saving the version | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5506 | IIRM-8326 | Bug | IIRM: Save Activity: Unable to save the activity without providing any data | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5507 | IIRM-8327 | Bug | IBP: Claims: For GPA, GTL policies dependent claims on UI showing it as self | Open | Akhila Gattu
5508 | IIRM-8328 | Bug | IIRM: Duplicate covers are displayed for RO activites RO-ID 678566 | Open | SaikumarMahanthi
5509 | IIRM-8329 | Task | IIRM: Ilean Testing and Ready for QA Issues Testing | Done | SaikumarMahanthi |  | IIRM-7604 — Production - Defects & Tasks
5510 | IIRM-8330 | Task | IIRM: Ready for QA Bugfixes verification and regression testing on latest build | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5511 | IIRM-8331 | Task | IIRM: UAT And Production backlog verification | Done | SaikumarMahanthi
5512 | IIRM-8332 | Bug | PROD Issue: Duplicate Covers - RO 675403, 675422 & 675461 – Standard Chartered | QA in Progress | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5513 | IIRM-8333 | Bug | PROD Issue: Broking Slip - Save Version failed (SCB) | Ready for QA | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5514 | IIRM-8334 | Story | India - Premium components & brokerage amount calculation | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5515 | IIRM-8335 | Task | PROD Request: Need to extract CD Details per policy | Done | NithinKrishna Sirigiri |  | IIRM-781 — SOW#54 - CD Management
5516 | IIRM-8336 | Task | PROD Request: Delete 31 policies (Refer to IIRM Email) | Draft | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5517 | IIRM-8337 | Task | PROD Request: Delete Opty. & It's related policy (Opp. No.1018657) | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5518 | IIRM-8338 | Task | PROD Request: Add Covers for Industrial All Risk (Refer Opty. ID: 175419, 1175556 & 1175558) | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5519 | IIRM-8339 | Bug | IBP: Inception/Endorsement: FOr GPA and GTL dependention adding should get restricted. | Open | Akhila Gattu
5520 | IIRM-8340 | Task | PROD Request: Premium Update - Opty. ID: 1175469 & 1175470 (From Kishore) | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
5521 | IIRM-8341 | Story | IBP: Switch between Employee & HR Role by HR User | Open | Jadhav Sai Prasad |  | IIRM-776 — SOW#49 - HR Portal View
5522 | IIRM-8342 | Story | IBP - Employee - User Profile | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5523 | IIRM-8343 | Story | Authorization Configuration | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5524 | IIRM-8344 | Bug | IIRM: Task Edit Button Enabled Even After Task Completion | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5525 | IIRM-8345 | Bug | IIRM: Task Status Not Updated After Task Completion | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5526 | IIRM-8346 | Task | PROD Request: Update Premium at inception and Net premium amount to same (Opty ID/ Policy: 968554/555522)) | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
5527 | IIRM-8347 | Story | AI Chatbot: Support Free form chat | WORK IN PROGRESS | Prabhakar Mantripragada | iWork | IIRM-789 — SOW#62 - AI Chatbot
5528 | IIRM-8348 | Story | AI Chatbot: BE: Nudge - API | WORK IN PROGRESS | Prabhakar Mantripragada | iWork | IIRM-789 — SOW#62 - AI Chatbot
5529 | IIRM-8349 | Story | AI Chatbot: FE: Show nudges relevant to the pages with static data | WORK IN PROGRESS | Prabhakar Mantripragada | iWork | IIRM-789 — SOW#62 - AI Chatbot
5530 | IIRM-8350 | Sub-task | AI Chatbot: Nudges: Develop the Nudge cards with Pagination (scroll) | Done | Prabhakar Mantripragada |  | IIRM-8349 — AI Chatbot: FE: Show nudges relevant to the pages with static data
5531 | IIRM-8351 | Sub-task | AI Chatbot: Nudges: Integrate the Nugget Response into Nugget Card | Done | Prabhakar Mantripragada |  | IIRM-8349 — AI Chatbot: FE: Show nudges relevant to the pages with static data
5532 | IIRM-8352 | Sub-task | AI Chatbot: Nudges: Enable the form for chat communication | Draft | Prabhakar Mantripragada |  | IIRM-8349 — AI Chatbot: FE: Show nudges relevant to the pages with static data
5533 | IIRM-8353 | Sub-task | AI Chatbot: Nudges: Bind the chat history to chat pannel | Draft | Prabhakar Mantripragada |  | IIRM-8349 — AI Chatbot: FE: Show nudges relevant to the pages with static data
5534 | IIRM-8354 | Sub-task | AI Chatbot: Nudges: Feeback UI development in chat panel | Draft | Prabhakar Mantripragada |  | IIRM-8349 — AI Chatbot: FE: Show nudges relevant to the pages with static data
5535 | IIRM-8355 | Sub-task | AI Chatbot: Nudges: UI development for Feedback list view | Draft | Prabhakar Mantripragada |  | IIRM-8349 — AI Chatbot: FE: Show nudges relevant to the pages with static data
5536 | IIRM-8356 | Story | AI Chatbot: Nudge - prompts from Database | WORK IN PROGRESS | Prabhakar Mantripragada | iWork
5537 | IIRM-8357 | Task | PROD Request: Update Company Name (28713, 28713) | Draft | NithinKrishna Sirigiri |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
5538 | IIRM-8358 | Story | AI Chatbot: Nudge - Run dynamic service to answer prompts | Draft | Prabhakar Mantripragada | iWork
5539 | IIRM-8359 | Story | AI Chatbot: Nudge - Put to cache & return to FE | WORK IN PROGRESS | Prabhakar Mantripragada | iWork
5540 | IIRM-8360 | Story | AI Chatbot: Chat - History per user | WORK IN PROGRESS | Prabhakar Mantripragada | iWork
5541 | IIRM-8361 | Story | AI Chatbot: Chat - Provide last 'n' prompts/context to AI | WORK IN PROGRESS | Prabhakar Mantripragada | iWork
5542 | IIRM-8362 | Story | AI Chatbot: Nudge - Pre-computation as required | Done | Prabhakar Mantripragada | iWork | IIRM-789 — SOW#62 - AI Chatbot
5543 | IIRM-8363 | Story | AI Chatbot: Chat - Feedback Mgmt | WORK IN PROGRESS | Prabhakar Mantripragada | iWork
5544 | IIRM-8364 | Story | AI Chatbot: Chat - Favorites Mgmt | WORK IN PROGRESS | Prabhakar Mantripragada | iWork
5545 | IIRM-8365 | Story | AI: Prepare Base Infrastructure for AI Chatbot and Nudges | WORK IN PROGRESS | Prabhakar Mantripragada | Framework | IIRM-789 — SOW#62 - AI Chatbot
5546 | IIRM-8366 | Sub-task | RAG setup | Open | Prabhakar Mantripragada |  | IIRM-8365 — AI: Prepare Base Infrastructure for AI Chatbot and Nudges
5547 | IIRM-8367 | Sub-task | PydanticAI agent implementation | Done | Prabhakar Mantripragada |  | IIRM-8365 — AI: Prepare Base Infrastructure for AI Chatbot and Nudges
5548 | IIRM-8368 | Sub-task | Schema ingestion pipeline | Done | Prabhakar Mantripragada |  | IIRM-8365 — AI: Prepare Base Infrastructure for AI Chatbot and Nudges
5549 | IIRM-8369 | Sub-task | Query validation & testing | WORK IN PROGRESS | Prabhakar Mantripragada |  | IIRM-8365 — AI: Prepare Base Infrastructure for AI Chatbot and Nudges
5550 | IIRM-8370 | Story | AI: Support chat based responses for the entities | WORK IN PROGRESS | Prabhakar Mantripragada | Framework | IIRM-789 — SOW#62 - AI Chatbot
5551 | IIRM-8371 | Bug | IIRM: Unable to Save Placement Slip Activity When No Data Is Entered(Placementship) | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5552 | IIRM-8372 | Story | QCR Comparison Excel download template for Lanka | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5553 | IIRM-8373 | QAlity Test | IIRM: Srilanka : Perform BD Opportunity Activties with privillaged user | Draft | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5554 | IIRM-8374 | Bug | IIRM: UAT: Save Activity: Not able to save partial data in the Mandate Details Entry activity | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5555 | IIRM-8375 | Bug | IIRM: Assignee Name not displayed in RFP Details Entry, blocking ISG Planning stage creation. | Done - Not Reproducible | KOWTRAPU KAVYA SRI | iWork
5556 | IIRM-8379 | Bug | IIRM: Create Task: Opportunity dropdown is empty | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5557 | IIRM-8380 | Bug | IIRM: Ai service not found is triggered when clicking Industry Intelligence When Company creation | Open | KOWTRAPU KAVYA SRI | iWork | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
5558 | IIRM-8381 | Bug | Inception: For expired policy inception/endorsement process should't get allowed | Open | Akhila Gattu
5559 | IIRM-8382 | Bug | IIRM: Save Activity: UAT: Partially saved data is not retained when the tab is refreshed in Broking Slip Generation | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5560 | IIRM-8383 | Story | Enable Endorsement after successful process of Inception file upload (step-2) (Only GMC) | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5561 | IIRM-8384 | Story | Show only dependent count in endorsement summary when adding dependents without employees | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5562 | IIRM-8385 | Story | File name convention - Inception/Endorsement | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5563 | IIRM-8386 | Story | In any file upload section, show file processing completion timestamp | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5564 | IIRM-8387 | Story | Download option for the Inception/Endorsement process file (Step-1) | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5565 | IIRM-8388 | Story | Support alphanumeric format for Provisional and Insurer Inception/Endorsement numbers | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5566 | IIRM-8389 | Story | Make Policy configuration for policy types - GMC Top-up, Parental & It's Top-up, OPD | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
5567 | IIRM-8390 | Story | Policy Configuration: Data Retrofit for IIRM-8393 Story | Draft | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
5568 | IIRM-8391 | Story | Add claim status column in endorsement upload template to determine deletion refund logic | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5569 | IIRM-8392 | Bug | IIRM: Auto-Population: Unable to approve the activity when brokerage percentage is 0 for multiple insurers | Done | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5570 | IIRM-8393 | Story | Policy Config: Link Policy Components with the Relationship & it's related flags | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
5571 | IIRM-8394 | Sub-task | Reorder Policy Configuration Steps: Move Policy Relationships Before Policy Template | Done | NithinKrishna Sirigiri |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
5572 | IIRM-8395 | Sub-task | Add Policy Number Fields to Policy Component Configuration: Provisional, IIRM & Insurer (Optional) | Done | NithinKrishna Sirigiri |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
5573 | IIRM-8396 | Sub-task | Policy Template - Define Relationship Mappings for Individual Policy Components | Done | NithinKrishna Sirigiri |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
5574 | IIRM-8397 | Sub-task | Policy Template - Add Combined SI and Linked Claims Flags to Policy Components | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
5575 | IIRM-8398 | Sub-task | Data retrofit for existing Policies | Draft | NithinKrishna Sirigiri |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
5576 | IIRM-8399 | Sub-task | Mid Year Enrollment Allowed? -- Can we move this to Policy level or company level? --Need Kapil's confimation for Policy Component - | Done | NithinKrishna Sirigiri |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
5577 | IIRM-8400 | Sub-task | Sum Insured Visible to Employee? -- Can we move this to Policy level or company level? -- Need Kapil's confirmation | Done | NithinKrishna Sirigiri |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
5578 | IIRM-8401 | Story | Display enrolment status in step-2 for IBP-configured policies with employee-only file inception | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5579 | IIRM-8402 | Story | Add Relationship Group Selection Column to Inception/Endorsement Upload Files | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5580 | IIRM-8403 | Story | Add "Re-Activate" action to Policy ACL category | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5581 | IIRM-8404 | Sub-task | Retain user-entered data in subsequent steps when policy components are modified | Done | NithinKrishna Sirigiri |  | IIRM-8403 — Add "Re-Activate" action to Policy ACL category
5582 | IIRM-8405 | Bug | IIRM: ISG Manager Unable to Assign ISG Executive from Assignment Tab | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5583 | IIRM-8406 | Story | Add configurable TPA ID assignment mode (per-member or per-family) in GMC policy configuration | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
5584 | IIRM-8407 | Story | Build file transformation utility for inbound/outbound client-specific format conversion | Done | NithinKrishna Sirigiri |  | IIRM-735 — SOW#8 - 11 Components / Modules
5585 | IIRM-8408 | Story | Show size for upload or download files | Draft | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5586 | IIRM-8409 | Bug | IIRM: Save Activity: Unable to save partial data in Final Negotiation activity when quote documents are uploaded | Done | Leela Pakalapati | iWork
5587 | IIRM-8410 | Sub-task | Need to show the completion timestamp in the UI | Done | VedaVyas |  | IIRM-8386 — In any file upload section, show file processing completion timestamp
5588 | IIRM-8411 | Bug | IIRM: Current Activity Not Displayed in Enter Quote Task After Version Save | Done | SaikumarMahanthi
5589 | IIRM-8412 | Bug | IIRM: Save Activity: Unable to save or submit the Placement Slip activity due to not-null constraint | Done - Not Reproducible | Leela Pakalapati | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5590 | IIRM-8413 | Bug | IIRM: Manager Able to Approve Opportunity While Assigned Tasks Are Still In Progress | Done | SaikumarMahanthi | iWork
5591 | IIRM-8414 | Bug | IIRM: Cannot Associate Task with Activity ID During Task Creation at Premium Calculation Stage | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5592 | IIRM-8417 | Bug | IIRM: Task ID Displayed Instead of Task Name While Updating Completed Task | Done | SaikumarMahanthi | iWork
5593 | IIRM-8418 | Bug | IIRM: Selected Assignee Name Displays as “--” in Task Table for Opportunity stages. | Done | KOWTRAPU KAVYA SRI |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5594 | IIRM-8419 | Bug | IIRM: Permission Issue When Task Assigned to Executive Role – Opportunity Details Not Visible | Open | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5595 | IIRM-8420 | Epic | IIRM (iWork) to External SSO | Draft | NithinKrishna Sirigiri
5596 | IIRM-8421 | Story | iWork to Poppins - SSO Implementation | Done | NithinKrishna Sirigiri |  | IIRM-8420 — IIRM (iWork) to External SSO
5597 | IIRM-8422 | Bug | IIRM: Edit button not visible for few users in Opportuntiy Task table | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5598 | IIRM-8423 | Bug | Inception/Endorsement: UI Enchancement: Step 3 remains disabled after document appears on refresh | Open | Akhila Gattu
5599 | IIRM-8424 | Sub-task | TASK-BE-001: Logo Upload Backend API (FR-01) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5600 | IIRM-8425 | Sub-task | TASK-FE-001: Logo Upload Frontend Interface (FR-01) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5601 | IIRM-8426 | Sub-task | TASK-BE-002: Header and Tagline Text Configuration Backend (FR-02) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5602 | IIRM-8427 | Sub-task | TASK-FE-002: Header and Tagline Text Frontend Interface (FR-02) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5603 | IIRM-8428 | Sub-task | TASK-BE-003: Portal URL Configuration and Validation Backend (FR-03) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5604 | IIRM-8429 | Sub-task | TASK-FE-003: Portal URL Configuration Frontend Interface (FR-03) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5605 | IIRM-8430 | Sub-task | TASK-BE-004: Login Method Configuration Backend (FR-04) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5606 | IIRM-8431 | Sub-task | TASK-FE-004: Login Method Configuration Frontend Interface (FR-04) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5607 | IIRM-8432 | Sub-task | TASK-BE-005: 2FA Enforcement Backend Configuration (FR-05) | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5608 | IIRM-8433 | Sub-task | TASK-FE-005: 2FA Configuration Frontend Interface (FR-05) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5609 | IIRM-8434 | Sub-task | TASK-BE-006: Login-Specific Notification Rules Backend (FR-06) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5610 | IIRM-8435 | Sub-task | TASK-FE-006: Notification Rules Display Frontend (FR-06) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5611 | IIRM-8436 | Sub-task | TASK-BE-007: Corporate Wellness Configuration Backend (FR-07) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5612 | IIRM-8437 | Sub-task | TASK-FE-007: Corporate Wellness Configuration Frontend Interface (FR-07) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5613 | IIRM-8438 | Sub-task | TASK-BE-008: Insurance Wellness Toggle Backend (FR-08) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5614 | IIRM-8439 | Sub-task | TASK-FE-008: Insurance Wellness Toggle Frontend Interface (FR-08 | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5615 | IIRM-8440 | Sub-task | TASK-BE-009: Insurance Wellness Type Selection Backend (FR-09) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5616 | IIRM-8441 | Sub-task | TASK-FE-009: Insurance Wellness Type Selection Frontend Interface (FR-09) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5617 | IIRM-8442 | Sub-task | TASK-BE-010: Wellness Benefit Sub-Configuration Backend (FR-10) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5618 | IIRM-8443 | Sub-task | TASK-FE-010: Wellness Benefit Sub-Configuration Frontend Interface (FR-10) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5619 | IIRM-8444 | Sub-task | TASK-BE-011: Policy Assignment Backend (FR-11) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5620 | IIRM-8445 | Sub-task | TASK-FE-011: Policy Assignment Frontend Interface (FR-11) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5621 | IIRM-8446 | Sub-task | TASK-BE-012: Enrollment Window Configuration Backend (FR-12) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5622 | IIRM-8447 | Sub-task | TASK-FE-012: Enrollment Window Configuration Frontend Interface (FR-12) | Done | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5623 | IIRM-8448 | Sub-task | TASK-BE-013: Financial Settings Configuration Backend (FR-13) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5624 | IIRM-8449 | Sub-task | TASK-FE-013: Financial Settings Configuration Frontend Interface (FR-13) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5625 | IIRM-8450 | Sub-task | TASK-BE-014: Family Eligibility Configuration Backend (FR-14) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5626 | IIRM-8451 | Sub-task | TASK-FE-014: Family Eligibility Configuration Frontend Interface (FR-14) | Draft | Richa Bagchi Mazumdar |  | IIRM-8058 — IBP: Portal Preferences - Company (Admin Module)
5627 | IIRM-8453 | Bug | IIRM: Save Activity: Error message displayed when saving Final Negotiation activity without providing any data | Done | Leela Pakalapati | iWork
5628 | IIRM-8455 | Bug | Unable to Find Insurer in Placementslip Page and also in Held Cover Note ¦ Opp. No.1175179 | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5629 | IIRM-8456 | Bug | Gross premium is not getting displayed for deletion endorsements in Track Endorsements section of Policy Details page.(521452,337820) | QA in Progress | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5630 | IIRM-8457 | Bug | Policy and CD account wise view | QA in Progress | Richa Bagchi Mazumdar |  | IIRM-797 — SOW#69 - Manage Opportunities
5631 | IIRM-8458 | Bug | GST value has been given in activity (not percentage as we dont have gst % field) however, GST % in policy details is 0 | Ready for QA | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5632 | IIRM-8459 | Bug | IIRM: The RFP Details Entry is blocking policy creation, as the system displays an ‘Employee ID not found’ error when the ‘Submit for Approval’ button is clicked.” | Done - Not Reproducible | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5633 | IIRM-8460 | Bug | IBP: Inception/Endorsement: No-of employee count 0 not accepting while adding only dependent through endorsement. | Open | Akhila Gattu
5634 | IIRM-8461 | Bug | IBP: Endorsement: Wrong dependent count showing on step 2 Relation when only adding dependent | Open | Akhila Gattu
5635 | IIRM-8462 | Bug | File name convention - Inception/Endorsement-IIRM IS PREFIX IS MISSING/in endorsement the file is named as enrollmen | Open | Akhila Gattu
5636 | IIRM-8463 | Story | AI: Support chat based responses for the Opportunity and related entities | WORK IN PROGRESS | Prabhakar Mantripragada | iWork | IIRM-789 — SOW#62 - AI Chatbot
5637 | IIRM-8464 | Story | AI: Support chart based responses for Tasks and Meetings | Done | Prabhakar Mantripragada | iWork
5638 | IIRM-8465 | Story | AI: Support the AI Agents are able to consume context and provide responses | Draft | Prabhakar Mantripragada | iWork | IIRM-789 — SOW#62 - AI Chatbot
5639 | IIRM-8466 | Story | AI: Optimise cost and improve query performance | Draft | Prabhakar Mantripragada | iWork
5640 | IIRM-8467 | Bug | IIRM :SO: Srilanka user got incorrect TC Brokerage Percentage in Meeting for final Negotiation | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5641 | IIRM-8468 | Bug | IWORK: Manage Policies: View Configuration button closes Nudges on first click and opens configuration only on second click | Open | PATIBANDLA VELANGINI RAJU |  | IIRM-777 — SOW#50 - Policy Configurator
5642 | IIRM-8469 | Bug | IBP: Inception/ Endorsement: Unable to upload claims file | Done | Akhila Gattu
5643 | IIRM-8470 | Bug | IWORK: Policy Dashboard shows Inception Completed even when TPA Upload step is not completed | Open | PATIBANDLA VELANGINI RAJU
5644 | IIRM-8471 | Bug | CD balance: Wrong CD balance shown for deletion of employee | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5645 | IIRM-8472 | QAlity Test | ContactMatrix: Verify Contact Matrix displays complete contact details for employee with single active policy | Draft | Akhila Gattu
5646 | IIRM-8473 | QAlity Test | ContactMatrix: Verify Contact Matrix displays policy-wise grouped contact details for employee with multiple active policies | Draft | Akhila Gattu
5647 | IIRM-8474 | QAlity Test | ContactMatrix: Verify Contact Matrix displays available contacts and shows "Unavailable" for missing TPA Coordinator without blocking page load | Draft | Akhila Gattu
5648 | IIRM-8475 | QAlity Test | ContactMatrix: Verify Contact Matrix displays universal Customer Service number when TPA Branch cannot be resolved | Draft | Akhila Gattu
5649 | IIRM-8476 | QAlity Test | ContactMatrix: Verify Contact Matrix displays appropriate error message and guidance when employee has no active policies | Draft | Akhila Gattu
5650 | IIRM-8477 | QAlity Test | ContactMatrix: Verify user can copy phone numbers from Contact Matrix to clipboard | Draft | Akhila Gattu
5651 | IIRM-8478 | QAlity Test | ContactMatrix: Verify click-to-call functionality initiates phone call on mobile device when user taps phone number | Draft | Akhila Gattu
5652 | IIRM-8479 | QAlity Test | ContactMatrix: Verify Contact Matrix maintains correct state when using browser back/forward navigation | Draft | Akhila Gattu
5653 | IIRM-8480 | QAlity Test | ContactMatrix: Verify system validates and handles invalid phone number formats in contact data | Draft | Akhila Gattu
5654 | IIRM-8481 | QAlity Test | ContactMatrix: Verify system validates email format and mailto: links work correctly in Contact Matrix | Draft | Akhila Gattu
5655 | IIRM-8482 | QAlity Test | ContactMatrix: Verify Contact Matrix correctly displays and handles special characters, Unicode, and symbols in contact details | Draft | Akhila Gattu
5656 | IIRM-8483 | QAlity Test | ContactMatrix: Verify Contact Matrix performs acceptably when employee has 20+ active policies | Draft | Akhila Gattu
5657 | IIRM-8484 | QAlity Test | ContactMatrix: Verify Contact Matrix data integrity when policy-TPA mapping is updated while user is viewing the page | Draft | Akhila Gattu
5658 | IIRM-8485 | QAlity Test | ContactMatrix: Verify Contact Matrix layout adapts correctly to different mobile orientations and screen sizes | Draft | Akhila Gattu
5659 | IIRM-8486 | QAlity Test | ContactMatrix: Verify Contact Matrix API and UI perform acceptably under load of 100 concurrent users | Draft | Akhila Gattu
5660 | IIRM-8487 | QAlity Test | ContactMatrix: Verify employee cannot view Contact Matrix for policies belonging to other employees | Draft | Akhila Gattu
5661 | IIRM-8488 | QAlity Test | ContactMatrix: Verify Contact Matrix displays appropriate error when accessed without network connection | Draft | Akhila Gattu
5662 | IIRM-8489 | QAlity Test | ContactMatrix: Verify Contact Matrix provides feedback and loads gracefully under slow network conditions (3G/2G speeds) | Draft | Akhila Gattu
5663 | IIRM-8490 | QAlity Test | ContactMatrix: Verify system prevents XSS injection through malicious TPA name in Contact Matrix display | Draft | Akhila Gattu
5664 | IIRM-8491 | QAlity Test | ContactMatrix: Verify system prevents SQL injection attacks through contact phone number fields | Draft | Akhila Gattu
5665 | IIRM-8492 | QAlity Test | ContactMatrix: Verify Contact Matrix correctly handles scenario when employee's policy is deactivated while viewing contacts | Draft | Akhila Gattu
5666 | IIRM-8493 | QAlity Test | ContactMatrix: Verify Contact Matrix updates correctly when TPA Branch is reassigned for an employee's policy | Draft | Akhila Gattu
5667 | IIRM-8494 | QAlity Test | ContactMatrix: Verify Contact Matrix correctly handles and displays contact data in multiple languages and scripts (Hindi, Arabic, Chinese) | Draft | Akhila Gattu
5668 | IIRM-8495 | QAlity Test | ClaimStatus: Verify Claim Status column exists in endorsement upload template | Draft | PATIBANDLA VELANGINI RAJU
5669 | IIRM-8496 | QAlity Test | ClaimStatus: Verify Claim Status column name | Draft | PATIBANDLA VELANGINI RAJU
5670 | IIRM-8497 | QAlity Test | ClaimStatus: Verify Claim Status accepts only Yes/No | Draft | PATIBANDLA VELANGINI RAJU
5671 | IIRM-8498 | QAlity Test | ClaimStatus: Verify Claim Status is mandatory | Draft | PATIBANDLA VELANGINI RAJU
5672 | IIRM-8499 | QAlity Test | ClaimStatus: Verify Refund should be 0 when Claim Status = Yes | Draft | PATIBANDLA VELANGINI RAJU
5673 | IIRM-8500 | QAlity Test | ClaimStatus: Verify Ignore proration when Claim Status = Yes | Draft | PATIBANDLA VELANGINI RAJU
5674 | IIRM-8501 | QAlity Test | ClaimStatus: Verify Prorated refund when Claim Status = No | Draft | PATIBANDLA VELANGINI RAJU
5675 | IIRM-8502 | QAlity Test | ClaimStatus: Verify Refund calculation based on effective date | Draft | PATIBANDLA VELANGINI RAJU
5676 | IIRM-8503 | QAlity Test | ClaimStatus: Verify Mismatch: system has claims but upload says No | Draft | PATIBANDLA VELANGINI RAJU
5677 | IIRM-8504 | QAlity Test | ClaimStatus: Verify Multiple employees with mixed Claim Status | Draft | PATIBANDLA VELANGINI RAJU
5678 | IIRM-8505 | QAlity Test | ClaimStatus: Verify Upload without Claim Status column | Draft | PATIBANDLA VELANGINI RAJU
5679 | IIRM-8506 | QAlity Test | ClaimStatus: Verify Lowercase yes/no handling | Draft | PATIBANDLA VELANGINI RAJU
5680 | IIRM-8507 | QAlity Test | ClaimStatus: Verify Leading/trailing spaces in Claim Status | Draft | PATIBANDLA VELANGINI RAJU
5681 | IIRM-8508 | QAlity Test | ClaimStatus: Verify Large volume upload | Draft | PATIBANDLA VELANGINI RAJU
5682 | IIRM-8509 | QAlity Test | ClaimStatus: Verify Claim Status stored in DB | Draft | PATIBANDLA VELANGINI RAJU
5683 | IIRM-8510 | QAlity Test | ClaimStatus: Verify CD amount and premiums in CD account tab | Draft | PATIBANDLA VELANGINI RAJU
5684 | IIRM-8520 | Bug | IIRM: Held Cover Note shows unexpected validation errors after Placement Slip Generation with multiple insurers | Done | Prathiphala Kandula |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5685 | IIRM-8521 | Bug | IIRM:SO: Sri Lanka Placement Slip Generation fails for Existing Account with “Numerical Field Overflow” error | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5686 | IIRM-8522 | Bug | IIRM: SO: Meeting for Final Negotiation: Basic Brokerage Amount do not auto-fill when only Basic Brokerage Percentage is entered | Done | Prathiphala Kandula |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5687 | IIRM-8523 | Bug | IIRM: SO:Sri Lanka users – TC Premium, Total Brokerage, and VAT (Percentage & Amount) auto-population inconsistencies across policy workflow | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5688 | IIRM-8524 | Bug | IIRM: SO: ISG Approval: “Navigate” button on approval notification card is not clickable | Done | Prathiphala Kandula |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5689 | IIRM-8525 | QAlity Test | RelationshipGroup: Valid Relationship Group Selection with No Dependents | Draft | Akhila Gattu
5690 | IIRM-8526 | QAlity Test | RelationshipGroup: Valid Relationship Group Selection with Fewer Dependents | Draft | Akhila Gattu
5691 | IIRM-8527 | QAlity Test | RelationshipGroup: Invalid Relationship Group Selection | Draft | Akhila Gattu
5692 | IIRM-8528 | QAlity Test | RelationshipGroup: Dependents Exceed Selected Relationship Group Limit | Draft | Akhila Gattu
5693 | IIRM-8529 | QAlity Test | RelationshipGroup: Valid SELF Relationship Group with No Dependents | Draft | Akhila Gattu
5694 | IIRM-8530 | QAlity Test | RelationshipGroup: Valid SELF+SPOUSE with Spouse Dependent | Draft | Akhila Gattu
5695 | IIRM-8531 | QAlity Test | RelationshipGroup: Missing Relationship Group Selection Column | Draft | Akhila Gattu
5696 | IIRM-8532 | QAlity Test | RelationshipGroup: Empty Relationship Group Selection Value | Draft | Akhila Gattu
5697 | IIRM-8533 | QAlity Test | RelationshipGroup: Endorsement - Upgrade Relationship Group (SELF to SELF+SPOUSE) | Draft | Akhila Gattu
5698 | IIRM-8534 | QAlity Test | RelationshipGroup: Endorsement - Downgrade Relationship Group (SELF+4 DEPENDENTS to SELF+2 DEPENDENTS) | Draft | Akhila Gattu
5699 | IIRM-8535 | QAlity Test | RelationshipGroup: Endorsement - Invalid Downgrade with Excess Dependents | Draft | Akhila Gattu
5700 | IIRM-8536 | QAlity Test | RelationshipGroup: Endorsement - No Change in Relationship Group | Draft | Akhila Gattu
5701 | IIRM-8537 | QAlity Test | RelationshipGroup: Bulk Upload with Mixed Valid and Invalid Relationship Groups | Draft | Akhila Gattu
5702 | IIRM-8538 | QAlity Test | RelationshipGroup: Case Sensitivity of Relationship Group Selection Values | Draft | Akhila Gattu
5703 | IIRM-8539 | QAlity Test | RelationshipGroup: FAMILY Relationship Group with Maximum Dependents | Draft | Akhila Gattu
5704 | IIRM-8540 | QAlity Test | RelationshipGroup: Multiple Endorsements in Single File with Different Relationship Group Changes | Draft | Akhila Gattu
5705 | IIRM-8541 | QAlity Test | RelationshipGroup: Special Characters in Relationship Group Selection | Draft | Akhila Gattu
5706 | IIRM-8542 | QAlity Test | RelationshipGroup: Premium Calculation Verification for Each Relationship Group Slab | Draft | Akhila Gattu
5707 | IIRM-8543 | QAlity Test | RelationshipGroup: Endorsement Date Impact on Premium Calculation | Draft | Akhila Gattu
5708 | IIRM-8544 | QAlity Test | RelationshipGroup: Template Download Includes Relationship Group Selection Column | Draft | Akhila Gattu
5709 | IIRM-8545 | QAlity Test | RelationshipGroup: Template Download for Endorsement Includes Relationship Group Selection | Draft | Akhila Gattu
5710 | IIRM-8546 | QAlity Test | RelationshipGroup: Policy Without Relationship Group Configuration | Draft | Akhila Gattu
5711 | IIRM-8547 | QAlity Test | RelationshipGroup: Numeric Values in Relationship Group Selection | Draft | Akhila Gattu
5712 | IIRM-8548 | QAlity Test | RelationshipGroup: Concurrent Endorsements with Relationship Group Change | Draft | Akhila Gattu
5713 | IIRM-8549 | QAlity Test | RelationshipGroup: Maximum Length of Relationship Group Selection Value | Draft | Akhila Gattu
5714 | IIRM-8550 | Bug | IIRM: SO: Meeting for Final Negotiation: Auto-calculations update slowly and show incorrect values before stabilizing | Done | Prathiphala Kandula |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5715 | IIRM-8551 | Bug | IIRM: SO: Enter Quote: Save shows schema error “quoteDetails.totalGrossPremiumIncTax: property totalGrossPremiumIncTax should not exist” | Done | Prathiphala Kandula |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5716 | IIRM-8552 | Bug | IIRM: SO: Sri Lanka – Meeting For Final Negotiation User Meeting Triggers Error for selectFinalisedQuote.totalGrossPremiumIncTax | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5717 | IIRM-8553 | Bug | IIRM: SO: Meeting for Final Negotiation: Brokerage Amount persists after clearing percentage and inflates multi-insurer totals (defaults to 1% of Basic Premium) | Ready for QA | Prathiphala Kandula
5718 | IIRM-8554 | Bug | IIRM: SO: India: Enter Quote: Terrorism Premium not displayed with Indian comma formatting | Done | Prathiphala Kandula |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5719 | IIRM-8555 | Bug | RelationshipGroup: Premiums not matching | Done | Akhila Gattu
5720 | IIRM-8556 | Story | iWork to iConnect - SSO Implementation | Done | NithinKrishna Sirigiri |  | IIRM-8420 — IIRM (iWork) to External SSO
5721 | IIRM-8557 | Story | Inception/Endorsement: AddTemplate helper static block | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5722 | IIRM-8558 | Bug | Only first 10 values can be visible /populated for Insurer contact details | Open | Prajakta Vijay Kadam
5723 | IIRM-8559 | Bug | Error File Not Generated and Upload Status Not Updated When Claim Upload Fails | Open | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
5724 | IIRM-8560 | Bug | Missing Field-Level and Business Rule Validations in Claim Upload | Open | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
5725 | IIRM-8561 | Bug | Dependent Claims Incorrectly Allowed for GTL and GPA Policies | Open | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
5726 | IIRM-8562 | Bug | Unable to Reopen or Navigate to Policy Step After Uploading Records | Open | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
5727 | IIRM-8563 | Bug | Track Claim Table Not Updating Claim Amount and Status Based on Upload Status | Open | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
5728 | IIRM-8564 | Story | Claim Upload Reprocessing and Status Validation Not Working; Processed Counts Incorrect | Draft | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
5729 | IIRM-8565 | Story | Claim Summary - Count not updating as expected | Draft | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
5730 | IIRM-8566 | Bug | Claim Summary Counts Not Updating and Missing Settled Status | Open | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
5731 | IIRM-8567 | Task | Iwork: Portal Configuration implementation (FE) | Done | Nikhil V
5732 | IIRM-8568 | Task | Iwork: Portal Configuration Implementation (BE) | WORK IN PROGRESS | Nikhil V
5733 | IIRM-8569 | Bug | IIRM: Basic Premium label is displayed incorrectly for Indian users | Done - Not Reproducible | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5734 | IIRM-8570 | Bug | IIRM: Task: QCR: Able to complete the activity even though an open task is linked | Done - Not Reproducible | Leela Pakalapati | iWork
5735 | IIRM-8571 | Bug | IIRM: Placement Slip Submission Fails Due to Missing Brokerage Percentage | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5736 | IIRM-8572 | Story | End User Onboarding | Done | Jadhav Sai Prasad |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
5737 | IIRM-8573 | Bug | IIRM: Failed to create employe Error-> missing FROM-clause entry for table "t | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-739 — SOW#12 - Manage Employees
5738 | IIRM-8574 | Bug | TPA Upload: TPA Step glitch is visible during Inception/Endorsement Flow Even When TPA Upload Constraint Is Set to “No” | Reopen | Akhila Gattu
5739 | IIRM-8575 | Bug | TPA: Completion process of inception popupnot showing , if TPA constriant set as no | Done | Akhila Gattu
5740 | IIRM-8576 | QAlity Test | Claim: Verify Employee addition and deletion for premium count | Draft | Akhila Gattu
5741 | IIRM-8577 | Bug | IIRM: Updated Insurer Section Not Populated After CD Details Change or Task Creation | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5742 | IIRM-8578 | Task | Premium needs to be changed to 0 for certain employees as there are some open claims - Total 6 requests so far. Sent separate email for each such request. (DB Change) | Draft | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5743 | IIRM-8579 | Task | Policy #337816 - Premium is not calculating correctly when deletion is there. There are 2 endorsements for this policy where premium is not correct. (Endorsement No 1461 and 1477) | Done | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5744 | IIRM-8580 | Task | While uploading the deletion file, receiving an error message stating that the employee with ID TR10396897 is not enrolled in the selected policy. (Policy no : 337814 and Endorsement id:1463) | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5745 | IIRM-8581 | Story | Opty.: "Select Insurer" drop-down show List of insurers from "Enter Quote" after Enter quote activity | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
5746 | IIRM-8582 | Story | Opty.: Final Negotiation - Provide option to "Edit Quote" | Draft | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
5747 | IIRM-8583 | Bug | Endorsement - Delete Emp - Show failed records in the Error File | Open | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5748 | IIRM-8584 | Bug | RelationshipGroup: On endorsement document download sheet we need to show relationship Group column | Open | Akhila Gattu
5749 | IIRM-8585 | QAlity Test | RelationshipGroup: Verify Premium calculation for PerLife and PerFamily | Draft | Akhila Gattu
5750 | IIRM-8586 | Story | Inception/Endorsement: Handling large files (Ex. 3L records) | QA in Progress | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5751 | IIRM-8587 | Bug | IIRM ¦ Bizdone: Lead Insurer Name and Location Not Displayed in Bizdone Output | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-778 — SOW#51 - Admin Reports
5752 | IIRM-8588 | QAlity Test | IBPLogin: Verify BD Executive can enable Email + Password authentication with all configuration options | Draft | Akhila Gattu
5753 | IIRM-8589 | QAlity Test | IBPLogin: Verify system prevents enabling Email + OTP when Email + Password is active | Draft | Akhila Gattu
5754 | IIRM-8590 | QAlity Test | IBPLogin: Verify end user can set up password for first time using email verification link | Draft | Akhila Gattu
5755 | IIRM-8591 | QAlity Test | IBPLogin: Verify successful login with correct email and password credentials | Draft | Akhila Gattu
5756 | IIRM-8592 | QAlity Test | IBPLogin: Verify account lockout after configured failed login attempts | Draft | Akhila Gattu
5757 | IIRM-8593 | QAlity Test | IBPLogin: Verify BD Executive can configure Email + OTP authentication with all OTP settings | Draft | Akhila Gattu
5758 | IIRM-8594 | QAlity Test | IBPLogin: Verify successful passwordless login using email and OTP | Draft | Akhila Gattu
5759 | IIRM-8595 | QAlity Test | IBPLogin: Verify system rejects expired OTP and shows appropriate error | Draft | Akhila Gattu
5760 | IIRM-8596 | QAlity Test | IBPLogin: Verify configuration of Phone + Password authentication with all settings | Draft | Akhila Gattu
5761 | IIRM-8597 | QAlity Test | IBPLogin: Verify successful login with phone number and password | Draft | Akhila Gattu
5762 | IIRM-8598 | QAlity Test | IBPLogin: Verify configuration of Phone + OTP authentication | Draft | Akhila Gattu
5763 | IIRM-8599 | QAlity Test | IBPLogin: Verify passwordless login using phone and SMS OTP | Draft | Akhila Gattu
5764 | IIRM-8600 | QAlity Test | IBPLogin: Verify configuration of Google OAuth authentication | Draft | Akhila Gattu
5765 | IIRM-8601 | QAlity Test | IBPLogin: Verify successful login using Google OAuth | Draft | Akhila Gattu
5766 | IIRM-8602 | QAlity Test | IBPLogin: Verify system rejects Google account not linked to Employee Master | Draft | Akhila Gattu
5767 | IIRM-8603 | QAlity Test | IBPLogin: Verify configuration of Username + Password authentication with username format selection | Draft | Akhila Gattu
5768 | IIRM-8604 | QAlity Test | IBPLogin: Verify login with username (Year + Employee ID) and Employee ID as password | Draft | Akhila Gattu
5769 | IIRM-8605 | QAlity Test | IBPLogin: Verify configuration of Universal URL Default Login (Employee ID + Date of Birth) | Draft | Akhila Gattu
5770 | IIRM-8606 | QAlity Test | IBPLogin: Verify login using Employee ID and Date of Birth on universal URL | Draft | Akhila Gattu
5771 | IIRM-8607 | QAlity Test | IBPLogin: Verify error handling for invalid Employee ID | Draft | Akhila Gattu
5772 | IIRM-8608 | QAlity Test | IBPLogin: Verify error handling for incorrect Date of Birth | Draft | Akhila Gattu
5773 | IIRM-8609 | QAlity Test | IBPLogin: Verify configuration of Email MFA as second factor after password | Draft | Akhila Gattu
5774 | IIRM-8610 | QAlity Test | IBPLogin: Verify complete MFA flow after successful password authentication | Draft | Akhila Gattu
5775 | IIRM-8611 | QAlity Test | IBPLogin: Verify password reset flow using email verification | Draft | Akhila Gattu
5776 | IIRM-8612 | QAlity Test | IBPLogin: Verify automatic session timeout after configured inactivity period | Draft | Akhila Gattu
5777 | IIRM-8613 | QAlity Test | IBPLogin: Verify system prevents malicious file uploads by validating file content, not just extension | Draft | Akhila Gattu
5778 | IIRM-8614 | Sub-task | Render buttons based on policy status in My Insurance page | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5779 | IIRM-8615 | Sub-task | List all policy choices in Multi-enrollment page with Title separation | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5780 | IIRM-8616 | Sub-task | Summary page with consolidated policy overview | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5781 | IIRM-8617 | Sub-task | Cross-Policy Dependent Management system | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5782 | IIRM-8618 | Sub-task | Unified enrollment submission workflow | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5783 | IIRM-8619 | Sub-task | Premium calculation aggregation across policies | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5784 | IIRM-8620 | Sub-task | Enrollment status tracking and progress indicators | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5785 | IIRM-8621 | Sub-task | Multi-policy validation and error handling | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5786 | IIRM-8622 | Sub-task | Navigation flow between enrollment steps | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5787 | IIRM-8623 | Sub-task | Enrollment confirmation and success handling | Done | Richa Bagchi Mazumdar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
5788 | IIRM-8624 | Bug | Premium is not getting calculated properly for relationship group | Open | Richa Bagchi Mazumdar |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5789 | IIRM-8625 | Sub-task | Implement Audit Logs for inception and endorsement | Done | Richa Bagchi Mazumdar |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
5790 | IIRM-8626 | Bug | IIRM: New insurer added in Broking Slip for Opty 1179915. | Open | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5791 | IIRM-8627 | Sub-task | Excel writing for the large record processing mainly for creating error files in inception flow | Done | Jagadeesh |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
5792 | IIRM-8628 | Bug | IIRM: Add 2-decimal precision and reverse auto-calculation for brokerage amount/percentage | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
5793 | IIRM-8629 | Sub-task | Backend Changes: Add per-component policy identifiers, relationships, and flags table for new Policy Configurator | WORK IN PROGRESS | Richa Bagchi Mazumdar |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
5794 | IIRM-8630 | QAlity Test | IIRM: Select Insurer should auto-prefill for single-insurer quote | EXTERNAL REVIEW PENDING | SaikumarMahanthi | iWork
5795 | IIRM-8631 | QAlity Test | IIRM: Select Insurer should auto-prefill for multiple-insurer quote | EXTERNAL REVIEW PENDING | SaikumarMahanthi | iWork
5796 | IIRM-8632 | QAlity Test | IIRM: Ensure data consistency from Final Negotiation stage till Policy Confirmation | EXTERNAL REVIEW PENDING | SaikumarMahanthi | iWork
5797 | IIRM-8633 | QAlity Test | IIRM: Verify auto-population of insurer and financial fields on Finalised Version Quote selection | EXTERNAL REVIEW PENDING | SaikumarMahanthi | iWork
5798 | IIRM-8634 | QAlity Test | IIRM: Verify updated Final Version details are carried forward to subsequent activities | EXTERNAL REVIEW PENDING | SaikumarMahanthi | iWork
5799 | IIRM-8635 | Story | Opty.: Enable decimals for all the amount fields in Opportunity flow | Draft | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5800 | IIRM-8636 | QAlity Test | UnifiedEnrollment: Verify enrollment eligibility enforcement based on policy-specific enrollment windows | Draft | Akhila Gattu
5801 | IIRM-8637 | QAlity Test | UnifiedEnrollment: Verify all eligible policies under a benefit category are auto-selected when enrollment is initiated at benefit level | Draft | Akhila Gattu
5802 | IIRM-8638 | QAlity Test | UnifiedEnrollment: Verify that only eligible policies are pre-selected when benefit-level enrollment is initiated with mixed policy eligibility | Draft | Akhila Gattu
5803 | IIRM-8639 | QAlity Test | UnifiedEnrollment: Verify that only the selected policy is included when enrollment is initiated at policy level | Draft | Akhila Gattu
5804 | IIRM-8640 | QAlity Test | UnifiedEnrollment: Verify global "Enroll All" includes all eligible policies across Compulsory, Flex, and Optional benefit categories | Draft | Akhila Gattu
5805 | IIRM-8641 | QAlity Test | UnifiedEnrollment: Verify "Enroll All" correctly filters and includes only eligible policies when eligibility is mixed across benefit categories | Draft | Akhila Gattu
5806 | IIRM-8642 | QAlity Test | UnifiedEnrollment: Verify partial enrollment behavior when user completes enrollment for subset of policies and resumes later | Draft | Akhila Gattu
5807 | IIRM-8643 | QAlity Test | UnifiedEnrollment: Verify behavior when enrollment window expires for incomplete policies during partial enrollment scenario | Draft | Akhila Gattu
5808 | IIRM-8644 | QAlity Test | UnifiedEnrollment: Verify dependent section is dynamically shown for GMC policy and hidden for GTL and GPA during unified enrollment | Draft | Akhila Gattu
5809 | IIRM-8645 | QAlity Test | UnifiedEnrollment: Verify accurate premium calculation and breakdown when enrolling in multiple policies with company and employee contributions | Draft | Akhila Gattu
5810 | IIRM-8646 | QAlity Test | UnifiedEnrollment: Verify premium calculation handles edge cases including zero amounts, missing contribution config, and calculation errors | Draft | Akhila Gattu
5811 | IIRM-8647 | QAlity Test | UnifiedEnrollment: Verify single confirmation action enrolls all selected policies and updates status atomically | Draft | Akhila Gattu
5812 | IIRM-8648 | QAlity Test | UnifiedEnrollment: Verify system handles enrollment confirmation failure gracefully with proper rollback and user notification | Draft | Akhila Gattu
5813 | IIRM-8649 | QAlity Test | UnifiedEnrollment: Verify post-enrollment details page displays all enrolled policies with complete coverage and premium information | Draft | Akhila Gattu
5814 | IIRM-8650 | QAlity Test | UnifiedEnrollment: Verify user cannot re-enroll or edit a frozen policy outside the modification window | Draft | Akhila Gattu
5815 | IIRM-8651 | QAlity Test | UnifiedEnrollment: Verify policy-specific validation rules are enforced during cross-category unified enrollment | Draft | Akhila Gattu
5816 | IIRM-8652 | QAlity Test | UnifiedEnrollment: Verify user can initiate enrollment only once per enrollment cycle and cannot re-initiate after completion | Draft | Akhila Gattu
5817 | IIRM-8653 | QAlity Test | UnifiedEnrollment: Verify policy-specific plan rules (e.g., GMC Silver/Gold/Platinum) are enforced and displayed correctly during enrollment | Draft | Akhila Gattu
5818 | IIRM-8654 | QAlity Test | UnifiedEnrollment: Verify policies outside enrollment window are correctly displayed as disabled and cannot be included in enrollment flow | Draft | Akhila Gattu
5819 | IIRM-8655 | Task | IIRM: Ready for QA Bugs verifications and regression testing | Done | SaikumarMahanthi | iWork
5820 | IIRM-8656 | Task | IIRM: Enter Quote changes Test cases authering | Done | SaikumarMahanthi |  | IIRM-797 — SOW#69 - Manage Opportunities
5821 | IIRM-8657 | Task | IIRM: SO/RO/Policy sync verification and retesting | Draft | SaikumarMahanthi
5822 | IIRM-8658 | Bug | IBP: Login: Reset password with mobile number not working | Open | Akhila Gattu
5823 | IIRM-8659 | Bug | IBP:Login: Resend count and change phone number not available in login with phone number screen | Done | Akhila Gattu
5824 | IIRM-8660 | Bug | IBP: Login: Email with password login not available | Open | Akhila Gattu
5825 | IIRM-8661 | Sub-task | Update the Excel format | Done | NithinKrishna Sirigiri |  | IIRM-8372 — QCR Comparison Excel download template for Lanka
5826 | IIRM-8662 | Sub-task | Update Address based on the Org. | Done | NithinKrishna Sirigiri |  | IIRM-8372 — QCR Comparison Excel download template for Lanka
5827 | IIRM-8663 | Bug | PolicyConfig: Typo in Policy Number Label – “Provision Policy Number” instead of “Provisional Policy Number” | Done | PATIBANDLA VELANGINI RAJU |  | IIRM-777 — SOW#50 - Policy Configurator
5828 | IIRM-8664 | Bug | PolicyConfig: Incorrect Relationship Options Displayed for Parent Policy Component | Open | PATIBANDLA VELANGINI RAJU |  | IIRM-777 — SOW#50 - Policy Configurator
5829 | IIRM-8665 | Bug | IBP: Login: Get OTP instead text missing as per design for login with mobilenumber+password | Ready for QA | Akhila Gattu
5830 | IIRM-8666 | Bug | IBP: Login: Reset password screen for mobile number not showing as per figma | Open | Akhila Gattu
5831 | IIRM-8667 | Story | Allow 2 decimals in all the amount fields in Opty. activities | Done | NithinKrishna Sirigiri |  | IIRM-756 — SOW#29 - Manage ISG Stages
5832 | IIRM-8668 | Bug | PolicyConfig: Policy Choices data is not fetched when navigating between policy steps using breadcrumb | Done | PATIBANDLA VELANGINI RAJU |  | IIRM-777 — SOW#50 - Policy Configurator
5833 | IIRM-8669 | Task | Add “Add New Quotation” button in Final Negotiation Activity | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5834 | IIRM-8670 | Task | Kenya localization for company fields | Open | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5835 | IIRM-8671 | Story | Localisation: Kenya - Fields | Open | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5836 | IIRM-8672 | Task | Kenya (Placement Slip and Broking Slip) changes | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5837 | IIRM-8673 | Story | Final Secure SSO Flow: iWork → iConnect → Supabase | Draft | Richa Bagchi Mazumdar |  | IIRM-8420 — IIRM (iWork) to External SSO
5838 | IIRM-8674 | QAlity Test | UnifiedEnrollment: Verify Single Policy Enrolment Flow | Draft | Akhila Gattu
5839 | IIRM-8675 | QAlity Test | UnifiedEnrollment: Verify Single Policy Enrolment Does Not Affect Other Policies | Draft | Akhila Gattu
5840 | IIRM-8676 | QAlity Test | UnifiedEnrollment: Verify Single Policy Edit After Enrolment | Draft | Akhila Gattu
5841 | IIRM-8677 | QAlity Test | UnifiedEnrollment: Verify Single Policy Enrolment Within Cutoff Period | Draft | Akhila Gattu
5842 | IIRM-8678 | QAlity Test | UnifiedEnrollment: Verify Single Policy Enrolment After Cutoff with Auto-Lock Disabled | Draft | Akhila Gattu
5843 | IIRM-8679 | QAlity Test | UnifiedEnrollment: Verify "Enroll All" CTA Displays When No Enrolment Started | Draft | Akhila Gattu
5844 | IIRM-8680 | QAlity Test | UnifiedEnrollment: Verify Unified Enrolment Screen Initialization | Draft | Akhila Gattu
5845 | IIRM-8681 | QAlity Test | UnifiedEnrollment: Verify Multiple Policy Selection in Unified Enrolment | Draft | Akhila Gattu
5846 | IIRM-8682 | QAlity Test | UnifiedEnrollment: Verify Default Selections for Collapsed Policies | Draft | Akhila Gattu
5847 | IIRM-8683 | QAlity Test | UnifiedEnrollment: Verify Ineligible Policy Display in Unified Enrolment | Draft | Akhila Gattu
5848 | IIRM-8684 | QAlity Test | UnifiedEnrollment: Verify Unified Enrolment with All Policies Ineligible | Draft | Akhila Gattu
5849 | IIRM-8685 | QAlity Test | UnifiedEnrollment: Verify Unified Enrolment for GMC Policies Only | Draft | Akhila Gattu
5850 | IIRM-8686 | QAlity Test | UnifiedEnrollment: Verify Unified Enrolment with Mixed Policy Types | Draft | Akhila Gattu
5851 | IIRM-8687 | QAlity Test | UnifiedEnrollment: Verify Policy Before Enrolment Start Date | Draft | Akhila Gattu
5852 | IIRM-8688 | QAlity Test | UnifiedEnrollment: Verify Policy After Enrolment End Date | Draft | Akhila Gattu
5853 | IIRM-8689 | QAlity Test | UnifiedEnrollment: Verify Policy Within Enrolment Period - Not Enrolled | Draft | Akhila Gattu
5854 | IIRM-8690 | QAlity Test | UnifiedEnrollment: Verify Policy Within Enrolment Period - Already Enrolled | Draft | Akhila Gattu
5855 | IIRM-8691 | QAlity Test | UnifiedEnrollment: Verify Auto-Lock After Cutoff Date | Draft | Akhila Gattu
5856 | IIRM-8692 | QAlity Test | UnifiedEnrollment: Verify Auto-Lock After Cutoff - Already Enrolled | Draft | Akhila Gattu
5857 | IIRM-8693 | QAlity Test | UnifiedEnrollment: Verify Lock After Confirmation | Draft | Akhila Gattu
5858 | IIRM-8694 | QAlity Test | UnifiedEnrollment: Verify Mid-Year Enrolment Allowed | Draft | Akhila Gattu
5859 | IIRM-8695 | QAlity Test | UnifiedEnrollment: Verify Mid-Year Enrolment Disabled | Draft | Akhila Gattu
5860 | IIRM-8696 | QAlity Test | UnifiedEnrollment: Verify Multiple Eligibility Criteria Evaluation | Draft | Akhila Gattu
5861 | IIRM-8697 | QAlity Test | UnifiedEnrollment: Verify Subsequent Eligibility Changes - Policy Becomes Eligible | Draft | Akhila Gattu
5862 | IIRM-8698 | QAlity Test | UnifiedEnrollment: Verify Subsequent Eligibility Changes - Policy Becomes Locked | Draft | Akhila Gattu
5863 | IIRM-8699 | QAlity Test | UnifiedEnrollment: Verify "Enroll All" CTA - Initial State | Draft | Akhila Gattu
5864 | IIRM-8700 | QAlity Test | UnifiedEnrollment: Verify "Continue Enrolment" CTA After Save | Draft | Akhila Gattu
5865 | IIRM-8701 | QAlity Test | UnifiedEnrollment: Verify "View Past Enrolment Summaries" CTA | Draft | Akhila Gattu
5866 | IIRM-8702 | QAlity Test | UnifiedEnrollment: Verify "Edit Enrolment" CTA | Draft | Akhila Gattu
5867 | IIRM-8703 | QAlity Test | UnifiedEnrollment: Verify Disabled CTA - No Action Available | Draft | Akhila Gattu
5868 | IIRM-8704 | QAlity Test | UnifiedEnrollment: Verify CTA Transition - Enroll All to Continue | Draft | Akhila Gattu
5869 | IIRM-8705 | QAlity Test | UnifiedEnrollment: Verify CTA After Full Enrolment Completion | Draft | Akhila Gattu
5870 | IIRM-8706 | QAlity Test | UnifiedEnrollment: Verify "Show Summary" for Enrolled & Editable Policy | Draft | Akhila Gattu
5871 | IIRM-8707 | QAlity Test | UnifiedEnrollment: Verify "Show Summary" for Enrolled & Non-Editable Policy | Draft | Akhila Gattu
5872 | IIRM-8708 | QAlity Test | UnifiedEnrollment: Verify "Enroll Now" for Eligible Policy | Draft | Akhila Gattu
5873 | IIRM-8709 | QAlity Test | UnifiedEnrollment: Verify "Notify" CTA for Future Policy | Draft | Akhila Gattu
5874 | IIRM-8710 | QAlity Test | UnifiedEnrollment: Verify CTA for Future Policy Without Email | Draft | Akhila Gattu
5875 | IIRM-8711 | QAlity Test | UnifiedEnrollment: Verify Lock Icon Display for Locked Policy | Draft | Akhila Gattu
5876 | IIRM-8712 | QAlity Test | UnifiedEnrollment: Verify Edit with No Lock Configuration | Draft | Akhila Gattu
5877 | IIRM-8713 | QAlity Test | UnifiedEnrollment: Verify Edit Blocked by Lock After Confirmation | Draft | Akhila Gattu
5878 | IIRM-8714 | QAlity Test | UnifiedEnrollment: Verify Edit Blocked by Cutoff Date Lock | Draft | Akhila Gattu
5879 | IIRM-8715 | QAlity Test | UnifiedEnrollment: Verify Edit Allowed Before Cutoff | Draft | Akhila Gattu
5880 | IIRM-8716 | QAlity Test | UnifiedEnrollment: Verify Lock Precedence Order | Draft | Akhila Gattu
5881 | IIRM-8717 | QAlity Test | UnifiedEnrollment: Verify Unified Summary View-Only Mode | Draft | Akhila Gattu
5882 | IIRM-8718 | QAlity Test | UnifiedEnrollment: Verify Aggregated Calculations Display | Draft | Akhila Gattu
5883 | IIRM-8719 | QAlity Test | UnifiedEnrollment: Verify Policy-Specific Information Display | Draft | Akhila Gattu
5884 | IIRM-8720 | QAlity Test | UnifiedEnrollment: Verify Past Enrolment Summaries Access | Draft | Akhila Gattu
5885 | IIRM-8721 | QAlity Test | UnifiedEnrollment: Verify Sum Insured Visibility Enabled | Draft | Akhila Gattu
5886 | IIRM-8722 | QAlity Test | UnifiedEnrollment: Verify Sum Insured Visibility Disabled | Draft | Akhila Gattu
5887 | IIRM-8723 | QAlity Test | UnifiedEnrollment: Verify Employer Contribution Visibility Enabled | Draft | Akhila Gattu
5888 | IIRM-8724 | QAlity Test | UnifiedEnrollment: Verify Employer Contribution Visibility Disabled | Draft | Akhila Gattu
5889 | IIRM-8725 | QAlity Test | UnifiedEnrollment: Verify Mixed Employer Contribution Visibility | Draft | Akhila Gattu
5890 | IIRM-8726 | QAlity Test | UnifiedEnrollment: Verify Disclaimer Requirement Enabled | Draft | Akhila Gattu
5891 | IIRM-8727 | QAlity Test | UnifiedEnrollment: Verify Disclaimer Requirement Disabled | Draft | Akhila Gattu
5892 | IIRM-8728 | QAlity Test | UnifiedEnrollment: Verify Auto-Enrolment with Default Selection | Draft | Akhila Gattu
5893 | IIRM-8729 | QAlity Test | UnifiedEnrollment: Verify Landing Screen Initialization | Draft | Akhila Gattu
5894 | IIRM-8730 | QAlity Test | UnifiedEnrollment: Verify Plan/Option Default Selection | Draft | Akhila Gattu
5895 | IIRM-8731 | QAlity Test | UnifiedEnrollment: Verify Plan Expansion and Collapse | Draft | Akhila Gattu
5896 | IIRM-8732 | QAlity Test | UnifiedEnrollment: Verify Dynamic Premium Summary Updates | Draft | Akhila Gattu
5897 | IIRM-8733 | QAlity Test | UnifiedEnrollment: Verify Policy Information Visibility Per Configuration | Draft | Akhila Gattu
5898 | IIRM-8734 | QAlity Test | UnifiedEnrollment: Verify Save and Exit Functionality | Draft | Akhila Gattu
5899 | IIRM-8735 | QAlity Test | UnifiedEnrollment: Verify Resume via Continue from Unified Enrolment | Draft | Akhila Gattu
5900 | IIRM-8736 | QAlity Test | UnifiedEnrollment: Verify Resume via Continue from Single Policy | Draft | Akhila Gattu
5901 | IIRM-8737 | QAlity Test | UnifiedEnrollment: Verify Navigation to Summary Screen | Draft | Akhila Gattu
5902 | IIRM-8738 | QAlity Test | UnifiedEnrollment: Verify Back Navigation from Summary | Draft | Akhila Gattu
5903 | IIRM-8739 | QAlity Test | UnifiedEnrollment: Verify Confirmation and Submission | Draft | Akhila Gattu
5904 | IIRM-8740 | QAlity Test | UnifiedEnrollment: Verify Submission Blocked Without Disclaimer Acceptance | Draft | Akhila Gattu
5905 | IIRM-8741 | QAlity Test | UnifiedEnrollment: Verify Post-Confirmation Lock - Immediate Lock Enabled | Draft | Akhila Gattu
5906 | IIRM-8742 | QAlity Test | UnifiedEnrollment: Verify Post-Confirmation Lock - Cutoff-Based Lock | Draft | Akhila Gattu
5907 | IIRM-8743 | QAlity Test | UnifiedEnrollment: Verify Unified Enrolment with Partial Eligibility | Draft | Akhila Gattu
5908 | IIRM-8744 | QAlity Test | UnifiedEnrollment: Verify Independent Dependent Lists per GMC Policy | Draft | Akhila Gattu
5909 | IIRM-8745 | QAlity Test | UnifiedEnrollment: Verify Dependent Eligibility Validation per Policy | Draft | Akhila Gattu
5910 | IIRM-8746 | QAlity Test | UnifiedEnrollment: Verify Separate Submission Records per GMC Policy | Draft | Akhila Gattu
5911 | IIRM-8747 | QAlity Test | UnifiedEnrollment: Verify GMC and Non-GMC Policy Mix | Draft | Akhila Gattu
5912 | IIRM-8748 | QAlity Test | UnifiedEnrollment: Verify Save Draft in Unified Enrolment | Draft | Akhila Gattu
5913 | IIRM-8749 | QAlity Test | UnifiedEnrollment: Verify Resume from Saved Draft - Unified Flow | Draft | Akhila Gattu
5914 | IIRM-8750 | QAlity Test | UnifiedEnrollment: Verify Resume from Saved Draft - Single Policy Flow | Draft | Akhila Gattu
5915 | IIRM-8751 | QAlity Test | UnifiedEnrollment: Verify Cross-Device Draft Consistency | Draft | Akhila Gattu
5916 | IIRM-8752 | QAlity Test | UnifiedEnrollment: Verify Multiple Save and Resume Cycles | Draft | Akhila Gattu
5917 | IIRM-8753 | QAlity Test | UnifiedEnrollment: Verify Draft Preservation During Session Expiry | Draft | Akhila Gattu
5918 | IIRM-8754 | QAlity Test | UnifiedEnrollment: Verify Consolidated Disclaimer Display | Draft | Akhila Gattu
5919 | IIRM-8755 | QAlity Test | UnifiedEnrollment: Verify Disclaimer Acceptance Requirement | Draft | Akhila Gattu
5920 | IIRM-8756 | QAlity Test | UnifiedEnrollment: Verify Mixed Disclaimer Configuration | Draft | Akhila Gattu
5921 | IIRM-8757 | QAlity Test | UnifiedEnrollment: Verify Disclaimer Content and Mapping | Draft | Akhila Gattu
5922 | IIRM-8758 | QAlity Test | UnifiedEnrollment: Verify Save Failure Handling | Draft | Akhila Gattu
5923 | IIRM-8759 | QAlity Test | UnifiedEnrollment: Verify Submission Failure Handling | Draft | Akhila Gattu
5924 | IIRM-8760 | QAlity Test | UnifiedEnrollment: Verify Session Expiry Handling | Draft | Akhila Gattu
5925 | IIRM-8761 | QAlity Test | UnifiedEnrollment: Verify Concurrent Session Handling | Draft | Akhila Gattu
5926 | IIRM-8762 | QAlity Test | UnifiedEnrollment: Verify Data Consistency During System Failures | Draft | Akhila Gattu
5927 | IIRM-8763 | QAlity Test | UnifiedEnrollment: Verify Real-Time Premium Widget Updates | Draft | Akhila Gattu
5928 | IIRM-8764 | QAlity Test | UnifiedEnrollment: Verify Aggregate Premium Calculations | Draft | Akhila Gattu
5929 | IIRM-8765 | QAlity Test | UnifiedEnrollment: Verify Premium Calculation with Hidden Employer Contribution | Draft | Akhila Gattu
5930 | IIRM-8766 | QAlity Test | UnifiedEnrollment: Verify Premium Breakdown by Policy | Draft | Akhila Gattu
5931 | IIRM-8767 | QAlity Test | UnifiedEnrollment: Verify Premium Calculation Exclusions | Draft | Akhila Gattu
5932 | IIRM-8768 | QAlity Test | UnifiedEnrollment: Verify Premium Calculation with Dependents | Draft | Akhila Gattu
5933 | IIRM-8769 | Task | Add GST fields in enter quote for Indian user | Done | Richa Bagchi Mazumdar |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
5934 | IIRM-8770 | Bug | IBP: Access denied while login with Email+OTP | Open | Akhila Gattu
5935 | IIRM-8771 | Bug | IIRM: Dev: Approval notification card appears in "Overdue & Today" instead of "Next 7 Days" after BD activities completion | Open | Prathiphala Kandula
5936 | IIRM-8772 | Bug | IBp: UnifiedEnrollment: Policy enroll card not showing for with/without choices employees | Done | Akhila Gattu
5937 | IIRM-8773 | Bug | IBp: UnifiedEnrollment: No policies found should not be shown on enrollment window | Open | Akhila Gattu
5938 | IIRM-8774 | Bug | IBP: UnifiedEnrollment: On clicking cancel , already enrolled card is getting change to not enrolled | Done - Not a Bug | Akhila Gattu
5939 | IIRM-8775 | Task | PROD Request: Update Employee Premium to '0' (Claim = Yes) in Endorsement | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5940 | IIRM-8776 | Task | PROD Request_7-Jan-2026: | Draft | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
5941 | IIRM-8777 | Bug | IIRM: SO – Terrorism Brokerage Percentage Does Not Allow Two Decimal Digits in Final Negotiation | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
5942 | IIRM-8778 | QAlity Test | PortalPreference: Upload Logo - Valid Format (PNG) | Draft | Akhila Gattu
5943 | IIRM-8779 | QAlity Test | PortalPreference: Upload Logo - Valid Format (JPG) | Draft | Akhila Gattu
5944 | IIRM-8780 | QAlity Test | PortalPreference: Upload Logo - Valid Format (SVG) | Draft | Akhila Gattu
5945 | IIRM-8781 | QAlity Test | PortalPreference: Upload Logo - Invalid Format | Draft | Akhila Gattu
5946 | IIRM-8782 | QAlity Test | Upload Logo - Exceeds Size Limit | Draft | Akhila Gattu
5947 | IIRM-8783 | QAlity Test | Logo Display in Login Page | Draft | Akhila Gattu
5948 | IIRM-8784 | QAlity Test | Logo Display in Portal Header | Draft | Akhila Gattu
5949 | IIRM-8785 | QAlity Test | Header Text - Within Character Limit | Draft | Akhila Gattu
5950 | IIRM-8786 | QAlity Test | Header Text - At Maximum Character Limit | Draft | Akhila Gattu
5951 | IIRM-8787 | QAlity Test | Header Text - Exceeds Character Limit | Draft | Akhila Gattu
5952 | IIRM-8788 | QAlity Test | Tagline Text - Within Character Limit | Draft | Akhila Gattu
5953 | IIRM-8789 | QAlity Test | Tagline Text - Exceeds Character Limit | Draft | Akhila Gattu
5954 | IIRM-8790 | QAlity Test | Character Counter Display - Real-Time Update | Draft | Akhila Gattu
5955 | IIRM-8791 | QAlity Test | No Color Configuration Option Available | Draft | Akhila Gattu
5956 | IIRM-8792 | QAlity Test | Replace Existing Logo | Draft | Akhila Gattu
5957 | IIRM-8793 | QAlity Test | Portal URL Slug - Valid Input | Draft | Akhila Gattu
5958 | IIRM-8794 | QAlity Test | Portal URL Preview - Real-Time Display | Draft | Akhila Gattu
5959 | IIRM-8795 | QAlity Test | Portal URL Preview - Labels Display | Draft | Akhila Gattu
5960 | IIRM-8796 | QAlity Test | Portal URL - Read-Only Preview | Draft | Akhila Gattu
5961 | IIRM-8797 | QAlity Test | Portal URL Validation - Empty Field | Draft | Akhila Gattu
5962 | IIRM-8798 | QAlity Test | Portal URL Validation - Uppercase Letters | Draft | Akhila Gattu
5963 | IIRM-8799 | QAlity Test | Portal URL Validation - Special Characters | Draft | Akhila Gattu
5964 | IIRM-8800 | QAlity Test | Portal URL Validation - Spaces | Draft | Akhila Gattu
5965 | IIRM-8801 | QAlity Test | Portal URL Validation - Starts with Hyphen | Draft | Akhila Gattu
5966 | IIRM-8802 | QAlity Test | Portal URL Validation - Ends with Hyphen | Draft | Akhila Gattu
5967 | IIRM-8803 | QAlity Test | Portal URL - Valid with Numbers | Draft | Akhila Gattu
5968 | IIRM-8804 | QAlity Test | Portal URL - Valid with Hyphens | Draft | Akhila Gattu
5969 | IIRM-8805 | QAlity Test | Enable Email + Password Login | Draft | Akhila Gattu
5970 | IIRM-8806 | QAlity Test | Enable Mobile + OTP Login | Draft | Akhila Gattu
5971 | IIRM-8807 | QAlity Test | Enable Employee ID + Year of Birth Login | Draft | Akhila Gattu
5972 | IIRM-8808 | QAlity Test | Enable Multiple Login Methods | Draft | Akhila Gattu
5973 | IIRM-8809 | QAlity Test | 2FA Configuration - Email Channel | Draft | Akhila Gattu
5974 | IIRM-8810 | QAlity Test | 2FA Configuration - Mobile Channel | Draft | Akhila Gattu
5975 | IIRM-8811 | QAlity Test | 2FA Configuration - Both Channels | Draft | Akhila Gattu
5976 | IIRM-8812 | QAlity Test | 2FA Not Configured - Publish Blocked | Draft | Akhila Gattu
5977 | IIRM-8813 | QAlity Test | Notification Rule - Email + Password Login | Draft | Akhila Gattu
5978 | IIRM-8814 | QAlity Test | Notification Rule - Mobile + OTP Login | Draft | Akhila Gattu
5979 | IIRM-8815 | QAlity Test | Notification Rule - Employee ID + YOB Login | Draft | Akhila Gattu
5980 | IIRM-8816 | QAlity Test | Notification Rules - Non-Editable | Draft | Akhila Gattu
5981 | IIRM-8817 | QAlity Test | Employee ID + YOB - Both Fields Required | Draft | Akhila Gattu
5982 | IIRM-8818 | QAlity Test | Disable All Login Methods | Draft | Akhila Gattu
5983 | IIRM-8819 | QAlity Test | Switch Login Method After Configuration | Draft | Akhila Gattu
5984 | IIRM-8820 | QAlity Test | 2FA Section Visibility - Non-Password Login | Draft | Akhila Gattu
5985 | IIRM-8821 | QAlity Test | Login Method Display on Portal | Draft | Akhila Gattu
5986 | IIRM-8822 | QAlity Test | Multiple 2FA Channels - User Choice | Draft | Akhila Gattu
5987 | IIRM-8823 | QAlity Test | Corporate Wellness - Always Enabled | Draft | Akhila Gattu
5988 | IIRM-8824 | QAlity Test | Corporate Wellness - Benefit Configuration Required | Draft | Akhila Gattu
5989 | IIRM-8825 | QAlity Test | Insurance Wellness Toggle - Allow | Draft | Akhila Gattu
5990 | IIRM-8826 | QAlity Test | Insurance Wellness Toggle - Not Allow | Draft | Akhila Gattu
5991 | IIRM-8827 | QAlity Test | Insurance Wellness Type - Corporate Policy | Draft | Akhila Gattu
5992 | IIRM-8828 | QAlity Test | Insurance Wellness Type - Retail Policy | Draft | Akhila Gattu
5993 | IIRM-8829 | QAlity Test | Insurance Wellness Type - Not Selected | Draft | Akhila Gattu
5994 | IIRM-8830 | QAlity Test | Wellness Benefit Sub-Configuration - Section Display | Draft | Akhila Gattu
5995 | IIRM-8831 | QAlity Test | Wellness Benefit Sub-Configuration - Complete Fields | Draft | Akhila Gattu
5996 | IIRM-8832 | QAlity Test | Wellness Benefit Sub-Configuration - Incomplete Fields | Draft | Akhila Gattu
5997 | IIRM-8833 | QAlity Test | Add Multiple Wellness Benefits - Corporate | Draft | Akhila Gattu
5998 | IIRM-8834 | QAlity Test | Remove Wellness Benefit | Draft | Akhila Gattu
5999 | IIRM-8835 | QAlity Test | Insurance Wellness - Switch Type After Configuration | Draft | Akhila Gattu
6000 | IIRM-8836 | QAlity Test | Wellness Benefits Label Visibility | Draft | Akhila Gattu
6001 | IIRM-8837 | QAlity Test | Corporate Wellness - Cannot Disable | Draft | Akhila Gattu
6002 | IIRM-8838 | QAlity Test | Insurance Wellness - Toggle State Persistence | Draft | Akhila Gattu
6003 | IIRM-8839 | QAlity Test | Wellness Configuration - Default State | Draft | Akhila Gattu
6004 | IIRM-8840 | QAlity Test | Benefit Configuration - Field Validation | Draft | Akhila Gattu
6005 | IIRM-8841 | QAlity Test | Multiple Benefits - Independent Configuration | Draft | Akhila Gattu
6006 | IIRM-8842 | QAlity Test | Insurance Wellness Not Allowed - No Type Selection | Draft | Akhila Gattu
6007 | IIRM-8843 | QAlity Test | Assign Single Policy | Draft | Akhila Gattu
6008 | IIRM-8844 | QAlity Test | Assign Multiple Policies | Draft | Akhila Gattu
6009 | IIRM-8845 | QAlity Test | Enrollment Start Date - Valid | Draft | Akhila Gattu
6010 | IIRM-8846 | QAlity Test | Enrollment End Date - Valid | Draft | Akhila Gattu
6011 | IIRM-8847 | QAlity Test | Enrollment Dates - Missing Start Date | Draft | Akhila Gattu
6012 | IIRM-8848 | QAlity Test | Enrollment Dates - Missing End Date | Draft | Akhila Gattu
6013 | IIRM-8849 | QAlity Test | Enrollment Dates - End Date Before Start Date | Draft | Akhila Gattu
6014 | IIRM-8850 | QAlity Test | Enrollment Dates - Same Date | Draft | Akhila Gattu
6015 | IIRM-8851 | QAlity Test | Overlapping Enrollment Windows | Draft | Akhila Gattu
6016 | IIRM-8852 | QAlity Test | Financial Settings Configuration | Draft | Akhila Gattu
6017 | IIRM-8853 | QAlity Test | Employer Contribution - Not Configurable | Draft | Akhila Gattu
6018 | IIRM-8854 | QAlity Test | Family Eligibility - Configure Relationships | Draft | Akhila Gattu
6019 | IIRM-8855 | QAlity Test | Family Eligibility - Dependent Limits | Draft | Akhila Gattu
6020 | IIRM-8856 | QAlity Test | Remove Assigned Policy | Draft | Akhila Gattu
6021 | IIRM-8857 | QAlity Test | Policy Configuration - All Sections Complete | Draft | Akhila Gattu
6022 | IIRM-8858 | QAlity Test | Non-Overlapping Enrollment Windows | Draft | Akhila Gattu
6023 | IIRM-8859 | QAlity Test | Preview Mode - Login Experience | Draft | Akhila Gattu
6024 | IIRM-8860 | QAlity Test | Preview Mode - Wellness Experience | Draft | Akhila Gattu
6025 | IIRM-8861 | QAlity Test | Preview Mode - Policy Enrollment Experience | Draft | Akhila Gattu
6026 | IIRM-8862 | QAlity Test | Preview Mode - Breadcrumb Navigation | Draft | Akhila Gattu
6027 | IIRM-8863 | QAlity Test | Preview Mode - Exit Preview | Draft | Akhila Gattu
6028 | IIRM-8864 | QAlity Test | Preview Mode - Before Publish | Draft | Akhila Gattu
6029 | IIRM-8865 | QAlity Test | Preview Mode - Incomplete Configuration | Draft | Akhila Gattu
6030 | IIRM-8866 | QAlity Test | Preview Mode - URL Preview | Draft | Akhila Gattu
6031 | IIRM-8867 | QAlity Test | Preview Mode - Responsive Design | Draft | Akhila Gattu
6032 | IIRM-8868 | QAlity Test | Preview Mode - Reflect Latest Changes | Draft | Akhila Gattu
6033 | IIRM-8869 | QAlity Test | Logo Format Validation - Valid | Draft | Akhila Gattu
6034 | IIRM-8870 | QAlity Test | Logo Size Validation - Exceeds Limit | Draft | Akhila Gattu
6035 | IIRM-8871 | QAlity Test | Character Limit Validation - Header Text | Draft | Akhila Gattu
6036 | IIRM-8872 | QAlity Test | URL Format Validation - Valid | Draft | Akhila Gattu
6037 | IIRM-8873 | QAlity Test | URL Hyphen Validation - Invalid | Draft | Akhila Gattu
6038 | IIRM-8874 | QAlity Test | 2FA Mandatory Validation | Draft | Akhila Gattu
6039 | IIRM-8875 | QAlity Test | Employee ID + YOB Fields Validation | Draft | Akhila Gattu
6040 | IIRM-8876 | QAlity Test | Insurance Wellness Type Mandatory Validation | Draft | Akhila Gattu
6041 | IIRM-8877 | QAlity Test | Wellness Sub-Config Complete Validation | Draft | Akhila Gattu
6042 | IIRM-8878 | QAlity Test | Enrollment Dates Mandatory Validation | Draft | Akhila Gattu
6043 | IIRM-8879 | QAlity Test | Start Date Less Than End Date Validation | Draft | Akhila Gattu
6044 | IIRM-8880 | QAlity Test | Multiple Validation Errors Display | Draft | Akhila Gattu
6045 | IIRM-8881 | QAlity Test | Real-Time Validation Feedback | Draft | Akhila Gattu
6046 | IIRM-8882 | QAlity Test | Validation Error Clearing | Draft | Akhila Gattu
6047 | IIRM-8883 | QAlity Test | Save Button State Based on Validation | Draft | Akhila Gattu
6048 | IIRM-8884 | QAlity Test | Complete Portal Configuration - New Company | Draft | Akhila Gattu
6049 | IIRM-8885 | QAlity Test | Modify Existing Portal Configuration | Draft | Akhila Gattu
6050 | IIRM-8886 | QAlity Test | Portal Configuration with Minimal Setup | Draft | Akhila Gattu
6051 | IIRM-8887 | QAlity Test | Portal Configuration with Maximum Features | Draft | Akhila Gattu
6052 | IIRM-8888 | QAlity Test | Publish Without Preview | Draft | Akhila Gattu
6053 | IIRM-8889 | QAlity Test | Save Draft and Resume Configuration | Draft | Akhila Gattu
6054 | IIRM-8890 | QAlity Test | Configuration Validation Before Publish | Draft | Akhila Gattu
6055 | IIRM-8891 | QAlity Test | Multi-Admin Configuration Conflict | Draft | Akhila Gattu
6056 | IIRM-8892 | Story | Show Employees Details in a Policy | Done | NithinKrishna Sirigiri |  | IIRM-6827 — Manage Policy
6057 | IIRM-8895 | Bug | IIRM: Unable to Submit Final Negotiation Meeting Due to Total Brokerage Amount decimal Mismatch | Done | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
6058 | IIRM-8898 | Bug | IIRM: Unable to submit for approval in CD Details/Cover Details tabs after configuration approval - "No user found with privileges for assigning activity with ID 4632358" error | Open | Prathiphala Kandula
6059 | IIRM-8899 | Bug | IIRM: Decimals are not accepted for few fields on Opporuniy creation/activities | Ready for QA | SaikumarMahanthi | iWork | IIRM-797 — SOW#69 - Manage Opportunities
6060 | IIRM-8900 | Bug | IIRM: SO : Excel columns order is changed with Generate Quote Comparison in QCR Generation activity. | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
6061 | IIRM-8901 | Bug | IIRM : SO :Sri Lanka: Policy Hard Copy Receipt Submission Failing with Error “deviationsAddressedSection.basicPremium should not exist” | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
6062 | IIRM-8902 | Bug | IIRM:SO : The terrorism premium and terrorism percentage is not giving the correctly calculated terrorism amount in Meeting for Final negotiation | Done - Not a Bug | KOWTRAPU KAVYA SRI | iWork | IIRM-740 — SOW#13 - Add/Manage Opportunity
6063 | IIRM-8903 | Bug | IIRM: TPA ID upload fails when "TPA ID common for family members" is set to No | Done | Prathiphala Kandula
6064 | IIRM-8904 | Bug | IIRM: TPA ID upload fails when "TPA ID common for family members" is set to Yes | Done | Prathiphala Kandula
6065 | IIRM-8905 | Bug | IIRm: Inception: TPA ID Upload: Irrelevant data is displayed in the error file | Done | Leela Pakalapati | IBP
6066 | IIRM-8906 | Bug | IRM: Inception Data: TPA ID Upload fails when “TPA ID common for family members?” is set to Yes | Done | Leela Pakalapati | IBP
6067 | IIRM-8907 | Bug | IIRM: Submit for Approval button remains enabled after policy Configuration approval | Open | Prathiphala Kandula
6068 | IIRM-8908 | Bug | IIRM: Stage navigation blocked after rejecting edited policy configuration | Open | Prathiphala Kandula
6069 | IIRM-8909 | NFR - Subtask | QA: Write Test Case | Done | NithinKrishna Sirigiri |  | IIRM-4559 — NFR-COM-012 - Avoid local storage for sensitive data in browser
6070 | IIRM-8910 | Bug | IBP: EnrollAll: Suminsured should not visible to employee if toggle set to NO | Open | Akhila Gattu
6071 | IIRM-8911 | Story | Portal Preference - Pending Items and Feedback | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6072 | IIRM-8912 | Sub-task | QA: Test cases creation | Done | SaikumarMahanthi |  | IIRM-4506 — NFR-SEC-047: PINS for Backend Authentication - Password should be accepted with NOT PII info in or as part of it. Maintain password policy to prevent this
6073 | IIRM-8913 | Sub-task | QA: Testing & Bug Fixes Verification | Done | SaikumarMahanthi |  | IIRM-4506 — NFR-SEC-047: PINS for Backend Authentication - Password should be accepted with NOT PII info in or as part of it. Maintain password policy to prevent this
6074 | IIRM-8914 | Story | Integration of the external links | Done | Richa Bagchi Mazumdar |  | IIRM-749 — SOW#22 - Data Security (NFR)
6075 | IIRM-8915 | QAlity Test | IIRM: Login: Reject PIN for backend authentication | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6076 | IIRM-8916 | QAlity Test | IIRM: Login: Accept password with minimum required length and no PII content | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6077 | IIRM-8917 | QAlity Test | IIRM: Login: Accept password with maximum allowed length and no PII content | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6078 | IIRM-8918 | QAlity Test | IIRM: Login: Accept password that does not contain partial match of name (less than 3 characters) | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6079 | IIRM-8919 | QAlity Test | IIRM:Login : Accept password change not matching last 5 password history | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6080 | IIRM-8920 | QAlity Test | IIRM: Login: Allow login using password within 90-day validity period | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6081 | IIRM-8921 | QAlity Test | IIRM: Login: Password reset link cannot be reused after password set | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6082 | IIRM-8922 | QAlity Test | IIRM: Login: Reject password when it violates password policy, PII rules, or authentication restrictions | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6083 | IIRM-8923 | Bug | IIRM: Inception: Incorrect data count is reflected on the quick cards in Inception Uploaded Data Table | Open | Leela Pakalapati | IBP
6084 | IIRM-8924 | Sub-task | Dynamic Cron Scheduler (Backend) | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6085 | IIRM-8925 | Sub-task | Cron Configuration Management APIs | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6086 | IIRM-8926 | Sub-task | Cron Job Persistence & Execution Tracking | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6087 | IIRM-8927 | Sub-task | Cron Jobs Management UI (Listing) | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6088 | IIRM-8928 | Sub-task | Edit Cron Schedule & Status UI | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6089 | IIRM-8929 | Bug | IIRM: Re-Activate: The Parental Policy condition is not appearing in the Policy Template step | Open | Leela Pakalapati | iWork
6090 | IIRM-8930 | Sub-task | DEV: Migrate data stored in local storage to session storage in IWORK application | Done | Kowshik Atmakuri |  | IIRM-4559 — NFR-COM-012 - Avoid local storage for sensitive data in browser
6091 | IIRM-8931 | Sub-task | DEV: Migrate data stored in local storage to session storage in IBP application | Done | Kowshik Atmakuri |  | IIRM-4559 — NFR-COM-012 - Avoid local storage for sensitive data in browser
6092 | IIRM-8932 | Bug | IIRM: Re-Activate: Unable to set newly added Sum Insured as default in Policy Choices step | Open | Leela Pakalapati | IBP
6093 | IIRM-8933 | Sub-task | Test IWORK application | Done | Kowshik Atmakuri |  | IIRM-4559 — NFR-COM-012 - Avoid local storage for sensitive data in browser
6094 | IIRM-8934 | Sub-task | Test IBP application | Done | Kowshik Atmakuri |  | IIRM-4559 — NFR-COM-012 - Avoid local storage for sensitive data in browser
6095 | IIRM-8935 | Sub-task | Iwork Frontend: Inactivity Session Timeout | Done | Nikhil V |  | IIRM-4491 — NFR-SEC-008: On inactivity, session should timeout and logout the user. Time out period must be coming from configuration
6096 | IIRM-8936 | Sub-task | IBP Frontend: Inactivity Timeout Integration with Shared Hook | Done | Nikhil V |  | IIRM-4491 — NFR-SEC-008: On inactivity, session should timeout and logout the user. Time out period must be coming from configuration
6097 | IIRM-8937 | Sub-task | Backend: Align Session & Token Expiry with Inactivity Timeout | Done | Nikhil V |  | IIRM-4491 — NFR-SEC-008: On inactivity, session should timeout and logout the user. Time out period must be coming from configuration
6098 | IIRM-8938 | Sub-task | QA & Rollout for Inactivity Session Timeout | Done | Nikhil V |  | IIRM-4491 — NFR-SEC-008: On inactivity, session should timeout and logout the user. Time out period must be coming from configuration
6099 | IIRM-8939 | Bug | IIRM: Re-Activate: Edited policy has no Save; back navigation clears entered fields. | Open | Prathiphala Kandula
6100 | IIRM-8940 | Sub-task | Create common data-security utility | Done | Lakshmi Gopalakrishna Ratnala |  | IIRM-4494 — NFR-SEC-016: The application must manual Key loading process - Use salt along with secure key where encryption is being implemented
6101 | IIRM-8941 | Sub-task | Integrate encryption on DB writes (create/update) | Done | Lakshmi Gopalakrishna Ratnala |  | IIRM-4494 — NFR-SEC-016: The application must manual Key loading process - Use salt along with secure key where encryption is being implemented
6102 | IIRM-8942 | Sub-task | Integrate decryption on API responses | Done | Lakshmi Gopalakrishna Ratnala |  | IIRM-4494 — NFR-SEC-016: The application must manual Key loading process - Use salt along with secure key where encryption is being implemented
6103 | IIRM-8943 | Bug | IIRM: Login: Forgot password is not triggering to reset password page | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6104 | IIRM-8944 | Sub-task | Backward compatibility handling | Done | Lakshmi Gopalakrishna Ratnala |  | IIRM-4494 — NFR-SEC-016: The application must manual Key loading process - Use salt along with secure key where encryption is being implemented
6105 | IIRM-8945 | Sub-task | Implement Field-Level Encryption and Dcryption For PAN Field | Done | Lakshmi Gopalakrishna Ratnala |  | IIRM-4494 — NFR-SEC-016: The application must manual Key loading process - Use salt along with secure key where encryption is being implemented
6106 | IIRM-8946 | QAlity Test | IIRM: Login: Verify that the user session automatically expires after the configured inactivity timeout. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6107 | IIRM-8947 | QAlity Test | IIRM:Login: Verify that user activity resets the inactivity timer. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6108 | IIRM-8948 | QAlity Test | IIRM:Login: Verify that a token captured before inactivity timeout cannot be reused. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6109 | IIRM-8949 | QAlity Test | IIRM:Login: Verify frontend detects inactivity and triggers logout behavior. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6110 | IIRM-8950 | QAlity Test | IIRM: Login: Verify backend invalidates session/token after inactivity timeout. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6111 | IIRM-8951 | QAlity Test | IIRM: Login: Ensure no security gap exists if frontend logs out user. | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6112 | IIRM-8952 | QAlity Test | IIRM: Login: Verify session timeout duration is configurable and not hardcoded. | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6113 | IIRM-8953 | QAlity Test | IIRM: Login: Verify re-authentication is required after session timeout. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6114 | IIRM-8954 | QAlity Test | IIRM: Login: Verify inactivity timeout applies even when multiple tabs are open. | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6115 | IIRM-8955 | QAlity Test | IIRM: Login: Verify API calls count as activity and keep session alive. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6116 | IIRM-8956 | QAlity Test | IIRM: Login: Verify session data is cleared on inactivity logout. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6117 | IIRM-8957 | QAlity Test | IIRM: Login: Verify closing browser does not bypass timeout. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6118 | IIRM-8958 | QAlity Test | IIRM: Login: Verify user cannot bypass timeout by changing system time. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6119 | IIRM-8959 | QAlity Test | IIRM: Login: Verify configuration timeout behavior with invalid timeout values. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6120 | IIRM-8960 | QAlity Test | IIRM: Login: Verify the behaviour of application when config changes mid session | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6121 | IIRM-8961 | QAlity Test | IIRM: Login: Verify warning appears before session expiry. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6122 | IIRM-8962 | QAlity Test | IIRM: Login: Verify inactivity timeout applies to all roles. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6123 | IIRM-8963 | QAlity Test | IIRM: Login: Verify timeout after network disconnect. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6124 | IIRM-8964 | QAlity Test | IIRM : Login : Verify per-device inactivity timeout. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6125 | IIRM-8965 | QAlity Test | IIRM: Login : Verify inactivity logout is logged | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6126 | IIRM-8966 | QAlity Test | IIRM: Login: API burst after session expiration | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6127 | IIRM-8967 | QAlity Test | IIRM: Login : Reduced timeout for automation | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6128 | IIRM-8968 | Bug | IIRM: Re-Activate: Inception summary doesn’t reflect uploaded counts; endorsement blocked | Open | Prathiphala Kandula
6129 | IIRM-8969 | Bug | IIRM: Scheduling Service : Sorting is failed on all columns | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6130 | IIRM-8970 | Bug | IIRM: Incorrect and Non-Standard Time Format Displayed in Scheduling Service | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6131 | IIRM-8971 | Bug | IIRM: Non Finance: Valid members fail when one member in the relationship group fails validation | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6132 | IIRM-8972 | Bug | IIRM: Re-Activate: Endorsement Summary card data is missing after deletion in Step 2 | Open | Leela Pakalapati | IBP
6133 | IIRM-8973 | Bug | IIRM: Non-Finance: Update functionality fails with duplicate employee validation error | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6134 | IIRM-8974 | Bug | IIRM: Session configuration failed for inactive session configuration. | Done - Not Reproducible | KOWTRAPU KAVYA SRI | IBP | IIRM-749 — SOW#22 - Data Security (NFR)
6135 | IIRM-8975 | Bug | IIRM: Scheduling Service Tooltip Displays Invalid Data on Column Hover | Done | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6136 | IIRM-8976 | Bug | IIRM: Session configuration failed for inactive user | Done - Not Reproducible | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6137 | IIRM-8977 | Bug | IIRM: Session configuration failed for active user as per the configuration in IBP Portal configuration. | Done - Not Reproducible | KOWTRAPU KAVYA SRI | IBP | IIRM-749 — SOW#22 - Data Security (NFR)
6138 | IIRM-8978 | Bug | IIRM : Session configuration failed for active user. | Done - Not Reproducible | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6139 | IIRM-8979 | Bug | IIRM: Session configuration fails for multiple tabs logged-in user | Done - Not Reproducible | KOWTRAPU KAVYA SRI | IBP | IIRM-749 — SOW#22 - Data Security (NFR)
6140 | IIRM-8980 | Story | GMC - Upload Claims (Per Policy & Per TPA) | Done | NithinKrishna Sirigiri |  | IIRM-782 — SOW#55 - Claim Management
6141 | IIRM-8981 | Bug | IIRM: Non-Finance: Unable to complete Create Endorsement step | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6142 | IIRM-8982 | Bug | IIRM: Sensitive data stored in Local Storage instead of Session Storage | Open | KOWTRAPU KAVYA SRI | IBP | IIRM-749 — SOW#22 - Data Security (NFR)
6143 | IIRM-8983 | Bug | IIRM: Session storage: Access token remains valid after logout, allowing access to sensitive API data without logging in. | Done - Not a Bug | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6144 | IIRM-8984 | Sub-task | Make TPA step Optional for Non-Financial Endorsement Process | Done | NithinKrishna Sirigiri |  | IIRM-8222 — Non-Financial Endorsements
6145 | IIRM-8985 | QAlity Test | IIRM: Non-Finance: Verify Endorsement Process for Policy c,onfigured where the Age is included in the Relationship Group | Completed | Prathiphala Kandula
6146 | IIRM-8986 | QAlity Test | IIRM: Non-Financial: Verify that DOB update is allowed when Age is not configured as a policy parameter | Completed | Prathiphala Kandula
6147 | IIRM-8987 | QAlity Test | IIRM: Non-Financial: Verify that Gender modification is blocked when Gender is configured as a policy parameter | Completed | Prathiphala Kandula
6148 | IIRM-8988 | QAlity Test | IIRM: Non-Financial: Verify that Gender update is allowed when Gender is not configured as a policy parameter | Completed | Prathiphala Kandula
6149 | IIRM-8989 | QAlity Test | IIRM: Non-Financial: Verify that DOB modification is blocked when Age is configured as a policy parameter | Completed | Prathiphala Kandula
6150 | IIRM-8990 | Bug | IBP: Inception/endorsement: File upload count shows 0, if file has only deletion records | Done - Not a Bug | Akhila Gattu
6151 | IIRM-8991 | Story | CD Management: PROD Bugs | Draft | NithinKrishna Sirigiri |  | IIRM-781 — SOW#54 - CD Management
6152 | IIRM-8992 | Bug | IIRM: QCR: Risk Location field is missing in the downloaded template | Done - Not Reproducible | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
6153 | IIRM-8993 | Story | NFR-INT-009-02 - Should support SMS and Whatsapp Notifications | Draft | Rama K |  | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
6154 | IIRM-8994 | Story | NFR-INT-009-03 - Should support Chatbot | Draft | Rama K |  | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
6155 | IIRM-8995 | Story | <Place Holder> | Draft | NithinKrishna Sirigiri |  | IIRM-782 — SOW#55 - Claim Management
6156 | IIRM-8996 | Bug | IIRM: Scheduling Service: Non group policies failed to load the data in Create inception stage | Open | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6157 | IIRM-8997 | Bug | IIRM: Scheduling Service: Inception file upload fails for Group Personal Accident Policy | Open | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6158 | IIRM-8998 | Sub-task | QA: Non-Finance: Documenting test cases | Done | Leela Pakalapati |  | IIRM-8222 — Non-Financial Endorsements
6159 | IIRM-8999 | Sub-task | QA:Non-Finance: Executing test cases and documenting bugs | Done | Leela Pakalapati |  | IIRM-8222 — Non-Financial Endorsements
6160 | IIRM-9000 | Sub-task | QA: Employee Tab: Documenting test cases | Done | Leela Pakalapati |  | IIRM-8892 — Show Employees Details in a Policy
6161 | IIRM-9001 | Sub-task | QA: Employee Tab: Executing test cases and documenting bugs | Done | Leela Pakalapati |  | IIRM-8892 — Show Employees Details in a Policy
6162 | IIRM-9002 | QAlity Test | IIRM : Scheduling Service: Verify cron job runs at scheduled time | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6163 | IIRM-9003 | Sub-task | QA: Executing test cases and bug reporting | Done | Leela Pakalapati |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6164 | IIRM-9004 | QAlity Test | IIRM : Scheduling Service: Verify data is processed only after cron execution | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6165 | IIRM-9005 | Sub-task | Update Statistics Section in Second Tab | Done | Karan Agarwal |  | IIRM-8222 — Non-Financial Endorsements
6166 | IIRM-9006 | Sub-task | Backend: Create Employee Listing API as per Defined Field Requirements | Done | Karan Agarwal |  | IIRM-8892 — Show Employees Details in a Policy
6167 | IIRM-9007 | QAlity Test | IIRM: Scheduling Service: Verify business rules and calculations for scheduled configuration time | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6168 | IIRM-9008 | Sub-task | Create testcases | Done | Akhila Gattu |  | IIRM-8401 — Display enrolment status in step-2 for IBP-configured policies with employee-only file inception
6169 | IIRM-9009 | Sub-task | Verify functionality | Done | Akhila Gattu |  | IIRM-8401 — Display enrolment status in step-2 for IBP-configured policies with employee-only file inception
6170 | IIRM-9010 | Sub-task | Retest bugs | Done | Akhila Gattu |  | IIRM-8401 — Display enrolment status in step-2 for IBP-configured policies with employee-only file inception
6171 | IIRM-9011 | Bug | IIRM: Inception/Endorsement: Unable to open Inception step after uploading 3L file | Open | Leela Pakalapati | IBP
6172 | IIRM-9012 | QAlity Test | IIRM : Scheduling Service : Verify cron job performance and completion within SLA | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6173 | IIRM-9013 | Sub-task | Backend: Implement the filters and search based on the specified fields | Done | Karan Agarwal |  | IIRM-8892 — Show Employees Details in a Policy
6174 | IIRM-9014 | QAlity Test | IIRM : Scheduling Service: Verify re-run behavior and error handling | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6175 | IIRM-9015 | Sub-task | QA: Documenting test cases | Draft | Leela Pakalapati |  | IIRM-8671 — Localisation: Kenya - Fields
6176 | IIRM-9016 | Sub-task | QA: Executing test cases and bug reporting | Draft | Leela Pakalapati |  | IIRM-8671 — Localisation: Kenya - Fields
6177 | IIRM-9017 | QAlity Test | Enrollment: Verify 'Not Started' status when no enrollment initiated | Draft | Akhila Gattu
6178 | IIRM-9018 | QAlity Test | Enrollment: Verify 'In Progress' status during partial enrollment | Draft | Akhila Gattu
6179 | IIRM-9019 | QAlity Test | Enrollment: Verify 'Completed' status after full enrollment | Draft | Akhila Gattu
6180 | IIRM-9020 | QAlity Test | Enrollment: Verify mixed enrollment statuses display | Draft | Akhila Gattu
6181 | IIRM-9021 | QAlity Test | Enrollment: Verify enrollment status after adding new employees | Draft | Akhila Gattu
6182 | IIRM-9022 | QAlity Test | Enrollment: Verify enrollment status after deleting employees in 'Not Started' state | Draft | Akhila Gattu
6183 | IIRM-9023 | QAlity Test | Enrollment: Verify enrollment status after deleting employees in 'In Progress' state | Draft | Akhila Gattu
6184 | IIRM-9024 | QAlity Test | Enrollment: Verify enrollment status after deleting employees in 'Completed' state | Draft | Akhila Gattu
6185 | IIRM-9025 | QAlity Test | Enrollment: Verify enrollment status transition from 'In Progress' to 'Completed' | Draft | Akhila Gattu
6186 | IIRM-9026 | QAlity Test | Enrollment: Verify premium calculation with 'Not Started' enrollment status | Draft | Akhila Gattu
6187 | IIRM-9027 | QAlity Test | Enrollment: Verify premium calculation with 'Completed' enrollment status | Draft | Akhila Gattu
6188 | IIRM-9028 | QAlity Test | Enrollment: Verify premium calculation with mixed enrollment statuses | Draft | Akhila Gattu
6189 | IIRM-9029 | QAlity Test | Enrollment: Verify enrollment status persistence after session timeout | Draft | Akhila Gattu
6190 | IIRM-9030 | QAlity Test | Enrollment: Verify enrollment status in Endorsement after Inception completion | Draft | Akhila Gattu
6191 | IIRM-9031 | QAlity Test | Enrollment: Verify enrollment status update during Endorsement with new employees | Draft | Akhila Gattu
6192 | IIRM-9032 | QAlity Test | Enrollment: Verify system behavior when no employees uploaded | Draft | Akhila Gattu
6193 | IIRM-9033 | QAlity Test | Enrollment: Verify enrollment status after all employees deleted | Draft | Akhila Gattu
6194 | IIRM-9034 | QAlity Test | Enrollment: Verify enrollment status with invalid/incomplete IBP login | Draft | Akhila Gattu
6195 | IIRM-9035 | QAlity Test | Enrollment: Verify concurrent enrollment updates from multiple users | Draft | Akhila Gattu
6196 | IIRM-9036 | QAlity Test | Enrollment: Verify enrollment status refresh/sync mechanism | Draft | Akhila Gattu
6197 | IIRM-9037 | QAlity Test | TC-NFR-COM-012-001: Verify HTTP response headers prevent caching of sensitive pages | Draft | SaikumarMahanthi
6198 | IIRM-9038 | QAlity Test | TC-NFR-COM-012-002: Verify sensitive data is stored ONLY in session storage with proper cleanup | Draft | SaikumarMahanthi
6199 | IIRM-9039 | QAlity Test | TC-NFR-COM-012-003: Verify browser back button does not display cached sensitive pages after logout | Draft | SaikumarMahanthi | iWork
6200 | IIRM-9040 | QAlity Test | TC-NFR-COM-012-004: Verify external application integrations (Poppins, IBP) follow cache and storage requirements | Draft | SaikumarMahanthi
6201 | IIRM-9041 | QAlity Test | TC-NFR-COM-012-005:Verify complete migration from local storage to session storage maintains data integrity | Draft | SaikumarMahanthi
6202 | IIRM-9042 | QAlity Test | TC-NFR-COM-012-006: Cross-browser security and performance verification | Draft | SaikumarMahanthi | iWork
6203 | IIRM-9043 | Sub-task | QA: Validating the data for the updated policies | Done | Leela Pakalapati |  | IIRM-8393 — Policy Config: Link Policy Components with the Relationship & it's related flags
6204 | IIRM-9044 | Bug | IIRM: Session storage: User tokens are stored in local storage instead of session storage in IBP | Done | KOWTRAPU KAVYA SRI | IBP | IIRM-749 — SOW#22 - Data Security (NFR)
6205 | IIRM-9045 | Story | Show Section Heading for Covers (Ref. to Package Policy) | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6206 | IIRM-9046 | Bug | IIRM: Session Storage Not Cleared When Navigating Back | Done | SaikumarMahanthi |  | IIRM-749 — SOW#22 - Data Security (NFR)
6207 | IIRM-9047 | Bug | IIRM: Scheduling Service – Invalid Cron Expression in Edit Configuration for the scheduler,schedule does not match the specified frequency. | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6208 | IIRM-9048 | QAlity Test | IIRM: Verify Asset Insured tab is displayed for Non‑Group policies | Completed | Prathiphala Kandula
6209 | IIRM-9049 | QAlity Test | IIRM: Verify Employee Insured tab is displayed for Group policies | Completed | Prathiphala Kandula
6210 | IIRM-9050 | Bug | IBP: Once employee got deleted through endorsement process( with/without choices), IBP login should't work for deleted employees | Done - Not a Bug | Akhila Gattu
6211 | IIRM-9051 | QAlity Test | IIRM: Verify that both the Asset Insured Tab and Employee Insured Tab doesn't display simultaneously for either of the policies(group or non group). | Completed | Prathiphala Kandula
6212 | IIRM-9052 | Bug | IIRM: Sensitive User Data Exposed in Session Storage Payload | Done - Not a Bug | SaikumarMahanthi |  | IIRM-749 — SOW#22 - Data Security (NFR)
6213 | IIRM-9057 | Bug | IIRM : Login - Weak Passwords Allowed During Login | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6214 | IIRM-9058 | Bug | IIRM Login – Previous 5 Passwords Can Be Reused | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6215 | IIRM-9059 | Bug | IIRM : Login – Reset Password Link Does Not Expire After Use | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6216 | IIRM-9060 | QAlity Test | IIRM: Verify the functionality of the Relationship Group filter for Self is only configured. | Completed | Prathiphala Kandula
6217 | IIRM-9061 | QAlity Test | IIRM: Verify that the Relationship Group filter displays Self and Dependent records correctly in the table when the policy is configured with Self and dependent relationships. | Completed | Prathiphala Kandula
6218 | IIRM-9062 | QAlity Test | IIRM: Verify Smart Search filters by Insured Name only | Completed | Prathiphala Kandula
6219 | IIRM-9063 | QAlity Test | IIRM: Verify that Inc/End ID column contains hyperlinks that navigate to the corresponding Inception or Endorsement page | Completed | Prathiphala Kandula
6220 | IIRM-9064 | Task | IIRM: NFR-OTH-020 : Test case Creation and testing | Done | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6221 | IIRM-9065 | Task | Automation: Write API Framework for company quick create and Opportunity stages up Placement Slip generation | Done | PATIBANDLA VELANGINI RAJU |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6222 | IIRM-9066 | Bug | IIRM: Policy Details: Cover details are not displayed in the Cover Details tab | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6223 | IIRM-9067 | Sub-task | Enable the toggle of right side pannel only when nudges privilege is avaialbe for the user | Done | Rama K |  | IIRM-8362 — AI Chatbot: Nudge - Pre-computation as required
6224 | IIRM-9068 | Story | Saferisk - SBU vs Vertical vs Department - Master Update (DB Request) | Open | NithinKrishna Sirigiri |  | IIRM-745 — SOW#18 - Master Data
6225 | IIRM-9069 | Bug | IIRM: Scheduling Service – Recently configured items should appear at the top. | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6226 | IIRM-9070 | Bug | IIRM: Scheduling Service – Configuration title is missing | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6227 | IIRM-9071 | Story | Saferisk - Hierarchy & Designations (DB Request) | Done | NithinKrishna Sirigiri |  | IIRM-745 — SOW#18 - Master Data
6228 | IIRM-9072 | Task | Automation: Refactor test data for opportunity stages up to Placement Slip Generation | Done | PATIBANDLA VELANGINI RAJU |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6229 | IIRM-9073 | Bug | IIRM: Inception: Inception document is not generated in Send Inception to Insurer step | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6230 | IIRM-9074 | Bug | IIRM: Inception: Failed records count and error file are not generated | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6231 | IIRM-9075 | Bug | IIRM: Employee Tab: Employee details are not reflected correctly | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6232 | IIRM-9076 | Sub-task | Refactor Scheduler Enrollment Upload to Run Shared IBP Processing Locally (Remove Axios, Continuous Single‑Batch Processing, Preserve Status Transitions | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6233 | IIRM-9077 | Story | Satrapi Implementation | WORK IN PROGRESS | Jadhav Sai Prasad |  | IIRM-750 — SOW#23 - Document Management - CMS
6234 | IIRM-9078 | Story | Logo management - Company , TPA, Insurer | Draft | Jadhav Sai Prasad |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6235 | IIRM-9079 | Task | RND Task - IBP Portal | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6236 | IIRM-9080 | Sub-task | TestCases for API | Done | Akhila Gattu |  | IIRM-8572 — End User Onboarding
6237 | IIRM-9081 | Sub-task | API verification on On boarding scenarios | Done | Akhila Gattu |  | IIRM-8572 — End User Onboarding
6238 | IIRM-9082 | Sub-task | Bugs revalidation. | Draft | Akhila Gattu |  | IIRM-8572 — End User Onboarding
6239 | IIRM-9083 | Sub-task | Add the new columns in the Employee Insured tab | Done | Karan Agarwal |  | IIRM-8892 — Show Employees Details in a Policy
6240 | IIRM-9084 | Sub-task | Database updates to support claim upload | Done | NithinKrishna Sirigiri |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6241 | IIRM-9085 | Sub-task | Backend changes to support claim upload at both Policy level and TPA level | Done | NithinKrishna Sirigiri |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6242 | IIRM-9086 | Sub-task | Update GET API to Support New KPI and Additional Fields | Done | NithinKrishna Sirigiri |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6243 | IIRM-9087 | Sub-task | Update CRON job to support the new claim template | Done | NithinKrishna Sirigiri |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6244 | IIRM-9088 | Sub-task | UI changes to support claims upload by policy | Done | NithinKrishna Sirigiri |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6245 | IIRM-9089 | Sub-task | UI changes to support claims upload by TPA | Done | NithinKrishna Sirigiri |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6246 | IIRM-9090 | Sub-task | API integration for both Policy-level and TPA-level uploads | Done | NithinKrishna Sirigiri |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6247 | IIRM-9091 | Sub-task | QA: Non Finance: Bug Fix verification | Done | Leela Pakalapati |  | IIRM-8222 — Non-Financial Endorsements
6248 | IIRM-9092 | Bug | EmployeeInsured: N/A claim status shown on API trigger | Done | Akhila Gattu |  | IIRM-6827 — Manage Policy
6249 | IIRM-9093 | Bug | EmployeeInsured: Search results not working companyEmpID includes "-" | Done | Akhila Gattu |  | IIRM-6827 — Manage Policy
6250 | IIRM-9094 | Sub-task | Epic Analysis & POC | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6251 | IIRM-9095 | Sub-task | BE-001: Set up new template module in notification-service | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6252 | IIRM-9096 | Sub-task | BE-002: Extend notification-service database schema for templates | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6253 | IIRM-9097 | Sub-task | BE-003: Implement template authorization in notification-service | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6254 | IIRM-9098 | Sub-task | BE-004: Implement template CRUD APIs | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6255 | IIRM-9099 | Sub-task | BE-005: Implement unified approval workflow system | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6256 | IIRM-9100 | Sub-task | BE-006: Implement template validation and sanitization | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6257 | IIRM-9101 | Sub-task | BE-007: Implement multi-channel support using existing CHANNEL_TYPE integration | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6258 | IIRM-9102 | Sub-task | BE-008: Implement insurance domain variable substitution system | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6259 | IIRM-9103 | Sub-task | FE-003: Create template pending approval and history routes, add necessary code and integrate template-service apis | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6260 | IIRM-9104 | Sub-task | BE-009: Implement approval workflow logging for template-service | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6261 | IIRM-9105 | Sub-task | FE-001: Implement template management route in iWork admin module and add base code | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6262 | IIRM-9106 | Sub-task | FE-002: Create template dashboard, editor pages and integrate with template-service | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6263 | IIRM-9107 | Sub-task | Create PRD, TRD, Dev Tasks | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6264 | IIRM-9108 | Sub-task | Refactor the CronJob to run Non Financial Endorsement | Done | sunilkumar.chitikina | iWork | IIRM-8222 — Non-Financial Endorsements
6265 | IIRM-9109 | Sub-task | Populate Stats in Step-2 to retrieve data from employee endorsement | Done | sunilkumar.chitikina | iWork | IIRM-8222 — Non-Financial Endorsements
6266 | IIRM-9110 | Sub-task | Refactor the Excel download utility for the “Sent to Insurer” step in Non-Financial Endorsements. | Done | sunilkumar.chitikina |  | IIRM-8222 — Non-Financial Endorsements
6267 | IIRM-9111 | Sub-task | QA: Employee Tab: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-8892 — Show Employees Details in a Policy
6268 | IIRM-9112 | Sub-task | Basic CRUD UI integrations for user details | Done | tharun |  | IIRM-8342 — IBP - Employee - User Profile
6269 | IIRM-9113 | Sub-task | Basic CRUD API's for user details | Done | tharun |  | IIRM-8342 — IBP - Employee - User Profile
6270 | IIRM-9114 | Sub-task | QA: Employee Tab: Documenting API testcases | Done | Akhila Gattu |  | IIRM-8892 — Show Employees Details in a Policy
6271 | IIRM-9115 | Sub-task | QA: Employee Tab: Validating API | Done | Akhila Gattu |  | IIRM-8892 — Show Employees Details in a Policy
6272 | IIRM-9116 | Sub-task | Frontend:Create tab for Employee details | Done | Mallela Pushyami |  | IIRM-8892 — Show Employees Details in a Policy
6273 | IIRM-9117 | QAlity Test | API: EmployeeInsured: Functionality Tests | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6274 | IIRM-9118 | QAlity Test | API: EmployeeInsured: Validate Pagination Tests | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6275 | IIRM-9119 | QAlity Test | API: EmployeeInsured: Validate Filter Tests (Individual Filters) | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6276 | IIRM-9120 | QAlity Test | API: EmployeeInsured: Validate Combined Filter Tests | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6277 | IIRM-9121 | QAlity Test | API: EmployeeInsured: Validate Date Range Tests | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6278 | IIRM-9122 | QAlity Test | API: EmployeeInsured: Validate Section Parameter Tests | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6279 | IIRM-9123 | QAlity Test | API: EmployeeInsured: Validate Invalid Policy ID | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6280 | IIRM-9124 | QAlity Test | API: EmployeeInsured: Verify Invalid Pagination | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6281 | IIRM-9125 | QAlity Test | API: EmployeeInsured: Verify Invalid Filters | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6282 | IIRM-9126 | QAlity Test | API: EmployeeInsured: Verify Missing Parameters and Data Validation | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6283 | IIRM-9127 | QAlity Test | API: EmployeeInsured: Verify Performance,Security and edge cases | Completed | Akhila Gattu |  | IIRM-6827 — Manage Policy
6284 | IIRM-9128 | Sub-task | POC on Google Maps APIs | SELF TESTED | Gayathri Anamala |  | IIRM-9079 — RND Task - IBP Portal
6285 | IIRM-9129 | Sub-task | POC on Image Cropping | SELF TESTED | Gayathri Anamala |  | IIRM-9079 — RND Task - IBP Portal
6286 | IIRM-9130 | Sub-task | Creating customizable Email Templates | WORK IN PROGRESS | Gayathri Anamala |  | IIRM-9079 — RND Task - IBP Portal
6287 | IIRM-9131 | Sub-task | Creating static html pages | SELF TESTED | Gayathri Anamala |  | IIRM-9079 — RND Task - IBP Portal
6288 | IIRM-9132 | Sub-task | BE- Post, put and get api's for company | Done | saigangadhar |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6289 | IIRM-9133 | Sub-task | BE- Post, put and get api's for Tpa | Done | saigangadhar |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6290 | IIRM-9134 | Sub-task | BE- Post, put and get api's for insurer | Done | saigangadhar |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6291 | IIRM-9135 | Sub-task | FE - POST, PUT and GET api integrations in Company Form and Company details pages | Done | Manjusha Paritala |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6292 | IIRM-9136 | Sub-task | FE - POST, PUT and GET api integrations in Insurer Form and Insurer details pages | Done | Manjusha Paritala |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6293 | IIRM-9137 | Sub-task | FE - POST, PUT and GET api integrations in TPA Form and TPA details pages | Done | Manjusha Paritala |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6294 | IIRM-9138 | Sub-task | Email notification - Enrollment Start API Endpoint | Done | tharun |  | IIRM-8572 — End User Onboarding
6295 | IIRM-9139 | Sub-task | Email notification - Enrollment Confirmation API Endpoint | Done | tharun |  | IIRM-8572 — End User Onboarding
6296 | IIRM-9140 | Sub-task | Email notification - Enrollment Reminder API Endpoint | Done | tharun |  | IIRM-8572 — End User Onboarding
6297 | IIRM-9141 | Sub-task | Email notification - Swagger Documentation & Email Template Implementation | Done | tharun |  | IIRM-8572 — End User Onboarding
6298 | IIRM-9142 | Sub-task | Email notification - Master Email Templates with Company-Level Scope Handling | Done | tharun |  | IIRM-8572 — End User Onboarding
6299 | IIRM-9143 | Sub-task | Email notification - Persisting Copies of Sent Emails for Audit & Tracking | Done | tharun |  | IIRM-8572 — End User Onboarding
6300 | IIRM-9144 | Story | Opportunities preproduction and auto population issues | Draft | Jadhav Sai Prasad |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6301 | IIRM-9145 | Story | Service flow pending DB requests, Premium issues and policy configuration errors | Open | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6302 | IIRM-9146 | QAlity Test | API: EndUser: Verify Enrollment -start endpoint | Draft | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
6303 | IIRM-9147 | QAlity Test | API: EndUser: Verify EnrollmentConfiguration endpoint | Draft | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
6304 | IIRM-9148 | QAlity Test | API: EndUser: Verify enrollment reminder endpoint | Draft | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
6305 | IIRM-9149 | Sub-task | Disable of auto calculation amount fields | Draft | Mallela Pushyami |  | IIRM-9144 — Opportunities preproduction and auto population issues
6306 | IIRM-9150 | Sub-task | Data generation for file upload process | Done | Akhila Gattu |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6307 | IIRM-9151 | Bug | API: Success response shown with invalid empid | Open | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
6308 | IIRM-9152 | Bug | IIRM: Inception: Duplicate mobile number validation is not applied during file processing | Done | Prathiphala Kandula |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6309 | IIRM-9153 | Bug | API:EndUser: 400 status should be shown for invalid triggered date. | Open | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
6310 | IIRM-9154 | Bug | API: EndUser: 200 success should not shown if payload got triggered with empty policies ID | Open | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
6311 | IIRM-9155 | Bug | API: EndUser: 400 series should be shown on response , if policy ID provided in string | Open | Akhila Gattu |  | IIRM-786 — SOW#59 - IBP: Landing Page (Admin Module)
6312 | IIRM-9156 | Sub-task | QA: TPA, Insurer testcases | Done | Akhila Gattu |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6313 | IIRM-9157 | Sub-task | QA: Validating the feature | Done | Akhila Gattu |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6314 | IIRM-9158 | Sub-task | QA: Revalidating bugs | Draft | Akhila Gattu |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6315 | IIRM-9159 | Sub-task | Implement validation for invalid intake types and refactor dependent retrieval based on TPA ID | Done | sunilkumar.chitikina |  | IIRM-8222 — Non-Financial Endorsements
6316 | IIRM-9160 | Story | Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6317 | IIRM-9161 | Story | Utility - File Transformation - Client - Outbound - Employee Data (Inception/Endorsement - Step-5: Send to Client) | Done | NithinKrishna Sirigiri |  | IIRM-735 — SOW#8 - 11 Components / Modules
6318 | IIRM-9162 | Story | Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer) | Done | NithinKrishna Sirigiri |  | IIRM-735 — SOW#8 - 11 Components / Modules
6319 | IIRM-9163 | Story | Utility - File Transformation - Client - Inbound - Employee Data (Inception/Endorsement - Step-1: Upload Employee Data) | Done | NithinKrishna Sirigiri |  | IIRM-735 — SOW#8 - 11 Components / Modules
6320 | IIRM-9164 | Story | Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA) | Done | NithinKrishna Sirigiri |  | IIRM-735 — SOW#8 - 11 Components / Modules
6321 | IIRM-9165 | Bug | IIRM: Non-Finance: Total records count is incorrect when empty rows are uploaded during endorsement | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6322 | IIRM-9166 | Story | Errors While Uploading Data in iWork Edge - Policy ID 635422 | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6323 | IIRM-9167 | Story | Utility - Policy Config - Import from One Policy to Another Policy | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
6324 | IIRM-9168 | Story | Update Claim Submission Notice Popup to Include TPA-Level Claims | Done | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
6325 | IIRM-9169 | Sub-task | Database request changes in service flow - Production | WORK IN PROGRESS | Jagadeesh |  | IIRM-9145 — Service flow pending DB requests, Premium issues and policy configuration errors
6326 | IIRM-9170 | Bug | IIRM: Claims: Manage Policies: UI: UI Issues | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6327 | IIRM-9171 | Bug | IIRM: Claims: Duplicate claim error is displayed when status is changed from Pending to Settled status. | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6328 | IIRM-9172 | Bug | IIRM: Non-Finance: File is processed successfully even when DOB conditions are not satisfied | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6329 | IIRM-9173 | Bug | IIRM: Claims: Incorrect validation message displayed for wrong Employee TPA ID | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6330 | IIRM-9174 | Sub-task | QA: Claims: Validate claims functionality | Done | Akhila Gattu |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6331 | IIRM-9175 | Task | Rebuild employee hierarchy issue | Done | VedaVyas
6332 | IIRM-9176 | Task | No premium calculation covers found for Opportunity | Done | VedaVyas |  | IIRM-797 — SOW#69 - Manage Opportunities
6333 | IIRM-9177 | Bug | IIRM: Non-Finance: Error file and record count are not generated when uploaded file fails | Done | Leela Pakalapati | iWork | IIRM-757 — SOW#30 - Manage Policy Endorsements
6334 | IIRM-9178 | Sub-task | QA: API Testing & bug verification | Done | SaikumarMahanthi |  | IIRM-4547 — NFR-INT-010: API kit documentation should be available - Application must expose API docs as Swagger docs for all the environments except Production
6335 | IIRM-9179 | Bug | IIRM: Non-Finance: TPA ID Upload step is displayed and accessible for Non-Financial Endorsement | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6336 | IIRM-9180 | Sub-task | Bugfixes and Regression testing | Done | SaikumarMahanthi |  | IIRM-4559 — NFR-COM-012 - Avoid local storage for sensitive data in browser
6337 | IIRM-9181 | Sub-task | QA: Test cases creation | Done | SaikumarMahanthi |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6338 | IIRM-9182 | Sub-task | QA: Testing & bug fixes verification | Done | SaikumarMahanthi |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6339 | IIRM-9183 | Sub-task | Add a new scheduler component with year, month and day. | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6340 | IIRM-9184 | Sub-task | Develop the api's to fetch the cron configurations and update the cron configuration | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6341 | IIRM-9185 | Sub-task | Implement the scheduler registry so that the cron job runs based on the DB registered time | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6342 | IIRM-9186 | Sub-task | Develop the UI to see all the scheduler and edit the scheduler configuration | Done | Pampana Ravi Kiran |  | IIRM-4531 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution.
6343 | IIRM-9187 | Sub-task | Create a utility to handle all the guessable words, personal info and pattern info to avoid those in the password | Done | Pampana Ravi Kiran |  | IIRM-4506 — NFR-SEC-047: PINS for Backend Authentication - Password should be accepted with NOT PII info in or as part of it. Maintain password policy to prevent this
6344 | IIRM-9188 | Sub-task | Define Download Restriction Rules | Done | Nikhil V |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6345 | IIRM-9189 | Sub-task | Backend Enforcement: Download Blocking | Done | Nikhil V |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6346 | IIRM-9190 | Sub-task | Password Protection for Approved Outbound Files | Done | Nikhil V |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6347 | IIRM-9191 | Sub-task | Configuration & Feature Flag Support | Done | Nikhil V |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6348 | IIRM-9192 | Sub-task | FE - add TPA and Insurer logos in IBP | Done | Manjusha Paritala |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6349 | IIRM-9193 | Sub-task | FE-get the user list by policy | SELF TESTED | Manjusha Paritala |  | IIRM-8341 — IBP: Switch between Employee & HR Role by HR User
6350 | IIRM-9194 | Bug | IIRM: Non-Finance: Unable to update Full Name and DOB when policy parameter includes Gender | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6351 | IIRM-9195 | Sub-task | BE-IBP- Get logs for TPA's and Insurers | Done | saigangadhar |  | IIRM-6438 — Client (Company, Insurer, & TPA) Logos - Upload, Save & Retrieve
6352 | IIRM-9196 | Bug | IIRM: Non-Finance: DOB can be updated even when Age is configured as a policy parameter | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6353 | IIRM-9197 | Sub-task | QA: Claims: Testing the claims flow | Done | Prathiphala Kandula |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6354 | IIRM-9198 | Sub-task | QA: Claims: Validate claim functionality | Done | PATIBANDLA VELANGINI RAJU |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6355 | IIRM-9199 | Bug | IIRM: Endorsement: Deleted employees count is not matching in Create Endorsement step | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6356 | IIRM-9200 | Sub-task | Location Id is not populating after submission in Final Negotiation activity | Done | Karan Agarwal |  | IIRM-9144 — Opportunities preproduction and auto population issues
6357 | IIRM-9201 | QAlity Test | Upload valid logo while creating TPA profile | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6358 | IIRM-9202 | QAlity Test | Create TPA profile without uploading logo | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6359 | IIRM-9203 | QAlity Test | Reject unsupported file type for TPA logo | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6360 | IIRM-9204 | QAlity Test | Reject TPA logo exceeding maximum file size | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6361 | IIRM-9205 | QAlity Test | Handle corrupted/invalid image content for TPA logo | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6362 | IIRM-9206 | QAlity Test | Preview/thumbnail display after selecting TPA logo | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6363 | IIRM-9207 | QAlity Test | Display TPA logo on iWork TPA details page | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6364 | IIRM-9208 | QAlity Test | Display TPA logo in IBP Customer Care tab | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6365 | IIRM-9209 | QAlity Test | Update TPA logo in iWork and verify propagation | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6366 | IIRM-9210 | QAlity Test | Prevent unauthorized TPA logo upload/update | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6367 | IIRM-9211 | QAlity Test | Upload valid logo while creating Insurer profile | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6368 | IIRM-9212 | QAlity Test | Create Insurer profile without uploading logo | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6369 | IIRM-9213 | QAlity Test | Reject unsupported file type for Insurer logo | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6370 | IIRM-9214 | QAlity Test | Reject Insurer logo exceeding maximum file size | Draft | PATIBANDLA VELANGINI RAJU
6371 | IIRM-9215 | QAlity Test | Display Insurer logo on iWork Insurer details page | Draft | PATIBANDLA VELANGINI RAJU
6372 | IIRM-9216 | QAlity Test | Display Insurer logo in IBP Customer Care tab | Draft | PATIBANDLA VELANGINI RAJU
6373 | IIRM-9217 | QAlity Test | Update Insurer logo in iWork and verify propagation | Draft | PATIBANDLA VELANGINI RAJU
6374 | IIRM-9218 | QAlity Test | Prevent unauthorized Insurer logo upload/update | Draft | PATIBANDLA VELANGINI RAJU
6375 | IIRM-9219 | QAlity Test | Upload valid logo while creating Company | Draft | PATIBANDLA VELANGINI RAJU
6376 | IIRM-9220 | QAlity Test | Create Company without uploading logo | Draft | PATIBANDLA VELANGINI RAJU
6377 | IIRM-9221 | QAlity Test | Display company logo on iWork company details page | Draft | PATIBANDLA VELANGINI RAJU
6378 | IIRM-9222 | QAlity Test | Update company logo in iWork | Draft | PATIBANDLA VELANGINI RAJU
6379 | IIRM-9223 | QAlity Test | Reject unsupported file type for company logo | Draft | PATIBANDLA VELANGINI RAJU
6380 | IIRM-9224 | QAlity Test | Prevent unauthorized company logo upload/update | Draft | PATIBANDLA VELANGINI RAJU
6381 | IIRM-9225 | QAlity Test | Verify correct logo mapping (no cross-entity mix-up) | Draft | PATIBANDLA VELANGINI RAJU
6382 | IIRM-9226 | QAlity Test | Logo removal/replace behavior on update (old logo not shown) | Draft | PATIBANDLA VELANGINI RAJU
6383 | IIRM-9227 | QAlity Test | Direct URL access control for logo assets | Draft | PATIBANDLA VELANGINI RAJU
6384 | IIRM-9228 | QAlity Test | Performance: logo loads within acceptable time and scales responsively | Draft | PATIBANDLA VELANGINI RAJU
6385 | IIRM-9229 | Sub-task | QA: Claims: Test Data Preparation | Done | Prathiphala Kandula |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6386 | IIRM-9230 | Sub-task | QA: Testing happy flow of Claims | Done | Prathiphala Kandula |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6387 | IIRM-9231 | Sub-task | QA: Executing Test cases on employee page | Done | Prathiphala Kandula |  | IIRM-8892 — Show Employees Details in a Policy
6388 | IIRM-9232 | Sub-task | QA: Test Data Preparation | Done | Prathiphala Kandula |  | IIRM-8892 — Show Employees Details in a Policy
6389 | IIRM-9233 | Sub-task | Enrollment navigation changes based on Feedback | Done | saigangadhar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
6390 | IIRM-9234 | Sub-task | Design changes based on feedback | Done | saigangadhar |  | IIRM-8242 — Unified Enrollment Process for Employee Insurance Policies
6391 | IIRM-9235 | Bug | IIRM: Claims Upload: Pending amount is duplicated when already processed records are re-uploaded | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6392 | IIRM-9236 | Bug | IIRM: Claims: Claim amount greater than Total Sum Insured is accepted and reflected in Pending Amount KPI | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6393 | IIRM-9237 | Bug | IIRM: Claims Upload: Record is accepted even when Total Sum Insured value is incorrect | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6394 | IIRM-9238 | Bug | IIRM: Claims Settlement: Settled Amount KPI is not updated correctly when claim status is changed to Settled | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6395 | IIRM-9239 | Bug | IIRM: Claims Upload: Record is accepted even when Total Available Balance value is incorrect | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6396 | IIRM-9240 | Bug | IIRM: Claims Upload: Settled Amount KPI is doubled when already successful records are re-uploaded after correcting failed records | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6397 | IIRM-9241 | Bug | IIRM: Claims Upload: Claim records are accepted even when Policy Dates are invalid | Done | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6398 | IIRM-9242 | Bug | IIRM: Claims Upload: Claim records are accepted even when Patient details are incorrect | Done - Not Reproducible | Prathiphala Kandula |  | IIRM-782 — SOW#55 - Claim Management
6399 | IIRM-9243 | Sub-task | FE-get the user list by policy | SELF TESTED | Dongari Abhilash Varma |  | IIRM-8341 — IBP: Switch between Employee & HR Role by HR User
6400 | IIRM-9244 | Sub-task | Enrollment Upload Optimization(with out choices):file streaming + Chunking + Redis Buckets + Timing Analysis | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6401 | IIRM-9245 | Story | NFR-SEC-020: Part-1: Disable Password Autocomplete and Prevent Browser Credential Saving | Done | Pampana Ravi Kiran |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
6402 | IIRM-9246 | Story | NFR-SEC-020: Part-3: Enforce CAPTCHA Validation on Public-Facing Authentication Forms | Done | Pampana Ravi Kiran |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
6403 | IIRM-9247 | Task | Implement Secure Forgot Password and Reset Password Flow | Done | Pampana Ravi Kiran |  | IIRM-749 — SOW#22 - Data Security (NFR)
6404 | IIRM-9248 | Task | Implement Forced Password Change for Enhanced Account Security | Done | Pampana Ravi Kiran |  | IIRM-749 — SOW#22 - Data Security (NFR)
6405 | IIRM-9249 | Sub-task | Column Sorting | Done | NithinKrishna Sirigiri |  | IIRM-8892 — Show Employees Details in a Policy
6406 | IIRM-9250 | Story | NFR-SEC-020: Part-2: Forgot Password - II | PENDING PEER or LEAD REVIEW | Sidhant Kumar Das |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
6407 | IIRM-9251 | Story | DPDP - Implementation - Application Level | Draft | Rama K
6408 | IIRM-9252 | Story | DPDP - Implementation Database Level | Draft | Rama K
6409 | IIRM-9253 | Story | DPDP - Implementation Infra Level | Draft | Rama K
6410 | IIRM-9254 | Sub-task | Privacy Notice Display | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6411 | IIRM-9255 | Sub-task | Consent Capture | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6412 | IIRM-9256 | Sub-task | Consent Withdrawal | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6413 | IIRM-9257 | Sub-task | Purpose Limitation | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6414 | IIRM-9258 | Sub-task | Data Minimization | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6415 | IIRM-9259 | Sub-task | Strong Authentication | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6416 | IIRM-9260 | Sub-task | RBAC | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6417 | IIRM-9261 | Sub-task | Remove Shared Accounts | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6418 | IIRM-9262 | Sub-task | Session Timeout | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6419 | IIRM-9263 | Sub-task | Input Validation | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6420 | IIRM-9264 | Sub-task | API Authentication | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6421 | IIRM-9265 | Sub-task | Rate Limiting | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6422 | IIRM-9266 | Sub-task | App Activity Logging | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6423 | IIRM-9267 | Sub-task | Failed Login Logging | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6424 | IIRM-9268 | Sub-task | App Activity Logging | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6425 | IIRM-9269 | Sub-task | Failed Login Logging | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6426 | IIRM-9270 | Sub-task | Log Retention 1 Year | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6427 | IIRM-9271 | Sub-task | SIEM Integration | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6428 | IIRM-9272 | Sub-task | Data Deletion Workflow | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6429 | IIRM-9273 | Sub-task | Data Correction | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6430 | IIRM-9274 | Sub-task | Data Export | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6431 | IIRM-9275 | Sub-task | Grievance/DPO Display | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6432 | IIRM-9276 | Sub-task | Secure Dev Practices | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6433 | IIRM-9277 | Sub-task | Static Code Scanning | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6434 | IIRM-9278 | Sub-task | Vulnerability Scanning | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6435 | IIRM-9279 | Sub-task | Pre-release Security Test | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6436 | IIRM-9280 | Sub-task | HTTPS/TLS - Enforce TLS 1.2+ | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6437 | IIRM-9281 | Sub-task | Secrets in Vault - Store secrets securely | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6438 | IIRM-9282 | Sub-task | Application Data Flow Map | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6439 | IIRM-9283 | Sub-task | No Prod Data in UAT - Mask PII | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6440 | IIRM-9284 | Sub-task | CAPTCHA Implementation | Draft | Rama K |  | IIRM-9251 — DPDP - Implementation - Application Level
6441 | IIRM-9285 | Sub-task | DB Encryption at Rest (TDE) - Enable TDE | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6442 | IIRM-9286 | Sub-task | Encrypted DB Backups | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6443 | IIRM-9287 | Sub-task | Least Privilege DB Access | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6444 | IIRM-9288 | Sub-task | Unique DBA Accounts | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6445 | IIRM-9289 | Sub-task | DB MFA | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6446 | IIRM-9290 | Sub-task | Privilege Review Quarterly | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6447 | IIRM-9291 | Sub-task | DB-Level Data Minimization | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6448 | IIRM-9292 | Sub-task | DB Log Retention 1 Year | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6449 | IIRM-9293 | Sub-task | Forward DB Logs to SIEM | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6450 | IIRM-9294 | Sub-task | PII Masking in Non-Prod | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6451 | IIRM-9295 | Sub-task | Data Deletion Workflow | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6452 | IIRM-9296 | Sub-task | Archival Policy | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6453 | IIRM-9297 | Sub-task | DB Restore Testing | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6454 | IIRM-9298 | Sub-task | Backup Retention Policy | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6455 | IIRM-9299 | Sub-task | DB Patch Compliance | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6456 | IIRM-9300 | Sub-task | DB Hardening | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6457 | IIRM-9301 | Sub-task | DB VLAN Segregation | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6458 | IIRM-9302 | Sub-task | No Internet Exposure | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6459 | IIRM-9303 | Sub-task | TLS for DB Connections | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6460 | IIRM-9304 | Sub-task | DB Data Flow Map | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6461 | IIRM-9305 | Sub-task | Legacy DB Cleanup | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6462 | IIRM-9306 | Sub-task | Vendor DPDP Clauses | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6463 | IIRM-9307 | Sub-task | Schema Change Control | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6464 | IIRM-9308 | Sub-task | DB DR Plan | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6465 | IIRM-9309 | Sub-task | DB Credentials in Vault | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6466 | IIRM-9310 | Sub-task | DB Performance Logging | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6467 | IIRM-9311 | Sub-task | No Prod PII in Test | Draft | Rama K |  | IIRM-9252 — DPDP - Implementation Database Level
6468 | IIRM-9312 | Story | Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data) | Done | NithinKrishna Sirigiri |  | IIRM-735 — SOW#8 - 11 Components / Modules
6469 | IIRM-9313 | Bug | IIRM: Inception: Incorrect “Employee ID mismatch for dependent” error for child records | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6470 | IIRM-9314 | Bug | IIRM: Forgot Password: Incorrect Toast Message Displayed When Password Link Expires | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6471 | IIRM-9315 | Bug | IIRM: Manage Claims: Incorrect timestamp displayed on hovering uploaded files | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6472 | IIRM-9316 | Bug | IIRM: Manage Claims: Incorrect total, success, and failure record counts displayed after upload | Done - Not Reproducible | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6473 | IIRM-9317 | Bug | IIRM: Manage Claims: Incorrect TPA validation error displayed while uploading claims | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6474 | IIRM-9319 | Bug | TPA_Insurer_Logo: Unable to view company, TPA, Insurer logo after upload | Done | Akhila Gattu
6475 | IIRM-9320 | Story | Lock User Account After Multiple Unsuccessful Login Attempts | Done | Vara Kumar Jagarapu |  | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
6476 | IIRM-9321 | QAlity Test | IIRM: Forgot password: Force password change on first login | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6477 | IIRM-9322 | Story | Make Copy–Paste Behavior Configurable at Application Level | Done | Vara Kumar Jagarapu |  | IIRM-749 — SOW#22 - Data Security (NFR)
6478 | IIRM-9323 | QAlity Test | IIRM: Forgot Password: Block application access until password change is completed | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6479 | IIRM-9324 | Story | Identify and Document Industry-Standard PII Fields | Draft | Vara Kumar Jagarapu |  | IIRM-749 — SOW#22 - Data Security (NFR)
6480 | IIRM-9325 | Sub-task | QA: Test cases creation | Done | SaikumarMahanthi |  | IIRM-9250 — NFR-SEC-020: Part-2: Forgot Password - II
6481 | IIRM-9326 | Sub-task | QA: Testing and Bug Fixes verification | Done | SaikumarMahanthi |  | IIRM-9250 — NFR-SEC-020: Part-2: Forgot Password - II
6482 | IIRM-9327 | Sub-task | Export to Excel | Done | NithinKrishna Sirigiri |  | IIRM-8892 — Show Employees Details in a Policy
6483 | IIRM-9328 | QAlity Test | IIRM: Forgot Password: Enforce password expiry and require reset | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6484 | IIRM-9329 | QAlity Test | IIRM: Forgot Password: Prevent usage of last 5 passwords | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6485 | IIRM-9330 | Bug | IIRM: Downloaded Password-Protected ZIP Files Fail to Open on Windows | Done | SaikumarMahanthi | iWork
6486 | IIRM-9331 | QAlity Test | IIRM: Forgot Password: Verify that the Forgot Password reset link can be used only once | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6487 | IIRM-9332 | Bug | IIRM: Password Protection Not Enforced for Certain Downloadable Files | Done | SaikumarMahanthi | iWork
6488 | IIRM-9334 | Bug | IIRM: Manage Claims: Claims upload is marked as Failed without generating error file | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6489 | IIRM-9335 | Sub-task | QA: Documenting Test Cases | Done | Prathiphala Kandula |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6490 | IIRM-9336 | Sub-task | QA: Documenting test cases | PENDING PEER or LEAD REVIEW | Prathiphala Kandula |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6491 | IIRM-9337 | Bug | PROD Bug: Insurer Location Getting Changed ¦ Opp. No.666698 ¦ Eurofins Amar ¦ GMC | Open | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6492 | IIRM-9338 | Bug | IIRM: Manage Policies: Claims Upload: Success KPI is not updated when an already settled claim record is edited | Done - Not Reproducible | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6493 | IIRM-9339 | Bug | IIRM: Manage Policies: Claims Upload: Pending Amount and Success KPI are not updated after re-uploading updated claim amount | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6494 | IIRM-9340 | Bug | IIRM: Manage Policies: Claims Upload: Settled Amount KPI is not updated after re-uploading updated settled amount | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6495 | IIRM-9341 | Bug | IIRM: Manage Policies: Claims Upload: Records are marked as Success even when an invalid Policy ID is provided | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6496 | IIRM-9342 | Sub-task | QA:Test cases Creation | Done | SaikumarMahanthi |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6497 | IIRM-9343 | Sub-task | QA: Testing and Bug fixes verification | Done | SaikumarMahanthi |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6498 | IIRM-9344 | Story | Non-visibility of updated Task Entries on i-Work Portal. - Iwork | Done | VedaVyas |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6499 | IIRM-9345 | Sub-task | cron-job for handling password hashing | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6500 | IIRM-9346 | Sub-task | FE - Refactored the utility to perform validations before saving configurations | Done | sunilkumar.chitikina |  | IIRM-9162 — Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer)
6501 | IIRM-9347 | Sub-task | BE - Refactored the ‘Send to Insurer’ step to generate Excel files based on the user-defined schema - Financial | Done | sunilkumar.chitikina |  | IIRM-9162 — Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer)
6502 | IIRM-9348 | Sub-task | BE - Refactored the ‘Send to Insurer’ step to generate Excel files based on the user-defined schema - Non Financial | Done | sunilkumar.chitikina |  | IIRM-9162 — Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer)
6503 | IIRM-9349 | Bug | IBP: relations-constraints-dependents API failed on login process for GMC policy | Done | Akhila Gattu
6504 | IIRM-9350 | Bug | IBP: ActivePolicy: Instead of logo 0 displays on Policy enrolled card | Ready for QA | Akhila Gattu
6505 | IIRM-9351 | Task | Policy Config - Per Mille - Allow Maximum of 4 Decimals | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
6506 | IIRM-9352 | Bug | IBP: Logo: Insurer logo not getting triggerd on customer care page | Done - Not a Bug | Akhila Gattu
6507 | IIRM-9353 | Bug | IBP:Logo: Insurer and TPA details not getting trigerred | Done - Not a Bug | Akhila Gattu
6508 | IIRM-9354 | Bug | IBP: Logo: Logo enchancement on active policy card | Ready for QA | Akhila Gattu
6509 | IIRM-9355 | Bug | IIRM: File download is failed for existing files on Knowledge central | Done - Not Reproducible | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6510 | IIRM-9356 | Bug | IIRM : Downloads are failed for some file formats | Not - Reproducible | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6511 | IIRM-9357 | Bug | IIRM: Manage Claims: Incorrect error message displayed when an invalid Employee ID is uploaded for a valid Policy ID | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6512 | IIRM-9358 | Bug | IIRM: Manage Claims: Error file is not generated when claims are uploaded for a different TPA than the selected TPA | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6513 | IIRM-9359 | Bug | IIRM: Employee tab: "Ack date from insurer” data is not displayed for Dependents | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6514 | IIRM-9360 | Bug | IIRM: Employee Tab: “Endorsement Effective Date” is displayed inconsistently for Self and Dependents | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6515 | IIRM-9361 | Bug | IIRM: Employee Tab: “Insurer Endorsement Number” data is displayed inconsistently across Inc/End steps | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6516 | IIRM-9362 | Bug | IIRM: UAT: Inception: Employee details are missing in the Inception Document file during the “Send Inception to Insurer” step | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6517 | IIRM-9363 | Bug | IIRM: Employee tab: Deleted employees are completely removed from the Employees table | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6518 | IIRM-9367 | Bug | IIRM: Inception: Addition/Deletion employees count is incorrectly displayed in the Create Endorsement step and Track Endorsement table | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6519 | IIRM-9368 | Sub-task | Add master seed data to the master table | Done | Karan Agarwal |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6520 | IIRM-9369 | Sub-task | Integrate utility for TPA configuration | Done | Karan Agarwal |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6521 | IIRM-9370 | Bug | IIRM: Employee tab: Filters are not working as expected | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6522 | IIRM-9371 | Sub-task | QA: Validating the New Columns and Download Details functionality | Done | Leela Pakalapati |  | IIRM-8892 — Show Employees Details in a Policy
6523 | IIRM-9372 | Sub-task | QA: Documenting Test Cases | Done | Leela Pakalapati |  | IIRM-9161 — Utility - File Transformation - Client - Outbound - Employee Data (Inception/Endorsement - Step-5: Send to Client)
6524 | IIRM-9373 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9161 — Utility - File Transformation - Client - Outbound - Employee Data (Inception/Endorsement - Step-5: Send to Client)
6525 | IIRM-9374 | Sub-task | QA: Test Case Execution and Documenting bugs | Done | Leela Pakalapati |  | IIRM-9161 — Utility - File Transformation - Client - Outbound - Employee Data (Inception/Endorsement - Step-5: Send to Client)
6526 | IIRM-9375 | Sub-task | QA: Test Data Preparation | Done | Leela Pakalapati |  | IIRM-9161 — Utility - File Transformation - Client - Outbound - Employee Data (Inception/Endorsement - Step-5: Send to Client)
6527 | IIRM-9376 | Sub-task | QA: Documenting Test Cases | PENDING PEER or LEAD REVIEW | Leela Pakalapati |  | IIRM-9164 — Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA)
6528 | IIRM-9377 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9164 — Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA)
6529 | IIRM-9378 | Sub-task | QA: Executing Test Cases and Documenting Bugs | Done | Leela Pakalapati |  | IIRM-9164 — Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA)
6530 | IIRM-9379 | Sub-task | QA: Test Data Preparation | Done | Leela Pakalapati |  | IIRM-9164 — Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA)
6531 | IIRM-9380 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6532 | IIRM-9381 | Sub-task | QA: Executing Test Cases and Documenting Bugs | Done | Leela Pakalapati |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6533 | IIRM-9382 | Sub-task | QA: Test Data Preparation | Done | Leela Pakalapati |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6534 | IIRM-9383 | Sub-task | QA: File Transformation: Send To Insurer(Step-3): Documenting Test Cases | Done | Leela Pakalapati |  | IIRM-9162 — Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer)
6535 | IIRM-9384 | Sub-task | QA: File Transformation: Send To Insurer(Step-3): Executing Test Cases and Documenting Bugs | Done | Leela Pakalapati |  | IIRM-9162 — Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer)
6536 | IIRM-9385 | Sub-task | QA: File Transformation: Send To Insurer(Step-3): Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9162 — Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer)
6537 | IIRM-9386 | Sub-task | QA: File Transformation: Send To Insurer(Step-3): Test Data Preparation | Done | Leela Pakalapati |  | IIRM-9162 — Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer)
6538 | IIRM-9387 | Sub-task | QA: Documenting Test Cases | Done | Leela Pakalapati |  | IIRM-9163 — Utility - File Transformation - Client - Inbound - Employee Data (Inception/Endorsement - Step-1: Upload Employee Data)
6539 | IIRM-9388 | Sub-task | QA: Testing and Documenting Bugs | Done | Leela Pakalapati |  | IIRM-9163 — Utility - File Transformation - Client - Inbound - Employee Data (Inception/Endorsement - Step-1: Upload Employee Data)
6540 | IIRM-9389 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9163 — Utility - File Transformation - Client - Inbound - Employee Data (Inception/Endorsement - Step-1: Upload Employee Data)
6541 | IIRM-9390 | Sub-task | QA: Test Data Preparation | Done | Leela Pakalapati |  | IIRM-9163 — Utility - File Transformation - Client - Inbound - Employee Data (Inception/Endorsement - Step-1: Upload Employee Data)
6542 | IIRM-9391 | Sub-task | Create a GET api for insurers and clients | Done | NithinKrishna Sirigiri |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6543 | IIRM-9392 | Sub-task | Create a POST api for insurers and clients | Done | NithinKrishna Sirigiri |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6544 | IIRM-9393 | Sub-task | Implementation of modal as per screens | Done | NithinKrishna Sirigiri |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6545 | IIRM-9394 | Sub-task | Implementation of add and edit contact | Done | NithinKrishna Sirigiri |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6546 | IIRM-9395 | Sub-task | API integration for both insurers and companies | Done | NithinKrishna Sirigiri |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6547 | IIRM-9396 | Sub-task | QA: File Transformation: TPA ID Upload(6th Step): Documenting Test Cases | Done | Leela Pakalapati |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6548 | IIRM-9397 | Sub-task | QA: File Transformation: TPA ID Upload(6th Step): Executing Test Cases and Documenting Bugs | Done | Leela Pakalapati |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6549 | IIRM-9398 | Sub-task | QA: File Transformation: TPA ID Upload(6th Step): Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6550 | IIRM-9399 | Sub-task | QA: File Transformation: TPA ID Upload(6th Step): Test Data Preparation | Done | Leela Pakalapati |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6551 | IIRM-9400 | Sub-task | Enrollment Batch Processing – Progress & DB Timing Logs | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6552 | IIRM-9401 | Sub-task | Run Incremental Enrollment Load Tests (10k → 20k → 100k) & Track Processing Time | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6553 | IIRM-9402 | Sub-task | QA: Testing& Bug fixes verification | Done | SaikumarMahanthi |  | IIRM-4494 — NFR-SEC-016: The application must manual Key loading process - Use salt along with secure key where encryption is being implemented
6554 | IIRM-9403 | Task | IIRM: Prepare Automation Test script for Bulk upload functionallity | WORK IN PROGRESS | SaikumarMahanthi
6555 | IIRM-9404 | QAlity Test | IIRM: Verify TPA-specific template download and usage during TPA ID Upload | Completed | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6556 | IIRM-9405 | QAlity Test | IIRM: Verify system behavior when TPA is selected but no template is configured | Completed | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6557 | IIRM-9406 | QAlity Test | IIRM: Verify error handling when TPA is not selected during Placement Slip Generation | Completed | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6558 | IIRM-9407 | QAlity Test | IIRM: Verify validation, error file generation, and remarks for TPA ID upload failures | Completed | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6559 | IIRM-9408 | Sub-task | Analysis of task | Done | Mallela Pushyami |  | IIRM-9160 — Send to Insurer/Client - View, Add, or Update receiver Email Id in Endorsement/Inception flow
6560 | IIRM-9409 | QAlity Test | IIRM: Verify data persistence and downstream consistency after successful TPA ID upload | Completed | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6561 | IIRM-9410 | QAlity Test | IIRM: Verify version-lock behavior when TPA template changes during upload | Completed | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6562 | IIRM-9411 | Sub-task | File Upload Infrastructure & Processing Pipeline | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-9164 — Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA)
6563 | IIRM-9412 | Sub-task | Template Management System with Versioning & Approval Workflow | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-9164 — Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA)
6564 | IIRM-9413 | Sub-task | Data Transformation Engine & Validation Framework | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-9164 — Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA)
6565 | IIRM-9414 | Sub-task | Database Schema Implementation & Enterprise Audit System | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-9164 — Utility - File Transformation - TPA - Inbound - Employee Data (Upload Claims per TPA)
6566 | IIRM-9415 | Sub-task | QA: API verification on notifications info API and email trigger API's | Done | Akhila Gattu |  | IIRM-8572 — End User Onboarding
6567 | IIRM-9416 | Sub-task | QA: Validating claims on manage claims page | Done | Akhila Gattu |  | IIRM-8980 — GMC - Upload Claims (Per Policy & Per TPA)
6568 | IIRM-9417 | Story | India: Send to Client/Insurer from email address must be configurable | Done | NithinKrishna Sirigiri |  | IIRM-761 — SOW#34 - Notifications Management
6569 | IIRM-9418 | Story | CR: Calculate premium based on age of dependent if policy is per life | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
6570 | IIRM-9419 | Bug | IIRM: The SI is not reflected correctly in the Policy Choices step | Done | Leela Pakalapati | IBP | IIRM-777 — SOW#50 - Policy Configurator
6571 | IIRM-9420 | Sub-task | R&D: For file password protection issue debbug in windows | Done | Nikhil V |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6572 | IIRM-9421 | Sub-task | Password configuration for files | Done | Nikhil V |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6573 | IIRM-9422 | Story | Policy Config: Calculate based on the live's (Self or Dependent) current age, not the running year from DOB | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
6574 | IIRM-9423 | Story | Inception/Endorsement File Processing - Trim the empty space in the "Intake Type" Column | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6575 | IIRM-9424 | Sub-task | Implement column mapping and persist mapped data to the database | Done | Karan Agarwal |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6576 | IIRM-9425 | Sub-task | Implement source-level validations | Done | Karan Agarwal |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6577 | IIRM-9426 | Sub-task | Analysis of the Story and Technical KT | Done | Karan Agarwal |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6578 | IIRM-9427 | Bug | IIRM: Manage Claims: Incorrect and irrelevant error message displayed when wrong dependent name is entered in Patient Name field | Done - Not Reproducible | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6579 | IIRM-9428 | Sub-task | R&D-trapi implementation | SELF TESTED | Manjusha Paritala |  | IIRM-9077 — Satrapi Implementation
6580 | IIRM-9429 | Sub-task | Task 1: Backend - Bulk Download API Implementation & Gateway Configuration | Done | Lakshmi Gopalakrishna Ratnala |  | IIRM-4483 — NFR-USA-022: Bulk document download facility should be available
6581 | IIRM-9430 | Sub-task | Task 2: Frontend - Bulk Download UI, User Interaction & Download Functionality | Done | Lakshmi Gopalakrishna Ratnala |  | IIRM-4483 — NFR-USA-022: Bulk document download facility should be available
6582 | IIRM-9431 | Sub-task | Task 3: Frontend - Performance Optimization & Multi-Page Integration | Done | Lakshmi Gopalakrishna Ratnala |  | IIRM-4483 — NFR-USA-022: Bulk document download facility should be available
6583 | IIRM-9432 | Sub-task | CITI_PRE_PROD: 647474 upload issues | Done | Jagadeesh |  | IIRM-9145 — Service flow pending DB requests, Premium issues and policy configuration errors
6584 | IIRM-9433 | Sub-task | PROD:526819 Issue with the file upload for the endorsement 1650 | Done | Jagadeesh |  | IIRM-9145 — Service flow pending DB requests, Premium issues and policy configuration errors
6585 | IIRM-9434 | Sub-task | PROD: 645592 issue with inception data | Done | Jagadeesh |  | IIRM-9145 — Service flow pending DB requests, Premium issues and policy configuration errors
6586 | IIRM-9435 | Sub-task | PROD: 645593 Issue with inception data | Done | Jagadeesh |  | IIRM-9145 — Service flow pending DB requests, Premium issues and policy configuration errors
6587 | IIRM-9436 | Sub-task | PROD: 337821 Issue with 1491 endorsement | Done | Jagadeesh |  | IIRM-9145 — Service flow pending DB requests, Premium issues and policy configuration errors
6588 | IIRM-9437 | Sub-task | PROD: 644584 Issue with premiums for inception | WORK IN PROGRESS | Jagadeesh |  | IIRM-9145 — Service flow pending DB requests, Premium issues and policy configuration errors
6589 | IIRM-9438 | QAlity Test | IIRM: Bulk Download: Verify that a user can successfully select multiple valid documents and download them as a single ZIP file. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6590 | IIRM-9439 | QAlity Test | IIRM: Bulk Download: Validate frontend UI behavior during document selection and download flow. | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6591 | IIRM-9440 | QAlity Test | IIRM: Bulk Download: Ensure smooth performance when selecting many documents and using “Select All”. | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6592 | IIRM-9441 | QAlity Test | IIRM: Bulk Download: Verify bulk download works consistently across all document sections with correct ZIP naming. | Draft | KOWTRAPU KAVYA SRI |  | IIRM-749 — SOW#22 - Data Security (NFR)
6593 | IIRM-9442 | Story | GMC- Claims KPIs enhancement | Draft | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
6594 | IIRM-9443 | Story | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) | Draft | NithinKrishna Sirigiri |  | IIRM-794 — SOW#67 - Portal Configuration
6595 | IIRM-9444 | Story | Migrate from Azure OpenAI gpt-4o-mini to a supported model by 9 Mar 2026 (retired on 31 Mar 2026) | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6596 | IIRM-9445 | Sub-task | QA: Testing and Documenting bugs | Done | Leela Pakalapati |  | IIRM-9422 — Policy Config: Calculate based on the live's (Self or Dependent) current age, not the running year from DOB
6597 | IIRM-9446 | Sub-task | QA: Testing and Documenting bugs | Done | Leela Pakalapati |  | IIRM-9423 — Inception/Endorsement File Processing - Trim the empty space in the "Intake Type" Column
6598 | IIRM-9447 | Sub-task | QA: Testing and Documenting bugs | Done | Leela Pakalapati |  | IIRM-9351 — Policy Config - Per Mille - Allow Maximum of 4 Decimals
6599 | IIRM-9448 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9351 — Policy Config - Per Mille - Allow Maximum of 4 Decimals
6600 | IIRM-9449 | Sub-task | FE-004: Add filters for approval_status, active_status, channel type & subject search and integrate with get templates api | Done | Balendra kumar |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6601 | IIRM-9450 | Bug | IIRM: Manage Claims: Claim batch Sorting is not matching throughout the application | Open | Leela Pakalapati |  | IIRM-782 — SOW#55 - Claim Management
6602 | IIRM-9451 | Bug | Inception/Endorsement: On downloaded template parents dummy data not showing. | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6603 | IIRM-9452 | Bug | IIRM: Bulk Download Fails for Large File Selection | Done | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6604 | IIRM-9453 | Bug | Endorsement: For invalid data failure count not showing | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6605 | IIRM-9454 | Bug | Endorsement: Count mismatch occured from uploaded file. | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6606 | IIRM-9455 | Bug | Endorsment: Single remark should not be shown 1 combination of 3 records | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6607 | IIRM-9456 | Bug | Endorsment: Invalid remark shown, if intake type is provided as NULL. | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6608 | IIRM-9457 | Bug | Endorsement: Self record should get success, if email is not provided for self record, invalid remark should't be shown | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6609 | IIRM-9458 | Bug | IIRM: Bulk Download Button is removed When Selecting All Entries | Done | SaikumarMahanthi | iWork
6610 | IIRM-9459 | Bug | IIRM: “Select All” Applies Only to Current Page, Not Across Paginated Pages | Done | SaikumarMahanthi | iWork
6611 | IIRM-9460 | Story | Create Company - Contact number - Duplicate check | Done | NithinKrishna Sirigiri |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6612 | IIRM-9461 | Story | Need to build the employee scope common function | Draft | NithinKrishna Sirigiri |  | IIRM-732 — SOW#5 - Access Control
6613 | IIRM-9462 | Story | Payline India Accounting Services Pvt Office Package Policy 1175653 Error in terrorism premium & GST calculation | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
6614 | IIRM-9463 | Story | On the My Company page, the Portfolio section should include a hyperlink for the Policy Number column | Done | NithinKrishna Sirigiri |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6615 | IIRM-9464 | Story | Non-visibility of updated Task Entries on i-Work Portal - Iwork | Done | NithinKrishna Sirigiri |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6616 | IIRM-9465 | Story | Employee Hierarchy (Ex: Ramakrishna Sir should not report to the system user) | Done | NithinKrishna Sirigiri |  | IIRM-732 — SOW#5 - Access Control
6617 | IIRM-9466 | Story | Link the Meetings into the Opportunity activities | Done | NithinKrishna Sirigiri |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6618 | IIRM-9467 | Story | Link the Notes into the Opportunity activities | Done | NithinKrishna Sirigiri |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6619 | IIRM-9468 | Story | Show only relevant Tasks, Meetings and notes when we are in the opportunity details page | Done | NithinKrishna Sirigiri |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6620 | IIRM-9469 | Story | Roles And Access needs to re-modify | Draft | NithinKrishna Sirigiri |  | IIRM-732 — SOW#5 - Access Control
6621 | IIRM-9470 | Story | Adding a policy to an existing CD account | Done | NithinKrishna Sirigiri |  | IIRM-781 — SOW#54 - CD Management
6622 | IIRM-9471 | Story | CD Statement - Export to Excel (CD Statement - Export to Excel ( Remove Export Visibility to all users except "System Admin") | Done | NithinKrishna Sirigiri |  | IIRM-781 — SOW#54 - CD Management
6623 | IIRM-9472 | Story | Manage Policy: Policy Id should be displayed in table & in table setting. Also should be in Smart Search | Done | NithinKrishna Sirigiri |  | IIRM-781 — SOW#54 - CD Management
6624 | IIRM-9473 | Story | Merging multiple CD accounts | Done | NithinKrishna Sirigiri |  | IIRM-781 — SOW#54 - CD Management
6625 | IIRM-9474 | Story | Create/edit email templates with versioning and send email, save a copy and scoping at a company level | Draft | NithinKrishna Sirigiri |  | IIRM-761 — SOW#34 - Notifications Management
6626 | IIRM-9475 | Story | Optimise FAQ's and hospital network by reducing the duplicates | Draft | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
6627 | IIRM-9476 | Story | Implement Rich text editor for email templates and FAQ's (POC) | Draft | NithinKrishna Sirigiri |  | IIRM-761 — SOW#34 - Notifications Management
6628 | IIRM-9477 | Story | Company level logo's for Insurer, TPA and Company | Draft | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
6629 | IIRM-9478 | Story | Maps integration to identify nearby locations (BE calculations and FE representation) | Done | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
6630 | IIRM-9479 | Story | IBP: HR Portal - Dashboard | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
6631 | IIRM-9480 | Sub-task | Process the TPA input file | Done | Karan Agarwal |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6632 | IIRM-9481 | Sub-task | Generate error file based on user-defined headers | Done | Karan Agarwal |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6633 | IIRM-9482 | Task | Endorsement Validation & Inception File Errors – Member Enrollment, Premium Mismatch, and Parameter Format Issue | Draft | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6634 | IIRM-9483 | Bug | Endorsement: Delay in template download | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6635 | IIRM-9484 | Bug | Endorsement: Unable to get endorsement file in step 3 for addition/deletion process. | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6636 | IIRM-9485 | Task | Create Privilege-Based UI Screen in iWork to Expose Swagger Links | Done | Rama K
6637 | IIRM-9486 | Task | NFR-INT-009 -01- Should support SMS, and WhatsappNote | Draft | Rama K
6638 | IIRM-9487 | Story | NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution. Part-2 | Done | VedaVyas |  | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
6639 | IIRM-9488 | Sub-task | We need to get the nature of the scheduler and the drill down | Done | VedaVyas |  | IIRM-9487 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution. Part-2
6640 | IIRM-9489 | Sub-task | Email communication for the failed schedulars | Done | VedaVyas |  | IIRM-9487 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution. Part-2
6641 | IIRM-9490 | Sub-task | Retriggering of the schedulers | Done | VedaVyas |  | IIRM-9487 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution. Part-2
6642 | IIRM-9491 | Task | Download Claims Template functionality | Open | Jadhav Sai Prasad |  | IIRM-782 — SOW#55 - Claim Management
6643 | IIRM-9492 | Bug | IIRM: Manage Claims: Incorrect TAT Display | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6644 | IIRM-9493 | Bug | IIRM: The 'Disable Password Autocomplete' and 'Prevent Browser Credential Saving' features are not working in the Firefox browser. | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6645 | IIRM-9494 | Bug | IIRM: TPA: Config Template: Upload Data File Step Issues | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6646 | IIRM-9495 | Bug | IIRM: Insurer: Config Template: Upload Data File Step Issues | Done - Not Reproducible | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6647 | IIRM-9496 | Bug | IIRM: TPA: Template Mapping: Few Client Columns Are Not Visible in the UI | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6648 | IIRM-9497 | Bug | IIRM: Insurer: Template Mapping: Few Client Columns Are Not Visible in the UI | Done - Not Reproducible | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6649 | IIRM-9498 | Story | Several opportunities have passed their expiry date (e.g., expired on 31/12/2025) but are still not being automatically marked as Lost. As a result, these opportunities cannot be extended. This issue is occurring in multiple cases(1175632) | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6650 | IIRM-9499 | Bug | IIRM: Password Still Enforced for Inception Files Even When Password Is Disabled in Configuration | Done | SaikumarMahanthi
6651 | IIRM-9500 | Bug | IIRM: File Utility: TPA/Insurer: Template Mapping: Date and Gender data transformation pop-up issues | Done | Leela Pakalapati | IBP
6652 | IIRM-9501 | Story | For RO Opportunities, covers captured/modified are not getting saved in broking slip stage | Open | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
6653 | IIRM-9502 | Story | RO opportunities starting with opportunity number of digit "6" have issue | Draft | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
6654 | IIRM-9503 | Story | Covers for Opportunity - Duplicate, Missing, Inactive, & Active | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
6655 | IIRM-9504 | Bug | IIRM: Default cursor is not present in the first text element on page load. | Open | KOWTRAPU KAVYA SRI | iWork | IIRM-62 — SOW#2 - Authentication
6656 | IIRM-9505 | Bug | IIRM: Incorrect and Inconsistent Text Messages in Password Protection Scenarios | Ready for QA | SaikumarMahanthi | iWork
6657 | IIRM-9506 | Story | Instalments for a Policy Premium including Inception/Endorsement/Others | Done | NithinKrishna Sirigiri |  | IIRM-781 — SOW#54 - CD Management
6658 | IIRM-9507 | Sub-task | QA: Test cases preparation | Done | SaikumarMahanthi |  | IIRM-9245 — NFR-SEC-020: Part-1: Disable Password Autocomplete and Prevent Browser Credential Saving
6659 | IIRM-9508 | Sub-task | Move endorsement summary/premium calculations to scheduler (persist counts + premiums) | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6660 | IIRM-9509 | Sub-task | QA: Testing and Bug fixes verification | Done | SaikumarMahanthi |  | IIRM-9245 — NFR-SEC-020: Part-1: Disable Password Autocomplete and Prevent Browser Credential Saving
6661 | IIRM-9510 | Sub-task | Optimize endorsement‑steps GET API with SQL aggregates (fix large‑endorsement performance/bind errors) | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6662 | IIRM-9511 | Sub-task | QA: API Test cases preparation | Done | SaikumarMahanthi |  | IIRM-4547 — NFR-INT-010: API kit documentation should be available - Application must expose API docs as Swagger docs for all the environments except Production
6663 | IIRM-9512 | Bug | IIRM: File Utility: Template Mapping: Screen refresh redirects to File Upload and mapping progress is lost | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6664 | IIRM-9513 | Bug | IIRM: File Utility: Preview/Edit/Download options are not available for versioned templates | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6665 | IIRM-9514 | Story | V TECHWEB (INDIA) PRIVATE LIMITED fire 1018648 Held cover note; brokerage calculation error | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
6666 | IIRM-9515 | Bug | IIRM: File Utility: Multiple template versions are created when configuration is saved without any changes | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6667 | IIRM-9516 | Bug | Endorsement: Unable to view endorsement step1 , if bulk files got uploaded. | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6668 | IIRM-9517 | Bug | IIRM: File Utility: Restore version functionality is not working | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6669 | IIRM-9518 | Sub-task | QA: Employee Tab: Re-Verification of Bugs and Sanity testing | Done | Leela Pakalapati |  | IIRM-8892 — Show Employees Details in a Policy
6670 | IIRM-9519 | QAlity Test | TC01 — Feature Flag OFF: Lockout disabled, failures still logged | Draft | SaikumarMahanthi | iWork
6671 | IIRM-9520 | QAlity Test | TC02 — Feature Flag ON: Lockout at configured threshold across sessions/devices/IPs | Draft | SaikumarMahanthi | iWork
6672 | IIRM-9521 | QAlity Test | IIRM: Login - no autofill and minimized save prompt | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6673 | IIRM-9522 | QAlity Test | IIRM: Login – Configuration to Enable/Disable Password Auto-Save | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6674 | IIRM-9523 | QAlity Test | TC-03 : Lock Duration Enforcement: Blocked during window, correct credentials do not bypass | Draft | SaikumarMahanthi | iWork
6675 | IIRM-9524 | QAlity Test | TC04 — Auto‑Unlock Enabled: Unlocks after duration and allows login | Draft | SaikumarMahanthi | iWork
6676 | IIRM-9525 | QAlity Test | TC05 — Auto‑Unlock Disabled: Manual unlock required before login | Draft | SaikumarMahanthi | iWork
6677 | IIRM-9526 | QAlity Test | TC: TC06 — Generic Error messages for All Scenarios | Draft | SaikumarMahanthi | iWork
6678 | IIRM-9527 | QAlity Test | IIRM: Verify Username, and Password are not saved to prevent autofill | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6679 | IIRM-9528 | QAlity Test | IIRM: Uniform behavior across different browsers - no autofill password | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6680 | IIRM-9529 | Sub-task | QA: Test Cases Creation | Done | SaikumarMahanthi |  | IIRM-9320 — Lock User Account After Multiple Unsuccessful Login Attempts
6681 | IIRM-9530 | Sub-task | QA:Testing and Bugfixes verification | Done | SaikumarMahanthi |  | IIRM-9320 — Lock User Account After Multiple Unsuccessful Login Attempts
6682 | IIRM-9531 | Sub-task | QA: Test cases Creation | Done | SaikumarMahanthi |  | IIRM-4483 — NFR-USA-022: Bulk document download facility should be available
6683 | IIRM-9532 | Sub-task | QA: Testing & Bug fixess verification | Done | SaikumarMahanthi |  | IIRM-4483 — NFR-USA-022: Bulk document download facility should be available
6684 | IIRM-9533 | QAlity Test | TC-01: Verify password Enforces for files Open when password protection is enabled | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6685 | IIRM-9534 | Bug | IIRM: Manage Policies: Claims Upload: Incorrect and misleading error message displayed for dependent claim records | Open | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6686 | IIRM-9535 | QAlity Test | TC-03: Verify file access using admin-configured custom password | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6687 | IIRM-9536 | QAlity Test | TC-02: Verify files open without password when file password protection is disabled | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6688 | IIRM-9537 | QAlity Test | TC-04: Verify file access using system-generated password | Draft | SaikumarMahanthi
6689 | IIRM-9538 | QAlity Test | TC-05: Verify system restricts file access when incorrect password is entered | Draft | SaikumarMahanthi | iWork
6690 | IIRM-9539 | Bug | IIRM: Employee tab: Effective Date is incorrectly displayed in the Employees table | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6691 | IIRM-9540 | Bug | Claims: Uploaded claims are not synced between Manage Claims and Manage Policies (Claims Uploaded Data table) | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6692 | IIRM-9541 | Bug | IIRM: Employee tab: Usability issues in filters and employee table display | Done | Leela Pakalapati | IBP | IIRM-6827 — Manage Policy
6693 | IIRM-9542 | QAlity Test | TC-01: Verify unpublished templates are not used for system notifications and communications | Draft | SaikumarMahanthi | iWork
6694 | IIRM-9543 | Bug | IIRM: Manage Policies: Upload Claims: Download File option still visible in Claims Uploaded Data table | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6695 | IIRM-9544 | QAlity Test | TC-02: Verify system admin approval using Publish option in Template Management screen | Draft | SaikumarMahanthi | iWork
6696 | IIRM-9545 | Bug | IIRM: Manage Policies: Upload Claims: Pending Amount KPI is not updated correctly for uploaded pending claims | Done | Prathiphala Kandula | IBP | IIRM-782 — SOW#55 - Claim Management
6697 | IIRM-9546 | Bug | IIRM : Exported file is corrupted in CD Management | Done - Not Reproducible | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6698 | IIRM-9547 | Bug | IIRM: “Request Processing Exceeded 10 Seconds Timeout” Error Displayed while attempt Login | Open | KOWTRAPU KAVYA SRI | iWork | IIRM-62 — SOW#2 - Authentication
6699 | IIRM-9548 | Sub-task | Convert password protection from zip to native | Done | Nikhil V |  | IIRM-4470 — NFR-USA-008: Except for approved flows, do not allow download featureFor the files that must not go out of IIRM (to Insurer or TPA) etc
6700 | IIRM-9549 | Sub-task | BE: Refactor the Send to Insurer step to fall back to the existing flow when no mappings are configured | Done | sunilkumar.chitikina |  | IIRM-9162 — Utility - File Transformation - Insurer - Outbound - Employee Data (Inception/Endorsement - Step-3: Send to Insurer)
6701 | IIRM-9550 | Sub-task | BE: Refactor the Send to Client step to fall back to the existing flow when no mappings are configured | Done | sunilkumar.chitikina |  | IIRM-9161 — Utility - File Transformation - Client - Outbound - Employee Data (Inception/Endorsement - Step-5: Send to Client)
6702 | IIRM-9551 | Sub-task | BE - Refactored the ‘Send to Client’ step to generate Excel files based on the user-defined schema - Financial | Done | sunilkumar.chitikina |  | IIRM-9161 — Utility - File Transformation - Client - Outbound - Employee Data (Inception/Endorsement - Step-5: Send to Client)
6703 | IIRM-9552 | Sub-task | BE - Refactored the ‘Send to Client’ step to generate Excel files based on the user-defined schema - Non Financial | Done | sunilkumar.chitikina |  | IIRM-9161 — Utility - File Transformation - Client - Outbound - Employee Data (Inception/Endorsement - Step-5: Send to Client)
6704 | IIRM-9553 | Bug | IIRM: Error Message for Account Lockout is static and not Not User-Friendly | Done | SaikumarMahanthi | iWork
6705 | IIRM-9554 | Bug | IIRM: Lockout Timer Message Does Not Show Remaining Lock Duration Correctly | Done | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6706 | IIRM-9555 | Sub-task | Analysis of task | Done | Mallela Pushyami |  | IIRM-9344 — Non-visibility of updated Task Entries on i-Work Portal. - Iwork
6707 | IIRM-9556 | Story | Disable Save Password & Auto Fill Features at Safari Browser | Draft | Vara Kumar Jagarapu
6708 | IIRM-9557 | Sub-task | Implementation of updated task visibility | PENDING PEER or LEAD REVIEW | Mallela Pushyami |  | IIRM-9344 — Non-visibility of updated Task Entries on i-Work Portal. - Iwork
6709 | IIRM-9558 | Bug | IIRM: Bulk Download Fails in Policy Tab with “Server Returned an Error Page” Message | Open | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6710 | IIRM-9559 | Bug | Mismatch in Dashboard and Bizdone December'25- Critical issue! | Ready for QA | NithinKrishna Sirigiri |  | IIRM-778 — SOW#51 - Admin Reports
6711 | IIRM-9560 | Bug | IIRM – “Something went wrong” error displayed when navigating to other modules | Open | KOWTRAPU KAVYA SRI | iWork | IIRM-62 — SOW#2 - Authentication
6712 | IIRM-9561 | Story | Request for Migration of RO's from old I WORK to new I WORK | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6713 | IIRM-9562 | Bug | Member not enrolled issue - 697721 | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6714 | IIRM-9563 | Bug | 574704 - Duplicate employee-policy mapping for employee ID 413 | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6715 | IIRM-9564 | Bug | Issue in Performing Held Cover Note ¦ Opp. No.985416 | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6716 | IIRM-9565 | Bug | ROs ¦ Opportunity Creation Date & Duplicate Covers ¦ Opp. No.678599, 678601, 678586 | Open | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6717 | IIRM-9566 | Sub-task | Verifying bulk records(10K, 20K, 50K, 80K, 10k)with combination of parameters for group policies. | Done | Akhila Gattu |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6718 | IIRM-9567 | Story | IBP – Employee Portal Dashboard Revamp with New Design | WORK IN PROGRESS | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6719 | IIRM-9568 | Sub-task | BE: POC on Google Maps API Integration | SELF TESTED | Navanitha Makulla |  | IIRM-9079 — RND Task - IBP Portal
6720 | IIRM-9569 | Story | Export Capability Across Multiple Listing Pages | Done | Jadhav Sai Prasad |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
6721 | IIRM-9570 | Sub-task | BE: Company - Company, Insurer, TPA, Broker | PENDING PEER or LEAD REVIEW | Navanitha Makulla |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6722 | IIRM-9571 | Sub-task | BE: Conatct - Contact, Insurer contact, TPA contact, Broker contact | PENDING PEER or LEAD REVIEW | Navanitha Makulla |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6723 | IIRM-9572 | Sub-task | BE: Export Excel: Opportunity | PENDING PEER or LEAD REVIEW | Navanitha Makulla |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6724 | IIRM-9573 | Sub-task | BE: Export Excel: Policy | PENDING PEER or LEAD REVIEW | Navanitha Makulla |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6725 | IIRM-9574 | Sub-task | IIRM-IBP: R&D on banner in Enrollment Summary page | SELF TESTED | PATIBANDLA VELANGINI RAJU |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6726 | IIRM-9575 | Sub-task | BE: Export Excel: Caution deposits | PENDING PEER or LEAD REVIEW | Navanitha Makulla |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6727 | IIRM-9576 | Sub-task | BE: Export Excel: Endorsements | PENDING PEER or LEAD REVIEW | Navanitha Makulla |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6728 | IIRM-9577 | Sub-task | BE: Export Excel: Claims | PENDING PEER or LEAD REVIEW | Navanitha Makulla |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6729 | IIRM-9578 | Bug | IIRM: Inception: Client Confirmation: Company contact not reflected in “Send Client” popup | Open | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6730 | IIRM-9579 | Bug | IIRM: Send to Insurer / Client Confirmation: Invalid selected email count displayed | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6731 | IIRM-9580 | Sub-task | IIRM-IBP: UI for Dashboard accordian benifit cards and FAQ's | SELF TESTED | Pampana Ravi Kiran |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6732 | IIRM-9581 | Sub-task | IIRM-IBP: UI for Accordian premium amounts component | SELF TESTED | Pampana Ravi Kiran |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6733 | IIRM-9582 | Sub-task | IIRM-IBP: UI for Multi and unified enrollment card | SELF TESTED | Pampana Ravi Kiran |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6734 | IIRM-9583 | Sub-task | FE: Adding Download functionality to download excel and integrating API related to Company page | PENDING PEER or LEAD REVIEW | Gayathri Anamala |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6735 | IIRM-9584 | Sub-task | FE: Integrating APIs related to Contact,opportuninty services | PENDING PEER or LEAD REVIEW | Gayathri Anamala |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6736 | IIRM-9585 | Sub-task | FE: Integrating API related to My Sales portfolio(RO,SO,Managebroker) | PENDING PEER or LEAD REVIEW | Gayathri Anamala |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6737 | IIRM-9586 | Sub-task | FE: integrating API related to Policies | PENDING PEER or LEAD REVIEW | Gayathri Anamala |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6738 | IIRM-9587 | Sub-task | FE: Integrating API related to CD Management, Endorsement,Cliams | PENDING PEER or LEAD REVIEW | Gayathri Anamala |  | IIRM-9569 — Export Capability Across Multiple Listing Pages
6739 | IIRM-9588 | Sub-task | Stream endorsement Excel generation to S3 to prevent heap OOM during create‑endorsement job step-3 | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6740 | IIRM-9589 | Sub-task | Analyze enrollment processing stats for Dev and UAT builds | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6741 | IIRM-9590 | Sub-task | Handling the default test case and required scenarios | Done | Karan Agarwal |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6742 | IIRM-9591 | Sub-task | IIRM-IBP: UI for the dashboard banner and enrollment cards | SELF TESTED | Manjusha Paritala |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6743 | IIRM-9592 | Sub-task | IIRM-IBP: UI for the unified enrollment page | SELF TESTED | Manjusha Paritala |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6744 | IIRM-9593 | Sub-task | Dashboard Strapi implimentation | SELF TESTED | Manjusha Paritala |  | IIRM-9077 — Satrapi Implementation
6745 | IIRM-9594 | Sub-task | FAQ's Strapi implimentation | SELF TESTED | Manjusha Paritala |  | IIRM-9077 — Satrapi Implementation
6746 | IIRM-9595 | Story | NFR-SEC-015 - Use secure mechanism to expose API Keys for external party conencting to the platformExpose the API keys only via https driven UI and must have timeout associated - 2 | Done | VedaVyas
6747 | IIRM-9596 | Story | Local Storage data should be encrypted as the data at Rest to be encrypted as per DPDP Act | Draft | VedaVyas
6748 | IIRM-9597 | Bug | IIRM: Send To Insurer: Policy Configure: Inception: Send to Insurer: Employee IDs missing for Dependents in downloaded insurer template | Done | Prathiphala Kandula | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6749 | IIRM-9598 | Bug | Unable to activate the policy - 697739 | Ready for QA | VedaVyas |  | IIRM-777 — SOW#50 - Policy Configurator
6750 | IIRM-9599 | Bug | IIRM: Inception: Employee upload fails with DB duplicate key error for valid data | Done | Prathiphala Kandula | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6751 | IIRM-9600 | Sub-task | QA: Testing & Bug fixes verification | Done | SaikumarMahanthi |  | IIRM-9322 — Make Copy–Paste Behavior Configurable at Application Level
6752 | IIRM-9601 | Task | NFR-USA-022: Enhancement: Password protection for bulkdownload files & Policy tab | Open | SaikumarMahanthi | iWork
6753 | IIRM-9602 | Story | Calculation of percentage when amount is entered | Ready for QA | Jadhav Sai Prasad |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6754 | IIRM-9603 | Bug | Endorsement: Premium not getting stored in step4: receive acknowledgement | Done | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6755 | IIRM-9604 | Bug | Endorsement: CD transaction details not getting captured on Cd details tab | Open | Akhila Gattu |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6756 | IIRM-9605 | Bug | IIRM: File Utility: TPA ID Upload: TPA-ID column is missing in template configuration | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6757 | IIRM-9606 | Bug | IIRM: Send to Insurer: File Utility: Inception data file is not generated based on the selected template version | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6758 | IIRM-9607 | Sub-task | QA: Test cases Creation | Done | SaikumarMahanthi |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6759 | IIRM-9608 | Sub-task | QA: Test execution and bug fixes verification | Pushed to UAT | SaikumarMahanthi |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6760 | IIRM-9609 | Bug | IIRM: Copy-paste functionality not working in Rich Text, Search, and Meeting “Any Remarks” fields | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6761 | IIRM-9610 | QAlity Test | IIRM: Verify creation of Email, SMS, and WhatsApp templates in Template management | Draft | KOWTRAPU KAVYA SRI | iWork
6762 | IIRM-9611 | QAlity Test | IIRM : Verify Template Viewing, Editing, and Deletion Functionality in Template Management | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6763 | IIRM-9612 | QAlity Test | IIRM: Verify variable/placeholder replacement in templates | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6764 | IIRM-9613 | QAlity Test | IIRM: Verify real-time template preview, validation, and approval workflow functionality | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6765 | IIRM-9614 | QAlity Test | IIRM: Verify template search and filtering and reusable utility components in Template Management | Draft | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6766 | IIRM-9615 | Bug | IIRM: Inception: Send to Insurer: Outbound file not displayed and Refresh button missing | Done | Prathiphala Kandula | IBP
6767 | IIRM-9616 | QAlity Test | IIRM: Bulkdownload: Verify bulk upload of documents in all supported modules | Draft | SaikumarMahanthi | iWork
6768 | IIRM-9617 | QAlity Test | IIRM:Bulk download: Verify secure document download using single, multiple, and “Select All” options | Draft | SaikumarMahanthi | iWork
6769 | IIRM-9618 | QAlity Test | IIRM: Bulkdownload: Verify role-based download access and password protection enforcement | Draft | SaikumarMahanthi | iWork
6770 | IIRM-9619 | QAlity Test | IIRM: Verify copy and paste is allowed when copy–paste control is set to false | Draft | SaikumarMahanthi | iWork
6771 | IIRM-9620 | QAlity Test | IIRM: Verify copy and paste is disabled when copy–paste control is set to true | Draft | SaikumarMahanthi | iWork
6772 | IIRM-9621 | Bug | IIRM: File Utility: Import Template: Invalid template mapping allowed and uploaded file not cleared | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6773 | IIRM-9622 | Sub-task | QA: File Utility: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-8407 — Build file transformation utility for inbound/outbound client-specific format conversion
6774 | IIRM-9623 | Bug | IIRM: Claim Amount, Policy Number, Employee ID and TPA ID fields do not accept numeric values | Done | Prathiphala Kandula | IBP
6775 | IIRM-9624 | Story | Preview Policy configuration capabilities | Draft | Jadhav Sai Prasad |  | IIRM-777 — SOW#50 - Policy Configurator
6776 | IIRM-9625 | Bug | IIRM: Send to Insurer: Header names are converted to uppercase and spaces are not trimmed | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6777 | IIRM-9626 | Bug | IIRM: TPA ID Upload: Unable to upload TPA ID in Step 6 when only Insurer template is configured | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6778 | IIRM-9627 | Bug | IIRM : Forgot Password Redirects to Login Page Instead of Password Reset | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-62 — SOW#2 - Authentication
6779 | IIRM-9628 | Bug | IIRM: Send to Client: Insurer template format is used when Client template is not configured | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6780 | IIRM-9629 | Sub-task | Implement reverse calculation logic in Final Negotiation and Placement Slip Generation modules | Done | Karan Agarwal |  | IIRM-9602 — Calculation of percentage when amount is entered
6781 | IIRM-9630 | Sub-task | Implement reverse calculation logic in deviations module | Done | Karan Agarwal |  | IIRM-9602 — Calculation of percentage when amount is entered
6782 | IIRM-9631 | Sub-task | Implement reverse calculation logic in insurer details modules | Done | Karan Agarwal |  | IIRM-9602 — Calculation of percentage when amount is entered
6783 | IIRM-9632 | Bug | IIRM: Send to Insurer / Send to Client: Emails are not sent to the selected email addresses | Reopen | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6784 | IIRM-9633 | Epic | ReInsurance | Draft | NithinKrishna Sirigiri
6785 | IIRM-9634 | Bug | IIRM: Manage Policies – Upload Claims: Incorrect error message displayed when no TPA is associated with the policy | Open | Prathiphala Kandula | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6786 | IIRM-9635 | Bug | IIRM: SO – Placement Slip Generation: Insurer Share & Brokerage Details are cleared after approval when reopened | Open | Prathiphala Kandula | IBP
6787 | IIRM-9636 | Bug | IIRM : Forgot Password Flow is blocked in all browsers due to captcha | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6788 | IIRM-9637 | Sub-task | QA: Executing Test Cases | Draft | Prathiphala Kandula |  | IIRM-9602 — Calculation of percentage when amount is entered
6789 | IIRM-9638 | Task | Enhancement- RBAC implementation for the bulk download | Open | VedaVyas
6790 | IIRM-9639 | Sub-task | SAST – Backend – Design vulnerabilities and security design flows need to be validated. | Done | Anantha Lakshmi Gatta |  | IIRM-4511 — NFR-SEC-060: The application must insecure Design is a new category currently, with a focus on risks related to design flaws
6791 | IIRM-9640 | Sub-task | SAST – Frontend – Design vulnerabilities and security design flows need to be validated. | Done | Anantha Lakshmi Gatta |  | IIRM-4511 — NFR-SEC-060: The application must insecure Design is a new category currently, with a focus on risks related to design flaws
6792 | IIRM-9641 | Bug | IIRM: MY SO – Placement Slip Generation, Broking Slip Generation: GST Amount auto-truncates digits and recalculates incorrectly when cleared | Ready for QA | Prathiphala Kandula | IBP
6793 | IIRM-9642 | Sub-task | SCA – Vulnerabilities and security design flows need to be validated. | Done | Anantha Lakshmi Gatta |  | IIRM-4511 — NFR-SEC-060: The application must insecure Design is a new category currently, with a focus on risks related to design flaws
6794 | IIRM-9643 | Task | 649929 - Invalid choices are mapped to this employee for this policy. Please verify. | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6795 | IIRM-9644 | Task | 649930 - Invalid choices are mapped to this employee for this policy. Please verify. | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6796 | IIRM-9645 | Task | 405625 - Policy status change | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
6797 | IIRM-9646 | Task | Issue with Inception Steps Upload - Client confirmation - 634581, 649656 | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6798 | IIRM-9647 | Bug | IIRM: CAPTCHA Verification Fails After Multiple Page Reloads on Login Screen | Open | SaikumarMahanthi | iWork
6799 | IIRM-9648 | Bug | IIRM: MY SO – Placement Slip Generation: Application crashes with “Maximum call stack size exceeded” after completion | Ready for QA | Prathiphala Kandula | IBP
6800 | IIRM-9649 | Bug | IIRM: MY SO – Sri Lanka: VAT Amount and VAT Percentage are not calculated correctly | Done | Prathiphala Kandula | IBP
6801 | IIRM-9650 | Bug | IIRM: MY SO – Held Cover Note (India): GST Amount is incorrectly calculated based on GST Percentage | Ready for QA | Prathiphala Kandula | IBP
6802 | IIRM-9651 | Sub-task | QA: Testing & Bug fixes verification | Done | SaikumarMahanthi |  | IIRM-9246 — NFR-SEC-020: Part-3: Enforce CAPTCHA Validation on Public-Facing Authentication Forms
6803 | IIRM-9652 | Bug | IIRM: Validation Failed message on Login After 10 Minutes of Idle Time | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-62 — SOW#2 - Authentication
6804 | IIRM-9653 | Sub-task | QA: Testing and Bug reporting | Done | Leela Pakalapati |  | IIRM-9344 — Non-visibility of updated Task Entries on i-Work Portal. - Iwork
6805 | IIRM-9654 | Sub-task | QA: Testing both India and Lanka and Bug Reporting | Draft | Leela Pakalapati |  | IIRM-9602 — Calculation of percentage when amount is entered
6806 | IIRM-9655 | Story | IBP - Landing Page | Done | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
6807 | IIRM-9656 | Story | IBP: Footer | Done | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
6808 | IIRM-9657 | Story | PROD Issue: Policy Config - Submit & Approval | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
6809 | IIRM-9658 | Bug | IIRM: File download fails for 10MB attachment and Date format is invalid | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-768 — SOW#41 - Knowledge Central
6810 | IIRM-9659 | Sub-task | BA: Write Functional Requirements | Done | NithinKrishna Sirigiri |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
6811 | IIRM-9660 | Sub-task | TL: Write Technical Notes | Done | NithinKrishna Sirigiri |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
6812 | IIRM-9661 | Sub-task | QA: Write Test Scenarios | Done | NithinKrishna Sirigiri |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
6813 | IIRM-9662 | Bug | IIRM: Password Protection Not Enforced for Utilization Reports Despite Configuration Enabled | Done | SaikumarMahanthi | iWork
6814 | IIRM-9663 | Bug | IIRM: Meetings – “Complete Activity” button is enabled when meeting status is still Scheduled | Done | Leela Pakalapati | IBP | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6815 | IIRM-9664 | Bug | IIRM: Meetings: Meeting time auto-updates to next half hour instead of auto-updating meeting status | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6816 | IIRM-9665 | Sub-task | link dashboard meetings to opportunities | Done | Mallela Pushyami |  | IIRM-9466 — Link the Meetings into the Opportunity activities
6817 | IIRM-9666 | Sub-task | Add create meeting in the opportunities for KDM meeting,final negotiation and hand over meet | Done | Mallela Pushyami |  | IIRM-9466 — Link the Meetings into the Opportunity activities
6818 | IIRM-9667 | Sub-task | IIRM-IBP: UI for Profile page | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6819 | IIRM-9668 | Sub-task | API for get call | Done | Mallela Pushyami |  | IIRM-9467 — Link the Notes into the Opportunity activities
6820 | IIRM-9669 | Sub-task | UI for create notes in opportunities | Done | Mallela Pushyami |  | IIRM-9467 — Link the Notes into the Opportunity activities
6821 | IIRM-9670 | Story | Policy must be in place and archival must log properly and intimated to Administrators | Draft | VedaVyas
6822 | IIRM-9671 | Story | NFR-COM-017: Audit/Logging of SMS: The application must capture SMS messages in audit logs | WORK IN PROGRESS | VedaVyas |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6823 | IIRM-9672 | Story | NFR-COM-021: The application must external Cloud Provider Approval | Open | VedaVyas |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6824 | IIRM-9673 | Story | NFR-COM-023 - TPISA. If the application is hosted by a Third Party or using a Third Party's service, the Third Party Risk Assessment Process must be completed in accordance with the Third Party Management (TPM) Policy. | Open | VedaVyas |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6825 | IIRM-9674 | Story | NFR-COM-024 - Audit trail should be available for every change. If there are any status changes in the application, the audit trail should capture date, time stamp, user ID along with effective date when the changed action takes into effect. | Done | VedaVyas |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6826 | IIRM-9675 | Story | NFR-DAT-007: The application must password Based Encryption (PBE) | Duplicate | VedaVyas |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6827 | IIRM-9676 | Story | NFR-SEC-010: The application must provide logout capability such that the users can completely log out of the application | Done | VedaVyas |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
6828 | IIRM-9677 | Sub-task | Enhance Amount and Percentage Fields to Support 4 Decimal Places | Done | Karan Agarwal |  | IIRM-9602 — Calculation of percentage when amount is entered
6829 | IIRM-9678 | Sub-task | IIRM-IBP: strapi integration for updated dashboard and Faq's page | SELF TESTED | Manjusha Paritala |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6830 | IIRM-9679 | Bug | IIRM: Notes: Notes issues | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6831 | IIRM-9680 | Bug | IIRM: Meetings – Multiple usability issues in document attachment display | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6832 | IIRM-9681 | Bug | IIRM: Meetings: Incorrect edit access and Complete Activity button behavior for Cancelled and Auto-Completed meetings | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6833 | IIRM-9682 | Bug | IIRM : SnackBar is missing after performing save template in Template management | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6834 | IIRM-9683 | Bug | IIRM: ID Displayed on snack bar while deleting the tempate | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6835 | IIRM-9684 | Bug | IIRM: Withdraw Action Is Visible and Enabled for Approver User | Done | SaikumarMahanthi | iWork
6836 | IIRM-9685 | Bug | IIRM-Template Mangement: UI Issues | Done | KOWTRAPU KAVYA SRI | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6837 | IIRM-9686 | Bug | IIRM: Template Creation Fails When Parameter Names Are Modified in Subject and Content | Done - Not Reproducible | SaikumarMahanthi | iWork | IIRM-749 — SOW#22 - Data Security (NFR)
6838 | IIRM-9687 | Sub-task | SECRETS - Resolve Secret Key Vulnerability in flying duck | Draft | Anantha Lakshmi Gatta |  | IIRM-4511 — NFR-SEC-060: The application must insecure Design is a new category currently, with a focus on risks related to design flaws
6839 | IIRM-9688 | Bug | IIRM: Meetings: Completed activities are displayed in Activity dropdown while creating a meeting | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6840 | IIRM-9689 | Bug | IIRM : Template Management Content Spacing Issues | On Hold | KOWTRAPU KAVYA SRI | iWork
6841 | IIRM-9690 | Bug | IIRM: Emails Are Triggered Even When Template Is in Inactive or Draft State | Done | SaikumarMahanthi | iWork
6842 | IIRM-9691 | Bug | IIRM: Calendar Tab Displays Only Latest 10 Notes When More Than 10 Notes Are Created | Done | Prathiphala Kandula | IBP | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6843 | IIRM-9692 | Bug | IIRM: Meetings: Inconsistent default duration between Create and Update actions | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6844 | IIRM-9693 | Bug | IIRM: Incorrect Error Message Displayed for Invalid or Empty Data During Template Creation | Done | SaikumarMahanthi | iWork
6845 | IIRM-9694 | Bug | IIRM: Updated Input Parameters Are Not Reflected in Template Subject and Content on Submit | Done - Not Reproducible | SaikumarMahanthi | iWork
6846 | IIRM-9695 | Sub-task | QA: Testing and Bug Reporting | Done | Prathiphala Kandula |  | IIRM-9467 — Link the Notes into the Opportunity activities
6847 | IIRM-9696 | Task | Enhancement- RBAC implementation for password configuration | WORK IN PROGRESS | Nikhil V
6848 | IIRM-9697 | Bug | IIRM: Meetings – Deleted meetings are still visible in the UI | Done | Leela Pakalapati | iWork | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6849 | IIRM-9698 | Task | Change the Policy configuration approval flow changes | Done | VedaVyas
6850 | IIRM-9699 | Story | Sync field names in Placementslip generation vs Add CD balance vs Transaction History Table | Done | Jadhav Sai Prasad |  | IIRM-781 — SOW#54 - CD Management
6851 | IIRM-9700 | Bug | IIRM: Newly Created Notes / Tasks / Meetings Not Displayed Until Refresh & Edit Button Missing for Tasks Created via Create Note | Done - Not a Bug | Prathiphala Kandula | IBP | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6852 | IIRM-9701 | Sub-task | QA: Testing and Bug reporting | Done | Leela Pakalapati |  | IIRM-9466 — Link the Meetings into the Opportunity activities
6853 | IIRM-9702 | Bug | IBP: UI: UI validation | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
6854 | IIRM-9703 | Bug | IBP: UI Validation for support, claims intimation, hospital list, quick links overlay, contact metrics, faqs, e-cards and my documents screens | Open | PATIBANDLA VELANGINI RAJU
6855 | IIRM-9704 | Bug | IIRM: Duplicate TPA ID Column Displayed in TPA ID Upload Template During Inception | Done | Prathiphala Kandula | IBP
6856 | IIRM-9705 | Bug | IIRM: TPA ID Upload Template Downloaded Even When No TPA Is Linked to Policy | Done | Prathiphala Kandula | IBP
6857 | IIRM-9706 | Sub-task | BE-009: Integrate task workflow of opportunity service for template approval workflow | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6858 | IIRM-9707 | Sub-task | BE-010: Create notifications for template approval workflow | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6859 | IIRM-9708 | Sub-task | FE-005: Add hyperlinks for template tasks in My calendar view, notifications to redirect to their respective template routes | Done | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6860 | IIRM-9709 | Sub-task | BE-011: Create a entity in db that is dedicated to specifically manage all inactive templates | Pushed to Backlog | Kowshik Atmakuri |  | IIRM-4480 — NFR-USA-019: Template confirmation should be done from application. Example: email - Templates used in notifications and communication via system must have been approved by system admin in the UI
6861 | IIRM-9710 | Bug | IIRM: “[object Object]” Displayed in Meeting Card When Creating Tasks in SO Activity | Done | Prathiphala Kandula | IBP | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6862 | IIRM-9711 | Sub-task | IIRM-IBP: E-Card UI | SELF TESTED | Pampana Ravi Kiran |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6863 | IIRM-9712 | Sub-task | Confirmation page for the unified enrollment | SELF TESTED | Pampana Ravi Kiran |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6864 | IIRM-9713 | Sub-task | IIRM-IBP: Strapi - Iwork token based login | WORK IN PROGRESS | Navanitha Makulla |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6865 | IIRM-9714 | Sub-task | IIRM-IBP: UI for SupportPage | SELF TESTED | Velisala Giresh |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6866 | IIRM-9715 | Sub-task | IIRM-IBP: UI for Claims Intimation Page | SELF TESTED | Velisala Giresh |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6867 | IIRM-9716 | Sub-task | IIRM-IBP: UI for Contact Metrix Page | SELF TESTED | Velisala Giresh |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6868 | IIRM-9717 | Sub-task | IIRM-IBP: UI for Identity Verify Popup With Flow | SELF TESTED | Velisala Giresh |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6869 | IIRM-9718 | Sub-task | IIRM-IBP: UI for Reset Password Popup And AskEko Component | SELF TESTED | Velisala Giresh |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6870 | IIRM-9719 | Sub-task | IIRM-IBP: UI for QuickLinks Popup And Document Cards Styling | SELF TESTED | Velisala Giresh |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6871 | IIRM-9720 | Sub-task | optimising the endorsement file creation | Done | Dongari Abhilash Varma |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6872 | IIRM-9721 | Bug | IBP: StaticData: Congratulations Vaccumgroup01! You have completed the enrolment - data not matching with figma | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
6873 | IIRM-9722 | Bug | IBP: Employee details not displayed on edit and footer not getting the dynamic data. | Open | PATIBANDLA VELANGINI RAJU |  | IIRM-773 — SOW#46 - Enrolment Portal
6874 | IIRM-9723 | Bug | IIRM: Self Records Not Reflected in Employee Insured Tab After Employee Upload in Inception Step 1 | Not - Reproducible | Prathiphala Kandula | IBP
6875 | IIRM-9724 | Sub-task | QA: Executing Test cases | Done | Prathiphala Kandula |  | IIRM-9468 — Show only relevant Tasks, Meetings and notes when we are in the opportunity details page
6876 | IIRM-9725 | Story | Reinsurance - Requirements from 13-Feb-2026 | Done | NithinKrishna Sirigiri |  | IIRM-9633 — ReInsurance
6877 | IIRM-9726 | Sub-task | QA: Testing and bug fixes verification | Draft | SaikumarMahanthi |  | IIRM-9638 — Enhancement- RBAC implementation for the bulk download
6878 | IIRM-9727 | Sub-task | IIRM-IBP: Testing on static areas in enrollment process | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6879 | IIRM-9728 | Bug | IBP: Designation field appears two times in employee details | Open | PATIBANDLA VELANGINI RAJU |  | IIRM-773 — SOW#46 - Enrolment Portal
6880 | IIRM-9729 | Bug | IIRM: Policy Config Import: Usability issue | Open | Leela Pakalapati | IBP
6881 | IIRM-9730 | Story | <Place Holder: Use it> | Draft | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
6882 | IIRM-9731 | QAlity Test | IIRM: Verify user is able to login successfully in a single browser session. | Draft | KOWTRAPU KAVYA SRI | iWork
6883 | IIRM-9732 | QAlity Test | IIRM: Verify login is blocked when user tries to login from a second browser | Draft | KOWTRAPU KAVYA SRI | iWork
6884 | IIRM-9733 | QAlity Test | IIRM: Verify user can login after closing the active browser session | Draft | KOWTRAPU KAVYA SRI | iWork
6885 | IIRM-9734 | QAlity Test | IIRM: Verify login restriction when accessing from different devices | Draft | KOWTRAPU KAVYA SRI | iWork
6886 | IIRM-9735 | QAlity Test | IIRM: Verify multiple tabs in the same browser are not allowed | Draft | KOWTRAPU KAVYA SRI | iWork
6887 | IIRM-9736 | Bug | IIRM: Policy: Incorrect Message and Time stamp is missing | Reopen | Leela Pakalapati | IBP | IIRM-777 — SOW#50 - Policy Configurator
6888 | IIRM-9737 | Story | IBP: Mobile responsive | Open | NithinKrishna Sirigiri |  | IIRM-734 — SOW#7 - UI Design System
6889 | IIRM-9738 | Bug | IIRM: Incorrect Timestamp Displayed in CD Management Transaction History | Done | Prathiphala Kandula | IBP
6890 | IIRM-9739 | Sub-task | QA: Testing and Bug Logging | Done | Prathiphala Kandula |  | IIRM-9699 — Sync field names in Placementslip generation vs Add CD balance vs Transaction History Table
6891 | IIRM-9740 | Sub-task | QA: Testing and Bug Reporting | Done | Prathiphala Kandula |  | IIRM-6672 — CD Management: Implement Filter
6892 | IIRM-9741 | Sub-task | QA: Testing and Bug Reporting | Draft | Prathiphala Kandula |  | IIRM-8457 — Policy and CD account wise view
6893 | IIRM-9742 | Task | IIRM: Automation Test script for Template Management | Draft | SaikumarMahanthi
6894 | IIRM-9743 | Sub-task | Show relevant tasks,meetings and notes for opportunity details | Done | Mallela Pushyami |  | IIRM-9468 — Show only relevant Tasks, Meetings and notes when we are in the opportunity details page
6895 | IIRM-9744 | Sub-task | Implement the add a policy to the CD account | Done | Mallela Pushyami |  | IIRM-9470 — Adding a policy to an existing CD account
6896 | IIRM-9745 | Sub-task | QA: Testing and Bug Reporting | Done | Leela Pakalapati |  | IIRM-9167 — Utility - Policy Config - Import from One Policy to Another Policy
6897 | IIRM-9746 | Sub-task | QA: Bug Fix verification and Sanity testing | Done | Leela Pakalapati |  | IIRM-9167 — Utility - Policy Config - Import from One Policy to Another Policy
6898 | IIRM-9747 | Sub-task | QA: Testing and Bug Reporting for template download | Done | Leela Pakalapati |  | IIRM-9312 — Utility - File Transformation - TPA - Inbound - TPA Data (Inception/Endorsement - Step-6: Upload TPA Data)
6899 | IIRM-9750 | Bug | IIRM: Inception Template: Usability issue | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
6900 | IIRM-9751 | Bug | IIRM: Shared CD Account Balance Not Updating Across Multiple Policies (Amount Not Summing Up) | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6901 | IIRM-9752 | Bug | IIRM: “[object, Object]” Displayed on Hover Over Empty CD Account Number Field | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6902 | IIRM-9753 | Sub-task | QA: Testing and Bug Reporting | Done | Prathiphala Kandula |  | IIRM-9470 — Adding a policy to an existing CD account
6903 | IIRM-9754 | Bug | IIRM: Inception: Default template is downloaded even when policy has a configured template | Done | Leela Pakalapati | IBP
6904 | IIRM-9755 | Bug | IIRM: Previous content is not displayed in Template Edit screen | Done | KOWTRAPU KAVYA SRI | iWork
6905 | IIRM-9756 | Sub-task | QA: Test Data Preparation | Done | Prathiphala Kandula |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6906 | IIRM-9757 | Bug | IIRM: Transaction History Does Not Display Policy Number/IIRM Policy Number for Transactions on Shared CD Account | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6907 | IIRM-9758 | Bug | IIRM: In Manage Policies, CD Details Shows Transactions from Another Policy When Both Share the Same CD Account | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6908 | IIRM-9759 | Bug | IIRM: CD Account Dropdown Appears Empty in Placement Slip Generation (My SO → Step 12) Even After Selecting Existing CD Account | Done | Prathiphala Kandula | IBP
6909 | IIRM-9760 | Bug | Tasks + Meetings of the logged in user & of all the people reporting to the logged in user | Done | NithinKrishna Sirigiri |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
6910 | IIRM-9761 | Sub-task | IIRM-IBP: UI fixes in enrollment flow | Draft | PATIBANDLA VELANGINI RAJU |  | IIRM-9567 — IBP – Employee Portal Dashboard Revamp with New Design
6911 | IIRM-9762 | Sub-task | QA: Retesting and Bug Reporting | Done | Prathiphala Kandula |  | IIRM-9470 — Adding a policy to an existing CD account
6912 | IIRM-9763 | Sub-task | Instalments - Add/Modify Instalments section in the ISG opportunity flow | Done | NithinKrishna Sirigiri |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
6913 | IIRM-9764 | Sub-task | Add/Modify the policy instalments tab | Done | NithinKrishna Sirigiri |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
6914 | IIRM-9765 | Sub-task | Modify the instalment addition logic in the CD balance | Done | NithinKrishna Sirigiri |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
6915 | IIRM-9766 | Sub-task | QA: Validating the Bulk Records(50K, 80K and 100K) | Done | Leela Pakalapati |  | IIRM-8586 — Inception/Endorsement: Handling large files (Ex. 3L records)
6916 | IIRM-9767 | Story | Allow endorsement after Policy Expiry Date | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6917 | IIRM-9768 | Story | MIR (Monthly Information Report) | QA Failed | NithinKrishna Sirigiri |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
6918 | IIRM-9769 | Story | Show TAT section (Planned vs Completed vs Approved Date) for Activities | Draft | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6919 | IIRM-9770 | Story | Restrict Printing of Specific GMC Asset Fields on Placement Slip Based on Broking Slip Data | Draft | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
6920 | IIRM-9771 | Bug | PROD Issue: Non-Group: Send to Insurer (Sri Lanka Demo) | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6921 | IIRM-9772 | Story | Send to Insurer - Show Preview of the file before sending - Utility or Default Template based on config | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6922 | IIRM-9773 | Story | Send to Client - Show Preview of the file before sending - Utility or Default Template based on config | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6923 | IIRM-9774 | Story | Add 4 decimals in the Policy Config - Company & Employee Contribution | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
6924 | IIRM-9775 | Story | Policy Config - Proration flag | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
6925 | IIRM-9776 | Story | Display From, To, and CC Email Fields with Add Option in Send to Insurer/Client Screen | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6926 | IIRM-9777 | Epic | SOW#22 - Data Security (2. NFR - Data Protection) | Draft | NithinKrishna Sirigiri
6927 | IIRM-9778 | Epic | SOW#22 - Data Security (1. NFR - Compliance) | Draft | NithinKrishna Sirigiri
6928 | IIRM-9779 | Epic | SOW#22 - Data Security (3. NFR - Interoperability) | Draft | NithinKrishna Sirigiri
6929 | IIRM-9780 | Epic | SOW#22 - Data Security (4. NFR - Maintainability) | Draft | NithinKrishna Sirigiri
6930 | IIRM-9781 | Epic | SOW#22 - Data Security (5. NFR - Security) | Draft | NithinKrishna Sirigiri
6931 | IIRM-9782 | Epic | SOW #22 - Data Security (6. NFR - Usability) | Draft | NithinKrishna Sirigiri
6932 | IIRM-9783 | Epic | SOW#22 - Data Security (7. NFR - Others) | Draft | NithinKrishna Sirigiri
6933 | IIRM-9784 | Story | Download - Premium Calculator in Step-2 | QA Verified | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
6934 | IIRM-9785 | Story | IBP - New Design ¦ Functional data handling with different states of users and UI changes | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6935 | IIRM-9786 | Story | IBP - New Design ¦ Implement claim intimation form and listing, recent request | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6936 | IIRM-9787 | Story | IBP - New Design ¦ Handling regular document view and policy feature document at entry points needed | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6937 | IIRM-9788 | Story | IBP - New Design ¦ I-work token based login ¦ CMS - Strapi | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6938 | IIRM-9789 | Story | IBP - New Design ¦ UI adustments for latest theme change ¦ Ecards | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6939 | IIRM-9790 | Story | IBP - New Design ¦ Portal Config | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6940 | IIRM-9791 | Story | IBP - New Design ¦ Card view theme updates ¦ Hospital Network | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6941 | IIRM-9792 | Story | IBP - New Design ¦ Dynamically creating company/policy level content ¦ CMS - Strapi | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6942 | IIRM-9793 | Story | IBP - New Design ¦ CMS - Strapi implementation of multiple elements | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6943 | IIRM-9794 | Story | IBP - New Design ¦ Change password ¦ User Profile | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6944 | IIRM-9795 | Story | IBP - New Design ¦ Adding dependents of each group policy and handling individual coverage | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6945 | IIRM-9796 | Story | IBP - New Design ¦ Support screen implementation | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6946 | IIRM-9797 | Story | IBP: New Design ¦ Enrolment confirmation with OTP/ verification | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6947 | IIRM-9798 | Story | IBP: New Design ¦ Functional data handling with different states of users | Done | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
6948 | IIRM-9799 | Bug | Incorrect Column Naming – “Transaction Date” Showing Entry Date; Need Separate “Creation Date” and “Transaction Date” Columns ( In policy Specific CD transaction history table) | Open | Jadhav Sai Prasad |  | IIRM-781 — SOW#54 - CD Management
6949 | IIRM-9800 | Sub-task | BE: Refactor Inception step to support inbound file transformation utility - Financial | Done | sunilkumar.chitikina |  | IIRM-9163 — Utility - File Transformation - Client - Inbound - Employee Data (Inception/Endorsement - Step-1: Upload Employee Data)
6950 | IIRM-9801 | Sub-task | BE: Refactor Inception step to support inbound file transformation utility - Non Financial | Done | sunilkumar.chitikina |  | IIRM-9163 — Utility - File Transformation - Client - Inbound - Employee Data (Inception/Endorsement - Step-1: Upload Employee Data)
6951 | IIRM-9802 | Sub-task | FE: Add mapping configuration tab for policy setup | Done | sunilkumar.chitikina |  | IIRM-9163 — Utility - File Transformation - Client - Inbound - Employee Data (Inception/Endorsement - Step-1: Upload Employee Data)
6952 | IIRM-9803 | Story | NFR-COM-002: Entitlement review of termination and revocation of the accounts must be captured and data must be stored in the audit log | Done | NithinKrishna Sirigiri |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6953 | IIRM-9804 | Story | NFR-COM-003: Data protection: Each time a record gets deleted, system or application should capture the deleted record in the audit log. | Draft | NithinKrishna Sirigiri |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6954 | IIRM-9805 | Story | NFR-COM-010: The application must prevent storing of confidential and above data that persistently stored on a system in the DMZ. Persistently stored means storage beyond the session lifetime. | Draft | NithinKrishna Sirigiri |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6955 | IIRM-9806 | Story | NFR-COM-015: The application must secure Cookies: If the application uses cookies containing Confidential or higher information | Open | NithinKrishna Sirigiri |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6956 | IIRM-9807 | Story | NFR-COM-016: Web Contents Cache | Draft | NithinKrishna Sirigiri |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6957 | IIRM-9808 | Story | NFR-COM-018: Sensitive Data Protection: The application must encrypt sensitive data such as PII, authentication data and business sensitive information during transit | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6958 | IIRM-9809 | Story | NFR-COM-019: Terms and Conditions: The application must ensure require the customer to accept the Terms & Conditions at the first login to the application. | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-9778 — SOW#22 - Data Security (1. NFR - Compliance)
6959 | IIRM-9810 | Story | NFR-DAT-002: RBAC – Role Based Access Control | Done | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6960 | IIRM-9811 | Story | NFR-DAT-003: Data encryption in transit | PENDING PEER or LEAD REVIEW | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6961 | IIRM-9812 | Story | NFR-DAT-004: Data encryption in Storage | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6962 | IIRM-9813 | Story | NFR-DAT-005: The application must data loss or data corruption preventions | Done | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6963 | IIRM-9814 | Story | NFR-DAT-006: Password encryption | Done | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6964 | IIRM-9815 | Story | NFR-DAT-008: The application must prevent any encryption keys or passkey for PBEs from being included in the source code or configuration files. | Done | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6965 | IIRM-9816 | Story | NFR-DAT-009: Key Backup and Archiving | Duplicate | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6966 | IIRM-9817 | Story | NFR-DAT-010: The application must prevent storing of confidential and above data that persistently stored on a system in the DMZ. | Duplicate | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6967 | IIRM-9818 | Story | NFR-DAT-011: Database Password Protection in Storage | Done | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6968 | IIRM-9819 | Story | NFR-DAT-012: Database Authorization | Done | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6969 | IIRM-9820 | Story | NFR-DAT-013: The application must sensitive Data Protection at Rest | Duplicate | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6970 | IIRM-9821 | Story | NFR-DAT-014: Token based Authentication Mechanism If the application makes use of SAML, Oauth, or JWT token for on-going Authentication; | Done | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6971 | IIRM-9822 | Story | NFR-DAT-015: Push Notification Controls | Duplicate | NithinKrishna Sirigiri |  | IIRM-9777 — SOW#22 - Data Security (2. NFR - Data Protection)
6972 | IIRM-9823 | Sub-task | QA: API Setups for Jmeter | WORK IN PROGRESS | SaikumarMahanthi |  | IIRM-4473 — NFR-USA-011: The system should support at least 100 concurrent users without performance degradation.
6973 | IIRM-9824 | Bug | IIRM: Inception Temp: Policies configured with Marital Status / Custom List / Custom Range parameters are not working during Employee Upload | Done | Leela Pakalapati | iWork
6974 | IIRM-9825 | Task | QA: End to End Testing on Pre -pod Environment | Open | SaikumarMahanthi | iWork
6975 | IIRM-9826 | Bug | IIRM: SO: Data population issues | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6976 | IIRM-9827 | Bug | IIRM: SO: Instalments: Unable to Save/Submit Placement Slip Generation Activity | Done | Leela Pakalapati | IBP | IIRM-781 — SOW#54 - CD Management
6977 | IIRM-9828 | Bug | IIRM: SO: Sri Lanka: “Total Installment Amount” Field Not Displayed When Premium is Installment Based = Yes | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6978 | IIRM-9829 | Bug | IIRM: SO:Instalments Usability Issue | Done | Leela Pakalapati | IBP | IIRM-781 — SOW#54 - CD Management
6979 | IIRM-9830 | Bug | IIRM: Preview: UI design not aligned with intended utility | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6980 | IIRM-9831 | Bug | IIRM: SO (Sri Lanka) – Page Becomes Unresponsive When Toggling from Single Insurer to Multiple Insurer in Policy Hard Copy Receipt | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6981 | IIRM-9832 | Bug | IIRM: SO (Sri Lanka and India) – Removed Installments in Held Covernote Not Reflected in Policy Hard Copy Receipt | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6982 | IIRM-9833 | Sub-task | QA: Testing and logging Bugs | Done | Prathiphala Kandula |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
6983 | IIRM-9834 | Sub-task | QA: Testing and Bug Reporting | Done | Leela Pakalapati |  | IIRM-9772 — Send to Insurer - Show Preview of the file before sending - Utility or Default Template based on config
6984 | IIRM-9835 | Sub-task | QA: Testing and bug reporting | Done | Leela Pakalapati |  | IIRM-9773 — Send to Client - Show Preview of the file before sending - Utility or Default Template based on config
6985 | IIRM-9836 | Bug | IIRM: Dummy data is not generated for Policy Parameter fields in configured templates | Done | Leela Pakalapati | iWork | IIRM-735 — SOW#8 - 11 Components / Modules
6986 | IIRM-9837 | Bug | IIRM: SO (Sri Lanka) – 400 Bad Request Error While Submitting Policy Hard Copy Receipt (tcBrokerageAmount Should Not Exist) | Not - Reproducible | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
6987 | IIRM-9838 | Story | NFR-SEC-049: The application must ensure that Any application that changes the state at the backend should have a one-time session/state ID associated with it | Done | VedaVyas |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
6988 | IIRM-9839 | Story | NFR-MAI-011: The application must security Logging and Monitoring Failures was previously Insufficient Logging & Monitoring and is added from the industry survey. | Done | SaikumarMahanthi |  | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
6989 | IIRM-9840 | Story | NFR-INT-002: System-to-System Authentication. Authentication mechanism must be implemented for system-to-system communication | Done | SaikumarMahanthi |  | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
6990 | IIRM-9841 | Story | NFR-SEC-057: The application must source Code Review: The application source code has to be reviewed for security flaws either via a manual source code review or via a corporate automated tool | Done | SaikumarMahanthi |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
6991 | IIRM-9842 | Story | NFR-SEC-061: The application must vulnerable and Outdated Components was previously titled Using Components with Known Vulnerabilities | Done | SaikumarMahanthi |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
6992 | IIRM-9843 | Bug | IIRM: CC Email Recipients Also Appearing in “To” Field While Sending Emails to Insurer in Inception Process | Done | Prathiphala Kandula | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6993 | IIRM-9844 | Bug | IIRM: Attachments Sent Inconsistently in “Send to Insurer” and “Send to Client” Email Sections | Done | Prathiphala Kandula | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
6994 | IIRM-9845 | Task | IIRM: Pre-pod and UAT End to End Testing | Done | SaikumarMahanthi
6995 | IIRM-9846 | Task | IIRM: Template Management Testing & Bug fixes | Draft | SaikumarMahanthi
6996 | IIRM-9847 | Task | IIRM: Forgot password functionality testing | Draft | SaikumarMahanthi
6997 | IIRM-9848 | Sub-task | QA: Test cases Preparation | Done | SaikumarMahanthi |  | IIRM-9487 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution. Part-2
6998 | IIRM-9849 | Sub-task | QA: Testing and bug fixes verification | Done | SaikumarMahanthi |  | IIRM-9487 — NFR-OTH-020: The scheduler service must allow for automated night jobs and event-driven task execution. Part-2
6999 | IIRM-9850 | Story | Generate the Business performance / Bizdone Report for policies and endorsements, which are enable for Business performance | Done | Rama K
7000 | IIRM-9851 | QAlity Test | IIRM - Scheduling Service : Retriggering the scheduler button should run the chron immediately . | Draft | KOWTRAPU KAVYA SRI | iWork
7001 | IIRM-9852 | QAlity Test | IIRM - Scheduling Service: Retrigger Scheduler Button Disabled When Job is Running | Draft | KOWTRAPU KAVYA SRI | iWork
7002 | IIRM-9853 | QAlity Test | IIRM – Scheduling Service: Tooltip Display When Cron is Running | Draft | KOWTRAPU KAVYA SRI | iWork
7003 | IIRM-9854 | QAlity Test | IIRM – Scheduling Service: Retrigger Scheduler Disabled During Edit Configuration | Draft | KOWTRAPU KAVYA SRI | iWork
7004 | IIRM-9855 | QAlity Test | IIRM – Scheduling Service: Display Detailed View of Cron/Chron Execution | Draft | KOWTRAPU KAVYA SRI | iWork
7005 | IIRM-9856 | Story | Add Insurer Endorsement No and Effective date columns in the Track Endorsement table | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7006 | IIRM-9857 | Story | NFR-INT-001: Data encryption in transit | Draft | NithinKrishna Sirigiri |  | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
7007 | IIRM-9858 | Story | NFR-INT-004: Push Notification Controls | Draft | NithinKrishna Sirigiri |  | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
7008 | IIRM-9859 | Story | NFR-INT-005: The application must external Cloud Provider Approval | Draft | NithinKrishna Sirigiri |  | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
7009 | IIRM-9860 | Story | NFR-INT-007: TPISA | Draft | NithinKrishna Sirigiri |  | IIRM-9779 — SOW#22 - Data Security (3. NFR - Interoperability)
7010 | IIRM-9861 | Story | NFR-MAI-001: The application must generate its own keys for cryptographic functions | Draft | NithinKrishna Sirigiri |  | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
7011 | IIRM-9862 | Story | NFR-MAI-003: The application must prevent unauthorized access | Draft | NithinKrishna Sirigiri |  | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
7012 | IIRM-9863 | Story | NFR-MAI-008: The application must patch Management | Draft | NithinKrishna Sirigiri |  | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
7013 | IIRM-9864 | Story | NFR-MAI-009: The application must source Code Review | Draft | NithinKrishna Sirigiri |  | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
7014 | IIRM-9865 | Story | NFR-MAI-010: Roles and responsibilities for each phase of the key management life cycle must be clearly defined | Draft | NithinKrishna Sirigiri |  | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
7015 | IIRM-9866 | Story | NFR-MAI-013: The system must allow template creation, editing, testing, and publishing for multi-channel communication | Draft | NithinKrishna Sirigiri |  | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
7016 | IIRM-9867 | Story | NFR-OTH-013: The application must uRL Redirection Controls | Done | NithinKrishna Sirigiri |  | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
7017 | IIRM-9868 | Story | NFR-OTH-014: The application must there are three new categories, four categories with naming and scoping changes, and some consolidation in the Top 10 for 2021. | Draft | NithinKrishna Sirigiri |  | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
7018 | IIRM-9869 | Sub-task | QA: Testing and bug reporting | Done | Leela Pakalapati |  | IIRM-9444 — Migrate from Azure OpenAI gpt-4o-mini to a supported model by 9 Mar 2026 (retired on 31 Mar 2026)
7019 | IIRM-9870 | Sub-task | QA: Testing and Bug reporting | Done | Leela Pakalapati |  | IIRM-9775 — Policy Config - Proration flag
7020 | IIRM-9871 | Sub-task | QA: Testing and Bug reporting | Done | Leela Pakalapati |  | IIRM-9776 — Display From, To, and CC Email Fields with Add Option in Send to Insurer/Client Screen
7021 | IIRM-9872 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
7022 | IIRM-9873 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9772 — Send to Insurer - Show Preview of the file before sending - Utility or Default Template based on config
7023 | IIRM-9874 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9773 — Send to Client - Show Preview of the file before sending - Utility or Default Template based on config
7024 | IIRM-9875 | Story | NFR-SEC-003: RBAC – Role Based Access Control | Duplicate | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7025 | IIRM-9876 | Story | NFR-SEC-004: The application must application Security | Done | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7026 | IIRM-9877 | Story | NFR-SEC-007: PINs must be made as one of the sole method of authentications to access Information Systems | Open | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7027 | IIRM-9878 | Story | NFR-SEC-011: User-specific entitlement information must not be built into the business logic of the application code | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7028 | IIRM-9879 | Story | NFR-SEC-012: The application must generate its own keys for cryptographic functions. | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7029 | IIRM-9880 | Story | NFR-SEC-013: The application must password Based Encryption (PBE) | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7030 | IIRM-9881 | Story | NFR-SEC-014: Signing Key Pair Generation | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7031 | IIRM-9882 | Story | NFR-SEC-019: Key Backup and Archiving | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7032 | IIRM-9883 | Story | NFR-SEC-021: The application must ensure that the application contains online forms which are available pre-authentication | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7033 | IIRM-9884 | Story | NFR-SEC-022: The application must prevent storing of confidential and above data that persistently stored on a system in the DMZ. Persistently stored means storage beyond the session lifetime. | Duplicate | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7034 | IIRM-9885 | Story | NFR-SEC-027: Session Identifier Manipulation: Application must prevent users from manipulating session identifiers that are being passed in query strings or form fields. | Done | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7035 | IIRM-9886 | Story | NFR-SEC-028: Session (authentication) cookies must be encrypted in transit to prevent session cookies from being stolen | Open | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7036 | IIRM-9887 | Story | NFR-SEC-029: Secure Cookies: Application uses cookies containing Confidential or higher information | Open | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7037 | IIRM-9888 | Story | NFR-SEC-030: Input Validation: Application must perform server side validation of the user supplied input | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7038 | IIRM-9889 | Story | NFR-SEC-035: The application must sensitive Data Protection: Does the application encrypt sensitive data such as PII , authentication data and business sensitive information during transit | Duplicate | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7039 | IIRM-9890 | Story | NFR-SEC-037: The application must ensure that the application contains online forms which are available pre-authentication | Duplicate | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7040 | IIRM-9891 | Story | NFR-SEC-036: The application must sensitive Data Protection at Rest. Does the application encrypt sensitive data such as PII, authentication data and business sensitive information during storage? | Duplicate | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7041 | IIRM-9892 | Story | NFR-SEC-038: The application must the login page must implement approved cryptographic algorithms and key lengths to protect authentication credentials in transit | Done | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7042 | IIRM-9893 | Story | NFR-SEC-039: Session Identifier Generation | Duplicate | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7043 | IIRM-9894 | Story | NFR-SEC-040: Session Identifier Manipulation: The application must prevent users from manipulating session identifiers that are being passed in query strings or form fields? | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7044 | IIRM-9895 | Story | NFR-SEC-041: The application must secure Cookies: If the application uses cookies containing Confidential or higher information | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7045 | IIRM-9896 | Bug | Preview document is overridden with last endorsement data | Done - Not Reproducible | sunilkumar.chitikina
7046 | IIRM-9897 | Story | NFR-SEC-042: Sensitive Data Protection: The application must encrypt sensitive data such as PII, authentication data and business sensitive information during transit | Duplicate | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7047 | IIRM-9898 | Story | NFR-SEC-043: Sensitive Data Logging Prevention: The application must exclude the logging of sensitive information such as PINs and passwords especially in transaction and interface logs | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7048 | IIRM-9899 | Story | NFR-SEC-045: The application must secure Cookies: The application must set both the Secure and HTTP Only flags for cookies which contain the session ID | Open | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7049 | IIRM-9900 | Story | NFR-SEC-046: SMS as Receiver of OTP/OAC: If SMS is used as a receiver of One-Time Password (OTP)/Online Authorization Codes (OAC) tokens | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7050 | IIRM-9901 | Story | NFR-SEC-048: Session ID Rotation: For session management solutions that are POST based due to browser limitations | Open | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7051 | IIRM-9902 | Bug | Bug fixes for Inception/Endorsement in UAT | Done | sunilkumar.chitikina
7052 | IIRM-9903 | Story | NFR-SEC-050: Token based Authentication Mechanism If the application makes use of SAML, Oauth, or JWT token for on-going Authentication | Duplicate | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7053 | IIRM-9904 | Story | NFR-SEC-051: Push Notification Controls | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7054 | IIRM-9905 | Story | NFR-SEC-055: Information Classification | Open | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7055 | IIRM-9906 | Story | NFR-SEC-056: System Security Testing | Draft | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7056 | IIRM-9907 | Story | NFR-SEC-058: Roles and responsibilities for each phase of the key management life cycle must be clearly defined | Done | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7057 | IIRM-9908 | Story | NFR-SEC-065: The platform must enforce secure session management including timeout and persistent session settings | Done | NithinKrishna Sirigiri |  | IIRM-9781 — SOW#22 - Data Security (5. NFR - Security)
7058 | IIRM-9909 | Story | NFR-USA-003: The application must ensure that the application contains online forms which are available pre-authentication | Duplicate | NithinKrishna Sirigiri |  | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
7059 | IIRM-9910 | Story | NFR-USA-004: The application must ensure that the application contains online forms which are available pre-authentication | Duplicate | NithinKrishna Sirigiri |  | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
7060 | IIRM-9911 | Story | NFR-USA-006: The system should have the logout functionality in case of no action from user for 15 minutes. | Done | NithinKrishna Sirigiri |  | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
7061 | IIRM-9912 | Story | NFR-USA-018: The session management should be configurable from UI | Draft | NithinKrishna Sirigiri |  | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
7062 | IIRM-9913 | Story | NFR-OTH-007: Perimeter Security: For applications deployed in the DMZ, the application must prevent the unauthenticated users from the Internet from accessing a server on our intranet | Done | NithinKrishna Sirigiri |  | IIRM-9783 — SOW#22 - Data Security (7. NFR - Others)
7063 | IIRM-9914 | Story | NFR-USA-023: The application should support implicit saving of data | Done | NithinKrishna Sirigiri |  | IIRM-9782 — SOW #22 - Data Security (6. NFR - Usability)
7064 | IIRM-9915 | Story | Document Management for Privileged role | WORK IN PROGRESS | Rama K
7065 | IIRM-9916 | Story | Biz Done - Report filter - Enhancements | Pushed to UAT | NithinKrishna Sirigiri |  | IIRM-778 — SOW#51 - Admin Reports
7066 | IIRM-9917 | Bug | IIRM: Installments: Wrong field mapping in CD Management screen | Done | Leela Pakalapati | iWork | IIRM-781 — SOW#54 - CD Management
7067 | IIRM-9918 | Sub-task | BE - Create an API to merge CD Accounts with swagger spec | Done | sunilkumar.chitikina |  | IIRM-9473 — Merging multiple CD accounts
7068 | IIRM-9919 | Sub-task | FE - Implement Merge CD Accounts integration as per design | Done | sunilkumar.chitikina |  | IIRM-9473 — Merging multiple CD accounts
7069 | IIRM-9920 | Bug | IIRM: Notifications and Approval Tasks Functionality Not Working in Template Management | Done | SaikumarMahanthi
7070 | IIRM-9921 | Sub-task | Proration with Claim Status combination issue (Ex. 697726 - 4350/4359) | Done | NithinKrishna Sirigiri |  | IIRM-9775 — Policy Config - Proration flag
7071 | IIRM-9922 | Bug | IIRM: Transaction History Time Format and Time Value Mismatch in Exported Excel from CD Management | Open | Prathiphala Kandula | IBP
7072 | IIRM-9923 | Bug | IIRM: CROSSSLOT Error Occurs When Logging In After Session Logout | Ready for QA | SaikumarMahanthi
7073 | IIRM-9924 | Bug | IIRM: Error Message Alignment Issue After Forced Logout Due to Permission Changes | Ready for QA | SaikumarMahanthi | iWork
7074 | IIRM-9925 | Story | Duplicate ROs were created in the application | Draft | Rama K
7075 | IIRM-9926 | Sub-task | NFR-SEC-047: PINS for Backend Authentication - Password should be accepted with NOT PII info in or as part of it. Maintain password policy to prevent this | Done | VedaVyas |  | IIRM-4506 — NFR-SEC-047: PINS for Backend Authentication - Password should be accepted with NOT PII info in or as part of it. Maintain password policy to prevent this
7076 | IIRM-9927 | Bug | IIRM: Unable to Create Email Template – “Validation Request Failed” Error | Open | SaikumarMahanthi | iWork | IIRM-9780 — SOW#22 - Data Security (4. NFR - Maintainability)
7077 | IIRM-9928 | Bug | IIRM: Active User Session Not Logged Out After Role/Permission Changes | Ready for QA | SaikumarMahanthi | iWork
7078 | IIRM-9929 | Sub-task | QA: Testing and Bug fixes verification | Done | SaikumarMahanthi |  | IIRM-4514 — NFR-SEC-064: iWork Application should not allow right click, copy(ctrl+c) and contents capturing, print screen functionality across all the forms in application.
7079 | IIRM-9930 | Sub-task | QA: Testing & Bugfixes verifications | PENDING PEER or LEAD REVIEW | SaikumarMahanthi |  | IIRM-9838 — NFR-SEC-049: The application must ensure that Any application that changes the state at the backend should have a one-time session/state ID associated with it
7080 | IIRM-9931 | Sub-task | QA: End to End Testing | WORK IN PROGRESS | SaikumarMahanthi |  | IIRM-9674 — NFR-COM-024 - Audit trail should be available for every change. If there are any status changes in the application, the audit trail should capture date, time stamp, user ID along with effective date when the changed action takes into effect.
7081 | IIRM-9932 | Bug | IIRM: Covers: Covers are duplicated in the Covers list | Done | Leela Pakalapati | IBP | AIML-740 — AI agents
7082 | IIRM-9933 | Sub-task | QA: Testing and Bug Reporting | Done | Leela Pakalapati |  | IIRM-6729 — Inception/Endorsement - File Processing Error Remarks - Update the messages
7083 | IIRM-9934 | Sub-task | QA: Testing And Bug Reporting | Done | Leela Pakalapati |  | IIRM-9471 — CD Statement - Export to Excel (CD Statement - Export to Excel ( Remove Export Visibility to all users except "System Admin")
7084 | IIRM-9935 | Sub-task | QA: Testing and Bug Reporting of Proration with claim status buils | Done | Leela Pakalapati |  | IIRM-9775 — Policy Config - Proration flag
7085 | IIRM-9936 | Sub-task | QA: Testing and Bug reporting | Done | Leela Pakalapati |  | IIRM-4975 — Instalment Reminders (Email): For Policy owners for each instalment
7086 | IIRM-9937 | Sub-task | QA: Testing and Bug reporting for policy installment tab | Done | Leela Pakalapati |  | IIRM-9506 — Instalments for a Policy Premium including Inception/Endorsement/Others
7087 | IIRM-9938 | Sub-task | QA: Re-Verification of bugs | Done | Leela Pakalapati |  | IIRM-9776 — Display From, To, and CC Email Fields with Add Option in Send to Insurer/Client Screen
7088 | IIRM-9939 | Bug | IIRM: Covers: Covers order and segregation not as per the provided sheet | Done | Leela Pakalapati | IBP | AIML-740 — AI agents
7089 | IIRM-9940 | Bug | IIRM: Merge CD Accounts – Incorrect CD Account Balance Displayed in “Select CD Accounts” Table | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
7090 | IIRM-9941 | Bug | IIRM: Merge CD Accounts – Source and Destination Accounts Show 0 Policies Even When Policies/SOs Are Linked | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
7091 | IIRM-9942 | Story | Implementation of Enrolment Start and End date | Draft | Jadhav Sai Prasad |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7092 | IIRM-9943 | Sub-task | QA: Testing and Logging bugs | Done | Prathiphala Kandula |  | IIRM-9473 — Merging multiple CD accounts
7093 | IIRM-9944 | Story | Enrolment Submission with Default choices | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7094 | IIRM-9945 | Bug | IIRM: CD Management: Filters are not working as expected | Done | Leela Pakalapati | IBP | IIRM-781 — SOW#54 - CD Management
7095 | IIRM-9946 | Story | TPA Integration - Claims SFTP - Read, Store & View Details | Draft | NithinKrishna Sirigiri |  | IIRM-783 — SOW#56 - Insurer / TPA integration
7096 | IIRM-9947 | Story | TPA Integration - Claims API - Read, Store & View Details | Draft | NithinKrishna Sirigiri |  | IIRM-783 — SOW#56 - Insurer / TPA integration
7097 | IIRM-9948 | Story | TPA Integration - Ecards API - Read & View Details | Draft | NithinKrishna Sirigiri |  | IIRM-783 — SOW#56 - Insurer / TPA integration
7098 | IIRM-9949 | Bug | IIRM: Merge CD Accounts – Transaction Number Missing in Transaction History for Merged CD Accounts | Done | Prathiphala Kandula | IBP | IIRM-781 — SOW#54 - CD Management
7099 | IIRM-9950 | Sub-task | QA: Re-Verifying the bugs | Done | Prathiphala Kandula |  | IIRM-9473 — Merging multiple CD accounts
7100 | IIRM-9951 | Bug | IIRM: CD Management: Transaction date is not updating correctly | Done | Leela Pakalapati | IBP | IIRM-781 — SOW#54 - CD Management
7101 | IIRM-9952 | Sub-task | Task-1: In Filter need to have an option of selecting multiple months in Month dropdown | Pushed to UAT | NithinKrishna Sirigiri |  | IIRM-9916 — Biz Done - Report filter - Enhancements
7102 | IIRM-9953 | Sub-task | Task-2: A new filter to select the income types – Policy, endorsements, rewards etc. | UAT Client Certified | NithinKrishna Sirigiri |  | IIRM-9916 — Biz Done - Report filter - Enhancements
7103 | IIRM-9954 | Bug | IRM: BizDone Report – UI Alignment Issue in Filter Section | Done | SaikumarMahanthi | iWork
7104 | IIRM-9955 | Story | Covers Master Management | QA Verified | NithinKrishna Sirigiri |  | IIRM-745 — SOW#18 - Master Data
7105 | IIRM-9956 | Bug | IIRM: BizDone Report – Applied Filters Not Reflected in Downloaded Report | Done | SaikumarMahanthi | iWork
7106 | IIRM-9957 | Sub-task | Whitelisting the vulnerabilities | Draft | Harshavardhan Reddy |  | IIRM-4511 — NFR-SEC-060: The application must insecure Design is a new category currently, with a focus on risks related to design flaws
7107 | IIRM-9958 | Sub-task | QA: Testing and Bug Reporting | Done | Leela Pakalapati |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7108 | IIRM-9959 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7109 | IIRM-9960 | Bug | IIRM: Employee Hierarchy Pattern Does Not Match Require Doc | Open | SaikumarMahanthi | iWork
7110 | IIRM-9961 | Sub-task | Add the cover sections in the activities level | Done | Karan Agarwal |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7111 | IIRM-9962 | Sub-task | Make UI changes as per the section bifurcation | Done | Karan Agarwal |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7112 | IIRM-9963 | Sub-task | Modify the covers in Placement slip PDF | Done | Karan Agarwal |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7113 | IIRM-9964 | Sub-task | Modify the covers section in the QCR Genration activity(Excel and table) | Done | Karan Agarwal |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7114 | IIRM-9965 | Sub-task | Modify the covers section in the Broking Slip Excel | Done | Karan Agarwal |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7115 | IIRM-9966 | Sub-task | Modify the API for the Covers section in the Policy Details | Done | Karan Agarwal |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7116 | IIRM-9967 | Sub-task | Modify the UI for the Covers section in the Policy Details | Done | Karan Agarwal |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7117 | IIRM-9968 | Sub-task | Add confirmation popup for confirmation | Done | Mallela Pushyami |  | IIRM-9470 — Adding a policy to an existing CD account
7118 | IIRM-9969 | Sub-task | Design creation for screen | Done | Mallela Pushyami |  | IIRM-9776 — Display From, To, and CC Email Fields with Add Option in Send to Insurer/Client Screen
7119 | IIRM-9970 | Sub-task | Implementation of screen | Done | Mallela Pushyami |  | IIRM-9776 — Display From, To, and CC Email Fields with Add Option in Send to Insurer/Client Screen
7120 | IIRM-9971 | Sub-task | Show Section Heading for Covers (Ref. to Package Policy) - Opty. Flow - Activity | Done | NithinKrishna Sirigiri |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7121 | IIRM-9972 | Sub-task | Show Section Heading for Covers (Ref. to Package Policy) - Policy Flow | Done | NithinKrishna Sirigiri |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7122 | IIRM-9973 | Bug | IIRM: BizDone Report Download Fails with Invalid Date Format Error When Using Select All Filter | Done | SaikumarMahanthi | iWork
7123 | IIRM-9974 | Bug | IIRM: Saved Filters Not Retained in BizDone Report | Done | SaikumarMahanthi | iWork
7124 | IIRM-9975 | Sub-task | Show Section Heading for Covers (Ref. to Package Policy) - Opty. Flow - QCR, Broking Slip, & Placement Slip | Done | NithinKrishna Sirigiri |  | IIRM-9045 — Show Section Heading for Covers (Ref. to Package Policy)
7125 | IIRM-9976 | Story | Biz Done - SBU column must be shown in table by default | Done | NithinKrishna Sirigiri |  | IIRM-778 — SOW#51 - Admin Reports
7126 | IIRM-9977 | Story | Opportunity corrections - Meeting date is not allowing to capture before Policy start date (Remove validations for date) | Done | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
7127 | IIRM-9978 | Story | Inception/Endorsement: Capture Brokerage amounts | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7128 | IIRM-9979 | Bug | IIRM: Quick Contact Creation Fails with “Query Contact Creation Failed” Error | Open | SaikumarMahanthi | iWork
7129 | IIRM-9980 | Bug | IIRM: Policy List Not Fetched While Creating SO for Holdings User | Open | SaikumarMahanthi | iWork
7130 | IIRM-9981 | Sub-task | QA: Testing and Bug Reporting | Done | Leela Pakalapati |  | IIRM-9463 — On the My Company page, the Portfolio section should include a hyperlink for the Policy Number column
7131 | IIRM-9982 | Bug | IIRM: Manage Policy: Partial Policy ID search is not functioning correctly | Done | Leela Pakalapati | IBP | IIRM-781 — SOW#54 - CD Management
7132 | IIRM-9983 | Bug | IIRM: Meetings: Edit option available for past meetings and status auto-updates to Completed on edit | Done | Leela Pakalapati | IBP | AIML-740 — AI agents
7133 | IIRM-9984 | Story | IBP: New Design ¦ Pre Login screen Implementation | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7134 | IIRM-9985 | Story | IBP: New Design ¦ Login Functionality | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7135 | IIRM-9986 | Story | IBP: New Design ¦ Enrolment flow | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7136 | IIRM-9987 | Story | IBP: New Design ¦ Client Feedbacks | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7137 | IIRM-9988 | Story | IBP: New Design ¦ Claims Corner | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7138 | IIRM-9989 | Sub-task | Dashboard: Shift the policy period date on top | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7139 | IIRM-9990 | Story | IBP: New Design ¦ Hospital Network | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7140 | IIRM-9991 | Sub-task | Dashboard: Life Event - card to be shown in the quick cards. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7141 | IIRM-9992 | Story | IBP: New Design ¦ Documents and Policy Features | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7142 | IIRM-9993 | Sub-task | Dashboard:“Add Dependent” and “Select Top-up” icons on the progress bar should activate only after the user navigates to the enrolment screen and saves enrolment. Even if no dependents are selected, saving enrolment should still trigger both icons. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7143 | IIRM-9994 | Sub-task | Dashboard: Policy Card on the dashboard, should show "Sum Insured" along with the "Members covered" | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7144 | IIRM-9995 | Sub-task | Dashboard: Ask Eco icon creating disturbance , need to adjust to bottom | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7145 | IIRM-9996 | Sub-task | Login flow: Copy Past is required for credentials ( remove dropdowns) | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7146 | IIRM-9997 | Sub-task | Login flow: Upon hower on policy details cards on, Animation is missing | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7147 | IIRM-9998 | Sub-task | Login flow: Policy sequencing - GMC to come first in the policy listing | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7148 | IIRM-9999 | Sub-task | Login flow : Show warning for logout for session expiry | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7149 | IIRM-10000 | Sub-task | Login flow: Warnig should show only when user is not interacting with the application until the experiry period | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7150 | IIRM-10001 | Sub-task | Enrolment: The calculator should be displayed immediately when the user lands on the enrolment screen, regardless of whether any options have been selected or not. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7151 | IIRM-10002 | Sub-task | Support screen: Tick Raise - rename to “Raise Ticket” | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7152 | IIRM-10003 | Sub-task | Support screen: "Contact Matrix Sequence --Escalation Matrix ( Primary / Secondary - IIRM contacts) --HR Contact ( Single contact) --DPO (Single contact) --Grivance (Single contact)" | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7153 | IIRM-10004 | Sub-task | Support screen: "Raise Ticket" - form submission should be there | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7154 | IIRM-10005 | Sub-task | Hospital network: Map View showing latitude longitude instead of address and map view not functional | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7155 | IIRM-10006 | Sub-task | Hospital network: "Claim Intimation Form 1. date of admission - hopistal name and location these 3 are not * fot other than GMC policies 2. multiple same names should not get" | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7156 | IIRM-10007 | Sub-task | Hospital network: Add "Date of Addmission" In Claim Form | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7157 | IIRM-10008 | Story | IBP: New Design ¦ Support & Raise Ticket | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7158 | IIRM-10009 | Sub-task | Other items: Footer should be consistent on prelogin screen and all other screens | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7159 | IIRM-10010 | Sub-task | Other items: If Ecard not available cases - show empty state | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7160 | IIRM-10011 | Sub-task | Other items: Multi browser - Need to test in multiple browsers types and resolve resolution issues ( Duplicate) | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7161 | IIRM-10012 | Sub-task | Enrolment flow: Components selection CTA name rename to "Select" and after selection should be changed to selected | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7162 | IIRM-10013 | Story | IBP: New Design ¦ Quick Links | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7163 | IIRM-10014 | Sub-task | Enrolment flow: Allow multiple disclaimer selections with optional handling. If configured as required (e.g., pre-submission confirmation), they must be mandatory. Disclaimers added via CMS (policy/portal config) should remain optional, with clear notes | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7164 | IIRM-10015 | Sub-task | User profile: User Profile - Secondary contact heading - Rename to "Alternate Numbers" | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7165 | IIRM-10016 | Sub-task | User profile: User Profile - Dependents details to be shown in the profile screen between Personal details and contact details | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7166 | IIRM-10017 | Story | IBP: New Design ¦ User Profile | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7167 | IIRM-10018 | Sub-task | Notification: No multiple mails should trigger , mail should be triggred per configuration not per policy | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7168 | IIRM-10019 | Sub-task | Dashboard: Dashboard and enrolment screens - Components to show as per compulsary and optional, need micro animation and transition effects on this screen also ( Pre and post enrolment scenarios) | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7169 | IIRM-10020 | Sub-task | Landing screen: Support (or) Need Help? Contact Support (or) Contact Support CTA's - Show Contact Support details. What to show discuss with Client and get confirmation. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7170 | IIRM-10021 | Sub-task | Footer :Currently it's NOT upto the mark. Try different Fonts and back-ground colour and apply the best | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7171 | IIRM-10022 | Sub-task | Login flow: Login options - Based on Portal configuration show only that option. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7172 | IIRM-10023 | Sub-task | Login flow: Test Scenario: Portal configure should allow multiple login options and validate by login with any option | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7173 | IIRM-10024 | Sub-task | Login flow: In Login screen for first-time users, currently displays “Forgot Password” option, which is NOT right. Change the wording to “Forgot Password / Reset Password” (or) the flow to first enter username then show "Reset password". | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7174 | IIRM-10025 | Sub-task | Dashboard: Hero Banner - Days Counter - Font is not looking good compared to other screens. Try different fonts and apply it. Refer to Contact Matrix names or Policy cards. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7175 | IIRM-10026 | Sub-task | Dashboard: Policy card - Both “Sum Insured” and “Members Covered” text should have different color. Highlight the key information. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7176 | IIRM-10027 | Sub-task | Dashboard: Have a transition from Compulsory to Optional benefits. Need better user experience. Either different colour in the background or something. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7177 | IIRM-10028 | Sub-task | Dashbaord: "Policy cards - Members covered - Show numbers for valid dependents. Example for Self & Spouse counts is not needed. For Parents & Children based on Policy configuration show them nicely. Like Parents or Parent-in-laws or 2 Children." | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7178 | IIRM-10029 | Story | IBP: New Design ¦ Portal Configuration | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7179 | IIRM-10030 | Sub-task | Dashboard: View Policy Details - On the blue banner - Simple UX scroll the page to the Policy Card because policy details already exists for each policy. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7180 | IIRM-10031 | Sub-task | Enrolment: Emrolment - Compulsay & Optional Category bifurcation - Similar to Dashboard | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7181 | IIRM-10032 | Sub-task | Enrolment flow: Multiple Sum Insured - By default, show sutle colour for all the options. Once user selected then highlight with different colour and also check-box icon. Sheild icon is NOT looking good. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7182 | IIRM-10033 | Sub-task | Enrolment flow: Multiple Sum Insured - Add micro animations on mouse hover for each option. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7183 | IIRM-10034 | Sub-task | Quick card: Quick card Section was displayed in the wrong place and looked aesthetically unpleasant | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7184 | IIRM-10035 | Sub-task | Quick card: Before enrolment dont show - Life events, enrolment status before enrolment confirmation | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7185 | IIRM-10036 | Sub-task | Others: Policy Feature to show the policy feature document uploaded in the portal configuration | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7186 | IIRM-10037 | Sub-task | Enrolment flow: The system should automatically populate the spouse’s gender based on the employee’s gender. However, a dropdown should be available to allow selection of other options, such as “Prefer not to disclose,” | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7187 | IIRM-10038 | Sub-task | Enrolment flow: Gender selection should have one more option to not disclose gender in the configuration. though this feature needs broder discussion does not need to be implemented immediately. and need requirement gathering | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7188 | IIRM-10039 | Sub-task | Enrolment flow: When adding dependents for another component, the dropdown should list previously added dependents eligible for that component. Selecting one auto-fills details. The dropdown should also provide an option to add a new dependent. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7189 | IIRM-10040 | Sub-task | Enrolment flow: Disclaimers that are mandatory to accept should be clearly marked with a “Mandatory” tag. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7190 | IIRM-10041 | Sub-task | Enrolment flow: On the Confirmation Screen, "Verify Your Identity" to be renamed as "Enrolment Confirmation Verification" | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7191 | IIRM-10042 | Sub-task | Enrolment flow: After Confirmation screen, Show "Congratulations" Instead of the Thank You | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7192 | IIRM-10043 | Sub-task | Enrolment flow: Self and dependent not aligned in same column (Remove left padding for dependents) | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7193 | IIRM-10044 | Sub-task | User profile: Show dependents list after personal info | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7194 | IIRM-10045 | Sub-task | Claims corner: Claims corner to show claims of only those policies which claim is raised ( example - if user has GMC, GTL and GPA policies, and user intimates the claim for GMC policy, show only GMC table in the claims corner | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7195 | IIRM-10046 | Sub-task | Claims : No differentiation when there are two same policies in claim intimation | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7196 | IIRM-10047 | Sub-task | others: Configurable pages currently appear too plain (“like a notepad”). Improve formatting, colors, and overall design. Enable support for table views, especially for FAQs and policy details, to enhance structure and visual clarity. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7197 | IIRM-10048 | Sub-task | Others: Define a list of supported browsers to ensure portal compatibility. Divami will share the list with resolutions by tomorrow for testing across stable versions. The IIRM team will review, approve, and may suggest additional browsers if needed. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7198 | IIRM-10049 | Sub-task | LIfe events: Reson for life event is mandatory | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7199 | IIRM-10050 | Sub-task | Life events: "Life Event -should design a new flow, need to reference of MB360 As of now provide functionality to natural addition and deletion" | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7200 | IIRM-10051 | Sub-task | Dashboard: No transition effect between components; users are unable to identify whether a component belongs to compulsory or optional benefits, and when navigating across components, the heading is missing, | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7201 | IIRM-10052 | Sub-task | Dashbaord: Enrolment screen should display compulsory and optional benefits as separate grouped trays | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7202 | IIRM-10053 | Sub-task | Dashbaord: Compulsory and optional sections should have clear visual distinction using colors and properly indicative headings | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7203 | IIRM-10054 | Sub-task | Dashboard: In the post enrolment scenario, show components cards ( currently we are showing policy cards) | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7204 | IIRM-10055 | Sub-task | Dashboard: When moving to the next component, there is no indication of previously selected components; add a “Selected” tag when the accordion is closed | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7205 | IIRM-10056 | Sub-task | Dashbaord: Hero banner should after enrolment scenario is not consistent with before enrolment in the length | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7206 | IIRM-10057 | Sub-task | Dashboard: Dashboard personal detail icons should be slightly larger for better visibility | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7207 | IIRM-10058 | Sub-task | Dashboard: After enrolment,inthe newly enrolled section, when the policy accordion is collapsed, show aggregated information such as company contribution and employee contribution along with a “View Details” indicator, and increase arrow size | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7208 | IIRM-10059 | Sub-task | Postenrolment:Dashboard: After enrolment,inthe newly enrolled section, when the policy accordion is collapsed, show aggregated information such as company contribution and employee contribution along with a “View Details” indicator | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7209 | IIRM-10060 | Sub-task | Postenrolment: Dashboard - amounts on cards cards should properly handle color states, especially when the available amount is zero | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7210 | IIRM-10061 | Sub-task | Postenrolment: Multiple sum insured values are not implemented on dashboard cards and should be supported | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7211 | IIRM-10062 | Sub-task | Enroment screen: Employee details card on enrolment screen should have a light blue background with a slightly darker shade for the lower section | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7212 | IIRM-10063 | Sub-task | Enrolment screen: Heading above the banner should be placed inside a box, and the calculator should be moved upward to align with the heading and improve layout | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7213 | IIRM-10064 | Sub-task | Enrolment screen: Total employee contribution in the calculator should be fixed (sticky) and always visible upfront | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7214 | IIRM-10065 | Sub-task | Enrolment screen: Add a scroll bar to the calculator section for better usability | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7215 | IIRM-10066 | Sub-task | Enrolment screen: Minimum age gap between mother and child should not be hardcoded to 18 and must be configurable | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7216 | IIRM-10067 | Sub-task | Policy details: Policy details page is not responsive on zoom; left-side content gets hidden and should be properly adjusted | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7217 | IIRM-10068 | Sub-task | Claim intimation: In claim intimation, remove policy number field and update fields as per shared requirements | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7218 | IIRM-10069 | Sub-task | Rasie ticket: In raise ticket module, remove policy number field | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7219 | IIRM-10070 | Story | CS manager role user should see the entities pertaining to the user's SBU | Open | NithinKrishna Sirigiri |  | IIRM-18 — SOW#1 - ACL & RBAC Control
7220 | IIRM-10071 | Sub-task | Raise ticket: Rename “Topic” to “Category” in raise ticket | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7221 | IIRM-10072 | Sub-task | Raise ticket: Name input field should not be required in raise ticket | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7222 | IIRM-10073 | Sub-task | Rasie ticket: Email ID should not be mandatory; show available email IDs by default, allow input if not available but keep optional | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7223 | IIRM-10074 | Sub-task | Rasie ticket: Implement document upload option in raise ticket | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7224 | IIRM-10075 | Sub-task | Footer: Footer hyperlinks should have enhanced color visibility for better accessibility | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7225 | IIRM-10076 | Sub-task | Claims intimation: In claim intimation, remove policy number field and update fields as per shared requirements | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7226 | IIRM-10077 | Sub-task | FE: Implement premium calculator download functionality | Done | sunilkumar.chitikina |  | IIRM-9784 — Download - Premium Calculator in Step-2
7227 | IIRM-10078 | Sub-task | BE: Implement premium calculator download functionality | Done | sunilkumar.chitikina |  | IIRM-9784 — Download - Premium Calculator in Step-2
7228 | IIRM-10079 | Story | IBP: New Design ¦ E-Cards | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7229 | IIRM-10080 | Story | IBP: New Design ¦ Mail Notifications | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7230 | IIRM-10081 | Story | IBP: New Design ¦ Life Events | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7231 | IIRM-10082 | Story | Inception/Endorsement: Instruction for file preparation (Static Text) | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7232 | IIRM-10083 | Bug | IIRM: Non GMC: Effective Date Validation Not Enforced for Non-GMC Policies in Inception Process | Open | Prathiphala Kandula | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7233 | IIRM-10084 | Bug | IIRM: Empty report downlaoded with applied filters | Open | Akhila Gattu
7234 | IIRM-10085 | Bug | IIRM: Non GMC: Missing Field Validations for Asset Upload Fields in Inception Process (Including Sub Limit Description Length) | Open | Prathiphala Kandula | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7235 | IIRM-10086 | Bug | IIRM: Non GMC: Asset Upload Allows Empty Premium and Sum Insured Values Without Validation | Open | Prathiphala Kandula | IBP
7236 | IIRM-10087 | Bug | IIRM: Non GMC: Asset Upload Allows Empty Intake Type and Effective Date Values Without Validation | Open | Prathiphala Kandula | IBP
7237 | IIRM-10088 | Bug | IIRM: Inception/Endorsement: Values are not pre-filled until page refresh | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7238 | IIRM-10089 | Bug | IIRM: Inception/Endorsement: Broking Details section is missing | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7239 | IIRM-10090 | Bug | IIRM: UI Issues in Inception/Endorsement Screen – Bullet Misalignment and Non-Sticky Right Panel | Done | Prathiphala Kandula | IBP
7240 | IIRM-10091 | Story | IBP: HR Portal - Enrolment | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7241 | IIRM-10092 | Story | IBP: HR Portal - Claims | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7242 | IIRM-10093 | Story | IBP: HR Portal - Hospital Network | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7243 | IIRM-10094 | Story | IBP: HR Portal - CD Management | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7244 | IIRM-10095 | Story | IBP: HR Portal - HR User Profile | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7245 | IIRM-10096 | Story | IBP: HR Portal - Claim - Intimate Claim on behalf of Employee | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7246 | IIRM-10097 | Story | IBP: HR Portal - Claim - Insights | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7247 | IIRM-10098 | Story | IBP: HR Portal - Enrolment - Reports | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7248 | IIRM-10099 | Story | IBP: HR Portal - Switch between Policy Year's | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7249 | IIRM-10100 | Story | IBP: HR Portal - Global Search | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7250 | IIRM-10101 | Story | IBP: HR Portal - Endorsement Management | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7251 | IIRM-10102 | Story | IBP: HR Portal - Employee Settings | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7252 | IIRM-10103 | Story | IBP: HR Portal - Upload Inception/Endorsement File | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7253 | IIRM-10104 | QAlity Test | Login Screen UI | Draft | PATIBANDLA VELANGINI RAJU
7254 | IIRM-10105 | QAlity Test | Single Login Option - Email | Draft | PATIBANDLA VELANGINI RAJU
7255 | IIRM-10106 | QAlity Test | Single Login Option - Phone | Draft | PATIBANDLA VELANGINI RAJU
7256 | IIRM-10107 | QAlity Test | Single Login Option - Employee ID | Draft | PATIBANDLA VELANGINI RAJU
7257 | IIRM-10108 | QAlity Test | Single Login Option UI | Draft | PATIBANDLA VELANGINI RAJU
7258 | IIRM-10109 | QAlity Test | Multiple Login Options | Draft | PATIBANDLA VELANGINI RAJU
7259 | IIRM-10110 | QAlity Test | Email Validation | Draft | PATIBANDLA VELANGINI RAJU
7260 | IIRM-10111 | QAlity Test | Phone Validation | Draft | PATIBANDLA VELANGINI RAJU
7261 | IIRM-10112 | QAlity Test | First-Time User (Email) | Draft | PATIBANDLA VELANGINI RAJU
7262 | IIRM-10113 | QAlity Test | First-Time User (Phone) | Draft | PATIBANDLA VELANGINI RAJU
7263 | IIRM-10114 | QAlity Test | First-Time Email Message | Draft | PATIBANDLA VELANGINI RAJU
7264 | IIRM-10115 | QAlity Test | First-Time Phone Message | Draft | PATIBANDLA VELANGINI RAJU
7265 | IIRM-10116 | QAlity Test | Reset Link Option | Draft | PATIBANDLA VELANGINI RAJU
7266 | IIRM-10117 | QAlity Test | Reset Flow | Draft | PATIBANDLA VELANGINI RAJU
7267 | IIRM-10118 | QAlity Test | Existing User Detection | Draft | PATIBANDLA VELANGINI RAJU
7268 | IIRM-10119 | QAlity Test | Password Field Display | Draft | PATIBANDLA VELANGINI RAJU
7269 | IIRM-10120 | QAlity Test | Valid Login | Draft | PATIBANDLA VELANGINI RAJU
7270 | IIRM-10121 | QAlity Test | Invalid Login | Draft | PATIBANDLA VELANGINI RAJU
7271 | IIRM-10122 | QAlity Test | Forgot Password Visibility | Draft | PATIBANDLA VELANGINI RAJU
7272 | IIRM-10123 | QAlity Test | Forgot Password Flow | Draft | PATIBANDLA VELANGINI RAJU
7273 | IIRM-10124 | QAlity Test | First-Time User UI | Draft | PATIBANDLA VELANGINI RAJU
7274 | IIRM-10125 | QAlity Test | Combined Label Check | Draft | PATIBANDLA VELANGINI RAJU
7275 | IIRM-10126 | QAlity Test | Empty Input Validation | Draft | PATIBANDLA VELANGINI RAJU
7276 | IIRM-10127 | QAlity Test | Input Trimming | Draft | PATIBANDLA VELANGINI RAJU
7277 | IIRM-10128 | QAlity Test | Email Case Handling | Draft | PATIBANDLA VELANGINI RAJU
7278 | IIRM-10129 | QAlity Test | Post Login Flow | Draft | PATIBANDLA VELANGINI RAJU
7279 | IIRM-10130 | Bug | IIRM: Unauthorized Access Error When CS Manager Selects Policy Type After Applying SBU Filter in My RO and My SO Tabs | Done | Prathiphala Kandula | IBP
7280 | IIRM-10131 | Sub-task | QA: Testing and Logging Bugs | Done | Prathiphala Kandula |  | IIRM-10070 — CS manager role user should see the entities pertaining to the user's SBU
7281 | IIRM-10132 | Sub-task | QA: Testing and Logging bugs | Done | Prathiphala Kandula |  | IIRM-10082 — Inception/Endorsement: Instruction for file preparation (Static Text)
7282 | IIRM-10133 | Sub-task | QA: Functional Testing and bug fixes verification | Done | SaikumarMahanthi |  | IIRM-9916 — Biz Done - Report filter - Enhancements
7283 | IIRM-10134 | Story | Non-GMC Bugs | Open | Leela Pakalapati |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7284 | IIRM-10135 | Sub-task | QA: Testing and Bug Reporting | Done | Leela Pakalapati |  | IIRM-9978 — Inception/Endorsement: Capture Brokerage amounts
7285 | IIRM-10136 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9978 — Inception/Endorsement: Capture Brokerage amounts
7286 | IIRM-10137 | Sub-task | QA: Testing and Logging bugs | Done | Prathiphala Kandula |  | IIRM-9418 — CR: Calculate premium based on age of dependent if policy is per life
7287 | IIRM-10138 | Sub-task | QA: Testing and Bug Reporting | Done | Leela Pakalapati |  | IIRM-9472 — Manage Policy: Policy Id should be displayed in table & in table setting. Also should be in Smart Search
7288 | IIRM-10139 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9472 — Manage Policy: Policy Id should be displayed in table & in table setting. Also should be in Smart Search
7289 | IIRM-10140 | Sub-task | QA: Testing and Bug Reporting | Done | Leela Pakalapati |  | IIRM-9977 — Opportunity corrections - Meeting date is not allowing to capture before Policy start date (Remove validations for date)
7290 | IIRM-10141 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9977 — Opportunity corrections - Meeting date is not allowing to capture before Policy start date (Remove validations for date)
7291 | IIRM-10142 | Sub-task | QA: Testing and Bug reporting | Done | Leela Pakalapati |  | IIRM-6697 — Non-GMC: Template helper not matching with Asset template
7292 | IIRM-10143 | Epic | DevOps | Draft | sravya.nanduri
7293 | IIRM-10144 | Task | Database Scripts execution and Deployments | Draft | sravya.nanduri |  | IIRM-10143 — DevOps
7294 | IIRM-10145 | Task | Static Images Configuration for IBP | Draft | sravya.nanduri |  | IIRM-10143 — DevOps
7295 | IIRM-10146 | Task | Call with IIRM Client - Saferisk app deployment | Draft | sravya.nanduri |  | IIRM-10143 — DevOps
7296 | IIRM-10147 | Task | Database Scripts and Deployments | Draft | Anyarambhatla Nitish Bharadwaj |  | IIRM-10143 — DevOps
7297 | IIRM-10148 | Sub-task | BE: Compute premium per life for each endorsement | Done | sunilkumar.chitikina |  | IIRM-9784 — Download - Premium Calculator in Step-2
7298 | IIRM-10149 | Bug | IIRM: Premium Calculation: Applicable Days for dependents are calculated incorrectly | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7299 | IIRM-10150 | Bug | IIRM: Inception (Per Family) – Optional Add-On Policies Incorrectly Appearing in Premium Calculator Download for Base and Parental Policies | Done | Prathiphala Kandula
7300 | IIRM-10151 | Bug | IIRM: Premium Calculation: Net Premium in summary card is incorrect when Self and dependent have different Effective From dates | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7301 | IIRM-10152 | Bug | IIRM: Duplicate Columns (SL No. and Serial Number) in Inception Document Download (Send Inception to Insurer) | Done | Prathiphala Kandula | IBP
7302 | IIRM-10153 | Bug | IIRM: Premium Calculator: Unable to add dependent for existing employee | Ready for QA | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7303 | IIRM-10154 | Bug | IIRM: Failed to Load Documents in Company Document Tab | Open | SaikumarMahanthi | iWork
7304 | IIRM-10155 | Sub-task | QA: Testing and Bug reporting | Done | Leela Pakalapati |  | IIRM-9784 — Download - Premium Calculator in Step-2
7305 | IIRM-10156 | Bug | IIRM: Premium Calculator: Incorrect premium calculation for dependent when Self and dependent belong to different age bands | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7306 | IIRM-10157 | Story | PROD Issue: Kirti - Opty. & Policies - Data Mis-Match (Refer to Neeraj email) | Pushed to Backlog | NithinKrishna Sirigiri |  | IIRM-778 — SOW#51 - Admin Reports
7307 | IIRM-10158 | Story | IBP: New Design ¦ New Login flow | Draft | Jadhav Sai Prasad |  | IIRM-773 — SOW#46 - Enrolment Portal
7308 | IIRM-10159 | Story | Toggle for Number Formatting Lakhs / Millions based on Country | Done | NithinKrishna Sirigiri |  | IIRM-764 — SOW#37 - Localisation
7309 | IIRM-10160 | Story | Dashboard: Display My tasks by default. Add radio button - Manager, Manager+Team, Organisation | Done | NithinKrishna Sirigiri |  | IIRM-738 — SOW#11 - Manage Tasks, Meetings
7310 | IIRM-10161 | Bug | IIRM: Claims TAT Functionality is not working as expected | Open | Leela Pakalapati | IBP
7311 | IIRM-10162 | Story | Dashboard: Hide - Widget - Smart Actions, My Delivery Performance widget & Others | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7312 | IIRM-10163 | Story | Dashboard: My Business Performance - Clickable for New & Renewal Business dials also - Same like Total | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7313 | IIRM-10164 | Story | Endorsement TAT: Show only these TAT buckets: <3 , <7 , <14 , >14 | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7314 | IIRM-10165 | Story | Claims TAT: Show only these TAT buckets: <3 , <7 , <14 , >14 | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7315 | IIRM-10166 | Story | Dashboard: My Business Performance - Include Mined in New & Update the sequence | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7316 | IIRM-10167 | Story | Dashboard: My Follow Up - Show All, SO, & RO's data | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7317 | IIRM-10168 | CR - Story | CR: My Company: Show data based on User Privileges | Done | NithinKrishna Sirigiri |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
7318 | IIRM-10169 | Story | Dashboard: Policy Distribution - Update design & values to show | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7319 | IIRM-10170 | Story | Dashboard: My Business Performance - Re-Design UI for Yearly / Quarterly | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7320 | IIRM-10171 | Story | Dashboard: Sales Funnel - Re-design | Draft | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7321 | IIRM-10172 | Story | Dashboard: New Chart "Brokerage Collected" - Premium vs Brokerage Invoice vs Brokerage Collected Data from Finops | Draft | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7322 | IIRM-10173 | Story | Dashboard: Brokerage to Collect - Buckets | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7323 | IIRM-10174 | Story | Utility - Add New columns in the Send to Client (Refer to different Client template) | Done | NithinKrishna Sirigiri |  | IIRM-735 — SOW#8 - 11 Components / Modules
7324 | IIRM-10175 | Story | Premium based on new dependent additions (Refer to DNV Policy - 649733) | Draft | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
7325 | IIRM-10176 | Bug | IIRM: Premium Calculator: Effective To Date is missing in downloaded document | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7326 | IIRM-10177 | Bug | IIRM: Premium Calculator: Parental policy premium is incorrectly derived from base policy | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7327 | IIRM-10178 | Story | PROD Request: Update "Income Month" based on "Date of Income" (Madhav's Request) | Done | NithinKrishna Sirigiri |  | IIRM-778 — SOW#51 - Admin Reports
7328 | IIRM-10179 | Story | Dashboard: My Business Performance - Quarterly View | Test on Staging | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7329 | IIRM-10180 | Bug | While creating or resetting a password, even if the required conditions (such as including at least one uppercase letter) are not satisfied, the system is still allowing the user to create/set the password. | Open | Akhila Gattu
7330 | IIRM-10181 | Bug | In the parental policy, other family members are being displayed even though they are not configured. Ideally, only parents should be shown. It seems this behavior is being carried forward from the normal base policy, which is causing the issue. | Open | Akhila Gattu
7331 | IIRM-10182 | Bug | As mentioned earlier, there should be a clear distinction or visual highlighting to indicate that the policy has changed from Group Mediclaim (Base) to Group Mediclaim (Parental). | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7332 | IIRM-10183 | Bug | if configuration per life then in permium calcuation it was not showing as expected ple check once for per life | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7333 | IIRM-10184 | Bug | At times, when we click on the parental policy, it is by default showing all family members that were added under the base policy. However, occasionally it shows a blank screen, and the “Add Dependents” option gets frozen. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7334 | IIRM-10185 | Bug | Please check the login functionality to ensure it is working properly. Currently, users are unable to log in when uppercase letters are used | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7335 | IIRM-10186 | Bug | Still the intimation claim can be done before enrolment of members | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7336 | IIRM-10187 | Bug | The character validation is not working correctly. Users are able to enter alphabets in numeric fields and numeric values in fields meant for characters in intimation of claim | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7337 | IIRM-10188 | Bug | In the “Select Member to Include” section, the dropdown is not displaying all the relationships as per the configuration | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7338 | IIRM-10189 | Bug | When the user selects the Login with Email OTP option, the system asks the user to enter the email ID again, even though it was already entered in the previous login step. This causes unnecessary repetition and affects user experience. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7339 | IIRM-10190 | Bug | While raising a ticket, when a document is uploaded, there is no indication or confirmation showing whether the document has been successfully uploaded or not. This creates confusion for the user. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7340 | IIRM-10191 | Bug | Sometimes, when the OTP attempts are exhausted and the user clicks on “Change Email ID”, the system navigates to the email ID screen. However, after entering the email and clicking on “Send OTP”, the application gets frozen and does not respond | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7341 | IIRM-10192 | Bug | The behaviour of adding members and managing the default member is not working properly. In some cases, members are getting automatically set or removed as default without user action, and sometimes default members are getting deleted directly | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7342 | IIRM-10193 | Bug | While creating or resetting a password, even if the required conditions (such as including at least one uppercase letter) are not satisfied, the system is still allowing the user to create/set the password. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7343 | IIRM-10194 | Bug | In the parental policy, other family members are being displayed even though they are not configured. Ideally, only parents should be shown. It seems this behaviour is being carried forward from the normal base policy | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7344 | IIRM-10195 | Bug | As mentioned earlier, there should be a clear distinction or visual highlighting to indicate that the policy has changed from Group Mediclaim (Base) to Group Mediclaim (Parental) | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7345 | IIRM-10196 | Bug | I----------------f configuration per life then in premium calculation it was not showing as expected ple check once for per life | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7346 | IIRM-10197 | Bug | If configuration per life then in premium calculation it was not showing as expected ple check once for per life | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7347 | IIRM-10198 | Bug | At times, when we click on the parental policy, it is by default showing all family members that were added under the base policy. However, occasionally it shows a blank screen, and the “Add Dependents” option gets frozen | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7348 | IIRM-10199 | Bug | Please check the login functionality to ensure it is working properly. Currently, users are unable to log in when uppercase letters are used. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7349 | IIRM-10200 | Bug | Still the intimation claim can be done before enrolment of members | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7350 | IIRM-10201 | Bug | The character validation is not working correctly. Users can enter alphabets in numeric fields and numeric values in fields meant for characters in intimation of claim | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7351 | IIRM-10202 | Bug | IIRM: Premium Calculator: Incorrect data and premium calculation in downloaded file when dependent is deleted | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7352 | IIRM-10203 | Bug | IIRM: Premium Calculator: Premium amount not handled correctly for deleted persons when proration is disabled | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7353 | IIRM-10204 | Sub-task | Email Notifications: User creation email notification should be triggered only once per user (not per policy). This should be managed by the service team, and executives should have the ability to manually send the welcome email. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7354 | IIRM-10205 | Sub-task | Email Notifications: All email communications should be configurable through Strapi CMS. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7355 | IIRM-10206 | Sub-task | Email Notifications: All email communications should be configurable through Strapi CMS. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7356 | IIRM-10207 | Sub-task | Enrolment: Premium calculator layout should be adjusted to a 70:30 ratio for better usability. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7357 | IIRM-10208 | Sub-task | Enrolment: Show the heading in the box rather than showing in by underline | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7358 | IIRM-10209 | Sub-task | Enrolment: The “Selected” CTA should be positioned on the right side of the card and highlighted in green. ( Later Changed to Orange) | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7359 | IIRM-10210 | Sub-task | Enrolment: When navigating between components, there should be a clear visual indication that the component heading has changed. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7360 | IIRM-10211 | Sub-task | Enrolment: Dependent selection across components should be implemented using checkbox selection instead of dropdowns. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7361 | IIRM-10212 | Sub-task | Enrolment: The premium calculator slider should be consistently visible across all operating systems. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7362 | IIRM-10213 | Sub-task | Enrolment: The premium calculator should occupy the full available width of the screen. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7363 | IIRM-10214 | Sub-task | Enrolment: Rename “Back to Dashboard” to “Go to Dashboard” on the enrolment confirmation screen. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7364 | IIRM-10215 | Sub-task | Policy Feature: Policy features should support a single document upload with multiple pages, displayed in a unified document view. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7365 | IIRM-10216 | Sub-task | View Policy Details: In CMS, enable document upload functionality for the “View Policy Details” section. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7366 | IIRM-10217 | Sub-task | View Policy Details: The UI should be responsive to zoom in/out, ensuring content adjusts properly without requiring horizontal scrolling. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7367 | IIRM-10218 | Sub-task | View Policy Details: Upload a brochure for the next demo under the “View Policy Details” section. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7368 | IIRM-10219 | Sub-task | View Policy Details: View Policy Details from the bottom banner, when click open the policy feature screen should navigate to policy section | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7369 | IIRM-10220 | Sub-task | My Documents: My Document screen is not looking good, lot of empty space | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7370 | IIRM-10221 | Sub-task | Claim Intimation: Claim intimation module should include document upload functionality. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7371 | IIRM-10222 | Sub-task | Claim Intimation: "Claim intimation Stepper Flow - As per the Jira story " | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7372 | IIRM-10223 | Sub-task | User Profile: The dependent list should be displayed in a separate card, positioned between Personal Details and Activity History. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7373 | IIRM-10224 | Sub-task | User Profile: User profile screen, the screen should open from top | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7374 | IIRM-10225 | Sub-task | Login: in the outlook, user is reciving the blank for the otm mail | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7375 | IIRM-10226 | Sub-task | Footer: Footer content font in enrolment screen | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7376 | IIRM-10227 | Sub-task | Login Flow: Login flow should be embedded within the same screen; avoid using popups. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7377 | IIRM-10228 | Sub-task | Login Flow: Login Method sequence should be - Email id > Phone Number > Employee Id | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7378 | IIRM-10229 | Sub-task | Login Flow: Last Login Method memory to show for next login by default | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7379 | IIRM-10230 | Sub-task | Login Flow: Continue to OTP Verification and Login with Email OTP creating confusion. Need to handle Login with OTP method appropiatly | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7380 | IIRM-10231 | Sub-task | Login Flow: System should handle first time user and user with password with out confusion | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7381 | IIRM-10232 | Sub-task | Login Flow: After I click with " Continue with OTP verification CTA on previous screen, in the next screen system ask for Send OTP again which create confusion | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7382 | IIRM-10233 | Sub-task | Login Flow: Need to enhance complete login flow | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7383 | IIRM-10234 | Sub-task | Dashboard: The blue banner (font, icons, overall styling) is not visually appealing and needs redesign. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7384 | IIRM-10235 | Sub-task | Dashboard: Personal information icons appear merged; they should be visually distinct and properly spaced. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7385 | IIRM-10236 | Sub-task | “Days Left” and “Start Your Enrolment” CTA are not appealing and need enhancement. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7386 | IIRM-10237 | Sub-task | Dashboard: Revisit sizing and color treatment of all elements within the blue banner. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7387 | IIRM-10238 | Sub-task | Dashboard: Policy listing cards require better padding and spacing. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7388 | IIRM-10239 | Sub-task | Dashboard: Policy information text lacks visual appeal; improve typography and readability. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7389 | IIRM-10240 | Sub-task | Dashboard: Background grey color feels unnecessary; explore alternative design treatments. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7390 | IIRM-10241 | Sub-task | Dashboard: “View Policy Details” should support document upload functionality. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7391 | IIRM-10242 | Sub-task | Dashboard: “View Policy Details” and “Policy Features” should open as full pages instead of overlays. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7392 | IIRM-10243 | Sub-task | Dashboard: Improve design and visibility of “Download” and “Continue Enrolment” CTAs. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7393 | IIRM-10244 | Sub-task | Dashboard: For Newly Enrolled Policies rename as "Enroled Policies" | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7394 | IIRM-10245 | Sub-task | Dashboard: Review All the taglines accrose the application and all taglines should be appropiate | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7395 | IIRM-10246 | Sub-task | Dashboard: Review All the taglines accrose the application and all taglines should be appropiate | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7396 | IIRM-10247 | Sub-task | Dashboard: Names fontos etc are better on the first time login dashboard rather than other dashboard | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7397 | IIRM-10248 | Sub-task | Dashboard: All the text, forns on the blue banners needs more experiment and enhancements | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7398 | IIRM-10249 | Sub-task | FAQ: FAQ section contains excessive empty space; optimize layout usage. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7399 | IIRM-10250 | Sub-task | FAQ: Handle variable content length (short vs long questions) effectively in UI. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7400 | IIRM-10251 | Sub-task | Enrolment: Enhance the premium calculator (layout, usability, visibility). | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7401 | IIRM-10252 | Sub-task | Enrolment: Improve section headings for better clarity and hierarchy. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7402 | IIRM-10253 | Sub-task | Enrolment: Add transition indicators when scrolling from compulsory to optional sections to clearly show progression. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7403 | IIRM-10254 | Sub-task | Enrolment: When the last compulsory component is selected and user moves to optional, clearly indicate completion of compulsory and start of optional. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7404 | IIRM-10255 | Sub-task | Enrolment: Improve grouping of “Compulsory” and “Optional” sections with better visual distinction (e.g., colors, trays). | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7405 | IIRM-10256 | Sub-task | Enrolment: Enhance visibility of selected components when the accordion is collapsed. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7406 | IIRM-10257 | Sub-task | Enrolment: Ensure compulsory vs optional segregation is clearly visible on the confirmation screen. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7407 | IIRM-10258 | Sub-task | Enrolment: Maintain consistency across Dashboard, Enrolment, and Summary screens. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7408 | IIRM-10259 | Sub-task | Enrolment: Claim intimation flow should include a stepper; for demo, include document upload and show GMC by default. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7409 | IIRM-10260 | Sub-task | Enrolment: Implement static E-card | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7410 | IIRM-10261 | Sub-task | Enrolment: Display dependent list in the user profile below personal details in a separate card. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7411 | IIRM-10262 | Sub-task | Enrolment: Whenever we do the edit enrolment we need to show the counters ( Edit date, time and counter (number of edits) and show in each confirmation mails | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7412 | IIRM-10263 | Sub-task | Enrolment: "On the Policy Cards in the left hand side, we should show some message that rates are with out gst ( Like GST excluded) Scenario 1 - GST is applicable and show GST can be displayed ( In the configuration Calculate GST, Display GST | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7413 | IIRM-10264 | Sub-task | Enrolment: Age Should be visible beside date of birth in the add dependent | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7414 | IIRM-10265 | Sub-task | Enrolment: Delete option required in the Add dependent and lot of white space when no dependents are available in the list | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7415 | IIRM-10266 | Sub-task | Enrolment: Check if the Dependent added in. inception, are they visible in the dependent list | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7416 | IIRM-10267 | Sub-task | Enrolment: Dashboard we are showing icons and enrolment we are showing lables, need to maintain consistancy, change to icons in the enrolment screen | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7417 | IIRM-10268 | Sub-task | Enrolment: "Add alternate phone / email, alignment was missing for client ( For us coming good, need to check Cancel and Update CTAs not required, simply show textbox, if come out of text box it should get updated " | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7418 | IIRM-10269 | Sub-task | Enrolment: "In the enrolment confirmation poppup show message Show reference number and Counter ( What is the number of time ) Reference number should gone to confirmation mail Reference number should be | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7419 | IIRM-10270 | Sub-task | Life Event: Avoid separate second screen; bring all elements into the first screen with appropriate CTAs. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7420 | IIRM-10271 | Sub-task | Life Event: Enable document upload during dependent addition; support multiple uploads (e.g., twins scenario). | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7421 | IIRM-10272 | Sub-task | Life Event: Component selection and approval flows will be defined by the client; retain current behavior for now. | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7422 | IIRM-10273 | Sub-task | Enrolment: Enrollment functionality ( Handle All Edge Cases) | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7423 | IIRM-10274 | Sub-task | Life Event: Life events | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7424 | IIRM-10275 | Sub-task | Claim Intimation: Claim intimation, Document type and document upload | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7425 | IIRM-10276 | Sub-task | My Documents: Proper My Documents - Section wise (Policies, Claim documents, Life events documents, Reminder mail copies, Confirmation mail copies). Date time stamps are very important | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7426 | IIRM-10277 | Sub-task | Others: Minimising data entry aspects, where applicable | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7427 | IIRM-10278 | Sub-task | User Profile: Dependants should be addable from profile page and selectable in enrollment. Other way around also, as currently done | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7428 | IIRM-10279 | Sub-task | Ask Eco: Change Ask Echo to TPA Login (For time being). | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7429 | IIRM-10280 | Sub-task | Email Notifications: All mail contents should be discussed with us for content modifications | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7430 | IIRM-10281 | Sub-task | Email Notifications: Template enhancements | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7431 | IIRM-10282 | Sub-task | Email Notifications: "Enrolment Start Mail and Enrolment Reminder Mails - Should show all the covered members along with the policy details **Warm regards section Say as ""Team IIRM"" instead of IIRM" | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7432 | IIRM-10283 | Sub-task | Email Notifications: "Enrolment confirmation message should show ( Should be on top somewhere) Show reference number and Counter ( What is the number of time ) Reference number should gone to confirmation mail Reference number | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7433 | IIRM-10284 | Sub-task | Email Notifications: Policy details, member details can be shown in the table formats. for 7th not required, but design and experiment for future | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7434 | IIRM-10285 | Sub-task | View Policy Details: Screen looks fully, can be given border to look it appeling ( The view not looking as our application and not looking appeling) Client need a better mechanism here | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7435 | IIRM-10286 | Sub-task | Popups: Popes are coming on the blank page, should come on the exesting pages | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7436 | IIRM-10287 | Sub-task | Quick Cards : Quick Cards should be visible all the time all the screens including policy feature and policy document screen, dont show quick links in the header | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7437 | IIRM-10288 | Sub-task | Claims Corner: Screen view to be enhanced | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7438 | IIRM-10289 | Sub-task | Others: Other page minor modifications should be discussed with us | Draft | Akhila Gattu |  | IIRM-9987 — IBP: New Design ¦ Client Feedbacks
7439 | IIRM-10290 | Story | New Tab: Financial Info - Commission, Invoice, Collected & Other details | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7440 | IIRM-10291 | Story | PROD Bug: Data Discrepancy - Inception/Endorsement vs Send to Client/Insurer (Preview & Excel) | QA Verified | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7441 | IIRM-10292 | Bug | IIRM: Incorrect Validation Message While Activating Already Approved Configured Policy | Done - Not a Bug | Prathiphala Kandula | IBP
7442 | IIRM-10293 | Story | Dashboard: Add new filter "Insuer" and apply across all widgets | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7443 | IIRM-10294 | Story | Smart Search: Financial Year must be dynamic based on the Current date and should be selected | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7444 | IIRM-10295 | Story | Dashboard: Replace "My Business Performance" widget with new Chart | Draft | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7445 | IIRM-10296 | Story | Dashboard: Floating Search | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7446 | IIRM-10297 | Bug | Prod: Dashboard: Policy Distribution issues | Open | Leela Pakalapati | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7447 | IIRM-10298 | Bug | IIRM: Net Premium Incorrectly Calculated After Deletion When Pro-Ration is Not Selected | Done | Prathiphala Kandula | IBP
7448 | IIRM-10299 | Bug | IIRM: Applicable Days Not Displayed for Dependent in Premium Calculator File When Pro-Ration is Not Selected | Done | Prathiphala Kandula | IBP
7449 | IIRM-10300 | Task | Performed testing in the Production Environment | Done | Leela Pakalapati
7450 | IIRM-10301 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-9784 — Download - Premium Calculator in Step-2
7451 | IIRM-10302 | Sub-task | QA: Testing and Bug reporting[Age Policy Parameter] | Done | Leela Pakalapati |  | IIRM-9784 — Download - Premium Calculator in Step-2
7452 | IIRM-10303 | Sub-task | QA: Re-Verifying the bugs [Age Policy Parameter] | Done | Leela Pakalapati |  | IIRM-9784 — Download - Premium Calculator in Step-2
7453 | IIRM-10304 | Sub-task | QA: Testing and Bug reporting | Done | Leela Pakalapati |  | IIRM-10163 — Dashboard: My Business Performance - Clickable for New & Renewal Business dials also - Same like Total
7454 | IIRM-10305 | Sub-task | QA: Testing and Bug reporting | QA Verified | Leela Pakalapati |  | IIRM-10164 — Endorsement TAT: Show only these TAT buckets: <3 , <7 , <14 , >14
7455 | IIRM-10306 | Sub-task | QA: Testing and Bug Reporting | Passed in QA | Leela Pakalapati |  | IIRM-10165 — Claims TAT: Show only these TAT buckets: <3 , <7 , <14 , >14
7456 | IIRM-10307 | Sub-task | QA: Testing and Bug Reporting | Passed in QA | Leela Pakalapati |  | IIRM-10166 — Dashboard: My Business Performance - Include Mined in New & Update the sequence
7457 | IIRM-10308 | Task | QA: Bizdoen and NFR Chages Testing | Done | SaikumarMahanthi
7458 | IIRM-10309 | Bug | IIRM: Net Premium is incorrect when users are deleted for proration-disabled (per-life) policy | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7459 | IIRM-10310 | Bug | IIRM: Per Family(Pro-ration unchecked): Incorrect Net Premium Calculation and Missing Premium Data in Endorsement Flow for Multiple Families | Done | Prathiphala Kandula | IBP
7460 | IIRM-10311 | Bug | IIRM: Endorsement (Per Family, Proration Unchecked) – Premium Calculator File Not Found Error and Download Disabled | Done | Prathiphala Kandula | IBP
7461 | IIRM-10312 | Sub-task | Dashboard: Income type should have All by default selected | Done | Leela Pakalapati |  | IIRM-10163 — Dashboard: My Business Performance - Clickable for New & Renewal Business dials also - Same like Total
7462 | IIRM-10313 | Bug | IIRM: Net Premium and Effective From Date are incorrect when Self and Dependents are uploaded in different files within same enrolment | Done | Leela Pakalapati | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7463 | IIRM-10314 | Story | Policy to RO - Mis-Match | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
7464 | IIRM-10315 | Sub-task | April 2025 Data | Draft | NithinKrishna Sirigiri |  | IIRM-10314 — Policy to RO - Mis-Match
7465 | IIRM-10316 | Sub-task | RO job's must be executed for ONLY Commercial lines | Draft | NithinKrishna Sirigiri |  | IIRM-10314 — Policy to RO - Mis-Match
7466 | IIRM-10317 | Story | Decouple - SBU's from Users. Build Logic to handle it | Draft | NithinKrishna Sirigiri |  | IIRM-745 — SOW#18 - Master Data
7467 | IIRM-10318 | Story | Dashboard: Move the Claims, Endorsement, & Policy Expiry TAT buckets into Center Page and apply filter | Passed in QA | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7468 | IIRM-10319 | Bug | IIRM: Unable to map Insurer utility – Database error and mapping flow issues | Done | Leela Pakalapati | iWork
7469 | IIRM-10320 | Bug | The actual claim status is completed, but it is still being shown under pending. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7470 | IIRM-10321 | Bug | Banner is showing - "The enrolment window for 2026-27 is now closed" | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7471 | IIRM-10322 | Bug | Dashboard: Claim amount should be visible on policy cards. If Total is provided by TPA show that as well | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7472 | IIRM-10323 | Bug | Document Preview: second page appears blank but the downloaded file displays the content correctly. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7473 | IIRM-10324 | Bug | FAQ: Hosipital network link should avalible in FAQS for the where we can find hosipital list question instead text. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7474 | IIRM-10325 | Bug | Iwork: Unable to upload documents into iWork and also download documents | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7475 | IIRM-10326 | Bug | Iwork: Unable to upload documents into iWork and also download documents | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7476 | IIRM-10327 | Bug | Life events: Cross gender should come in life events | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7477 | IIRM-10328 | Bug | Life Events Management: trying to add Dependent, getting error "Invalid choice of component id 88" | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7478 | IIRM-10329 | Bug | unable to login showing error as link has expired while trying reset password | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7479 | IIRM-10330 | Bug | On a laptop using Microsoft Edge at 100% resolution, the login page is not scrolling properly, making it difficult to access all fields and options. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7480 | IIRM-10331 | Bug | When attempting to log in as an employee id, users are unable to proceed as the login field is labeled as “Email ID,” causing confusion and preventing login with other credentials. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7481 | IIRM-10332 | Bug | Logout button is overlapped by Quick link in 100% resolution. Shows better in 80% | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7482 | IIRM-10333 | Bug | My Documents showing documents not related to the logged-in company & policy | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7483 | IIRM-10334 | Bug | "In policies document there is no ""Back button"" Pls add back button to all pages either at the top or bottom. Users are using browser back button" | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7484 | IIRM-10335 | Bug | "- Premium amount is showing different at diffferent places - At top board premium is showing with GST where as down with out GST is showing policy details " | Done | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7485 | IIRM-10336 | Bug | Request - Need a report daily to show the list of all Support Request raised. Include Life event requests as well. User must be able to view the tickets he /she has raised | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7486 | IIRM-10337 | Bug | Form got submitted by entering only spaces in description. Hope the validation to be done post trim. Also please check if ticket is raised | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7487 | IIRM-10338 | Bug | Outlook App: A large amount of blank white space appears where content should be visible, requiring excessive scrolling to reach the actual text, similar to an issue encountered previously. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7488 | IIRM-10339 | Bug | Title of page is showing as ibp | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7489 | IIRM-10340 | Bug | Add Dependents: Newly added dependents are automatically mapped to the GMC policy | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7490 | IIRM-10341 | Bug | Users are able to edit the enrolled dependents | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7491 | IIRM-10342 | Bug | Request - Implement a visibility toggle (eye icon) for the Date of Birth field in the User Profile, with the field hidden by default. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7492 | IIRM-10343 | Bug | when trying to update alternate email getting error "Http Exception" | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7493 | IIRM-10344 | Bug | Employee date of joining is missing | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7494 | IIRM-10345 | Bug | Employee desigination and role is missing in employee profile | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7495 | IIRM-10346 | Bug | Request - GPA and GTL policies should support dependent addition - This should configuration | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7496 | IIRM-10347 | Bug | Dependent counts are missing | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7497 | IIRM-10348 | Bug | Alt. Phone & Alt. Email doesn't have format validations | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7498 | IIRM-10349 | Bug | Inception/Endorsement: Premium calculation per life is not correct | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7499 | IIRM-10350 | Bug | Policy Document is not showing all the page. second page is missing | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7500 | IIRM-10351 | Bug | E-Card page is showing some random text in the empty page | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7501 | IIRM-10352 | Bug | Request - Daily report if any additions or deletions happend in the IBP Portal | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7502 | IIRM-10353 | Bug | Request - Need login implemented for IBP Login flow | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7503 | IIRM-10354 | Bug | Show the pre-requisite for Claims | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7504 | IIRM-10355 | Bug | Ecard - Directly downlaoded instead of showing in the page. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7505 | IIRM-10356 | Task | QA: Testing And Bug reporting the Send to Insurer/Client utility | Done | Leela Pakalapati
7506 | IIRM-10357 | Sub-task | QA: Testing and logging bugs | QA Verified | Prathiphala Kandula |  | IIRM-10169 — Dashboard: Policy Distribution - Update design & values to show
7507 | IIRM-10358 | Bug | Banner is showing - "The enrolment window for 2026-27 is now closed" | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7508 | IIRM-10359 | Bug | Hosipital network link should avalible in FAQS for the where we can find hosipital list question instead text. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7509 | IIRM-10360 | Bug | Unable to Login - Page is stuck after entering email | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7510 | IIRM-10361 | Bug | Users are able to set a password even without meeting the required password rules, indicating missing or ineffective validation. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7511 | IIRM-10362 | Bug | Unable login using Employee ID & Password | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7512 | IIRM-10363 | Bug | "Unable to login using Mobile number Users are unable to log in using their mobile number, preventing access to the application." | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7513 | IIRM-10364 | Bug | Password validation mismatch | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7514 | IIRM-10365 | Bug | "Also please note special characters like ' "" ; -- can cause sql injection These are being blocked while PASSWORD update post login but not when resetting password" | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7515 | IIRM-10366 | Bug | For the login issue: here all the parameters are fulfilled still systame is not accepting password If there is a maximum validation of characters , pls mention. Also there must be a scroll bar for change password window. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7516 | IIRM-10367 | Bug | "In policies document there is no ""Back button"" Pls add back button to all pages either at the top or bottom. Users are using browser back button" | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7517 | IIRM-10368 | Bug | Welcome Email - Not received | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7518 | IIRM-10369 | Bug | Permium is not showing | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7519 | IIRM-10370 | Bug | "- Premium amount is showing different at diffferent places - At top board premium is showing with GST where as down with out GST is showing policy details " | Done | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7520 | IIRM-10371 | Bug | Users are unable to attach documents properly while raising a ticket. Even after attaching and submitting, the same document remains visible and does not update or change for subsequent actions. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7521 | IIRM-10372 | Bug | Request - Need a report daily to show the list of all Support Request raised. Include Life event requests as well. User must be able to view the tickets he /she has raised | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7522 | IIRM-10373 | Bug | Supported Formats displaying as pdf, doc, png but it is accepting jpg file also while raising ticket. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7523 | IIRM-10374 | Bug | Employee date of joining is missing | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7524 | IIRM-10375 | Story | IBP: Company-Scoped Employee Access for Client HR | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7525 | IIRM-10376 | Story | IBP: HR Portal - HR's Department/Branch/Vertical Access | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7526 | IIRM-10377 | Bug | Dashboard: TAT: Filters not applied when navigating from Endorsemet TAT by SBU table to Manage Endorsement | Done | Leela Pakalapati | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7527 | IIRM-10378 | Bug | Send to Client/Insurer: Data Mismatch | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
7528 | IIRM-10379 | Bug | Send to Insurer/Client: Deleted records are not correctly displayed in preview | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
7529 | IIRM-10380 | Story | Inception/Endorsement: Premium Calculation | Draft | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7530 | IIRM-10381 | Bug | IIRM: Per Family (Age Parameter) – Incorrect Member Count Displayed After Dependent Deletion in Endorsement | Done | Prathiphala Kandula | IBP | IIRM-757 — SOW#30 - Manage Policy Endorsements
7531 | IIRM-10382 | Story | Step-1: Enrollment issues in Inception/Endorsement | Draft | sunilkumar.chitikina |  | IIRM-735 — SOW#8 - 11 Components / Modules
7532 | IIRM-10383 | Bug | IIRM: Incorrect “Age Cannot Be Changed” Error While Updating Employee Name in Endorsement | Open | Prathiphala Kandula | IBP
7533 | IIRM-10384 | Bug | IIRM: Company Pincode: Invalid pincode shown on updating company logo. | Open | Akhila Gattu
7534 | IIRM-10385 | Story | IBP: HR Portal - Login | Draft | NithinKrishna Sirigiri |  | IIRM-744 — SOW#17 - User Management
7535 | IIRM-10386 | Story | Dashboard: Add Insurer Filter | Done | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7536 | IIRM-10387 | Story | Policy Details - Financial Info | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7537 | IIRM-10388 | Bug | IIRM: Send to Insurer/Client Utility – Missing columns in utility mapping | Done | Leela Pakalapati | IBP | IIRM-735 — SOW#8 - 11 Components / Modules
7538 | IIRM-10389 | Bug | IIRM: Incorrect Date Filtering Logic for “Beyond 90 Days” in Policy Expiry Timeline by SBU | Done | Prathiphala Kandula | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7539 | IIRM-10390 | Bug | IIRM: Incorrect SBU Endorsement Count and Duplicate SBU Rows in Manage Endorsements | Done | Prathiphala Kandula | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7540 | IIRM-10391 | Sub-task | QA: Testing and Logging bugs | Draft | Prathiphala Kandula |  | IIRM-10318 — Dashboard: Move the Claims, Endorsement, & Policy Expiry TAT buckets into Center Page and apply filter
7541 | IIRM-10392 | Sub-task | QA: Testing and Bug reporting | QA Verified | Leela Pakalapati |  | IIRM-10174 — Utility - Add New columns in the Send to Client (Refer to different Client template)
7542 | IIRM-10393 | Sub-task | QA: Re-Verifying the bugs | QA Verified | Leela Pakalapati |  | IIRM-10174 — Utility - Add New columns in the Send to Client (Refer to different Client template)
7543 | IIRM-10394 | Task | QA: Uploading claims in the production | QA Verified | Leela Pakalapati | IBP | IIRM-782 — SOW#55 - Claim Management
7544 | IIRM-10395 | Bug | IIRM: Duplicate SBU Display with Different Spellings in Dashboard Sections (Endorsement TAT, Policy Expiry Timeline, Claims TAT) | Open | Prathiphala Kandula | IBP
7545 | IIRM-10396 | QAlity Test | TC-001: Insurer Filter — Rendering, Default State, Options Load, and Selection Behavior | Draft | Prathiphala Kandula | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7546 | IIRM-10397 | QAlity Test | TC-002: Run Button Applies Insurer Filter to All Widgets; Combined with All Other Filters; No Premature Re-fetch | Draft | Prathiphala Kandula |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7547 | IIRM-10398 | QAlity Test | TC-003: Non-Applicable Widgets Show Zero/Empty State; Reset Restores Defaults; API Error Graceful Degradation | Draft | Prathiphala Kandula | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7548 | IIRM-10399 | QAlity Test | TC-004: Last-Mile Clickability (Drill-Down) and Role-Based Insurer Scope | Draft | Prathiphala Kandula | IBP | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7549 | IIRM-10400 | Sub-task | QA: Documenting Test Cases | Done | Prathiphala Kandula |  | IIRM-10387 — Policy Details - Financial Info
7550 | IIRM-10401 | Sub-task | QA: Documenting Test Cases | Done | Prathiphala Kandula |  | IIRM-10386 — Dashboard: Add Insurer Filter
7551 | IIRM-10402 | QAlity Test | TC-001: Financial Info Tab — Role-Based Visibility and Tab Access | Draft | Prathiphala Kandula
7552 | IIRM-10403 | QAlity Test | TC-002: Endorsement Frequency and Client Policy SPOC — Data Rendering | Draft | Prathiphala Kandula
7553 | IIRM-10404 | QAlity Test | TC-003: Premium Receipts — Data Rendering and Business Booked Label | Draft | Prathiphala Kandula
7554 | IIRM-10405 | QAlity Test | TC-004: Invoices and Collections — Data Rendering, Labels, and Full Category Coexistence | Draft | Prathiphala Kandula | IBP
7555 | IIRM-10406 | Bug | The screen is not allowing scroll down (edge issue)" | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7556 | IIRM-10407 | Bug | "Home Page: There is no scroll down option, so not able to see the USERNAME & Password Tab ,Have to click on ‘tab’ button currently on laptop, so that the curser lands on Username and password tab " | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7557 | IIRM-10408 | Bug | Policy benefits & summary: Page 1 shows all the policy details, whereas Page 2 is blank, needs to be removed | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7558 | IIRM-10409 | Bug | Look and feel can be enhanced more may be by changing some Fonts and color style. | On Hold | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7559 | IIRM-10410 | Bug | Age band slab year fixation is required, as the parent age band is currently considered up to 139 years. Although the system may not be factoring this correctly, it is advisable to restrict the slab up to 90 years as per policy T&C. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7560 | IIRM-10411 | Bug | Post completion of parental selection, the system does not allow any modifications on the portal. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7561 | IIRM-10412 | Bug | The option to opt out of the Critical Illness plan after selection is not available. The “Unselect Plan” tab is not functioning properly. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7562 | IIRM-10413 | Bug | For Parent covers (Critical Illness / OPD / Dental & Vision), the “Select” tab is not working, although the contribution amount is displayed on the screen. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7563 | IIRM-10414 | Bug | IIRM: Insurer filter is missing in listing pages | Ready for QA | Leela Pakalapati |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7564 | IIRM-10415 | Bug | Send to Insurer/Client Utility – Finance details displayed for non-financial endorsements | Done | Leela Pakalapati |  | IIRM-735 — SOW#8 - 11 Components / Modules
7565 | IIRM-10416 | Story | IBP: CRM HR Admin - User Management | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7566 | IIRM-10417 | Bug | Suppose one employee 2nd delivery is Twins and if he wants to add twins (1st delivery is one kid and 2nd delivery is 2 kids so total he want to add 3 kids its should show option to add as twins) | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7567 | IIRM-10418 | Bug | Let’s say employee age is 40 and if I enter mother age is 40 and father age is 40 portal is accepting it should give pop up that to check the age before submitting | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7568 | IIRM-10419 | Bug | While adding dependents- the drop down list showing the relation is not visible fully ( just initial 2-3 letter are seen, for example: If its Spouse then dropdown I can see only ‘sp’, similarly for daughter its seen as ‘dau’.. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7569 | IIRM-10420 | Bug | Same is for Gender drop down listing – the page just shows ‘ Fe’ or | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7570 | IIRM-10421 | Bug | Can the font size reduce to see the exact details about OPTIONAL PLAN- currently as per screenshot shared below, employee may get confused as what would be the optional plan( OPD or CI ) unless he clicks on drop down arrow | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7571 | IIRM-10422 | Bug | The confirmation email subject needs to be changed- it currently says-‘’ Welcome to Insurance Benefits Portal’’, suggest if it gets changed to ‘’ Enrolment successfully submitted/registered’ | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7572 | IIRM-10423 | Bug | Once I click on quick links tab called ‘ Enrolment status’ – it should show YOUR ENROLMENT IS COMPLETE. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7573 | IIRM-10424 | Bug | On raising ticket- its better if employee gets some email confirmation with the ticket number | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7574 | IIRM-10425 | Bug | Unable to add two daughters under dependents. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7575 | IIRM-10426 | Bug | No gender validation across all relationships | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7576 | IIRM-10427 | Bug | Optional benefits are appearing multiple times (duplication issue). - parental optional tag not showing | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7577 | IIRM-10428 | Bug | Once I click on quick links tab called ‘ Enrolment status’ – it should show YOUR ENROLMENT IS COMPLETE. | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7578 | IIRM-10429 | Story | PROD Issue: Placement Slip - Show Lead Insurer Brokerage Amount (Opty. ID: 681871) | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7579 | IIRM-10430 | Story | PROD Issue: Policy Confirmation - Unable to upload document | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7580 | IIRM-10431 | CR - Story | Expiring policy terms(last year) of GMC policy are getting captured/carry forwarded in both enter quote and QCR and in Placement Slip activities (Opty. ID: 1996928 & 2228826) | Draft | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7581 | IIRM-10432 | Story | IBP - Claims - Chatbot - Similar to GHTL | Draft | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
7582 | IIRM-10433 | Story | IBP - TPA Integration - Launch TPA - SSO | Draft | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
7583 | IIRM-10434 | Bug | IIRM: Dashboard – Multiple Issues in My Follow Up Navigation, Filter-Based Metrics, and Total Overview Distribution | Open | Prathiphala Kandula | IBP
7584 | IIRM-10435 | Story | Add/Manage Insurer - Enhancements (VRK Feedback) | QA Verified | NithinKrishna Sirigiri |  | IIRM-759 — SOW#32 - Asset/Member Data Mgmt
7585 | IIRM-10436 | Sub-task | Utility mapping for newly added columns Sent to Insurer/Client | Done | sunilkumar.chitikina |  | IIRM-10174 — Utility - Add New columns in the Send to Client (Refer to different Client template)
7586 | IIRM-10437 | Sub-task | Default template mapping for newly added columns Sent to Insurer/Client | Done | sunilkumar.chitikina |  | IIRM-10174 — Utility - Add New columns in the Send to Client (Refer to different Client template)
7587 | IIRM-10438 | Bug | Inception: Employee enrollment failed and Policy Extension error file generated | Open | Leela Pakalapati | iWork
7588 | IIRM-10439 | Bug | Insurer: Incorrect toast message displayed while adding insurer with invalid GST number | Open | Leela Pakalapati | IBP
7589 | IIRM-10440 | Story | Policy Config - By Pass Config and Perform Inception/Endorsement (Premium Rater Table) | Done | NithinKrishna Sirigiri |  | IIRM-777 — SOW#50 - Policy Configurator
7590 | IIRM-10441 | Bug | Policy Config Bypass: Unable to enroll dependents for data type “Employee Details with Premium” | Done | Leela Pakalapati | IBP | IIRM-777 — SOW#50 - Policy Configurator
7591 | IIRM-10442 | Sub-task | QA: Documenting test cases and Bug reporting | Done | Leela Pakalapati |  | IIRM-10440 — Policy Config - By Pass Config and Perform Inception/Endorsement (Premium Rater Table)
7592 | IIRM-10443 | CR - Story | CR: My SO & My RO - Update Search Criteria | QA Verified | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7593 | IIRM-10444 | CR - Story | CR: Enhance QCR - 1. Remove RFP column. 2. Remove Variance row | QA Verified | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7594 | IIRM-10445 | Story | Using AI - Read every document(s), validate it and confirm in the Opty. flow | Draft | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7595 | IIRM-10446 | Story | Upload Document - Mandatory in all the activities of Opty. flow (SO & RO) | Done | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7596 | IIRM-10447 | Bug | Filters – Period filter is not working as expected | Done | Leela Pakalapati | iWork | IIRM-797 — SOW#69 - Manage Opportunities
7597 | IIRM-10448 | Bug | Policy Config Bypass: “Enrollment Premium Based” state is not updated until page refresh | Done | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
7598 | IIRM-10449 | Bug | Policy Config Bypass : Premium is incorrectly calculated and displayed in KPI cards in Step 2 | Done | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
7599 | IIRM-10450 | Bug | Policy Config Bypass: Net Premium (Excl. GST) and Additional Premium (Excl. GST) displayed incorrectly | Development in Progress | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
7600 | IIRM-10451 | Bug | Policy Config Bypass: Duplicate email and phone number validation is not working during employee enrollment | Ready for QA | Leela Pakalapati | IBP | IIRM-777 — SOW#50 - Policy Configurator
7601 | IIRM-10452 | Bug | Policy Config Bypass: Unable to download TPA ID upload template | Done | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7602 | IIRM-10453 | Bug | Documents: Mandatory validation message displayed even after uploading document | Done | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7603 | IIRM-10454 | Bug | Documents: Able to submit Broking Slip/Enter Quote/Placement slip activities without uploading documents | Done | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7604 | IIRM-10455 | Bug | IIRM: Policy Extension Endorsement Does Not Retain Step 2 Data on Reopen | Done | Prathiphala Kandula
7605 | IIRM-10456 | Story | RO Scheduler Enhancements | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7606 | IIRM-10457 | Bug | Policy Config Bypass: “Download failed. Try Again” message displayed while downloading endorsement template | Done | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7607 | IIRM-10458 | Story | Non-GMC/Group - Endorsement Enhancements | Passed in QA | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7608 | IIRM-10459 | Bug | Prod: Endorsement Type Field Gets Cleared When Navigating Back to Step 1 in Policy Extension Endorsement | Done | Prathiphala Kandula
7609 | IIRM-10460 | QAlity Test | My SO Filters: Verify SO creation date logic in My SO search filters | Completed | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7610 | IIRM-10461 | QAlity Test | My SO Filters: Verify updated UI changes in My SO search filters | Completed | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7611 | IIRM-10462 | QAlity Test | My RO Filters: Verify updated search criteria behavior in My RO module | Completed | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7612 | IIRM-10463 | QAlity Test | Manage Company: Verify inactive companies are restricted from SO creation | Completed | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7613 | IIRM-10464 | Bug | Prod: Incorrect “Endorsement Already in Progress” Popup Displayed While Updating Premium in Existing Policy Extension Endorsement | Done | Prathiphala Kandula
7614 | IIRM-10465 | Bug | Prod: Duplicate IIRM Policy Number Displayed in Both “IIRM Policy Number” and “Insurer Policy Number” Columns in Extension History | Done | Prathiphala Kandula
7615 | IIRM-10466 | QAlity Test | Manage Company: Verify company visibility for Owner and Manager users without “View All Companies” privilege | To Do | Leela Pakalapati |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
7616 | IIRM-10467 | QAlity Test | Manage Company: Verify company visibility with “View All Companies” privilege enabled | Draft | Leela Pakalapati |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
7617 | IIRM-10468 | QAlity Test | Manage Company: Verify “View All Companies” privilege configuration in Roles module | Draft | Leela Pakalapati |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
7618 | IIRM-10469 | Bug | Manage Company: Owners filter is not working correctly for users with “View All Companies” privilege | Open | Leela Pakalapati |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
7619 | IIRM-10470 | QAlity Test | TC 01: Policy Extension – Successful submission with Financial Endorsement Type | Completed | Prathiphala Kandula
7620 | IIRM-10471 | QAlity Test | TC 02: Policy Extension – Successful submission with Non-Financial Endorsement Type | Completed | Prathiphala Kandula
7621 | IIRM-10472 | QAlity Test | TC 03: Policy Extension – Extension Date validation (date less than or equal to current policy end date) | Completed | Prathiphala Kandula
7622 | IIRM-10473 | QAlity Test | TC 04: Policy Extension – Intermediate state verification (policy end date not updated after Step 1 only) | Completed | Prathiphala Kandula
7623 | IIRM-10474 | QAlity Test | QCR: Verify removal of RFP column from QCR Comparison report table and downloaded excel | Completed | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7624 | IIRM-10475 | QAlity Test | QCR: Verify removal of Variance row from Premium comparison table in QCR report and downloaded excel | Completed | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7625 | IIRM-10476 | QAlity Test | QCR: Verify updated column order in QCR Comparison report based on selected insurers | Completed | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7626 | IIRM-10477 | QAlity Test | TC 05: Policy Extension – Upload document functionality in Step 1 (Positive) | Completed | Prathiphala Kandula
7627 | IIRM-10478 | QAlity Test | TC 06: Policy Extension – Verify no additional endorsement steps beyond Step 2 exist (Structural Positive) | Completed | Prathiphala Kandula
7628 | IIRM-10479 | QAlity Test | Documents: Verify document upload is mandatory in all SO and RO activities | To Do | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7629 | IIRM-10480 | QAlity Test | Documents: Verify uploaded documents are reflected in Documents tab of SO | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7630 | IIRM-10481 | QAlity Test | Documents: Verify policy document upload is mandatory in Policy Hard Copy step for SO and RO | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7631 | IIRM-10482 | Sub-task | QA: Documenting Test Cases | Done | Leela Pakalapati |  | IIRM-10443 — CR: My SO & My RO - Update Search Criteria
7632 | IIRM-10483 | Sub-task | QA: Executing test cases and bug reporting | Done | Leela Pakalapati |  | IIRM-10443 — CR: My SO & My RO - Update Search Criteria
7633 | IIRM-10484 | Sub-task | QA: Re verification of bugs | Done | Leela Pakalapati |  | IIRM-10443 — CR: My SO & My RO - Update Search Criteria
7634 | IIRM-10485 | Sub-task | QA: Documenting Test Cases | Done | Leela Pakalapati |  | IIRM-10168 — CR: My Company: Show data based on User Privileges
7635 | IIRM-10486 | Sub-task | QA: Executing Test Cases and Bug reporting | Done | Leela Pakalapati |  | IIRM-10168 — CR: My Company: Show data based on User Privileges
7636 | IIRM-10487 | Sub-task | QA: Re-testing and bug reporting | Done | Leela Pakalapati |  | IIRM-10168 — CR: My Company: Show data based on User Privileges
7637 | IIRM-10488 | Sub-task | QA: Sanity testing in Prod | Done | Leela Pakalapati |  | IIRM-10168 — CR: My Company: Show data based on User Privileges
7638 | IIRM-10489 | Sub-task | QA: Documenting test cases | Done | Leela Pakalapati |  | IIRM-10444 — CR: Enhance QCR - 1. Remove RFP column. 2. Remove Variance row
7639 | IIRM-10490 | Sub-task | QA: Executing test cases and Bug Reporting | Done | Leela Pakalapati |  | IIRM-10444 — CR: Enhance QCR - 1. Remove RFP column. 2. Remove Variance row
7640 | IIRM-10491 | Sub-task | QA: Re-Verification of Bugs | Done | Leela Pakalapati |  | IIRM-10444 — CR: Enhance QCR - 1. Remove RFP column. 2. Remove Variance row
7641 | IIRM-10492 | Sub-task | QA: Sanity Testing in Prod | Done | Leela Pakalapati |  | IIRM-10444 — CR: Enhance QCR - 1. Remove RFP column. 2. Remove Variance row
7642 | IIRM-10493 | Sub-task | QA: Sanity test in prod | Done | Leela Pakalapati |  | IIRM-10443 — CR: My SO & My RO - Update Search Criteria
7643 | IIRM-10494 | QAlity Test | TC 07: Policy Extension – Track Endorsement table navigation and completed state verification after both steps | Completed | Prathiphala Kandula
7644 | IIRM-10495 | Bug | IIRM: RO Mandatory Document Upload Validation Is Not Working for All Expected Activities | Done | Prathiphala Kandula
7645 | IIRM-10496 | QAlity Test | Policy Bypass: Verify policy activation and inception flow when “Enrollment Premium Based” is set to Yes/True | Draft | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7646 | IIRM-10497 | QAlity Test | Policy Bypass: Verify existing policy configuration and inception flow when “Enrollment Premium Based” is set to No/False | Draft | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7647 | IIRM-10498 | QAlity Test | Policy Bypass: Verify policy activation validations based on approval status | Draft | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7648 | IIRM-10499 | QAlity Test | Policy Bypass: Verify restrictions and behavior after approvals before policy activation | Draft | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7649 | IIRM-10500 | QAlity Test | Policy Bypass: Verify employee and dependent management through Inception/Endorsement flow | Draft | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7650 | IIRM-10501 | Sub-task | QA: Executing test cases and bug reporting | Done | Leela Pakalapati |  | IIRM-10440 — Policy Config - By Pass Config and Perform Inception/Endorsement (Premium Rater Table)
7651 | IIRM-10502 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-10440 — Policy Config - By Pass Config and Perform Inception/Endorsement (Premium Rater Table)
7652 | IIRM-10503 | Sub-task | QA: Documenting test cases | Done | Leela Pakalapati |  | IIRM-10446 — Upload Document - Mandatory in all the activities of Opty. flow (SO & RO)
7653 | IIRM-10504 | Sub-task | QA: Executing test cases and bug reporting | Done | Leela Pakalapati |  | IIRM-10446 — Upload Document - Mandatory in all the activities of Opty. flow (SO & RO)
7654 | IIRM-10505 | Sub-task | QA: Re-Verifying the bugs | Done | Leela Pakalapati |  | IIRM-10446 — Upload Document - Mandatory in all the activities of Opty. flow (SO & RO)
7655 | IIRM-10506 | QAlity Test | TC 08: Policy Extension – Extension History table records displayed correctly after saving Step 1 | Completed | Prathiphala Kandula
7656 | IIRM-10507 | Bug | Policy Config Bypass: Able to enroll employees without premium data for premium-based policies | Done - Not a Bug | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7657 | IIRM-10508 | Bug | Policy Config Bypass: Premium details displayed as “0” in Send to Insurer/Client files for premium based policies | Reopen | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7658 | IIRM-10509 | Story | iWork - User Mgmt. - Delete Employee | QA Failed | NithinKrishna Sirigiri |  | IIRM-744 — SOW#17 - User Management
7659 | IIRM-10510 | Sub-task | UX/UI: Need to enhance the current user journey for Insurer CRUD Operations. | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-10435 — Add/Manage Insurer - Enhancements (VRK Feedback)
7660 | IIRM-10511 | Bug | Policy Config: Net Premium is incorrectly calculated in Step 2 while adding dependents to existing Self | Done | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7661 | IIRM-10512 | Bug | IIRM: Incorrect “Cannot Remove Policy Location Address” Popup Displayed While Adding Additional Policy Location Address | Done | Prathiphala Kandula
7662 | IIRM-10513 | Bug | IIRM: Policy Location Address Gets Deleted Despite Validation Error Popup During Address Deletion | Done | Prathiphala Kandula
7663 | IIRM-10514 | Bug | Policy Config Bypass – Net Premium is incorrectly calculated while deleting dependents | Done | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7664 | IIRM-10515 | Bug | IIRM: Incorrect “Cannot Remove Policy Location Address” Popup Displayed While Saving Unrelated Company Edits | Done | Prathiphala Kandula
7665 | IIRM-10516 | Story | Policy Configuration - Company Associated Locations (Policy Location) | Done | NithinKrishna Sirigiri |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7666 | IIRM-10517 | Bug | [BUG] User Profile - Age column missing in Dependents table | Open | PATIBANDLA VELANGINI RAJU
7667 | IIRM-10518 | Bug | [BUG] Support Tickets - Raise Tickets section visible in pre-login state | Open | PATIBANDLA VELANGINI RAJU
7668 | IIRM-10519 | Bug | [BUG] Life Events - Cancel button on Add Dependent form navigates to Life Events management page | Open | PATIBANDLA VELANGINI RAJU
7669 | IIRM-10520 | Story | IBP: Enrolment & HR - Demo Company Setup (Feedback) | Draft | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7670 | IIRM-10521 | Bug | Policy Config Bypass: Premium Calculator File Displays Duplicate Self Record and Incorrect Total Premium After Adding Dependent in Endorsement | Ready for QA | Prathiphala Kandula
7671 | IIRM-10522 | QAlity Test | Verify that the Income Type filter loads with "All" selected by default, displays exactly three options (All, Policy, Endorsements), and that selecting each option correctly updates the record grid to show only matching records. | Draft | Prathiphala Kandula
7672 | IIRM-10523 | QAlity Test | Verify that for each Income Type filter selection the on-screen record count exactly matches the actual records in the dataset, and that no cross-type contamination exists (policy records never appear under Endorsements filter and vice versa). | Draft | Prathiphala Kandula
7673 | IIRM-10524 | QAlity Test | Verify the filter behaves gracefully when the selected income type has no records in the dataset — empty state is shown without errors, and switching to another type still works correctly. | Draft | Prathiphala Kandula
7674 | IIRM-10525 | QAlity Test | Verify that clicking "Download Report" produces a file whose records exactly match the current Income Type filter selection — All, Policy, or Endorsements — and that the file contains no extra or missing records. | Draft | Prathiphala Kandula
7675 | IIRM-10526 | QAlity Test | Verify that the "Download Report" button is always visible and enabled for all filter states, the downloaded file uses the correct format, the file name is meaningful, and no corrupt or empty file is produced. | Draft | Prathiphala Kandula
7676 | IIRM-10527 | QAlity Test | Verify that downloading the report when the active filter yields zero records produces a graceful outcome — either a header-only file or a clear user message — without any crash or unhandled error. | Draft | Prathiphala Kandula
7677 | IIRM-10528 | Bug | Policy Config Bypass: Net Premium is displayed for non-financial endorsements when premium data is updated | Done | Leela Pakalapati | iWork | IIRM-777 — SOW#50 - Policy Configurator
7678 | IIRM-10529 | QAlity Test | Verify that in Step 7 of policy configuration any number of labels can be added, the configuration can be submitted for approval, and upon approval the labels are saved and associated with the policy correctly. | Draft | Prathiphala Kandula
7679 | IIRM-10530 | QAlity Test | Verify that after the policy configuration is approved, all labels added in Step 7 appear as new columns in the download template for both the inception process and the endorsement process — in the correct order and with correct header names. | Draft | Prathiphala Kandula
7680 | IIRM-10531 | QAlity Test | Verify that during employee upload in both inception and endorsement processes, the label columns added from Step 7 accept any kind of data — plain text, numbers, special characters, alphanumeric combinations | Draft | Prathiphala Kandula
7681 | IIRM-10532 | Bug | Policy Config: Employees are displayed as "Not Started" after successful completion of Step 1 enrollment | Done | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7682 | IIRM-10533 | Bug | IIRM: Table Count Displays 0 When "All" Option Is Selected in Income Type Filter | Done | Prathiphala Kandula
7683 | IIRM-10534 | Bug | IIRM: BizDone Report Download Ignores Income Type Filter and Exports All Income Type Data | Done | Prathiphala Kandula
7684 | IIRM-10535 | Story | IBP: Portfolio Overview | Draft | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7685 | IIRM-10536 | QAlity Test | Policy Bypass: Verify employee enrollment using "Only Employee Data" data type when "Enrollment Premium Based" is set to False/No | Draft | Leela Pakalapati |  | IIRM-777 — SOW#50 - Policy Configurator
7686 | IIRM-10537 | Bug | IIRM: Employee Only Enrollment - Employee Deletion Is Not Processed When Add and Delete Transactions Are Uploaded Together in Endorsement File | Done | Prathiphala Kandula
7687 | IIRM-10538 | Bug | IIRM: Employee Only Enrollment - Premium Amount and Additions Stats Count Are Not Updated Correctly After Employee Addition in Step 2 | Done | Prathiphala Kandula
7688 | IIRM-10539 | Story | Redesign of Import Policy Configuration | Done | Prathiphala Kandula |  | IIRM-757 — SOW#30 - Manage Policy Endorsements
7689 | IIRM-10540 | QAlity Test | Verify that clicking "Import Policy Configuration" opens the confirmation popup with all 3 dropdowns, that Policy Type and Live Configuration dropdowns are disabled until their parent is selected | Completed | Prathiphala Kandula
7690 | IIRM-10541 | Bug | Manage Employees: UI and usability issues | Done | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7691 | IIRM-10542 | QAlity Test | Verify import policy configuration — complete selection and verify all config data is imported correctly into current policy | Completed | Prathiphala Kandula
7692 | IIRM-10543 | QAlity Test | Verify import overwrite — importing into a partially configured policy replaces existing data correctly | Completed | Prathiphala Kandula
7693 | IIRM-10544 | QAlity Test | Verify import Policy Configuration button — visible only on non-activated policies, hidden on activated policies | Completed | Prathiphala Kandula
7694 | IIRM-10545 | Bug | Manage Employees: Deactivate option is displayed for inactive employees and allows repeated deactivation | Done | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7695 | IIRM-10546 | QAlity Test | Verify import button — validation error shown when clicked without completing all 3 dropdowns | Completed | Prathiphala Kandula
7696 | IIRM-10551 | Bug | Manage Employees: Inactive Employees KPI count is not auto-updating after employee deactivation | Done | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7697 | IIRM-10552 | Bug | Manage Employees: Unable to filter Active and Inactive users from the listing page | Done | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7698 | IIRM-10553 | Story | Sorting Functionality for SO Table and Our Portfolio Table in Manage Companies Page | QA Verified | Prathiphala Kandula |  | IIRM-736 — SOW#9 - Add/Manage Company (Prospects)
7699 | IIRM-10554 | QAlity Test | Verify SO Table — alphabetical sorting for Policy Type, Priority Level and Activity Name columns | Completed | Prathiphala Kandula
7700 | IIRM-10555 | QAlity Test | Verify SO Table — date sorting for Expiry Date column (ascending, descending, no sort) | Completed | Prathiphala Kandula
7701 | IIRM-10556 | QAlity Test | Verify SO Table — numeric sorting for Premium and Estimated Brokerage columns | Completed | Prathiphala Kandula
7702 | IIRM-10557 | QAlity Test | Verify Our Portfolio Table — alphanumeric sorting for Policy Number and alphabetical for Policy Type | Completed | Prathiphala Kandula
7703 | IIRM-10558 | QAlity Test | Verify Our Portfolio Table — date sorting for Policy From and Policy To columns | Completed | Prathiphala Kandula
7704 | IIRM-10559 | QAlity Test | Verify Our Portfolio Table — numeric sorting for Premium (WOST), Brokerage and RO Id columns | Completed | Prathiphala Kandula
7705 | IIRM-10560 | QAlity Test | Verify Our Portfolio Table — numeric sorting for Premium (WOST), Brokerage and RO Id columns | Completed | Prathiphala Kandula
7706 | IIRM-10561 | Bug | IIRM: Lookup Value Text Box Is Misaligned Between Select Entity and Status Fields | Done | Prathiphala Kandula
7707 | IIRM-10562 | Bug | IIRM: Policy Type Master Allows Invalid Record Management Due to Missing Mandatory Indicators, Duplicate Lookup Values, and Inconsistent Mandatory Field Validation | Done | Prathiphala Kandula
7708 | IIRM-10563 | Sub-task | QA: Documenting Test Cases | Draft | Leela Pakalapati |  | IIRM-10509 — iWork - User Mgmt. - Delete Employee
7709 | IIRM-10564 | Sub-task | QA: Employee Management: Test Case Execution and Bug Reporting | Passed in QA | Leela Pakalapati |  | IIRM-10509 — iWork - User Mgmt. - Delete Employee
7710 | IIRM-10565 | Sub-task | QA: Re-Verifying the bugs | Draft | Leela Pakalapati |  | IIRM-10509 — iWork - User Mgmt. - Delete Employee
7711 | IIRM-10566 | Bug | Master Covers: Able to add cover without selecting Organization and Policy Type | Done | Leela Pakalapati |  | IIRM-745 — SOW#18 - Master Data
7712 | IIRM-10567 | Bug | Policy Config Bypass: Selected Data Type Changes Automatically After Uploading Employee-Only Endorsement File | Ready for QA | Prathiphala Kandula |  | IIRM-777 — SOW#50 - Policy Configurator
7713 | IIRM-10568 | Bug | Master Covers: Mandatory icon and validation message displayed for non-mandatory covers | Done | Leela Pakalapati |  | IIRM-745 — SOW#18 - Master Data
7714 | IIRM-10569 | Bug | SO: Unable to complete Data Validation activity when no covers are configured for the selected policy | Done | Leela Pakalapati |  | IIRM-745 — SOW#18 - Master Data
7715 | IIRM-10570 | QAlity Test | Verify Create Cover — all four attributes with all input types and verify cover is created without policy type linkage | Completed | Prathiphala Kandula
7716 | IIRM-10571 | QAlity Test | Verify Create Cover — validation for missing fields, duplicate cover name and search functionality in covers list | Completed | Prathiphala Kandula
7717 | IIRM-10572 | QAlity Test | Verify Map to Policy Type — select Organisation, Policy Type and Cover with search on all 3 fields and verify successful mapping | Completed | Prathiphala Kandula
7718 | IIRM-10573 | QAlity Test | Verify Organisation isolation — cover mapped to one org must appear only in that org's policies and not in others | Completed | Prathiphala Kandula
7719 | IIRM-10574 | QAlity Test | Organisation isolation — same policy type in multiple orgs, cover mapped to each org independently and verified separately | Completed | Prathiphala Kandula
7720 | IIRM-10575 | QAlity Test | Employee Management: Verify Employees listing page KPIs, Status filter and KPI count updates | Draft | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7721 | IIRM-10576 | QAlity Test | Employee Management: Verify employee deactivation popup details and available actions | Draft | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7722 | IIRM-10577 | QAlity Test | Verify Map to Policy Type — add multiple covers, set mandatory flag, drag to reorder and submit mappings | Completed | Prathiphala Kandula
7723 | IIRM-10578 | QAlity Test | Employee Management: Verify Cancel functionality during employee deactivation | Draft | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7724 | IIRM-10579 | QAlity Test | Employee Management: Verify Auto Assign & Deactivate functionality and data visibility | Draft | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7725 | IIRM-10580 | QAlity Test | Verify Map to Policy Type — delete a mapped cover, validation for empty fields, and Submit Mappings without changes | Completed | Prathiphala Kandula
7726 | IIRM-10581 | QAlity Test | Employee Management: Verify manual assignment stepper functionality during employee deactivation | Draft | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7727 | IIRM-10582 | QAlity Test | Employee Management: Verify employee activation functionality | Draft | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7728 | IIRM-10583 | Bug | IIRM: Cover Values Added/Updated During Broking Slip Generation Are Not Persisted Across Subsequent SO Stages | Done | Prathiphala Kandula
7729 | IIRM-10584 | Bug | IIRM: QCR Generation Displays Incomplete Cover List and Incorrect Cover Values | Done | Prathiphala Kandula
7730 | IIRM-10585 | Epic | Cut Off Management | Draft | NithinKrishna Sirigiri
7731 | IIRM-10586 | Bug | Final Negotiation: GST percentage is getting doubled during prefill | Ready for QA | Leela Pakalapati
7732 | IIRM-10587 | CR - Story | Policy Details - Business Month & Date of Business | QA in Progress | NithinKrishna Sirigiri |  | IIRM-6827 — Manage Policy
7733 | IIRM-10588 | CR - Story | iWork - My Sales Portfolio & Manage Placements & their rule (Request 8-June-2026) | QA Failed | NithinKrishna Sirigiri |  | IIRM-797 — SOW#69 - Manage Opportunities
7734 | IIRM-10589 | CR - Story | iWork - My Client Portfolio (Request 8-June-2026) | Passed in QA | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7735 | IIRM-10590 | CR - Story | Policy Config: Dependent Based Configurations | QA Failed | NithinKrishna Sirigiri |  | IIRM-6827 — Manage Policy
7736 | IIRM-10591 | CR - Story | IBP - Enrolment Journey - Reset | Draft | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
7737 | IIRM-10592 | CR - Story | iWork - SSO with Microsoft AD | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-8420 — IIRM (iWork) to External SSO
7738 | IIRM-10593 | QAlity Test | Policy Config: Verify premium calculation when Apply Dependents flag is not selected | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7739 | IIRM-10594 | QAlity Test | Verify SO creation — newly mapped covers appear in correct display order with correct mandatory flag during SO creation | Completed | Prathiphala Kandula
7740 | IIRM-10595 | QAlity Test | Verify Policy covers details tab — all mapped covers displayed in correct order with correct mandatory status after SO is converted to policy | Completed | Prathiphala Kandula
7741 | IIRM-10596 | QAlity Test | Policy Config: Verify premium calculation while adding employee/family when Apply Dependents flag is selected | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7742 | IIRM-10597 | QAlity Test | Policy Config: Verify premium calculation when updating employee or dependent details with Apply Dependents enabled | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7743 | IIRM-10598 | QAlity Test | Policy Config: Verify premium recalculation when deleting employee or dependent with Apply Dependents enabled | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7744 | IIRM-10599 | QAlity Test | Policy Config: Verify premium calculation when adding existing dependent to an existing family with Apply Dependents flag enabled | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7745 | IIRM-10600 | Bug | Employee Management: Policies and SOs are displayed for a reactivated employee | Open | Leela Pakalapati |  | IIRM-744 — SOW#17 - User Management
7746 | IIRM-10601 | Bug | Dependent Base Config: Sum Insured values are displayed incorrectly when Dependent Count is selected as Policy Parameter | Done | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7747 | IIRM-10602 | Bug | My Sales Portfolio & Manage Quote: ISG user is able to create an Opportunity through Quick Create | Done | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7748 | IIRM-10603 | Bug | My Sales Portfolio & Manage Quote: Unauthorised modules can access through direct URL navigation | Done | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7749 | IIRM-10604 | CR - Story | Policy Config: Constraints (New Request 13-Jun-2026) | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-794 — SOW#67 - Portal Configuration
7750 | IIRM-10605 | CR - Subtask | Policy Configuration Changes | Draft | NithinKrishna Sirigiri |  | IIRM-10604 — Policy Config: Constraints (New Request 13-Jun-2026)
7751 | IIRM-10606 | CR - Subtask | IBP: Honour New Constraints | QA Verified | NithinKrishna Sirigiri |  | IIRM-10604 — Policy Config: Constraints (New Request 13-Jun-2026)
7752 | IIRM-10607 | Bug | My Sales Portfolio & Manage Quote: Activity owner is not updated after activity completion and users are missing in Assignee/Participants dropdowns | Reopen | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7753 | IIRM-10608 | Bug | My Sales Portfolio & Manage Quote: Remove BD Planning and ISG Planning from Status filter | Done | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7754 | IIRM-10609 | CR - Story | One IBP Portal (URL) for a set of Companies (1 configuration for children companies) | Draft | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
7755 | IIRM-10610 | Bug | My Sales Portfolio & Manage Quote: Opportunity opens at ISG Planning activity instead of the current activity | Reopen | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7756 | IIRM-10611 | Bug | My Sales Portfolio & Manage Quote: ISG user is able to create an SO through the Create widget | Done | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7757 | IIRM-10612 | Bug | My Sales Portfolio & Manage Quote: Unable to complete activity when selecting an existing CD Account | Done | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7758 | IIRM-10613 | Bug | My Sales Portfolio & Manage Quote: Incorrect activity name displayed for newly created SO in the listing table | Done | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7759 | IIRM-10614 | Bug | IIRM: My Client Portfolio: RO Premium (#Count) and SO Premium (#Count) are not updating in Company Overview table | Done | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7760 | IIRM-10615 | Bug | My Client Portfolio: Navigation link is missing for SOs and ROs in Company Overview | Done | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7761 | IIRM-10616 | Epic | Insurer Rewards | WORK IN PROGRESS | NithinKrishna Sirigiri
7762 | IIRM-10617 | QAlity Test | My Client Portfolio: Verify company visibility in Client Portfolio for Active Companies | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7763 | IIRM-10618 | QAlity Test | My Client Portfolio: Verify Client Portfolio table columns and premium/count calculations | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7764 | IIRM-10619 | QAlity Test | My Client Portfolio: Verify Policy Premium (#Count) data integrity | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7765 | IIRM-10620 | QAlity Test | Verify SO creation and Placement Slip — Business Month and Date of Business correctly captured from Policy_start_date | Completed | Prathiphala Kandula
7766 | IIRM-10621 | QAlity Test | My Client Portfolio: Verify SO Premium (#Count) data integrity | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7767 | IIRM-10622 | QAlity Test | Verify Manage Policies — Business Month and Date of Business columns in listing table and Business Month filter work correctly | Completed | Prathiphala Kandula
7768 | IIRM-10623 | QAlity Test | Verify BizDone Report — Business Month and Date of Business columns, filter, and Policy Details navigation show consistent values | Completed | Prathiphala Kandula
7769 | IIRM-10624 | QAlity Test | My Client portfolio: Verify RO Premium (#Count) data integrity | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7770 | IIRM-10625 | QAlity Test | My Client Portfolio: Verify Policy Details table from the my client portfolio | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7771 | IIRM-10626 | QAlity Test | My Client Portfolio: Verify Renewal Opportunities table from My Client Portfolio | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7772 | IIRM-10627 | QAlity Test | My Client Portfolio: Verify Sales Opportunities table from the My client portfolio | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7773 | IIRM-10628 | QAlity Test | Verify Manage Endorsements and Dashboard — Business Month filter only (no columns) works correctly in both modules | Completed | Prathiphala Kandula
7774 | IIRM-10629 | QAlity Test | My Client Portfolio: Verify Past Companies functionality | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7775 | IIRM-10630 | QAlity Test | Verify Data migration — all 2025 policies have Business Month and Date of Business = Income Month across all modules and Policy Details tab | Completed | Prathiphala Kandula
7776 | IIRM-10631 | QAlity Test | My Client Portfolio: Verify Past Companies premium and count calculations | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7777 | IIRM-10632 | QAlity Test | Verify End-to-end — SO → Placement Slip → verify Business Month and Date of Business consistently across Manage Policies, BizDone, Manage Endorsements, Dashboard and Policy Details tab | Completed | Prathiphala Kandula
7778 | IIRM-10633 | QAlity Test | My Client Portfolio: Verify companies displayed in my Client Portfolio and Past Companies tab | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7779 | IIRM-10634 | QAlity Test | My Client Portfolio: Verify functionality between Active Companies and Past Companies views | Completed | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7780 | IIRM-10635 | QAlity Test | My sales Portfolio & Manage Placements: Verify menu visibility for user having only BD role | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7781 | IIRM-10636 | QAlity Test | My sales Portfolio & Manage Placements: Verify menu visibility for user having only ISG role | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7782 | IIRM-10637 | QAlity Test | My sales Portfolio & Manage Placements: Verify menu visibility for user having both BD and ISG roles | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7783 | IIRM-10638 | QAlity Test | My sales Portfolio & Manage Placements: Verify opportunity visibility in Manage SO for BD users | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7784 | IIRM-10639 | QAlity Test | My sales Portfolio & Manage Placements: Verify opportunity visibility in Manage Quotes for ISG users | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7785 | IIRM-10640 | QAlity Test | My sales Portfolio & Manage Placements: Verify opportunity visibility for BD+ISG role user | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7786 | IIRM-10641 | QAlity Test | My sales Portfolio & Manage Placements: Verify Manage SO filters | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7787 | IIRM-10642 | QAlity Test | My sales Portfolio & Manage Placements: Verify Manage Quotes filters | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7788 | IIRM-10643 | QAlity Test | My sales Portfolio & Manage Placements: Verify hyperlink navigation from Manage Quotes | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7789 | IIRM-10644 | QAlity Test | My sales Portfolio & Manage Placements: Verify ISG user is restricted from creating a Sales Opportunity (SO) | Draft | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7790 | IIRM-10645 | QAlity Test | Verify Add Insurer — create new insurer with all mandatory fields, HQ details, branch contact and KYC details; verify in listing table | Completed | Prathiphala Kandula
7791 | IIRM-10646 | QAlity Test | Verify Add Insurer — validation for mandatory fields, Insurance Company Type dropdown values and edit restrictions on Insurer Name | Completed | Prathiphala Kandula
7792 | IIRM-10647 | QAlity Test | Verify Add Branch — add a new branch to an existing insurer with Branch Type, Code, Name, Parent Branch and Contact; verify branch display name and listing | Completed | Prathiphala Kandula
7793 | IIRM-10648 | QAlity Test | Verify Add multiple branches — add branches with different types under same insurer and verify Parent Branch dropdown shows all existing branches | Completed | Prathiphala Kandula
7794 | IIRM-10649 | QAlity Test | Verify SO creation — newly added insurer and branch appear in Preferred Insurer, Excluded Insurer and all insurer-related dropdowns across all 18 SO stages | Completed | Prathiphala Kandula
7795 | IIRM-10650 | QAlity Test | Verify SO creation — newly added branch (after SO creation feature was already used) appears immediately in all insurer dropdowns without any page refresh or rebuild | Completed | Prathiphala Kandula
7796 | IIRM-10651 | QAlity Test | Verify Manage Insurer listing — filter by Org, Insurer Name, Branch Type, Branch Code and City; verify result columns and KPI cards respect filters | Completed | Prathiphala Kandula
7797 | IIRM-10652 | Bug | Policy Configuration: Employee Insured tab is not displaying updated premium values correctly | On Hold | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7798 | IIRM-10653 | Bug | Policy Config: Marital Status is not displayed in Send to Insurer/Client document | Reopen | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7799 | IIRM-10654 | Bug | IIRM: Family Validation Fails for Allowed Twin and Triplet Child Combination Despite Policy Configuration | Done | Prathiphala Kandula
7800 | IIRM-10655 | Bug | Policy Config: Stats are displayed as zero when only dependents are deleted | Done | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7801 | IIRM-10656 | Bug | Policy Config: Dependent premium amount(refund) is calculated incorrectly when self is deleted | Reopen | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7802 | IIRM-10657 | Bug | IIRM: Per Life Premium Configuration Applies Premium Only to Self Instead of All Eligible Family Members | Done | Prathiphala Kandula
7803 | IIRM-10658 | Bug | Policy Config: Dependent records are missing in Send to Insurer/Client files when self is deleted | Done | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7804 | IIRM-10659 | Bug | Policy Config(Non-Finance): Self record is displayed when only a dependent is updated | Done | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7805 | IIRM-10660 | Bug | IIRM: Valid Twin/Triplet Child Combination Is Rejected During Inception and Error File Contains Incomplete Dependent Records | Done | Prathiphala Kandula
7806 | IIRM-10661 | Task | Add Insurer branch (Concat on Branch Code + Branch Name + Address1) | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7807 | IIRM-10662 | Bug | IIRM: Valid Child Combination (First Child: Single, Second Child: Triplet) Is Incorrectly Rejected During Inception | Done | Prathiphala Kandula
7808 | IIRM-10663 | Bug | IIRM: Invalid Child Combination (First Child: Single, Second Child: Twin) Is Incorrectly Accepted During Inception | Done | Prathiphala Kandula
7809 | IIRM-10664 | Bug | IIRM: Valid Child Combination (First Child: Single, Second Child: Triplet) Is Incorrectly Rejected During Inception | Done | Prathiphala Kandula
7810 | IIRM-10665 | Bug | IIRM: Valid Child Combination (First Child: Single, Second Child: Single) Is Incorrectly Rejected During Inception | Done | Prathiphala Kandula
7811 | IIRM-10666 | Story | IBP - Policy Component Card Re-design | Draft | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
7812 | IIRM-10667 | CR - Story | iWork - Knowledge Central Re-Design | Draft | NithinKrishna Sirigiri |  | IIRM-768 — SOW#41 - Knowledge Central
7813 | IIRM-10668 | Story | iLearn: Document Preview in-app | Draft | NithinKrishna Sirigiri |  | IIRM-750 — SOW#23 - Document Management - CMS
7814 | IIRM-10669 | Bug | IIRM: Sum Insured Per Life Is Applied Only to Employee and Not to Dependents | Done | Prathiphala Kandula
7815 | IIRM-10670 | Bug | IIRM: Inception "Send to Insurer" Step Displays Only Employee Data Instead of Employee and Dependents | Done | Prathiphala Kandula
7816 | IIRM-10671 | Bug | Placement Slip Generation: Placement details are not reflecting in the generated placement slip pdf | Ready for QA | Leela Pakalapati |  | IIRM-797 — SOW#69 - Manage Opportunities
7817 | IIRM-10672 | Bug | Policy Config: Unable to update dependent First Name and DOB in Non-Finance endorsement when Gender is configured as a Policy Parameter | Open | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7818 | IIRM-10673 | Bug | When OTP verification is required after entering the password, please mention it clearly as “2-Factor Authentication” or “Additional Security Verification”. | Development in Progress | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7819 | IIRM-10674 | Bug | Hospital network filters were not working | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7820 | IIRM-10675 | Bug | learn more banner is alo navigating to login page | Open | Akhila Gattu |  | IIRM-773 — SOW#46 - Enrolment Portal
7821 | IIRM-10676 | Bug | PDF Policy Configuration Import Exhibits UI, Validation, and Inconsistent Import Behavior Issues | Open | Prathiphala Kandula
7822 | IIRM-10677 | Bug | Biz-Done Report: 'All' option does not select all months in the Business Month filter | Reopen | Leela Pakalapati
7823 | IIRM-10678 | Bug | Biz-Done Report: "No data to show" message is displayed when filtering records using Income Month | Done | Leela Pakalapati
7824 | IIRM-10679 | Bug | Biz-Done Report: From Date and To Date are not pre-filled when all months are selected for the income Month | Done | Leela Pakalapati
7825 | IIRM-10680 | Bug | Policy Config: Dependent premium is calculated incorrectly when dependent actions are performed independently | Open | Leela Pakalapati
7826 | IIRM-10681 | Task | Policy: Extract Policy Configuration from PDF | QA Failed | Prathiphala Kandula |  | IIRM-6827 — Manage Policy
7827 | IIRM-10682 | QAlity Test | Verify Twins/Triplets — each constraint individually enabled/disabled; verify inception and endorsement honour the setting | Completed | Prathiphala Kandula
7828 | IIRM-10683 | QAlity Test | Verify Twins/Triplets — all possible combinations of the three constraints verified in inception and endorsement | Completed | Prathiphala Kandula
7829 | IIRM-10684 | QAlity Test | Verify Sum Insured Per Life — each family member gets individual SI; verify correct SI assignment in inception and endorsement | Completed | Prathiphala Kandula
7830 | IIRM-10685 | QAlity Test | Verify Sum Insured Per Family — single SI for employee shared by all dependents; verify SI and premium in all toggle combinations | Completed | Prathiphala Kandula
7831 | IIRM-10686 | QAlity Test | Policy Config: Verify employee and dependent data consistency in Employee Insured tab/Send to Insurer/Send to Client document | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7832 | IIRM-10687 | QAlity Test | Verify Parental Lock-in Period = 0 — no "Parental Lock" column in inception and endorsement download templates | Completed | Prathiphala Kandula
7833 | IIRM-10688 | QAlity Test | Verify Parental Lock-in Period ≥ 1 — "Parental Lock" column appears in inception and endorsement templates with Yes/No pre-filled | Completed | Prathiphala Kandula
7834 | IIRM-10689 | QAlity Test | Verify End-to-end — all constraints combined: twins/triplets + SI Per Life + Parental Lock ≥ 1; verify inception and endorsement honour all simultaneously | Completed | Prathiphala Kandula
7835 | IIRM-10690 | QAlity Test | Verify Policy Extension Step 2 — Net Premium and Gross Premium KPIs correctly calculated and displayed from Step 1 input | Completed | Prathiphala Kandula
7836 | IIRM-10691 | QAlity Test | Verify Policy Extension Step 2 — Gross Premium edge cases: decimal Net Premium, zero GST, and GST rate boundary values | Completed | Prathiphala Kandula
7837 | IIRM-10692 | QAlity Test | Verify CD Balance — Submit enabled only when CD Balance entered equals Gross Premium exactly; any other value keeps Submit disabled | Completed | Prathiphala Kandula
7838 | IIRM-10693 | QAlity Test | Verify CD transaction — must NOT appear in Policy CD Details tab or CD Management Transaction History after Policy Extension endorsement is submitted | Completed | Prathiphala Kandula
7839 | IIRM-10694 | QAlity Test | Verify Negative — CD Balance with incorrect values, decimal mismatch, and attempting to bypass Submit disable via direct actions | Completed | Prathiphala Kandula
7840 | IIRM-10695 | QAlity Test | Verify Filter cascade — selecting Insurer loads only that insurer's branches in Branch dropdown; changing Insurer resets Branch | Completed | Prathiphala Kandula
7841 | IIRM-10696 | QAlity Test | View By toggle — "Branch" shows exact branch records only; "Branch + Head" shows selected branch plus all sub-branches | Completed | Prathiphala Kandula
7842 | IIRM-10697 | QAlity Test | Verify My RO tab — Insurer + Branch + View By filters show correct ROs for Branch and Branch + Head modes | Completed | Prathiphala Kandula
7843 | IIRM-10698 | QAlity Test | Verify Manage Policies tab — Insurer + Branch + View By filters show correct policies for Branch and Branch + Head modes | Completed | Prathiphala Kandula
7844 | IIRM-10699 | QAlity Test | Verify BizDone Report — Insurer + Branch + View By filters show correct policy records for Branch and Branch + Head modes | Completed | Prathiphala Kandula
7845 | IIRM-10700 | QAlity Test | Policy: Verify Extract policy from PDF popup and document upload functionality | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7846 | IIRM-10701 | QAlity Test | Policy Config: Verify successful extraction of all policy configuration stages | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7847 | IIRM-10702 | QAlity Test | Policy Config: Verify partial extraction of policy configuration | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7848 | IIRM-10703 | QAlity Test | Policy Config: Verify behavior when no policy configuration can be extracted | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7849 | IIRM-10704 | QAlity Test | Policy Config: Verify extracted configuration accuracy across all policy configuration stages | Draft | Leela Pakalapati |  | IIRM-6827 — Manage Policy
7850 | IIRM-10705 | QAlity Test | Verify Edge cases — insurer with one branch, branch with no sub-branches, branch with no records, and clearing filters mid-selection | Completed | Prathiphala Kandula
7851 | IIRM-10706 | QAlity Test | Verify consistent extraction results when uploading the same policy configuration PDF multiple times | Draft | Leela Pakalapati
7852 | IIRM-10707 | QAlity Test | Verify policy configuration extraction for a valid PDF containing supported policy configuration data | Draft | Leela Pakalapati
7853 | IIRM-10708 | Bug | Rewards: Financial Year filter is missing in the Rewards listing and Add Reward screens | Done | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7854 | IIRM-10709 | Bug | Rewards – Listing page UI and navigation issues | Done | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7855 | IIRM-10710 | Bug | Rewards: Usability issues in the Add Reward screen | Done | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7856 | IIRM-10711 | Bug | Rewards: Insurer field is blank and disabled while editing a reward | Done | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7857 | IIRM-10712 | QAlity Test | Verify Privilege combinations — user with all 5 permissions sees all UI elements; partial combinations show only the corresponding subset | Draft | Prathiphala Kandula
7858 | IIRM-10713 | QAlity Test | Verify Add New Record — all fields filled correctly, Income Month pre-fill logic, and per-insurer rewards table visibility | Draft | Prathiphala Kandula
7859 | IIRM-10714 | QAlity Test | Verify Add New Record — mandatory field validation, Edit existing record, and Delete record from Actions column | Draft | Prathiphala Kandula
7860 | IIRM-10715 | QAlity Test | Verify Listing filters — Reward Category, Insurer, Financial Year, From Date and To Date filter the rewards table correctly | Draft | Prathiphala Kandula
7861 | IIRM-10716 | QAlity Test | Verify Period Type filter — "Income Month" vs "Business Month" mode correctly changes which date field From/To Date filters apply to | Draft | Prathiphala Kandula
7862 | IIRM-10717 | Bug | Rewards: "Existing Rewards for the Selected Insurer" section is displayed on the Edit Reward screen | Open | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7863 | IIRM-10718 | QAlity Test | Verify Documents column — displays "1 file" or "2 files" as clickable links that navigate to the correct document; Export downloads full report | Draft | Prathiphala Kandula
7864 | IIRM-10719 | QAlity Test | Save View — applied filters persist after page refresh and after logout/login; updating a saved view overwrites the previous filter set | Draft | Prathiphala Kandula
7865 | IIRM-10720 | Bug | Rewards: Save View functionality is not working in Insurer rewards module | Reopen | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7866 | IIRM-10721 | Bug | Rewards: Uploaded documents are not retained in Edit Reward mode | Done | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7867 | IIRM-10722 | Bug | Rewards: Unable to update reward after deleting an existing document | Done | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7868 | IIRM-10723 | Bug | Rewards: Document issues | Reopen | Leela Pakalapati |  | IIRM-10616 — Insurer Rewards
7869 | IIRM-10724 | Story | Dashboard: Funnel Enhancements | QA Verified | Prathiphala Kandula |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7870 | IIRM-10725 | QAlity Test | Verify Dashboard layout — all sections appear in correct order with new sections inserted between existing sections without breaking existing ones | Completed | Prathiphala Kandula
7871 | IIRM-10726 | QAlity Test | Verify Sales Schedule by SBU — SO counts per SBU displayed correctly across all 4 time bucket columns (≤30, ≤60, ≤90, Beyond 90 days) | Completed | Prathiphala Kandula
7872 | IIRM-10727 | QAlity Test | Verify Sales Follow Up — SO activity counts displayed across all 4 time buckets; verify activities are SO-specific and not mixed with RO activities | Completed | Prathiphala Kandula
7873 | IIRM-10728 | QAlity Test | Verify Renewal Schedule by SBU — RO counts per SBU across all 4 time buckets; verify parity with Sales Schedule by SBU structure | Completed | Prathiphala Kandula
7874 | IIRM-10729 | QAlity Test | Verify Renewal Follow Up — RO activity counts across all 4 time buckets; verify only RO activities shown and parity with My Follow Up RO toggle | Completed | Prathiphala Kandula
7875 | IIRM-10730 | QAlity Test | Verify Cross-section integrity — SO/RO counts in new sections are consistent with My Sales Funnel, My Renewal Funnel and My Follow Up; no data mixing | Completed | Prathiphala Kandula
7876 | IIRM-10731 | QAlity Test | Verify Edge cases — sections with zero data, SBU with no SOs or ROs, time bucket boundary dates and real-time count updates | Completed | Prathiphala Kandula
7877 | IIRM-10732 | Bug | IIRM: Upload Policy Document: Valid data is not pre-filled after document upload | Open | Leela Pakalapati
7878 | IIRM-10733 | Bug | IIRM: Saved Views Are Not Persisted for "Rewards" Income Type in BizDone Report | Open | Prathiphala Kandula |  | IIRM-10616 — Insurer Rewards
7879 | IIRM-10734 | Story | Biz done Report: Filters enhancements (Group Company, Brokerage agent) | Draft | Prathiphala Kandula
7880 | IIRM-10735 | Bug | IIRM: BizDone Report - Group Company Filter Displays Incorrect Results and Duplicate Company Entries | Open | Prathiphala Kandula
7881 | IIRM-10736 | Bug | Dashboard Issues | Done | Leela Pakalapati |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7882 | IIRM-10737 | Bug | IIRM: MIR Report Displays Inception Premium as Basic Premium in "Critical Issues Needing Your Immediate Attention" Section | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7883 | IIRM-10738 | Bug | IIRM: MIR Report Displays Duplicate Entries for the Same Policy Type in "Critical Issues Needing Your Immediate Attention" Section | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7884 | IIRM-10739 | Bug | IIRM: Past Generated Reports Do Not Reflect Updated Lead CRM for Existing Company | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7885 | IIRM-10740 | Bug | IIRM: MIR Report Allows Data Changes After Report Publication and Permits Report Generation for Current and Future Periods | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7886 | IIRM-10741 | Bug | IIRM: Credit and Debit Columns Are Displayed Empty in Cash Deposit Account Section | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7887 | IIRM-10742 | Bug | IIRM: Policy Extension Endorsements Are Incorrectly Counted as Pending in MIR Report Claims Documentation Section | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7888 | IIRM-10743 | Bug | IIRM: Claims Section in MIR Report Displays Incorrect Values for Received, Paid, and End of the Month Columns | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7889 | IIRM-10744 | Story | Enrolment Drive Report | Ready for QA | NithinKrishna Sirigiri |  | IIRM-776 — SOW#49 - HR Portal View
7890 | IIRM-10745 | Bug | IIRM: Portfolio Details Section Displays Incorrect Claim YTD Values in MIR Report | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7891 | IIRM-10746 | Bug | IIRM: Service Tracker Section in MIR Report Displays Incorrect Endorsement and Non-Health Claims Policy Counts | Done | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7892 | IIRM-10747 | Bug | IIRM: Our Service Tracker Section Displays Blank Values for MIR, Quarterly Meeting, Monthly Meeting, and Renewal Notice Services | Ready for QA | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7893 | IIRM-10748 | Bug | IIRM: Rejected MIR Notification Does Not Navigate to the Corresponding Report or Display Rejection Comments | Ready for QA | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7894 | IIRM-10749 | Story | My Client Portfolio | WORK IN PROGRESS | NithinKrishna Sirigiri |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7895 | IIRM-10750 | CR - Story | My Client Portfolio - VRK Feedback (23-Jun-2026) | QA Verified | NithinKrishna Sirigiri | iWork | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7896 | IIRM-10751 | QAlity Test | Verify Access control — only the Lead CRM (company owner) can generate MIR; unauthorised users see validation message; ownership transfer updates access | EXTERNAL REVIEW PENDING | Prathiphala Kandula
7897 | IIRM-10752 | QAlity Test | Verify MIR generation — navigate to form, generate for new company, duplicate report validation, and verify Post Generated Reports list | EXTERNAL REVIEW PENDING | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7898 | IIRM-10753 | QAlity Test | Verify Policy table, Ince. Premium calculation, Portfolio details and policy count updates after approval/publish | EXTERNAL REVIEW PENDING | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7899 | IIRM-10754 | QAlity Test | Verify Renewals due in 3 months, Claims table and Claim Documentation table — data accuracy and completeness | EXTERNAL REVIEW PENDING | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7900 | IIRM-10755 | QAlity Test | Verify MIR status flow — both flows (Reject back to Draft and Approve to Published) work correctly with correct status transitions | EXTERNAL REVIEW PENDING | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7901 | IIRM-10756 | QAlity Test | Verify Edit, Reject flow and authorisation — only Draft reports editable; reject includes mandatory comment; unauthorised user cannot edit; text fields saved in draft state | EXTERNAL REVIEW PENDING | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7902 | IIRM-10757 | QAlity Test | Verify Head Count, CD Account and Service Tracker tables — data accuracy and column verification | Draft | Prathiphala Kandula
7903 | IIRM-10758 | QAlity Test | Verify Policy Insurer details, Renewal dates match and View functionality in Past Generated Reports | EXTERNAL REVIEW PENDING | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7904 | IIRM-10759 | QAlity Test | Verify Head Count, CD Account and Service Tracker tables — data accuracy and column verification | EXTERNAL REVIEW PENDING | Prathiphala Kandula |  | IIRM-758 — SOW#31 - MIR Entry Mgmt. (Monthly Information Report)
7905 | IIRM-10760 | QAlity Test | Verify MIR Notifications — correct person notified on each status event via both Email and In-App channels; no notification sent to wrong recipient | EXTERNAL REVIEW PENDING | Prathiphala Kandula
7906 | IIRM-10761 | Bug | Prod: Manage SO: Incorrect Activity Name is displayed when navigating from the SO funnel | Open | Leela Pakalapati |  | IIRM-740 — SOW#13 - Add/Manage Opportunity
7907 | IIRM-10762 | Bug | Dashboard Enhancement issues | Reopen | Leela Pakalapati |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7908 | IIRM-10763 | Sub-task | KPI should display. Endorsment TAT, Claims TAT, Service score trend line month-wise, KPI trend graph | Draft | Leela Pakalapati |  | IIRM-10750 — My Client Portfolio - VRK Feedback (23-Jun-2026)
7909 | IIRM-10764 | CR - Story | IBP - Enrolment without Policy Configuration | Draft | NithinKrishna Sirigiri |  | IIRM-773 — SOW#46 - Enrolment Portal
7910 | IIRM-10765 | Task | VRK Feedback changes on the Dashboard | WORK IN PROGRESS | Leela Pakalapati |  | IIRM-751 — SOW#24 - Dashboard & Drilldowns
7911 | IIRM-10766 | QAlity Test | Verify Dependent Attribute setup — fields, Display Name default, Target Relation Category shows only Step 2 relations, Attribute Name column in template | Draft | Prathiphala Kandula
7912 | IIRM-10767 | QAlity Test | Verify Attribute Kind = Range — configure bands with min/max/premiums; verify correct band premium applied in Inception and Endorsement Step 2 stats | Draft | Prathiphala Kandula
7913 | IIRM-10768 | QAlity Test | Verify Attribute Kind = List — configure options with premiums; verify correct option premium applied in Inception and Endorsement Step 2 stats | Draft | Prathiphala Kandula
7914 | IIRM-10769 | QAlity Test | Verify Default premium fallback — when Attribute Name column is left empty, Policy Choices default premium is applied for that relation | Draft | Prathiphala Kandula
7915 | IIRM-10770 | QAlity Test | Verify Step 2 Net Premium and Gross Premium stats — correct totals when multiple relations have different bands/options and some have default premium | Draft | Prathiphala Kandula
7916 | IIRM-10771 | QAlity Test | Verify Edge cases — multiple Dependent Attributes, invalid band/option values, and Dependent Attribute applied to multiple relations | Draft | Prathiphala Kandula
7917 | IIRM-10772 | QAlity Test | Verify Edge cases — multiple Dependent Attributes, invalid band/option values, and Dependent Attribute applied to multiple relations | Draft | Prathiphala Kandula
7918 | IIRM-10773 | Bug | IIRM: Net Premium Is Calculated Incorrectly When Dependent Attribute Premium Is Applied During Inception | Done | Prathiphala Kandula |  | IIRM-6827 — Manage Policy
7919 | IIRM-10774 | Bug | IIRM: Inception Job Fails Instead of Generating Error File When Invalid Dependent Attribute Name Is Configured | Done | Prathiphala Kandula |  | IIRM-6827 — Manage Policy
7920 | IIRM-10775 | Bug | IIRM: Inception Template Displays Multiple Dependent Attribute Columns for Multiple Dependent Attribute Parameters | Done | Prathiphala Kandula
7921 | IIRM-10776 | Bug | IIRM: Inception Template Does Not Display Attribute Name Column for Configured Dependent Attribute | Done | Prathiphala Kandula
7922 | IIRM-10777 | Bug | IIRM: Service Score Table Displays "0" Instead of "--" for Empty Score Values | Done | Prathiphala Kandula
7923 | IIRM-10778 | Bug | IIRM: Service Score Displays Incorrect Meeting Data for Monthly, Multilateral, and Quarterly Meetings | Reopen | Prathiphala Kandula
7924 | IIRM-10779 | Bug | IIRM: Service Score UI Does Not Display Meeting Completed Date, MIR Published Date, and QCR Generated Date | Done | Prathiphala Kandula
7925 | IIRM-10780 | QAlity Test | Cut-Off: Verify the placement slip cut-off is calculated correctly in the background, only the planned date is shown in the UI, and placement slips with no planned date are not restricted | Draft | Leela Pakalapati
7926 | IIRM-10781 | QAlity Test | Cut-Off: Verify a placement slip finished on time is accepted, and one finished late is blocked with the correct message | Draft | Leela Pakalapati
7927 | IIRM-10782 | QAlity Test | Cut-Off: Verify the cut-off is enforced to the exact minute in India time and is not moved for weekends or holidays | Draft | Leela Pakalapati
7928 | IIRM-10783 | QAlity Test | Cut-Off: Verify Income Month is set correctly for on-time, late-without-override, and late-with-override placement slips | Draft | Leela Pakalapati
7929 | IIRM-10784 | QAlity Test | Cut-Off: Verify the placement slip date can be typed manually in ISG Planning activity with no restriction (known limitation) | Draft | Leela Pakalapati
7930 | IIRM-10785 | QAlity Test | Cut-Off: Verify endorsement window and cut-off are calculated and shown, and late submissions are accepted into the next month's cycle | Draft | Leela Pakalapati
7931 | IIRM-10786 | QAlity Test | Cut-Off: Verify an authorised admin can change the endorsement end date (cut-off follows and is logged), but an unauthorised user cannot | Draft | Leela Pakalapati
7932 | IIRM-10787 | QAlity Test | Cut-Off: Verify a manager can open an override with a reason, it unblocks the placement slip and books it to the correct month, and the manager can see the person's past blocked attempts | Draft | Leela Pakalapati
7933 | IIRM-10788 | QAlity Test | Cut-Off: Verify only allowed people can open an override, and only once per person per cycle | Draft | Leela Pakalapati
7934 | IIRM-10789 | QAlity Test | Cut-Off: Verify the override closes automatically at the end of its window, can be closed early, and never changes any dates | Draft | Leela Pakalapati
7935 | IIRM-10790 | QAlity Test | Cut-Off: Verify only the Super Admin can change settings, changes apply only to new records, the buffer is shared, and the on/off switches work | Draft | Leela Pakalapati
7936 | IIRM-10791 | QAlity Test | Cut-Off: Verify reports(Biz done) group records by the correct month/cycle and older pre-feature records are unaffected | Draft | Leela Pakalapati
7937 | IIRM-10792 | QAlity Test | Cut-Off: Verify override actions, date changes, and setting changes are recorded and cannot be edited or deleted | Draft | Leela Pakalapati
7938 | IIRM-10793 | QAlity Test | Cut-Off: Verify past business can always be entered, late entries book to the current month, and data entry is never blocked | Draft | Leela Pakalapati
7939 | IIRM-10794 | QAlity Test | Cut-Off: Verify the go-live grace period, the protection of closed months, the gradual rollout stages, and the manager heads-up | Draft | Leela Pakalapati
7940 | IIRM-10795 | QAlity Test | Cut-Off: Verify reminder and override emails are sent to the right people | Draft | Leela Pakalapati
7941 | IIRM-10796 | QAlity Test | Cut-Off: Verify managers cannot open overrides until the override permission is assigned, and can once it is | Draft | Leela Pakalapati
7942 | IIRM-10797 | Bug | IIRM: Net Premium Statistics Display Incorrect Value When Deleting Dependents with Dependent Attributes in Proration-Enabled Policy | Open | Prathiphala Kandula
7943 | IIRM-10798 | Bug | IIRM: Dependent Attribute Premium Is Not Deducted from Net Premium Statistics When Deleting Self in Proration-Enabled Policy | Open | Prathiphala Kandula
7944 | IIRM-10799 | Story | Application - Performance (Database & Infra) | Draft | NithinKrishna Sirigiri |  | IIRM-749 — SOW#22 - Data Security (NFR)
7945 | IIRM-10800 | Bug | IIRM: Dependent Attribute Premium Is Not Applied for List-Type Dependent Attributes During Inception | Open | Prathiphala Kandula
7946 | IIRM-10801 | Bug | IIRM: Employee Enrollment Fails When Both Dependent Attribute and Dependent Count Are Configured in Policy | Open | Prathiphala Kandula
7947 | IIRM-10802 | Bug | System Admin Read User UI issues | Open | Leela Pakalapati
7948 | IIRM-10803 | Bug | System Admin Read – Data inconsistency between System Admin and System Admin Read users in Manage SO | Open | Leela Pakalapati
7949 | IIRM-10804 | Bug | IIRM: Service Score Company Dropdown Is Not Updated Based on Selected Owner in Dashboard | Ready for QA | Prathiphala Kandula
7950 | IIRM-10805 | Bug | IIRM: Approve Button Is Visible to Activity Submitter Despite Dual Approval Configuration | Open | Prathiphala Kandula |  | IIRM-735 — SOW#8 - 11 Components / Modules
7951 | IIRM-10806 | Bug | IIRM: Second-Level Approver Name Is Incorrectly Displayed as Lead CRM in Dual Approval Workflow | Open | Prathiphala Kandula |  | IIRM-735 — SOW#8 - 11 Components / Modules
7952 | IIRM-10807 | CR - Story | Dual Approval Process | QA Failed | NithinKrishna Sirigiri |  | IIRM-735 — SOW#8 - 11 Components / Modules
7953 | IIRM-10808 | Bug | IIRM: Incorrect Next Approver Displayed in ISG Activity Dual Approval Workflow | Open | Prathiphala Kandula |  | IIRM-735 — SOW#8 - 11 Components / Modules
7954 | IIRM-10809 | Bug | IIRM: Incorrect Approval Status Message Displayed for BD Executive in Parallel Dual Approval Workflow | Open | Prathiphala Kandula |  | IIRM-735 — SOW#8 - 11 Components / Modules
7955 | IIRM-10810 | Bug | IIRM: Lead CRM Cannot Approve ISG Activities When Configured as Approver 2 in Parallel Dual Approval Workflow | Open | Prathiphala Kandula |  | IIRM-735 — SOW#8 - 11 Components / Modules
7956 | IIRM-10811 | Bug | IIRM: Next ISG Activity Is Navigated After First Approval Instead of Waiting for Final Approval | Open | Prathiphala Kandula |  | IIRM-735 — SOW#8 - 11 Components / Modules
7957 | IIRM-10812 | Bug | Cut-Off: Placement Slip Planned Date is Considered as the Income Date | QA in Progress | Leela Pakalapati
7958 | IIRM-10813 | Bug | Cut-off: Activity Override Is Applied to the Entire Opportunity Flow Instead of the Selected Opportunity for the User | Reopen | Leela Pakalapati

## Helper (hidden)
Module | Phase | Status | Category | Bucket | ReqDate
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Pre-PROD | Pre-PROD / UAT | Pending | 45763
Framework | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
Framework | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending | 45818
Framework | Milestone 4 | Not in scope | Delivered | Delivered | 45818
DPDP | Milestone 4 | Yet to start | Not Started | Pending | 45818
Framework | Milestone 4 | Not in scope | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Yet to start | Not Started | Pending | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Yet to start | Not Started | Pending | 45818
Framework | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 45818
IBP/iWork | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending | 45818
iWork | Milestone 4 | Yet to start | Not Started | Pending | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
NFR | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 45818
IBP | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending | 45818
iWork | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 45869
IBP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 45869
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 45869
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 45869
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 45869
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 45869
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 45869
DPDP | Milestone 5 | DEV - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | DEV - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | DEV - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | DEV - Done | Dev Complete | Delivered | 45869
DPDP | Milestone 5 | DEV - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | DEV - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | DEV - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | QA - WIP | In QA | Pending | 45869
DPDP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
IBP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP/iWork | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
IBP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
IBP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
IBP/iWork | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
IBP | Milestone 5 | Not in scope | Delivered | Delivered | 45869
IBP | Milestone 5 | Not in scope | Delivered | Delivered | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP/iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP/iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
DPDP | Milestone 5 | DEV - WIP | In Development | Pending | 45869
NFR | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
NFR | Milestone 5 | Yet to start | Not Started | Pending | 45869
NFR | Milestone 5 | DEV - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46070
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46119
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46143
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46143
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46143
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46143
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46143
IBP - CR | Milestone 6 | Pre-PROD | Pre-PROD / UAT | Pending | 46150
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46150
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46150
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46163
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46167
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46167
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46170
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46174
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46176
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46178
iWork - CR | Milestone 6 | DEV - WIP | In Development | Pending | 46178
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46179
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Not a bug | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Not a bug | Delivered | Delivered | 46181
iWork | Milestone 6 | Pre-PROD | Pre-PROD / UAT | Pending | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46183
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46183
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46184
IBP/iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46184
IBP/iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46188
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46188
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46188
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46191
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46192
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46192
IBP | Milestone 6 | Yet to start | Not Started | Pending | 46194
IBP | Milestone 6 | DEV - WIP | In Development | Pending | 46194
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46195
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46195
IBP/iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46196
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46198
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46198
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46198
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46198
IBP/iWork - CR | Milestone 6 | DEV - WIP | In Development | Pending | 46204
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46204
IBP - CR | Milestone 6 | Delivered | Delivered | Delivered | 46206
IBP/iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46207
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46209
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46209
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46210
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46210
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46211
IBP/iWork | Milestone 6 | Yet to start | Not Started | Pending | 46212
IBP - CR | Milestone 6 | Delivered | Delivered | Delivered | 46213
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46214
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Not in scope | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46216
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46217
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46220
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46223
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46223
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46223
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46223
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46223
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46223
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46223
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46224
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46224
IBP | Milestone 6 | Yet to start | Not Started | Pending | 46224
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46225
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46226
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46226
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46226
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46226
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46226
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46227
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46227
IBP/iWork | Milestone 6 | Yet to start | Not Started | Pending | 46227
IBP/iWork | Milestone 6 | Pre-PROD | Pre-PROD / UAT | Pending | 46228
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46228
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46230
iWork | Milestone 6 | Pre-PROD | Pre-PROD / UAT | Pending | 46230
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46230
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46230
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46231
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46231
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46232
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46232
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46233
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46235
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46237
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46235
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork - CR | Milestone 6 | DEV - WIP | In Development | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46221
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
IBP | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46228
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46221
IBP | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46221
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork/IBP | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork/IBP | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork/IBP | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork/IBP | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46198
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46133
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46234
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
IBP/iWork | Milestone 6 | Yet to start | Not Started | Pending | 46217
IBP/iWork | Milestone 6 | Yet to start | Not Started | Pending | 46204
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46220
iWork/IBP | Milestone 6 | Yet to start | Not Started | Pending | 46132
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46132
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235

## Config (hidden)
Status_Raw | Category | Bucket
Delivered | Delivered | Delivered
Dev - Done | Dev Complete | Delivered
Dev - WIP | In Development | Pending
DEV - WIP | In Development | Pending
QA - WIP | In QA | Pending
Pre-PROD | Pre-PROD / UAT | Pending
Yet to start | Not Started | Pending
Delivered - Deficit | Partial Delivery | Pending
Duplicate | N/A | N/A
Not a bug | Delivered | Delivered
Not in scope | Delivered | Delivered