## iWork,IBP & Framework_SOW Items
Area | Feature | Functionality | Module | Phase | Status | Remarks | Requested Date | ETA | Resource
FRAMEWORK: Frontend | Project setup | Basic project / Development environment setup | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | UI Approach Design System | Building Design System | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Core Infrastructure | Core Infra | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Build UI components | This includes all the UI componnets to compose the application and module definitions: Form, Toast, Filter, Cards, Visualisation, Grid, Menu, Header, Footer, Maps Integration | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | UI Approach Style Establishment | UI Style Establishment | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Service Workers Implementation |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Core System |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | ACL & RBAC Control Framework |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Micro Frontend Setup |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Landing Page |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Services - Basic Modules | Access Control Management |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Services - Larger Modules | Auth Module (Simple Auth) |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Services - Larger Modules | Micro Service Framework Setup |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Employee Mgmt |  | iWork | Milestone 1 | Delivered | User deletion need to be handled | 2025-03-01 | 2026-06-12
iWORK: Common Components | Common - Audit Trail Mgmt - Becomes critical in this phase iteself |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Opportunity | Add Medium size form with 1->N list of Claims; Multiple drop downs Large View with several widgets, Simple Edit | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Manage TPA/Insurer | Basic Add, View with edit of basic data, with lists of policies/companies | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Core Infra | Infrastructure | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Company | Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. Simple edit like Add; View is multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Insurer/TPA Hub | List with Filter/Search | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Contact | Simple edit like Add Contacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Company (Prospect) Hub | Top 10/Latest companies, with search/filter, Table of basic attributes with GPS etc. | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Contact Hub | Top 10/Latest Contacts, with search/filter, list with basic attributes | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Opportunity Hub | Top Opportunities with search/filter, List of opportunities with high level summaries | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Contact /Company/Insurer/TPA Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Task Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Meeting Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | RBAC and ACL setup for Iwork Module |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Opportunity Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Master Data Management |  | Framework | Milestone 2 | Delivered |  | 2025-04-16 | 2026-05-27
FRAMEWORK: Frontend | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion | 2025-04-16 | 2026-06-12
FRAMEWORK: Services - Basic Modules | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion | 2025-04-16 | 2026-06-12
FRAMEWORK: Services - Larger Modules | Data Security Considerations |  | Framework | Milestone 2 | Delivered | Duplicate of Covers in DPDP items | 2025-04-16 | 2026-06-30
FRAMEWORK: Frontend | Visualization framework | Charts and KPIs | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Frontend | Document Management | Create, Upload, Seach, Download | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Frontend | Caching of API Data |  | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Services - Basic Modules | Audit Data Capturing |  | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Services - Larger Modules | CMS |  | Framework | Milestone 2 | Delivered | Used in IBP | 2025-04-16
FRAMEWORK: Services - Basic Modules | Notification and Communication Management |  | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Services - Basic Modules | Usage Tracking System (Reports) | 23-May: Handle as a part of Reports | Framework | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Common Data Mapping Component | Map input fields to output fields & Order | iWork | Milestone 2 | Delivered | Pending: Additional/Dynamic columns | 2025-04-16 | 2026-06-09
iWORK: AI Components | AI - (Non-OCR) Digital Document Processing for Content recognition (Company/Opportunity/Contact Creation from Previous Policy Document, Bizcard document) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: AI Components | AI - OCR for Content Collection |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: AI Components | AI - Company Information by AI Search |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Common Components | Common, Contexual Upload Component |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Common Components | Common, Contexual Read and Spread Component (Utility) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Manage Stage Planning/Performance/Approval | Add iWork Stages (table) - Dates with each iWork Stage and who are the team members assigned to each Stage; Once all iWork stages are complete, ISG Team activities must be planned ISG Team can approve/reject each iWork Stage. Approving RFP Stage approves all iWork stages Completion of each iWork Stage (Activity) & ISG Stage - Comments, Attach Document, Date recorded, submit | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Smart Add Component | Allow Upload of Document/Image, select what to create (Company/Contact/Opportunity) | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Dashboard - Drilldowns | Drill down from the Tables (Targets vs. Actuals, Pending Activities, Followups, AR Report, Schedule) | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Sales Team Hierarchy | Hierarchy / Org chart tied to Platform Users | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | View Policy | Long View, multiple widgets/entities, endorsements (each month), Claims, etc. | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Dashboard | Multiple KPI Cards: Business Performance, Svc Performance, Table of targets vs. actuals vs. lost, Sales Funnel, Renewal Funnel, Servce Funnel, AR from Insurers, Pending Activities(iWork Stages) Widget, Followups widget, Meetings widget Filters available (Geo, Branch, Team/Team Member, Dates), Approvals, iWork Stages, Tasks, Meetings | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Dashboard - Pending tasks, approvals | Pending tasks/approvals, | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Reports - Biz Done | Report View, Download, List of earlier snaps of the report, Search and Filter | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Core Infrastructure | Core Infra | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Organisation, Branch, Employee, & Hierarchy Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Dashboard (Place Holder) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Planning, Perform and Approval Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Policy Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Master Data Mgmt {Common, Contexual Master Data Mgmt} |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Cut Off Mgmt |  | iWork | Milestone 2 | Yet to start |  | 2025-04-16 | 2026-07-17 | Karan
FRAMEWORK: Services - Larger Modules | Document Generation |  | Framework | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Cover Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16 | 2026-06-10 | Karan
iWORK: Frontend | Manage Policy (Endorsements) | Add Endorsement - basic form with uploads of excel/document Validations of endorsement format - Map customer fields to internal fields Map internal fields to TPA fields (occasional per TPA) View/Update Endorsement, List View, Endorsement Performance | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Stage Mgmt (Activity/Transaction/Quote) |  | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Asset/Member Data Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Endorsement Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Frontend | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | iWork | Milestone 3 | Pre-PROD |  | 2025-05-16 | 2026-07-15 | Sunil
iWORK: Services - Basic Modules | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | iWork | Milestone 3 | Pre-PROD |  | 2025-05-16 | 2026-07-15 | Sunil
FRAMEWORK: Services - Larger Modules | Workflow Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-07-24 | Nithin
FRAMEWORK: Frontend | Notifications Management | Different email notification - Madhav excel. 1. Renewal Reminders - ASAP 2. Instalment Reminders 3. Others......... | Framework | Milestone 4 | Delivered - Deficit |  | 2025-06-10 | 2026-07-17 | Jagadeesh
FRAMEWORK: Services - Basic Modules | Configuration Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Services - Basic Modules | Feature Flag Control Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Services - Larger Modules | Localistation Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Services - Larger Modules | Caching Implementation |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Services - Larger Modules | Rule Definition Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-07-24 | Jagadeesh
Framework | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | IBP | Milestone 4 | Pre-PROD | Fine tuning the API's where there is a delay | 2025-06-10 | 2026-07-17 | Akhila
iWORK: Services - Basic Modules | TPA Integration Mgmt [Framework] | 1. Framework in iWork 2. Validate the integration for the existing 6 TPA's | IBP/iWork | Milestone 4 | Dev - WIP |  | 2025-06-10 | 2026-07-17 | Ravi
iWORK: Services - Basic Modules | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | DPDP | Milestone 4 | Yet to start | Duplicate of Archival from NFR & DPDP | 2025-06-10 | 2026-07-15 | Rama
IBP: Services - Larger Modules | IBP - User Management | IBP: HR Portal - Company-Scoped Employee Access for Client HR (Ex. TeamLease's Customer) | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-05-26
IBP: Services - Larger Modules | IBP - Portal Setup | Post policy creation, create default IBP Portal Config for all the company-policy(ies) | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-19 | Manjusha
IBP: SERVICES - Basic Modules | Personal Profile Mgmt | Profile settings | IBP | Milestone 4 | Delivered | Pending:Add Dependents | 2025-06-10 | 2026-06-10 | Manjusha
IBP: FRONTEND | HR Portal View | Employee Search, Resend Email, Delete Employees, Extend Enrollment Windows, Reports, Bulk Email | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-11 | Abhilash
IBP: Common Components | Simple Auth | Username and Password based authentication and RBAC on simple-auth users. Auth rules needs configuration capability. IBP - HR User Management | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-12 | Abhilash
IBP: FRONTEND | My Documents | Document Hub - Covers Policies, Prescriptions, Reports | IBP | Milestone 4 | Delivered | Pending: Design | 2025-06-10 | 2026-06-12 | Manjusha
IBP: SERVICES - Basic Modules | Document Mgmt for End User | Insurance, Health Reports and Prescriptions {No automatic pull from Partners} | IBP | Milestone 4 | Delivered | Pending: Design | 2025-06-10 | 2026-06-12 | Manjusha
Framework | NFR_Usability | NFR-USA-018: The session management should be configurable from UI 23-May: Configure from UI & store in DB; When changed then restart server | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-15 | Manjusha
IBP: FRONTEND | Policy Document | IBP-Risk Watch: Show the each policy document | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-19 | Tharun
Framework | NFR_Usability | NFR-USA-015: The system must show personalized welcome messages and profile information based on locale. | IBP | Milestone 4 | Delivered |  | 2025-06-10
Framework | NFR_Usability | NFR-USA-016: Notification banners must be dismissible and configurable based on role. | IBP | Milestone 4 | Delivered | No notifications in IBP | 2025-06-10
IBP: Common Components | Whitelabelling Support |  | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Company Plans | 6 Policies - GMC, GPA, GTL, Parental Plicy, Top-ups, OPD Policy (Summary view of policies) | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | IBP Landing Page - Basic | Basic Landing Page with only company plans and summart | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Contact Matrix View | Contact Matrix View for end user | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Core Infrastructure | Core Infra | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Per-policy Enrolment | Enrolment and addon policy selection | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | My Insurance | Part-1: Hub of all plans I have as an employee - Company provided. Mostly a navigational page | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Basic Modules | Basic Landing Page Services | Company provided plans only | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment | Enrollment (Adding Dependents, Choosing Options available). Submit the enrollment to Insurer or TPA 6 Types of Policies to be considered | IBP | Milestone 4 | Delivered | Need Confirmation: If scope has, Insurer & TPA integrations, then they are pending | 2025-06-10
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment Configurator | Enrollment Configurator (Set of benefits and type of Dependent combinations allowed etc). This is more of an Iwork feature to configure the policy | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | End User onboarding | Generate Users, Send Emails, Password Rest | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | Contact Matrix Configuration | Matrix of Contact Infomration | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | HR/Admin Portal View | Supporting services for Admin Portal | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | Admin Reports | Services for multiple reports | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-10 | Abhilash
FRAMEWORK: Frontend | Localisation |  | Framework | Milestone 4 | Delivered - Deficit | Pending: Service Flow Pending: IBP | 2025-06-10 |  | Tharun
iWork: Services - Basic Modules | Client - Associated Location (IBP HR Module) | IBP - HR: Policy Location - Add Company Associated Locations, Flow to Opty., Policy & Policy Config | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Karan
IBP: FRONTEND | Company Plan Configurator | Admin side of IBP should configure (per Corporate) how to define a Policy and determine how it breaks down the Premium and Coverage rules | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Auth Config UI | Config for Auth Rules setup | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Contact Matrix | Configure the Conact Info Matrix (IBP Admin) | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Whitelabelling | Whitelabelling based on Org needs (IBP Admin) | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
| Policy Component - Strapi | IBP Portal - Each card should have seperate points & Policy feature documents | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Manjusha
FRAMEWORK: Frontend | Accessibility |  | Framework | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-07-24
iWORK: Frontend | View Service Score | Servicing Stats Dashboard - Single Table (drillable) to calculate an overall score | iWork | Milestone 4 | Delivered - Deficit | Pending: Meeting, MIR calculation | 2025-06-10 | 2026-07-15 | Sunil
iWork: Services - Basic Modules | Reports - Biz Done | Bizonde filter/table - Add "Income type" | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Karan
iWork: Services - Basic Modules | Opportunity | Opportunity History details are unavailable for the end user to view. Show TAT section (Planned date, Performed/Completed date, Approved date) for planned acitivites | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Pushyami
iWork: Services - Basic Modules | Endorsement Mgmt | Additional columns in file like Department, DOJ, Emp. Location, Vertical, Others | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Pushyami
iWork: Services - Basic Modules | Opportunity | RO Scheduler Enhancements | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Jagadeesh
iWORK: Frontend | Knowledge Central | Grouped list of Documents/Resources, Add a Document, Remove a Document (Add/remove only for admins) | iWork | Milestone 4 | Delivered |  | 2025-06-10
iWORK: Services - Basic Modules | Knowledge Central |  | iWork | Milestone 4 | Delivered |  | 2025-06-10
iWORK: Services - Basic Modules | TAT/SLA Mgmt (Including Service Score) |  | iWork | Milestone 4 | Delivered |  | 2025-06-10
iWORK: Services - Basic Modules | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | IBP/iWork | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-07-24
iWork: Services - Larger Modules | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | iWork | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-07-24 | Rama
Framework | NFR_Security | DPDP NFR | NFR | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-07-17 | Tharun
Framework | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | NFR | Milestone 4 | Delivered - Deficit | Pending: Provide the document on how do we store and view it | 2025-06-10 |  | Jagadeesh
IBP: Services - Larger Modules | Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-07-02 | Ravi
Framework: DPDP | Enable SAST |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-15
Framework: DPDP | Integrate SSO / MFA |  | DPDP | Milestone 5 | Dev - Done |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Capture consent within app |  | DPDP | Milestone 5 | Dev - Done |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Allow easy consent withdrawal |  | DPDP | Milestone 5 | Dev - Done |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Approval workflow |  | DPDP | Milestone 5 | Dev - Done |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Show privacy notice with purpose, retention, rights |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-24
Framework: DPDP | App vulnerability scans |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Document Flows |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Perform security UAT |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Enforce business logic to restrict purpose |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Remove unnecessary fields |  | DPDP | Milestone 5 | Dev - Done |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Map PII tables |  | DPDP | Milestone 5 | QA - WIP |  | 2025-07-31
Framework: DPDP | Enable delete pipeline |  | DPDP | Milestone 5 | Yet to start |  | 2025-07-31
Framework: DPDP | Allow user corrections |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Delete expired data |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Sign DPDP clauses |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-24
Framework: DPDP | Define archival |  | DPDP | Milestone 5 | Yet to start |  | 2025-07-31
Framework: DPDP | Quarterly restore tests |  | DPDP | Milestone 5 | Pre-PROD |  | 2025-07-31
IBP: Common Components | 3rd Party SSO | Props based SSO links to 3rd Parties | IBP | Milestone 5 | Delivered | SSO Framework implemented fro TPA | 2025-07-31 | 2026-06-01 | Abhilash
IBP: SERVICES - Basic Modules | Hospital Network Mgmt | Based on the Insurer and TPA, network of hospitals needs to be presented in a consolidated view | IBP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-11
IBP: FRONTEND | Static Info Sections - Landing | Benefits Guide, FAQs, Help | IBP | Milestone 5 | Delivered |  | 2025-07-31
IBP: FRONTEND | Initiate Claim | Initiate claim for GMC (non-cashless), upload docs etc. | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations | 2025-07-31
IBP: FRONTEND | Claims Corner | View Claim Data for Individual Plans (if available), Track Status for Claims initiated from IBP for Group Plans, Track Status for Claims initiated with TPA directly, TAT reporting for Cashless (for Preauth and Discharge) | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations | 2025-07-31
IBP: Services - Larger Modules | Claims Mgmt | Part-1: Company Provided Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Delivered |  | 2025-07-31
IBP: FRONTEND | Profile Migration | Request migration of Corporate Profile to Individual | IBP | Milestone 5 | Yet to start |  | 2025-07-31 |  | Abhilash
IBP: FRONTEND | Profile Migration | Request migration of Individual Profile to Corporate | IBP | Milestone 5 | Yet to start |  | 2025-07-31 |  | Abhilash
IBP: SERVICES - Basic Modules | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | IBP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-21 | Manjusha
IBP: Services - Larger Modules | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | IBP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-21 | Ravi
IBP: SERVICES - Basic Modules | Feedback Mgmt | User Feedback capture service | IBP | Milestone 5 | Delivered | IBP support is already in place | 2025-07-31
IBP: Services - Larger Modules | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | IBP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-22 | Abhilash
IBP: FRONTEND | Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | IBP | Milestone 5 | Delivered - Deficit | Pending: Offers & Discuounts | 2025-07-31 | 2026-07-24 | Manjusha
IBP: FRONTEND | User Profile | Profile, Service Subscriptions, Feedback | IBP | Milestone 5 | Delivered - Deficit | Pending: Service Subscriptions, Feedback | 2025-07-31 | 2026-07-24 | Ravi
IBP: FRONTEND | IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | IBP | Milestone 5 | Delivered |  | 2025-07-31
IBP: Services - Larger Modules | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-23 | Manjusha
IBP: Services - Larger Modules | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | IBP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-23 | Ravi
IBP: Services - Larger Modules | Evexia Club Integration | Integration to Evexia | IBP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-24 | Abhilash
IBP: Services - Larger Modules | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | IBP | Milestone 5 | Delivered - Deficit | Pending: Offer, Feature flagging (UI) | 2025-07-31 | 2026-07-24 | Manjusha
IBP: FRONTEND | Book Ambulance | Floater on the screen - Integrate to Ambulance Service | IBP | Milestone 5 | Yet to start |  | 2025-07-31
IBP: FRONTEND | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | IBP | Milestone 5 | Yet to start |  | 2025-07-31
IBP: Services - Larger Modules | Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | IBP | Milestone 5 | Yet to start |  | 2025-07-31
iWORK: Services - Basic Modules | TPA Integration Mgmt [GHPL] | Launch TPA - SSO Ecards API - Read & View Details Hospital Network Claims Status API - Read, Store & View Details Claim Intimation API Claim Live Status - Single Claim | IBP/iWork | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-12 | Ravi
IBP: FRONTEND | IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | IBP/iWork | Milestone 5 | Delivered |  | 2025-07-31
IBP: Services - Larger Modules | Core Infrastructure | Core Infra | IBP/iWork | Milestone 5 | Delivered - Deficit | Pending: Mobile responsive | 2025-07-31 | 2026-07-17 | Velangini Raju
IBP: FRONTEND | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | IBP/iWork | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-24 | Ravi
IBP: FRONTEND | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | IBP/iWork | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-24 | Ravi
iWORK: Frontend | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) Similar to TPA API Integration Framework for any 3'rd Party | iWork | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-17
iWORK: Frontend | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | iWork | Milestone 5 | Yet to start | Need inputs from Kapil | 2025-07-31
iWORK: Services - Basic Modules | Reconciliation Mgmt |  | iWork | Milestone 5 | Yet to start |  | 2025-07-31
iWORK: Services - Basic Modules | Insurer Integration Mgmt | Can be used as a part of External API Intergration | iWork | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-17
iWORK: Frontend | Claim Management (Add Claim, Import Claims & Claim Activities) | Basic Form with fields and upload for adding claim Bulk import to validate and map from TPA format to internal fields 3 stage workflow - each stage, update data on claim form | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | Report Hub | Landing Page and generic hub | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | CD Creation | Show current CD Balance against pooled/individual policies / Allow new CD creation, update CD balance and map policies to CD balances | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | CD Mgmt |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | Reports |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | Claim Mgmt |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | iWork | Milestone 5 | Delivered - Deficit |  | 2025-07-31 | 2026-07-24
iWORK: Services - Basic Modules | HRMS Integration Mgmt | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? HRMS - integrations with enrolment portal (POC - with Zoho People), client mentioned that they have already integrated MB360 for HCL IBP & HRMS Integration - HCL | iWork | Milestone 5 | Yet to start |  | 2025-07-31
Framework: NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | NFR | Milestone 5 | Yet to start | Discussed this with Surya sir last visit to Divami office | 2025-07-31
Framework: NFR | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure, which was broad symptom rather than a root cause. The renewed focus here is on failures related to cryptography which often leads to sensitive data exposure or system compromise. |  | NFR | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-05
Framework: NFR | NFR-COM-019: Terms and Conditions: The application must ensure require the customer to accept the Terms & Conditions at the first login to the application. This ensures compliance with PII regulations requiring Company group to inform the user of why Company is accessing/collecting personal data and why Company is using it. IIRM-4480 |  | NFR | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-05
IBP: FRONTEND | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | IBP | Milestone 5 | Yet to start | Retail insurance(facility to load user insurance policies) | 2025-07-31 |  | Ravi
IBP: FRONTEND | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | IBP | Milestone 5 | Yet to start | wellness | 2025-07-31 |  | Manjusha
IBP: FRONTEND | Wellness HR View | HR View of Wellness usage by Employees | IBP | Milestone 5 | Yet to start | wellness | 2025-07-31 |  | Manjusha
IBP: FRONTEND | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | IBP | Milestone 5 | Yet to start | wellness | 2025-07-31 |  | Manjusha
IBP: FRONTEND | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | IBP | Milestone 5 | Yet to start | Pending: Retail insurance | 2025-07-31 |  | Ravi
IBP: FRONTEND | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | IBP | Milestone 5 | Yet to start | Pending: Retail insurance | 2025-07-31 |  | Ravi
IBP: SERVICES - Basic Modules | Benefits Summary | End User's Summary View | IBP | Milestone 5 | Delivered - Deficit | Pending: Retail Insurance | 2025-07-31 | 2026-07-24 | Ravi
IBP: Services - AI Components | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | IBP | Milestone 5 | Yet to start | External chatbot integration? | 2025-07-31 |  | Abhilash
iWork & IBP | InsureEasy | InsureEasy Integration - Retail Business | IBP | Milestone 5 | Yet to start |  | 2026-06-25
| Cover Mgmt | Asset fields which are captured at Broking slip, few of the asset fields should not be printed at the time of Placement slip (example, no of members at inception, total lives, prev policy expiring year etc.) only for GMC | iWork - CR | Milestone 6 | Delivered |  | 2026-02-17 | 2026-06-25 | Karan
| Policy Configuration | DNV Group - Dependent based SI & Premium configuration | iWork - CR | Milestone 6 | Dev - WIP |  | 2026-04-07 | 2026-07-15 | Jagadeesh
| Policy Configuration | Premium Rater Table | iWork - CR | Milestone 6 | Yet to start |  | 2026-04-21 |  | Jagadeesh
| VRK - PROD Feedback | Manage Insurer - Add Insurer Flow | iWork | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-09 | Pushyami
| VRK - PROD Feedback | Opty. Flow - Add new Insurer Branch Details | iWork | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-12 | Pushyami
| Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | iWork - CR | Milestone 6 | Delivered |  | 2026-05-01 | 2026-07-09 | Karan
| Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | iWork - CR | Milestone 6 | Yet to start |  | 2026-05-01 |  | Sunil
| Insurer Management | Enhance Insurer - Add, Edit, & Contacts | iWork - CR | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-09 | Pushyami
| Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | IBP - CR | Milestone 6 | Pre-PROD |  | 2026-05-08 |  | Abhilash
| Policy Configuration | Using AI - Extract the Policy document and perform Policy Configuration (Premium, Family, Parameters, & Others) | iWork - CR | Milestone 6 | Delivered |  | 2026-05-08 | 2026-07-01 | Jagadeesh
| Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | iWork - CR | Milestone 6 | Yet to start | Need some information about the document rules that defines the idenity of it | 2026-05-08
| Endorsement Mgmt (Non-Group / Non-GMC / Non-EB) | Enhance the Non-GMC Process (Based on Kishore feedback) | iWork - CR | Milestone 6 | Delivered |  | 2026-05-21 | 2026-05-28 | Pushyami
| Endorsement Mgmt | PROD Bug: Data Discrepancy - Inception/Endorsement vs Send to Client/Insurer (Preview & Excel) | iWork | Milestone 6 | Delivered |  | 2026-05-25 | 2026-05-27 | Prathiphala
| Endorsement Mgmt | PROD Bug: When download the TPA file, dependents are Missing in the file | iWork | Milestone 6 | Delivered |  | 2026-05-25 | 2026-05-27 | Sunil
| IIRM-10587 | Add new fields - Business Month & Date of Business - Capture in Opty. & Flow to Policy and add filters in BizDone --> Refer to Madhav email "Business Month Requirement" | iWork | Milestone 6 | Delivered | Pending: Additional filters | 2026-05-28 | 2026-07-02 | Sunil
| End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | IBP/iWork | Milestone 6 | Yet to start |  | 2026-06-01 | 2026-07-28 | Abhilash
| IIRM-10591 | IBP - Enrolment Journey - Reset | IBP | Milestone 6 | Delivered |  | 2026-06-03 | 2026-06-09 | Abhilash
| VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | iWork | Milestone 6 | Delivered |  | 2026-06-05 | 2026-06-08
| SSO - MS AD Account | iWork - SSO with Microsoft AD (POC) | iWork - CR | Milestone 6 | Delivered | Showed Demo to Venu | 2026-06-05 | 2026-06-10 | Rama
|  | Based on recent billing - Identifying the gaps in Redis data storage and gaps in implementation | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-06 | 2026-06-08 | Tharun
| VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
| IIRM-10588 | Hide "Manage Policy" in "Manage Placements" link. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-09 | Pushyami
| VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-09 | Karan
| VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-10
| VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-12 | Karan
| VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-12
| VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-19 | Rama
| VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-24
| VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | iWork | Milestone 6 | Delivered |  | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | iWork | Milestone 6 | Not a bug | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-30 | Jagadeesh
| VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-07-02
| VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | iWork | Milestone 6 | Not a bug |  | 2026-06-08
| VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09
| VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 | Pushyami
| VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 | Pushyami
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 | Pushyami
| VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 | Pushyami
| VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 | Prathiphala
| VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 | Jagadeesh
| VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 | Jagadeesh
| VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-12 | Prathiphala
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 | Karan
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 | Karan
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 | Karan
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 | Karan
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-16
| VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-19 | Karan
| VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | iWork | Milestone 6 | Yet to start |  | 2026-06-09 | 2026-07-24
| Risk Watch - Endorsement - Documents & Communication | Risk Watch - Endorsement - Documents & Communication | IBP | Milestone 6 | Delivered |  | 2026-06-10 | 2026-07-01 | Abhilash
| Wellness Banner & SSO | Add banner and SSO to Alyve Wellness (Only Banner) | IBP | Milestone 6 | Delivered |  | 2026-06-10 | 2026-06-10
| Security | InfoSec - IBP Portal (Security Issue) | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-11 |  | Manjusha
| IIRM-10590 | Policy Config: Dependent Based Configurations - Per life depedent addition & increase SI - Apply Policy Parameters for dependents | iWork | Milestone 6 | Delivered |  | 2026-06-11 | 2026-06-15 | Jagadeesh
| Policy Config | New Policy constraints 1. Allow first child as Twin 2. Allow second child as Triplet 3. SI per Dependent 4. Parent Lock-in period | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-15 | 2026-06-16
PROD-Bug | Export to Excel | Export to excel - iWork all the results table; Download is on Previlage | iWork | Milestone 6 | Yet to start |  | 2026-06-15
| IIRM-10667 | iWork - Knowledge Central Re-Design | iWork | Milestone 6 | Yet to start |  | 2026-06-15
| IIRM-10668 | iLearn: Document Preview in-app | iWork | Milestone 6 | Yet to start |  | 2026-06-15
2026-06-19 | Discuss with Madhav | Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard) Also, check if we are there are any data loads for 2025-26 | iWork | Milestone 6 | Yet to start |  | 2026-06-15
|  | Dashboard - Hide the widgets where there is NO data in the cards | iWork | Milestone 6 | Delivered |  | 2026-06-15 | 2026-07-10
| Installment & Fee Requirements | Installments & Fee to BizDone | iWork | Milestone 6 | Yet to start |  | 2026-06-15
| Rewards | Rewards - Generic (Specific - Out of scope) | iWork | Milestone 6 | Delivered |  | 2026-06-18 | 2026-07-01 | Karan
|  | Risk Watch: Showing policy feature documents at each policy | IBP | Milestone 6 | Delivered |  | 2026-06-19 | 2026-06-19 | Ravi
| Wellness | IBP Portal Configure - Wellness - Buttons, CMS, & any other - Flag Driven | IBP | Milestone 6 | Delivered |  | 2026-06-19 | 2026-06-22 | Manjusha
| Claims Corner | Claims Corner - Screen Re-design | IBP | Milestone 6 | Dev - WIP |  | 2026-06-21 | 2026-07-28 | Ravi
| IIRM-10666 | IBP - Policy Component Card Re-design | IBP | Milestone 6 | Yet to start |  | 2026-06-21 | 2026-07-28 | Manjusha
| Risk Watch - Enrolment Drive | Risk Watch - List view to see the list of enrolment dritve | IBP - CR | Milestone 6 | Delivered |  | 2026-06-22 | 2026-07-10 | Ravi
| Claims Process | Process claims without TPA ID (GPA & GTL - flag based) | iWork - CR | Milestone 6 | Delivered |  | 2026-06-22 | 2026-07-01 | Jagadeesh
| Teamlease - Request | Flexibility to configure multiple companies & policies on a single domain | IBP/iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 | Abhilash
| VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-07 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-14 | Karan
| VRK - PROD Feedback: 23-Jun-2026 | Additional section display: Placement Funnel, Schedule, Followup | iWork - CR | Milestone 6 | Yet to start |  | 2026-06-23 | 2026-07-16 | Pushyami
| VRK - PROD Feedback: 23-Jun-2026 | Dashboard - Filter & drill-down | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-14 | Karan
| VRK - PROD Feedback: 23-Jun-2026 | iWork and iTicket should be accessible via VPN | iWork - CR | Milestone 6 | Yet to start |  | 2026-06-23 |  | Pushyami
| BizDone | Computed value & Reported values * Computed values - It’s the real-time values base on Policy inception/endorsement * Reported values - It’s validated by the mgmt. and share this number to update in the column. * Reported value MUST be used for the Dashboard & BizDone, which was declared by the company to public. * In the admin a feature to update the Reported values from the computed values * Legacy data - Premiums, Brokerage, CD Balance | iWork - CR | Milestone 6 | Yet to start |  | 2026-06-25
| AI | Wherever AI is implemented, there should be fallback if one day we turnoff AI then there shouldn’t be any impact in the working functionality | iWork | Milestone 6 | Yet to start |  | 2026-06-25 |  | Rama
| AI | AI Nudges are NOT working. If there is NO AI, then DB scripts should run and show data | iWork | Milestone 6 | Yet to start |  | 2026-06-25 |  | Rama
| Inception/Endorsement | Endorsement data upload related * Track-1: TeamLease - 2024-2025 Year policies * All endorsement -> Headers, Member data, & endorsement Document * Track-2: Old Financial data * Track-3: Current Financial data * Track-4: Handle the data in IBP-Risk Watch | iWork | Milestone 6 | Dev - WIP |  | 2026-06-25 |  | Rama
| IBP - Raise Ticket | Edit the ticket and update the status by the Lead CRM & System Admin | IBP/iWork | Milestone 6 | Yet to start |  | 2026-07-01 | 2026-07-27 | Manjusha
| One URL multiple companies | Flexibility to configure multiple companies on a single domain | IBP/iWork | Milestone 6 | Delivered |  | 2026-07-01 | 2026-07-07
| Inception/Endorsement | Whenever we get Employee Details (Email, Phone & DOB) uploaded then update the existing record as this is the latest data | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-07-01 |  | Jagadeesh
| Enrolment Journey | Add GPA note based on employee type (Leadership vs Employee) | IBP - CR | Milestone 6 | Delivered |  | 2026-07-03 | 2026-07-03 | Manjusha
| No Policy Config - Enrolment Journey | Enrolment Journey - Collect Dependents Details ONLY | IBP/iWork - CR | Milestone 6 | Dev - WIP | 1. IBP - Enrolment - Completed 2. Service - WIP | 2026-07-04 | 2026-07-17 | Manjusha
| Madhav & Veera | Data Load - Company, Policy, Broker & Insurer - 30 Files | iWork | Milestone 6 | Delivered |  | 2026-07-06 | 2026-07-12 | Rama
| Neeraj Joshi | Policy - Inception/Endorsement - Data Load - 13 Files | iWork | Milestone 6 | Delivered |  | 2026-07-06 | 2026-07-12 | Rama
| Employee Details | Trim spaces in the dependent names | IBP | Milestone 6 | Delivered |  | 2026-07-07 | 2026-07-07 | Manjusha
| Employee Details | Show Insurer Policy Details | IBP | Milestone 6 | Delivered |  | 2026-07-07 | 2026-07-07 | Manjusha
| Employee Details | Hide DOJ as there is NO source for us. | IBP - CR | Milestone 6 | Delivered |  | 2026-07-08 | 2026-07-08 | Manjusha
| IBP - Email Communication | Send employee emails - Either AWS or Send Grid - Company Config | IBP - CR | Milestone 6 | Delivered |  | 2026-07-10 | 2026-07-10 | Abhilash
| IBP - FAQ | Policy Level - FAQ | IBP - CR | Milestone 6 | Yet to start |  | 2026-07-11 | 2026-07-17 | Manjusha
| IBP - Welcome Emails | Dual approval/confirmation - Before sending to Employees. 1. 2 levels in iWork 2. CRM will submit & HR will approve in Risk Watch | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-07-14
iWork | Help Info - Field formulaes or field values | In any of the screen, we have to provide an info icon where it will help the users how critical fields in that screen are derieved or got populated | iWork - CR | Milestone 6 | Yet to start |  | 2026-07-17
iWork - Report | PROD Issue | When we generate 2025-2026 data for IIRM India then API request is a failure. Need to find a solution | iWork | Milestone 6 | Yet to start |  | 2026-07-17

## ① Executive Summary
PROJECT DELIVERY PLAN
iWork · IBP · Framework (IIRM SOW) ¦ Status Overview & Forward Roadmap · As of 14-Jul-2026
OVERALL COMPLETION | [6 empty] | REMAINING WORK
71.8% |  |  | 216 of 301 scope items delivered |  |  |  | 85 |  | items still to deliver across all modules — planned week by week in the weekly sheets
WEEKLY INTAKE — items requested (by Requested Date)
Period | Added | Delivered | Pending | % Closed
Before 01-Jun-2026 | 208 | 143 | 65 | 68.75%
Week of 01 Jun 2026 | 5 | 4 | 1 | 80%
Week of 08 Jun 2026 | 43 | 42 | 1 | 97.67%
Week of 15 Jun 2026 | 12 | 5 | 7 | 41.67%
Week of 22 Jun 2026 | 21 | 14 | 7 | 66.67%
Week of 29 Jun 2026 | 5 | 2 | 3 | 40%
Week of 06 Jul 2026 — last week | 7 | 6 | 1 | 85.71%
Week of 13 Jul 2026 — this week | 0 | 0 | 0 | 0%
Requested ahead (after 19 Jul) | 0 | 0 | 0 | 0%
No Requested Date | 0 | 0 | 0 | 0%
TOTAL | 301 | 216 | 85 | 71.76%
STATUS BREAKDOWN (all items)
211 |  |  | 5 |  |  | 14 |  |  | 1
Delivered |  |  | Dev Complete |  |  | In Development |  |  | In QA
5 |  |  | 55 |  |  | 10 |  |  | 0
Pre-PROD / UAT |  |  | Not Started |  |  | Partial Delivery |  |  | N/A
PROGRESS BY MODULE
Module | Type | Total | Delivered | Pending | N/A | % Complete | Progress
iWork (Backlog) | Backlog | 123 | 103 | 20 | 0 | 83.74% | 83.74%
iWork (Change Requests) | Change Request | 25 | 18 | 7 | 0 | 72% | 72%
IBP (Backlog) | Backlog | 67 | 41 | 26 | 0 | 61.19% | 61.19%
IBP (Change Requests) | Change Request | 6 | 4 | 2 | 0 | 66.67% | 66.67%
IBP / iWork (Shared) | Backlog | 19 | 12 | 7 | 0 | 63.16% | 63.16%
IBP / iWork (Shared CRs) | Change Request | 3 | 1 | 2 | 0 | 33.33% | 33.33%
Framework | Backlog | 34 | 29 | 5 | 0 | 85.29% | 85.29%
DPDP | Backlog | 19 | 6 | 13 | 0 | 31.58% | 31.58%
NFR | Backlog | 5 | 2 | 3 | 0 | 40% | 40%
TOTAL | All | 301 | 216 | 85 | 0 | 71.76% | 71.76%
PENDING BY MILESTONE & MODULE
Milestone | iWork | iWork - CR | IBP | IBP - CR | IBP/iWork | IBP/iWork - CR | Framework | DPDP | NFR | TOTAL PENDING
Milestone 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Milestone 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Milestone 4 | 2 | 0 | 1 | 0 | 2 | 0 | 5 | 1 | 2 | 13
Milestone 5 | 6 | 0 | 23 | 0 | 3 | 0 | 0 | 12 | 1 | 45
Milestone 6 | 9 | 7 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 24
TOTAL | 20 | 7 | 26 | 2 | 7 | 2 | 5 | 13 | 3 | 85
ITEMS BY MILESTONE & STATUS
Milestone | Delivered | Dev Complete | In Development | In QA | Pre-PROD / UAT | Not Started | Partial Delivery | TOTAL
Milestone 1 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 29
Milestone 2 | 31 | 0 | 0 | 0 | 0 | 1 | 0 | 32
Milestone 3 | 6 | 0 | 0 | 0 | 2 | 0 | 0 | 8
Milestone 4 | 43 | 0 | 1 | 0 | 1 | 7 | 4 | 56
Milestone 5 | 19 | 5 | 9 | 1 | 1 | 28 | 6 | 69
Milestone 6 | 83 | 0 | 4 | 0 | 1 | 19 | 0 | 107
TOTAL | 211 | 5 | 14 | 1 | 5 | 55 | 10 | 301
% Complete = Delivered ÷ (Delivered + Pending). N/A items (duplicates) are excluded from the calculation. All figures update live from the 'iWork,IBP & Framework_SOW Items' sheet.

## 📅 06-Jul
WEEK OF 06 Jul 2026 → 12 Jul 2026 — 11 items · 11 delivered · 0 pending · LAST WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 6 items · 6 delivered · 0 pending
1 | IBP/iWork | One URL multiple companies | Flexibility to configure multiple companies on a single domain | Delivered | Milestone 6 | 01-Jul-2026 | 07-Jul-2026
2 | IBP/iWork - CR | Teamlease - Request | Flexibility to configure multiple companies & policies on a single domain | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Abhilash
3 | iWork - CR | Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | Delivered | Milestone 6 | 01-May-2026 | 09-Jul-2026 | Karan
4 | iWork |  | Dashboard - Hide the widgets where there is NO data in the cards | Delivered | Milestone 6 | 15-Jun-2026 | 10-Jul-2026
5 | iWork | Madhav & Veera | Data Load - Company, Policy, Broker & Insurer - 30 Files | Delivered | Milestone 6 | 06-Jul-2026 | 12-Jul-2026 | Rama
6 | iWork | Neeraj Joshi | Policy - Inception/Endorsement - Data Load - 13 Files | Delivered | Milestone 6 | 06-Jul-2026 | 12-Jul-2026 | Rama
IBP (Backlog & CRs) · 5 items · 5 delivered · 0 pending
7 | IBP | Employee Details | Trim spaces in the dependent names | Delivered | Milestone 6 | 07-Jul-2026 | 07-Jul-2026 | Manjusha
8 | IBP | Employee Details | Show Insurer Policy Details | Delivered | Milestone 6 | 07-Jul-2026 | 07-Jul-2026 | Manjusha
9 | IBP - CR | Employee Details | Hide DOJ as there is NO source for us. | Delivered | Milestone 6 | 08-Jul-2026 | 08-Jul-2026 | Manjusha
10 | IBP - CR | Risk Watch - Enrolment Drive | Risk Watch - List view to see the list of enrolment dritve | Delivered | Milestone 6 | 22-Jun-2026 | 10-Jul-2026 | Ravi
11 | IBP - CR | IBP - Email Communication | Send employee emails - Either AWS or Send Grid - Company Config | Delivered | Milestone 6 | 10-Jul-2026 | 10-Jul-2026 | Abhilash

## 📍 13-Jul
WEEK OF 13 Jul 2026 → 19 Jul 2026 — 15 items · 0 delivered · 15 pending · CURRENT WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 10 items · 0 delivered · 10 pending
1 | iWork | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | Pre-PROD | Milestone 3 | 16-May-2025 | 15-Jul-2026 | Sunil
2 | iWork | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | Pre-PROD | Milestone 3 | 16-May-2025 | 15-Jul-2026 | Sunil
3 | iWork | View Service Score | Servicing Stats Dashboard - Single Table (drillable) to calculate an overall score | Delivered - Deficit | Milestone 4 | 10-Jun-2025 | 15-Jul-2026 | Sunil | Pending: Meeting, MIR calculation
4 | iWork - CR | Policy Configuration | DNV Group - Dependent based SI & Premium configuration | Dev - WIP | Milestone 6 | 07-Apr-2026 | 15-Jul-2026 | Jagadeesh
5 | iWork | Cut Off Mgmt |  | Yet to start | Milestone 2 | 16-Apr-2025 | 17-Jul-2026 | Karan
6 | IBP/iWork | TPA Integration Mgmt [Framework] | 1. Framework in iWork 2. Validate the integration for the existing 6 TPA's | Dev - WIP | Milestone 4 | 10-Jun-2025 | 17-Jul-2026 | Ravi
7 | IBP/iWork | Core Infrastructure | Core Infra | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 17-Jul-2026 | Velangini Raju | Pending: Mobile responsive
8 | iWork | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) Similar to TPA API Integration Framework for any 3'rd Party | Dev - WIP | Milestone 5 | 31-Jul-2025 | 17-Jul-2026
9 | iWork | Insurer Integration Mgmt | Can be used as a part of External API Intergration | Yet to start | Milestone 5 | 31-Jul-2025 | 17-Jul-2026
10 | IBP/iWork - CR | No Policy Config - Enrolment Journey | Enrolment Journey - Collect Dependents Details ONLY | Dev - WIP | Milestone 6 | 04-Jul-2026 | 17-Jul-2026 | Manjusha | 1. IBP - Enrolment - Completed 2. Service - WIP
IBP (Backlog & CRs) · 2 items · 0 delivered · 2 pending
11 | IBP | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | Pre-PROD | Milestone 4 | 10-Jun-2025 | 17-Jul-2026 | Akhila | Fine tuning the API's where there is a delay
12 | IBP - CR | IBP - FAQ | Policy Level - FAQ | Yet to start | Milestone 6 | 11-Jul-2026 | 17-Jul-2026 | Manjusha
Framework (DPDP, NFR, Framework) · 3 items · 0 delivered · 3 pending
13 | DPDP | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | Yet to start | Milestone 4 | 10-Jun-2025 | 15-Jul-2026 | Rama | Duplicate of Archival from NFR & DPDP
14 | Framework | Notifications Management | Different email notification - Madhav excel. 1. Renewal Reminders - ASAP 2. Instalment Reminders 3. Others......... | Delivered - Deficit | Milestone 4 | 10-Jun-2025 | 17-Jul-2026 | Jagadeesh
15 | NFR | NFR_Security | DPDP NFR | Yet to start | Milestone 4 | 10-Jun-2025 | 17-Jul-2026 | Tharun

## 📅 20-Jul
WEEK OF 20 Jul 2026 → 26 Jul 2026 — 31 items · 5 delivered · 26 pending · NEXT WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 5 items · 0 delivered · 5 pending
1 | IBP/iWork | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | Yet to start | Milestone 4 | 10-Jun-2025 | 24-Jul-2026
2 | iWork | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | Yet to start | Milestone 4 | 10-Jun-2025 | 24-Jul-2026 | Rama
3 | IBP/iWork | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | Yet to start | Milestone 5 | 31-Jul-2025 | 24-Jul-2026 | Ravi
4 | IBP/iWork | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | Yet to start | Milestone 5 | 31-Jul-2025 | 24-Jul-2026 | Ravi
5 | iWork | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
IBP (Backlog & CRs) · 10 items · 0 delivered · 10 pending
6 | IBP | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | Yet to start | Milestone 5 | 31-Jul-2025 | 21-Jul-2026 | Manjusha
7 | IBP | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | Yet to start | Milestone 5 | 31-Jul-2025 | 21-Jul-2026 | Ravi
8 | IBP | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | Yet to start | Milestone 5 | 31-Jul-2025 | 22-Jul-2026 | Abhilash
9 | IBP | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | Yet to start | Milestone 5 | 31-Jul-2025 | 23-Jul-2026 | Manjusha
10 | IBP | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | Yet to start | Milestone 5 | 31-Jul-2025 | 23-Jul-2026 | Ravi
11 | IBP | Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 24-Jul-2026 | Manjusha | Pending: Offers & Discuounts
12 | IBP | User Profile | Profile, Service Subscriptions, Feedback | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 24-Jul-2026 | Ravi | Pending: Service Subscriptions, Feedback
13 | IBP | Evexia Club Integration | Integration to Evexia | Yet to start | Milestone 5 | 31-Jul-2025 | 24-Jul-2026 | Abhilash
14 | IBP | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 24-Jul-2026 | Manjusha | Pending: Offer, Feature flagging (UI)
15 | IBP | Benefits Summary | End User's Summary View | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 24-Jul-2026 | Ravi | Pending: Retail Insurance
Framework (DPDP, NFR, Framework) · 16 items · 5 delivered · 11 pending
16 | Framework | Workflow Management | 23-May: Integrate the 3'rd party libraries | Yet to start | Milestone 4 | 10-Jun-2025 | 24-Jul-2026 | Nithin
17 | Framework | Rule Definition Management | 23-May: Integrate the 3'rd party libraries | Yet to start | Milestone 4 | 10-Jun-2025 | 24-Jul-2026 | Jagadeesh
18 | Framework | Accessibility |  | Yet to start | Milestone 4 | 10-Jun-2025 | 24-Jul-2026
19 | DPDP | Integrate SSO / MFA |  | Dev - Done | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
20 | DPDP | Capture consent within app |  | Dev - Done | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
21 | DPDP | Allow easy consent withdrawal |  | Dev - Done | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
22 | DPDP | Approval workflow |  | Dev - Done | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
23 | DPDP | Show privacy notice with purpose, retention, rights |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
24 | DPDP | App vulnerability scans |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
25 | DPDP | Document Flows |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
26 | DPDP | Perform security UAT |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
27 | DPDP | Enforce business logic to restrict purpose |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
28 | DPDP | Remove unnecessary fields |  | Dev - Done | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
29 | DPDP | Allow user corrections |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
30 | DPDP | Delete expired data |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
31 | DPDP | Sign DPDP clauses |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 24-Jul-2026

## 📅 Upcoming
UPCOMING (ETA beyond 20 Jul week) — 4 items · 0 delivered · 4 pending
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 2 items · 0 delivered · 2 pending
1 | IBP/iWork | IBP - Raise Ticket | Edit the ticket and update the status by the Lead CRM & System Admin | Yet to start | Milestone 6 | 01-Jul-2026 | 27-Jul-2026 | Manjusha
2 | IBP/iWork | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | Yet to start | Milestone 6 | 01-Jun-2026 | 28-Jul-2026 | Abhilash
IBP (Backlog & CRs) · 2 items · 0 delivered · 2 pending
3 | IBP | Claims Corner | Claims Corner - Screen Re-design | Dev - WIP | Milestone 6 | 21-Jun-2026 | 28-Jul-2026 | Ravi
4 | IBP | IIRM-10666 | IBP - Policy Component Card Re-design | Yet to start | Milestone 6 | 21-Jun-2026 | 28-Jul-2026 | Manjusha

## Unplanned (no ETA)
UNPLANNED — PENDING, NO ETA · 37 items
Pending items with no ETA yet. Assign an ETA in the source sheet to move an item into its week. Static snapshot — re-run to refresh.
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 16 items
1 | iWork | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | Yet to start | Milestone 5 | 31-Jul-2025 |  |  | Need inputs from Kapil
2 | iWork | Reconciliation Mgmt |  | Yet to start | Milestone 5 | 31-Jul-2025
3 | iWork | HRMS Integration Mgmt | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? HRMS - integrations with enrolment portal (POC - with Zoho People), client mentioned that they have already integrated MB360 for HCL IBP & HRMS Integration - HCL | Yet to start | Milestone 5 | 31-Jul-2025
4 | iWork - CR | Policy Configuration | Premium Rater Table | Yet to start | Milestone 6 | 21-Apr-2026 |  | Jagadeesh
5 | iWork - CR | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | Yet to start | Milestone 6 | 01-May-2026 |  | Sunil
6 | iWork - CR | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | Yet to start | Milestone 6 | 08-May-2026 |  |  | Need some information about the document rules that defines the idenity of it
7 | iWork | Export to Excel | Export to excel - iWork all the results table; Download is on Previlage | Yet to start | Milestone 6 | 15-Jun-2026
8 | iWork | IIRM-10667 | iWork - Knowledge Central Re-Design | Yet to start | Milestone 6 | 15-Jun-2026
9 | iWork | IIRM-10668 | iLearn: Document Preview in-app | Yet to start | Milestone 6 | 15-Jun-2026
10 | iWork | Discuss with Madhav | Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard) Also, check if we are there are any data loads for 2025-26 | Yet to start | Milestone 6 | 15-Jun-2026
11 | iWork | Installment & Fee Requirements | Installments & Fee to BizDone | Yet to start | Milestone 6 | 15-Jun-2026
12 | iWork - CR | BizDone | Computed value & Reported values * Computed values - It’s the real-time values base on Policy inception/endorsement * Reported values - It’s validated by the mgmt. and share this number to update in the column. * Reported value MUST be used for the Dashboard & BizDone, which was declared by the company to public. * In the admin a feature to update the Reported values from the computed values * Legacy data - Premiums, Brokerage, CD Balance | Yet to start | Milestone 6 | 25-Jun-2026
13 | iWork | AI | Wherever AI is implemented, there should be fallback if one day we turnoff AI then there shouldn’t be any impact in the working functionality | Yet to start | Milestone 6 | 25-Jun-2026 |  | Rama
14 | iWork | AI | AI Nudges are NOT working. If there is NO AI, then DB scripts should run and show data | Yet to start | Milestone 6 | 25-Jun-2026 |  | Rama
15 | IBP/iWork - CR | Inception/Endorsement | Whenever we get Employee Details (Email, Phone & DOB) uploaded then update the existing record as this is the latest data | Yet to start | Milestone 6 | 01-Jul-2026 |  | Jagadeesh
16 | iWork | Inception/Endorsement | Endorsement data upload related * Track-1: TeamLease - 2024-2025 Year policies * All endorsement -> Headers, Member data, & endorsement Document * Track-2: Old Financial data * Track-3: Current Financial data * Track-4: Handle the data in IBP-Risk Watch | Dev - WIP | Milestone 6 | 25-Jun-2026 |  | Rama
IBP (Backlog & CRs) · 14 items
17 | IBP | Profile Migration | Request migration of Corporate Profile to Individual | Yet to start | Milestone 5 | 31-Jul-2025 |  | Abhilash
18 | IBP | Profile Migration | Request migration of Individual Profile to Corporate | Yet to start | Milestone 5 | 31-Jul-2025 |  | Abhilash
19 | IBP | Book Ambulance | Floater on the screen - Integrate to Ambulance Service | Yet to start | Milestone 5 | 31-Jul-2025
20 | IBP | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | Yet to start | Milestone 5 | 31-Jul-2025
21 | IBP | Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | Yet to start | Milestone 5 | 31-Jul-2025
22 | IBP | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | Yet to start | Milestone 5 | 31-Jul-2025 |  | Ravi | Retail insurance(facility to load user insurance policies)
23 | IBP | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | Yet to start | Milestone 5 | 31-Jul-2025 |  | Manjusha | wellness
24 | IBP | Wellness HR View | HR View of Wellness usage by Employees | Yet to start | Milestone 5 | 31-Jul-2025 |  | Manjusha | wellness
25 | IBP | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | Yet to start | Milestone 5 | 31-Jul-2025 |  | Manjusha | wellness
26 | IBP | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | Yet to start | Milestone 5 | 31-Jul-2025 |  | Ravi | Pending: Retail insurance
27 | IBP | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | Yet to start | Milestone 5 | 31-Jul-2025 |  | Ravi | Pending: Retail insurance
28 | IBP | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | Yet to start | Milestone 5 | 31-Jul-2025 |  | Abhilash | External chatbot integration?
29 | IBP | InsureEasy | InsureEasy Integration - Retail Business | Yet to start | Milestone 5 | 25-Jun-2026
30 | IBP - CR | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | Pre-PROD | Milestone 6 | 08-May-2026 |  | Abhilash
Framework (DPDP, NFR, Framework) · 7 items
31 | DPDP | Enable delete pipeline |  | Yet to start | Milestone 5 | 31-Jul-2025
32 | DPDP | Define archival |  | Yet to start | Milestone 5 | 31-Jul-2025
33 | NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | Yet to start | Milestone 5 | 31-Jul-2025 |  |  | Discussed this with Surya sir last visit to Divami office
34 | DPDP | Map PII tables |  | QA - WIP | Milestone 5 | 31-Jul-2025
35 | DPDP | Quarterly restore tests |  | Pre-PROD | Milestone 5 | 31-Jul-2025
36 | Framework | Localisation |  | Delivered - Deficit | Milestone 4 | 10-Jun-2025 |  | Tharun | Pending: Service Flow Pending: IBP
37 | NFR | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | Delivered - Deficit | Milestone 4 | 10-Jun-2025 |  | Jagadeesh | Pending: Provide the document on how do we store and view it

## VRK Feedbacks
VRK — PROD FEEDBACK TRACKER · 52 items · 49 delivered · 3 pending
All 'VRK - PROD Feedback:' items, broken up by week (status then ETA within a week). Excluded from the other views. Static snapshot.
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
📅 WEEK OF 08 Jun → 14 Jun 2026 · PAST · 24 items
1 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
2 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
3 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
4 | iWork | VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
5 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
7 | iWork | VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | Delivered | Milestone 6 | 05-Jun-2026 | 08-Jun-2026
8 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
9 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
10 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
11 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
12 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026
13 | iWork | VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
14 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
15 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | Delivered | Milestone 6 | 08-Jun-2026 | 09-Jun-2026 | Karan
16 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
17 | iWork | VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
18 | iWork | VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Prathiphala
19 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | Delivered | Milestone 6 | 08-Jun-2026 | 10-Jun-2026
20 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Jagadeesh
21 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Jagadeesh
22 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | Delivered | Milestone 6 | 09-Jun-2026 | 12-Jun-2026 | Prathiphala
23 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | Delivered | Milestone 6 | 08-Jun-2026 | 12-Jun-2026 | Karan
24 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | Delivered | Milestone 6 | 08-Jun-2026 | 12-Jun-2026
📅 WEEK OF 15 Jun → 21 Jun 2026 · PAST · 8 items
25 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
26 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
27 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
28 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026
29 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
30 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | Delivered | Milestone 6 | 09-Jun-2026 | 16-Jun-2026
31 | iWork | VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | Delivered | Milestone 6 | 09-Jun-2026 | 19-Jun-2026 | Karan
32 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | Delivered | Milestone 6 | 08-Jun-2026 | 19-Jun-2026 | Rama
📅 WEEK OF 22 Jun → 28 Jun 2026 · PAST · 1 item
33 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | Delivered | Milestone 6 | 08-Jun-2026 | 24-Jun-2026
📅 WEEK OF 29 Jun → 05 Jul 2026 · PAST · 8 items
34 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | Delivered | Milestone 6 | 08-Jun-2026 | 30-Jun-2026 | Jagadeesh
35 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
36 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
37 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
38 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
39 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
40 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
41 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | Delivered | Milestone 6 | 08-Jun-2026 | 02-Jul-2026
📅 WEEK OF 06 Jul → 12 Jul 2026 · LAST WEEK · 3 items
42 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 07-Jul-2026 | Pushyami
43 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Pushyami
44 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Pushyami
📍 WEEK OF 13 Jul → 19 Jul 2026 · CURRENT WEEK · 3 items
45 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Additional section display: Placement Funnel, Schedule, Followup | Yet to start | Milestone 6 | 23-Jun-2026 | 16-Jul-2026 | Pushyami
46 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 14-Jul-2026 | Karan
47 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - Filter & drill-down | Delivered | Milestone 6 | 23-Jun-2026 | 14-Jul-2026 | Karan
📅 WEEK OF 20 Jul → 26 Jul 2026 · NEXT WEEK · 1 item
48 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | Yet to start | Milestone 6 | 09-Jun-2026 | 24-Jul-2026
🗓 No ETA assigned · 4 items
49 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | iWork and iTicket should be accessible via VPN | Yet to start | Milestone 6 | 23-Jun-2026 |  | Pushyami
50 | iWork | VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | Delivered | Milestone 6 | 08-Jun-2026
51 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | Not a bug | Milestone 6 | 08-Jun-2026 |  |  | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only
52 | iWork | VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | Not a bug | Milestone 6 | 08-Jun-2026

## Helper (hidden)
Module | Phase | Status | Category | Bucket | ReqDate
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
iWork | Milestone 1 | Delivered | Delivered | Delivered | 45717
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
Framework | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Delivered | Delivered | Delivered | 45763
iWork | Milestone 2 | Yet to start | Not Started | Pending | 45763
Framework | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Delivered | Delivered | Delivered | 45793
iWork | Milestone 3 | Pre-PROD | Pre-PROD / UAT | Pending | 45793
iWork | Milestone 3 | Pre-PROD | Pre-PROD / UAT | Pending | 45793
Framework | Milestone 4 | Yet to start | Not Started | Pending | 45818
Framework | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 45818
Framework | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Yet to start | Not Started | Pending | 45818
IBP | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending | 45818
IBP/iWork | Milestone 4 | Dev - WIP | In Development | Pending | 45818
DPDP | Milestone 4 | Yet to start | Not Started | Pending | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
Framework | Milestone 4 | Yet to start | Not Started | Pending | 45818
iWork | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
iWork | Milestone 4 | Delivered | Delivered | Delivered | 45818
IBP/iWork | Milestone 4 | Yet to start | Not Started | Pending | 45818
iWork | Milestone 4 | Yet to start | Not Started | Pending | 45818
NFR | Milestone 4 | Yet to start | Not Started | Pending | 45818
NFR | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 45818
IBP | Milestone 4 | Delivered | Delivered | Delivered | 45818
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 45869
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered | 45869
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered | 45869
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered | 45869
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered | 45869
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered | 45869
DPDP | Milestone 5 | QA - WIP | In QA | Pending | 45869
DPDP | Milestone 5 | Yet to start | Not Started | Pending | 45869
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 45869
DPDP | Milestone 5 | Yet to start | Not Started | Pending | 45869
DPDP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 45869
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 45869
IBP | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP/iWork | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 45869
IBP/iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP/iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
iWork | Milestone 5 | Dev - WIP | In Development | Pending | 45869
iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered | Delivered | Delivered | 45869
iWork | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 45869
iWork | Milestone 5 | Yet to start | Not Started | Pending | 45869
NFR | Milestone 5 | Yet to start | Not Started | Pending | 45869
NFR | Milestone 5 | Delivered | Delivered | Delivered | 45869
NFR | Milestone 5 | Delivered | Delivered | Delivered | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 45869
IBP | Milestone 5 | Yet to start | Not Started | Pending | 46198
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46070
iWork - CR | Milestone 6 | Dev - WIP | In Development | Pending | 46119
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46133
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46143
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46143
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46143
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46143
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46143
IBP - CR | Milestone 6 | Pre-PROD | Pre-PROD / UAT | Pending | 46150
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46150
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46150
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46163
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46167
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46167
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46170
IBP/iWork | Milestone 6 | Yet to start | Not Started | Pending | 46174
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46176
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46178
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46178
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46179
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Not a bug | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46181
iWork | Milestone 6 | Not a bug | Delivered | Delivered | 46181
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46182
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46182
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46183
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46183
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46184
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46184
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46188
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46188
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46191
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46192
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46192
IBP | Milestone 6 | Dev - WIP | In Development | Pending | 46194
IBP | Milestone 6 | Yet to start | Not Started | Pending | 46194
IBP - CR | Milestone 6 | Delivered | Delivered | Delivered | 46195
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46195
IBP/iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46196
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46196
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46196
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46198
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46198
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46198
iWork | Milestone 6 | Dev - WIP | In Development | Pending | 46198
IBP/iWork | Milestone 6 | Yet to start | Not Started | Pending | 46204
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 46204
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46204
IBP - CR | Milestone 6 | Delivered | Delivered | Delivered | 46206
IBP/iWork - CR | Milestone 6 | Dev - WIP | In Development | Pending | 46207
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46209
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46209
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46210
IBP | Milestone 6 | Delivered | Delivered | Delivered | 46210
IBP - CR | Milestone 6 | Delivered | Delivered | Delivered | 46211
IBP - CR | Milestone 6 | Delivered | Delivered | Delivered | 46213
IBP - CR | Milestone 6 | Yet to start | Not Started | Pending | 46214

## Config (hidden)
Status_Raw | Category | Bucket
Delivered | Delivered | Delivered
Dev - Done | Dev Complete | Delivered
Dev - WIP | In Development | Pending
QA - WIP | In QA | Pending
Pre-PROD | Pre-PROD / UAT | Pending
Yet to start | Not Started | Pending
Delivered - Deficit | Partial Delivery | Pending
Duplicate | N/A | N/A
Not a bug | Delivered | Delivered