## ① Executive Summary
PROJECT DELIVERY PLAN
iWork · IBP · Framework (IIRM SOW) ¦ Status Overview & Forward Roadmap · As of 21-May-2026
OVERALL COMPLETION | [6 empty] | REMAINING WORK
66.2% |  |  | 172 of 260 scope items delivered |  |  |  | 88 | items still to deliver across all modules — broken down by milestone in the Pending Roadmap sheet
STATUS BREAKDOWN (all items)
166 |  |  | 6 |  |  | 8 |  | 2
Delivered |  |  | Dev Complete |  |  | In Development |  | In QA
5 |  |  | 60 |  |  | 13 |  | 0
Pre-PROD / UAT |  |  | Not Started |  |  | Partial Delivery |  | N/A
PROGRESS BY MODULE
Module | Type | Total | Delivered | Pending | N/A | % Complete | Progress
iWork (Backlog) | Backlog | 116 | 94 | 22 | 0 | 81.03% | 81.03%
iWork (Change Requests) | Change Request | 7 | 2 | 5 | 0 | 28.57% | 28.57%
IBP (Backlog) | Backlog | 62 | 31 | 31 | 0 | 50% | 50%
IBP (Change Requests) | Change Request | 1 | 0 | 1 | 0 | 0% | 0%
IBP / iWork (Shared) | Backlog | 18 | 10 | 8 | 0 | 55.56% | 55.56%
Framework | Backlog | 34 | 28 | 6 | 0 | 82.35% | 82.35%
DPDP | Backlog | 19 | 5 | 14 | 0 | 26.32% | 26.32%
NFR | Backlog | 3 | 2 | 1 | 0 | 66.67% | 66.67%
TOTAL | All | 260 | 172 | 88 | 0 | 66.15% | 66.15%
% Complete = Delivered ÷ (Delivered + Pending). N/A items (duplicates) are excluded. All figures update live from the 'iWork,IBP & Framework_SOW Items' sheet.

## iWork,IBP & Framework_SOW Items
Area | Feature | Functionality | Module | Phase | Status | Remarks | Need Design Approval | ETA | Actual Delivery | Resource
FRAMEWORK: Frontend | Project setup | Basic project / Development environment setup | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | UI Approach Design System | Building Design System | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | Core Infrastructure | Core Infra | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | Build UI components | This includes all the UI componnets to compose the application and module definitions: Form, Toast, Filter, Cards, Visualisation, Grid, Menu, Header, Footer, Maps Integration | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | UI Approach Style Establishment | UI Style Establishment | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | Service Workers Implementation |  | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | Core System |  | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | ACL & RBAC Control Framework |  | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | Micro Frontend Setup |  | Framework | Milestone 1 | Delivered
FRAMEWORK: Frontend | Landing Page |  | Framework | Milestone 1 | Delivered
FRAMEWORK: Services - Basic Modules | Access Control Management |  | Framework | Milestone 1 | Delivered
FRAMEWORK: Services - Larger Modules | Auth Module (Simple Auth) |  | Framework | Milestone 1 | Delivered
FRAMEWORK: Services - Larger Modules | Micro Service Framework Setup |  | Framework | Milestone 1 | Delivered
iWORK: Common Components | Common - Audit Trail Mgmt - Becomes critical in this phase iteself |  | iWork | Milestone 1 | Delivered
iWORK: Frontend | Add/View/Edit Opportunity | Add Medium size form with 1->N list of Claims; Multiple drop downs Large View with several widgets, Simple Edit | iWork | Milestone 1 | Delivered
iWORK: Frontend | Manage TPA/Insurer | Basic Add, View with edit of basic data, with lists of policies/companies | iWork | Milestone 1 | Delivered
iWORK: Frontend | Core Infra | Infrastructure | iWork | Milestone 1 | Delivered
iWORK: Frontend | Add/View/Edit Company | Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. Simple edit like Add; View is multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | iWork | Milestone 1 | Delivered
iWORK: Frontend | Insurer/TPA Hub | List with Filter/Search | iWork | Milestone 1 | Delivered
iWORK: Frontend | Add/View/Edit Contact | Simple edit like Add Contacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | iWork | Milestone 1 | Delivered
iWORK: Frontend | Company (Prospect) Hub | Top 10/Latest companies, with search/filter, Table of basic attributes with GPS etc. | iWork | Milestone 1 | Delivered
iWORK: Frontend | Contact Hub | Top 10/Latest Contacts, with search/filter, list with basic attributes | iWork | Milestone 1 | Delivered
iWORK: Frontend | Opportunity Hub | Top Opportunities with search/filter, List of opportunities with high level summaries | iWork | Milestone 1 | Delivered
iWORK: Services - Basic Modules | Employee Mgmt |  | iWork | Milestone 1 | Delivered | User deletion need to be handled |  | 2026-06-12
iWORK: Services - Basic Modules | Contact /Company/Insurer/TPA Mgmt |  | iWork | Milestone 1 | Delivered
iWORK: Services - Basic Modules | Task Mgmt |  | iWork | Milestone 1 | Delivered
iWORK: Services - Basic Modules | Meeting Mgmt |  | iWork | Milestone 1 | Delivered
iWORK: Services - Basic Modules | RBAC and ACL setup for Iwork Module |  | iWork | Milestone 1 | Delivered
iWORK: Services - Basic Modules | Opportunity Mgmt |  | iWork | Milestone 1 | Delivered
FRAMEWORK: Frontend | Visualization framework | Charts and KPIs | Framework | Milestone 2 | Delivered
FRAMEWORK: Frontend | Document Management | Create, Upload, Seach, Download | Framework | Milestone 2 | Delivered
FRAMEWORK: Frontend | Master Data Management |  | Framework | Milestone 2 | Delivered |  |  | 2026-05-27
FRAMEWORK: Frontend | Caching of API Data |  | Framework | Milestone 2 | Delivered
FRAMEWORK: Services - Basic Modules | Audit Data Capturing |  | Framework | Milestone 2 | Delivered
FRAMEWORK: Services - Larger Modules | CMS |  | Framework | Milestone 2 | Delivered | Used in IBP
iWORK: AI Components | AI - (Non-OCR) Digital Document Processing for Content recognition (Company/Opportunity/Contact Creation from Previous Policy Document, Bizcard document) |  | iWork | Milestone 2 | Delivered
iWORK: AI Components | AI - OCR for Content Collection |  | iWork | Milestone 2 | Delivered
iWORK: AI Components | AI - Company Information by AI Search |  | iWork | Milestone 2 | Delivered
iWORK: Common Components | Common, Contexual Upload Component |  | iWork | Milestone 2 | Delivered
iWORK: Common Components | Common, Contexual Read and Spread Component (Utility) |  | iWork | Milestone 2 | Delivered
iWORK: Frontend | Manage Stage Planning/Performance/Approval | Add iWork Stages (table) - Dates with each iWork Stage and who are the team members assigned to each Stage; Once all iWork stages are complete, ISG Team activities must be planned ISG Team can approve/reject each iWork Stage. Approving RFP Stage approves all iWork stages Completion of each iWork Stage (Activity) & ISG Stage - Comments, Attach Document, Date recorded, submit | iWork | Milestone 2 | Delivered
iWORK: Frontend | Smart Add Component | Allow Upload of Document/Image, select what to create (Company/Contact/Opportunity) | iWork | Milestone 2 | Delivered
iWORK: Frontend | Dashboard - Drilldowns | Drill down from the Tables (Targets vs. Actuals, Pending Activities, Followups, AR Report, Schedule) | iWork | Milestone 2 | Delivered
iWORK: Frontend | Sales Team Hierarchy | Hierarchy / Org chart tied to Platform Users | iWork | Milestone 2 | Delivered
iWORK: Frontend | View Policy | Long View, multiple widgets/entities, endorsements (each month), Claims, etc. | iWork | Milestone 2 | Delivered
iWORK: Frontend | Common Data Mapping Component | Map input fields to output fields & Order | iWork | Milestone 2 | Delivered | Pending: Additional/Dynamic columns |  | 2026-06-09
iWORK: Frontend | Dashboard | Multiple KPI Cards: Business Performance, Svc Performance, Table of targets vs. actuals vs. lost, Sales Funnel, Renewal Funnel, Servce Funnel, AR from Insurers, Pending Activities(iWork Stages) Widget, Followups widget, Meetings widget Filters available (Geo, Branch, Team/Team Member, Dates), Approvals, iWork Stages, Tasks, Meetings | iWork | Milestone 2 | Delivered
iWORK: Frontend | Dashboard - Pending tasks, approvals | Pending tasks/approvals, | iWork | Milestone 2 | Delivered
iWORK: Frontend | Reports - Biz Done | Report View, Download, List of earlier snaps of the report, Search and Filter | iWork | Milestone 2 | Delivered
iWORK: Services - Basic Modules | Core Infrastructure | Core Infra | iWork | Milestone 2 | Delivered
iWORK: Services - Basic Modules | Organisation, Branch, Employee, & Hierarchy Mgmt |  | iWork | Milestone 2 | Delivered
iWORK: Services - Basic Modules | Dashboard (Place Holder) |  | iWork | Milestone 2 | Delivered
iWORK: Services - Basic Modules | Planning, Perform and Approval Mgmt |  | iWork | Milestone 2 | Delivered
iWORK: Services - Basic Modules | Policy Mgmt |  | iWork | Milestone 2 | Delivered
iWORK: Services - Basic Modules | Master Data Mgmt {Common, Contexual Master Data Mgmt} |  | iWork | Milestone 2 | Delivered
FRAMEWORK: Frontend | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion |  | 2026-06-12
FRAMEWORK: Services - Basic Modules | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion |  | 2026-06-12
FRAMEWORK: Services - Larger Modules | Data Security Considerations |  | Framework | Milestone 2 | Delivered | Duplicate of Covers in DPDP items |  | 2026-06-30
FRAMEWORK: Services - Basic Modules | Notification and Communication Management | 23-May: In-App, Emails, SMS, both or all. Template vs Channel | Framework | Milestone 2 | Delivered - Deficit | Pending: Configuration UI |  | 2026-06-24
FRAMEWORK: Services - Basic Modules | Usage Tracking System (Reports) | 23-May: Handle as a part of Reports | Framework | Milestone 2 | Delivered - Deficit | Pending: IBP usage |  | 2026-06-25
| IIRM-10587 | Add new fields - Business Month & Date of Business - Capture in Opty. & Flow to Policy and add filters in BizDone --> Refer to Madhav email "Business Month Requirement" | iWork | Milestone 6 | Delivered - Deficit | Pending: Additional filters |  | 2026-06-22 |  | Pushyami
FRAMEWORK: Services - Larger Modules | Document Generation |  | Framework | Milestone 3 | Delivered
iWORK: Frontend | Manage Policy (Endorsements) | Add Endorsement - basic form with uploads of excel/document Validations of endorsement format - Map customer fields to internal fields Map internal fields to TPA fields (occasional per TPA) View/Update Endorsement, List View, Endorsement Performance | iWork | Milestone 3 | Delivered
iWORK: Services - Basic Modules | Cover Mgmt |  | iWork | Milestone 3 | Delivered |  |  | 2026-06-10 |  | Karan
iWORK: Services - Basic Modules | Stage Mgmt (Activity/Transaction/Quote) |  | iWork | Milestone 3 | Delivered
iWORK: Services - Basic Modules | Asset/Member Data Mgmt |  | iWork | Milestone 3 | Delivered
iWORK: Services - Basic Modules | Endorsement Mgmt |  | iWork | Milestone 3 | Delivered
|  | Risk Watch: Showing policy feature documents at each policy | IBP | Milestone 3 | Pre-PROD |  |  | 2026-06-09 |  | Ravi
iWork: Services - Basic Modules | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | iWork - CR | Milestone 6 | Yet to start |  |  | 2026-06-12
| IIRM-10590 | Policy Config: Dependent Based Configurations - Per life depedent addition & increase SI - Apply Policy Parameters for dependents | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 |  | Jagadeesh
Framework | NFR_Usability | NFR-USA-015: The system must show personalized welcome messages and profile information based on locale. | IBP | Milestone 4 | Delivered
Framework | NFR_Usability | NFR-USA-016: Notification banners must be dismissible and configurable based on role. | IBP | Milestone 4 | Delivered | No notifications in IBP
Framework | NFR_Usability | NFR-USA-018: The session management should be configurable from UI 23-May: Configure from UI & store in DB; When changed then restart server | IBP | Milestone 4 | Delivered |  |  | 2026-06-15 |  | Manjusha
FRAMEWORK: Frontend | Notifications Management |  | Framework | Milestone 4 | Delivered
FRAMEWORK: Services - Basic Modules | Configuration Management |  | Framework | Milestone 4 | Delivered | Considered Policy Config
FRAMEWORK: Services - Basic Modules | Feature Flag Control Management |  | Framework | Milestone 4 | Delivered
FRAMEWORK: Services - Larger Modules | Localistation Management |  | Framework | Milestone 4 | Delivered
FRAMEWORK: Services - Larger Modules | Caching Implementation |  | Framework | Milestone 4 | Delivered
IBP: Common Components | Simple Auth | Username and Password based authentication and RBAC on simple-auth users. Auth rules needs configuration capability. IBP - HR User Management | IBP | Milestone 4 | Delivered |  |  | 2026-06-12 |  | Abhilash
IBP: Common Components | Whitelabelling Support |  | IBP | Milestone 4 | Delivered
IBP: FRONTEND | Company Plans | 6 Policies - GMC, GPA, GTL, Parental Plicy, Top-ups, OPD Policy (Summary view of policies) | IBP | Milestone 4 | Delivered
IBP: FRONTEND | Company Plan Configurator | Admin side of IBP should configure (per Corporate) how to define a Policy and determine how it breaks down the Premium and Coverage rules | IBP/iWork | Milestone 4 | Delivered
IBP: FRONTEND | IBP Landing Page - Basic | Basic Landing Page with only company plans and summart | IBP | Milestone 4 | Delivered
IBP: FRONTEND | Auth Config UI | Config for Auth Rules setup | IBP/iWork | Milestone 4 | Delivered
IBP: FRONTEND | Contact Matrix | Configure the Conact Info Matrix (IBP Admin) | IBP/iWork | Milestone 4 | Delivered
IBP: FRONTEND | Contact Matrix View | Contact Matrix View for end user | IBP | Milestone 4 | Delivered
IBP: FRONTEND | Core Infrastructure | Core Infra | IBP | Milestone 4 | Delivered
IBP: FRONTEND | My Documents | Document Hub - Covers Policies, Prescriptions, Reports | IBP | Milestone 4 | Delivered | Pending: Design |  | 2026-06-12 |  | Manjusha
IBP: FRONTEND | HR Portal View | Employee Search, Resend Email, Delete Employees, Extend Enrollment Windows, Reports, Bulk Email | IBP | Milestone 4 | Delivered |  |  | 2026-06-11 |  | Abhilash
IBP: FRONTEND | Per-policy Enrolment | Enrolment and addon policy selection | IBP | Milestone 4 | Delivered
IBP: FRONTEND | Policy Document | IBP-Risk Watch: Show the each policy document | IBP | Milestone 4 | Delivered |  |  | 2026-06-19 |  | Tharun
IBP: FRONTEND | My Insurance | Part-1: Hub of all plans I have as an employee - Company provided. Mostly a navigational page | IBP | Milestone 4 | Delivered
IBP: FRONTEND | Whitelabelling | Whitelabelling based on Org needs (IBP Admin) | IBP/iWork | Milestone 4 | Delivered
IBP: Services - Basic Modules | Basic Landing Page Services | Company provided plans only | IBP | Milestone 4 | Delivered
IBP: SERVICES - Basic Modules | Document Mgmt for End User | Insurance, Health Reports and Prescriptions {No automatic pull from Partners} | IBP | Milestone 4 | Delivered | Pending: Design |  | 2026-06-12 |  | Manjusha
IBP: SERVICES - Basic Modules | Personal Profile Mgmt | Profile settings | IBP | Milestone 4 | Delivered | Pending:Add Dependents |  | 2026-06-10 |  | Manjusha
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment | Enrollment (Adding Dependents, Choosing Options available). Submit the enrollment to Insurer or TPA 6 Types of Policies to be considered | IBP | Milestone 4 | Delivered | Need Confirmation: If scope has, Insurer & TPA integrations, then they are pending
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment Configurator | Enrollment Configurator (Set of benefits and type of Dependent combinations allowed etc). This is more of an Iwork feature to configure the policy | IBP | Milestone 4 | Delivered
IBP: Services - Larger Modules | End User onboarding | Generate Users, Send Emails, Password Rest | IBP | Milestone 4 | Delivered
IBP: Services - Larger Modules | IBP - User Management | IBP: HR Portal - Company-Scoped Employee Access for Client HR (Ex. TeamLease's Customer) | IBP | Milestone 4 | Delivered |  |  | 2026-05-26
IBP: Services - Larger Modules | Contact Matrix Configuration | Matrix of Contact Infomration | IBP | Milestone 4 | Delivered
IBP: Services - Larger Modules | HR/Admin Portal View | Supporting services for Admin Portal | IBP | Milestone 4 | Delivered
iWORK: Frontend | Knowledge Central | Grouped list of Documents/Resources, Add a Document, Remove a Document (Add/remove only for admins) | iWork | Milestone 4 | Delivered
iWork: Services - Basic Modules | Endorsement Mgmt | Additional columns in file like Department, DOJ, Emp. Location, Vertical, Others | iWork | Milestone 4 | Delivered |  |  | 2026-05-29 |  | Pushyami
iWork: Services - Basic Modules | Reports - Biz Done | Bizonde filter/table - Add "Income type" | iWork | Milestone 4 | Delivered |  |  | 2026-05-26 |  | Karan
iWork: Services - Basic Modules | Client - Associated Location (IBP HR Module) | IBP - HR: Policy Location - Add Company Associated Locations, Flow to Opty., Policy & Policy Config | IBP/iWork | Milestone 4 | Delivered |  |  | 2026-05-25 |  | Karan
iWork: Services - Basic Modules | Opportunity | Opportunity History details are unavailable for the end user to view. Show TAT section (Planned date, Performed/Completed date, Approved date) for planned acitivites | iWork | Milestone 4 | Delivered |  |  | 2026-05-28 |  | Pushyami
iWork: Services - Basic Modules | Opportunity | RO Scheduler Enhancements | iWork | Milestone 4 | Delivered |  |  | 2026-05-29 |  | Jagadeesh
iWORK: Services - Basic Modules | Knowledge Central |  | iWork | Milestone 4 | Delivered
iWORK: Services - Basic Modules | TAT/SLA Mgmt (Including Service Score) |  | iWork | Milestone 4 | Delivered
| Security | InfoSec - IBP Portal (Security Issue) 19-Jun: Critical - 0 High - 3 Pending Medium - 24 pending Low - 2 pending | IBP/iWork | Milestone 4 | Dev - WIP |  |  | 2026-06-22
iWork: Services - Basic Modules | Policy Configuration | Using AI - Extract the Policy document and perform Policy Configuration (Premium, Family, Parameters, & Others) | iWork - CR | Milestone 6 | QA - WIP |  |  | 2026-06-16 |  | Jagadeesh
IBP: Services - Larger Modules | IBP - Portal Setup | Post policy creation, create default IBP Portal Config for all the company-policy(ies) | IBP | Milestone 4 | Pre-PROD |  |  | 2026-06-10 |  | Manjusha
IBP: Services - Larger Modules | Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | IBP | Milestone 4 | Pre-PROD | Pending: HR Module - Endorsement |  | 2026-06-24 |  | Tharun
Framework | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | IBP | Milestone 4 | Pre-PROD |  |  | 2026-06-17 |  | Akhila
FRAMEWORK: Frontend | Localisation |  | Framework | Milestone 4 | Delivered - Deficit | Pending: Service Flow & IBP |  | 2026-06-25 |  | Karan
Framework | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | IBP/iWork | Milestone 4 | Delivered - Deficit | Pending: Provide the document on how do we store and view it |  | 2026-06-24 |  | Manjusha
iWork: Services - Basic Modules | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | iWork - CR | Milestone 6 | Yet to start |  |  | 2026-06-24 |  | Sunil
FRAMEWORK: Services - Larger Modules | Workflow Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Yet to start |  |  | 2026-06-26 |  | Nithin
FRAMEWORK: Services - Larger Modules | Rule Definition Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Yet to start |  |  | 2026-06-26 |  | Nithin
FRAMEWORK: Frontend | Accessibility |  | Framework | Milestone 4 | Yet to start |  |  | 2026-06-24
Framework | NFR_Security | DPDP NFR | IBP | Milestone 4 | Yet to start |  |  | 2026-06-24 |  | Tharun
IBP: Services - Larger Modules | Admin Reports | Services for multiple reports | IBP | Milestone 4 | Yet to start |  |  | 2026-06-23 |  | Abhilash
iWORK: Services - Basic Modules | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | IBP/iWork | Milestone 4 | Yet to start | Check with Gopal |  | 2026-06-24 |  | Tharun
iWORK: Services - Basic Modules | Cut Off Mgmt |  | iWork | Milestone 2 | Yet to start | Need inputs related to the implementation |  | 2026-06-26
iWORK: Frontend | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | iWork | Milestone 3 | Yet to start |  |  | 2026-06-24 |  | Pushyami
iWORK: Services - Basic Modules | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | iWork | Milestone 3 | Yet to start |  |  | 2026-06-24 |  | Pushyami
Framework: NFR | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure, which was broad symptom rather than a root cause. The renewed focus here is on failures related to cryptography which often leads to sensitive data exposure or system compromise. |  | NFR | Milestone 5 | Delivered |  |  | 2026-06-05
Framework: NFR | NFR-COM-019: Terms and Conditions: The application must ensure require the customer to accept the Terms & Conditions at the first login to the application. This ensures compliance with PII regulations requiring Company group to inform the user of why Company is accessing/collecting personal data and why Company is using it. IIRM-4480 |  | NFR | Milestone 5 | Delivered |  |  | 2026-06-05
IBP: Common Components | 3rd Party SSO | Props based SSO links to 3rd Parties | IBP | Milestone 5 | Delivered | SSO Framework implemented fro TPA |  | 2026-06-01 |  | Abhilash
IBP: FRONTEND | Static Info Sections - Landing | Benefits Guide, FAQs, Help | IBP | Milestone 5 | Delivered
IBP: FRONTEND | Initiate Claim | Initiate claim for GMC (non-cashless), upload docs etc. | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations
IBP: FRONTEND | IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | IBP/iWork | Milestone 5 | Delivered
IBP: FRONTEND | Claims Corner | View Claim Data for Individual Plans (if available), Track Status for Claims initiated from IBP for Group Plans, Track Status for Claims initiated with TPA directly, TAT reporting for Cashless (for Preauth and Discharge) | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations
IBP: SERVICES - Basic Modules | Hospital Network Mgmt | Based on the Insurer and TPA, network of hospitals needs to be presented in a consolidated view | IBP | Milestone 5 | Delivered |  |  | 2026-06-11
IBP: Services - Larger Modules | Claims Mgmt | Part-1: Company Provided Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Delivered
iWORK: Frontend | Claim Management (Add Claim, Import Claims & Claim Activities) | Basic Form with fields and upload for adding claim Bulk import to validate and map from TPA format to internal fields 3 stage workflow - each stage, update data on claim form | iWork | Milestone 5 | Delivered
iWORK: Frontend | Report Hub | Landing Page and generic hub | iWork | Milestone 5 | Delivered
iWORK: Frontend | CD Creation | Show current CD Balance against pooled/individual policies / Allow new CD creation, update CD balance and map policies to CD balances | iWork | Milestone 5 | Delivered
iWORK: Services - Basic Modules | TPA Integration Mgmt [GHPL] | Launch TPA - SSO Ecards API - Read & View Details Hospital Network Claims Status API - Read, Store & View Details Claim Intimation API Claim Live Status - Single Claim | IBP/iWork | Milestone 5 | Delivered |  |  | 2026-06-12 |  | Ravi
iWORK: Services - Basic Modules | CD Mgmt |  | iWork | Milestone 5 | Delivered
iWORK: Services - Basic Modules | Reports |  | iWork | Milestone 5 | Delivered
iWORK: Services - Basic Modules | Claim Mgmt |  | iWork | Milestone 5 | Delivered
| Wellness Banner & SSO | Add banner and SSO to Alyve Wellness (Only Banner) | IBP | Milestone 5 | Delivered |  |  | 2026-06-10
Framework: DPDP | Integrate SSO / MFA |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-06-24 |  | Sunil
Framework: DPDP | Capture consent within app |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-06-24 |  | Sunil
Framework: DPDP | Allow easy consent withdrawal |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-06-24 |  | Sunil
Framework: DPDP | Remove unnecessary fields |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-06-25 |  | Sunil
Framework: DPDP | Approval workflow |  | DPDP | Milestone 5 | Dev - Done |  |  | 2026-06-24
Framework: DPDP | Show privacy notice with purpose, retention, rights |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-06-24 |  | Sunil
Framework: DPDP | App vulnerability scans |  | DPDP | Milestone 5 | Dev - WIP |  |  | 2026-06-24
Framework: DPDP | Enable SAST |  | DPDP | Milestone 5 | Dev - WIP
iWORK: Services - Basic Modules | TPA Integration Mgmt [Framework] | 1. Framework - KIT 2. WBS - with details -Medi Assist India Pvt. Ltd. -Family Health Plan Ltd. -Health India -MD India Healthcare Services (Pvt.) Ltd. -Vidal Health TPA Private Limited -Paramount Health Services Pvt. Ltd. | IBP/iWork | Milestone 5 | Dev - WIP | 9-Jun: Shared errors to Neeraj |  | 2026-06-24
Framework: DPDP | Quarterly restore tests |  | DPDP | Milestone 5 | Pre-PROD |  |  | 2026-06-24
IBP: FRONTEND | IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | IBP | Milestone 5 | Delivered - Deficit | Pending: Wellness Program related
IBP: FRONTEND | Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | IBP | Milestone 5 | Delivered - Deficit | Pending: Offers & Discuounts |  |  |  | Manjusha
IBP: FRONTEND | User Profile | Profile, Service Subscriptions, Feedback | IBP | Milestone 5 | Delivered - Deficit | Pending: Service Subscriptions, Feedback |  |  |  | Abhilash
IBP: SERVICES - Basic Modules | Benefits Summary | End User's Summary View | IBP | Milestone 5 | Delivered - Deficit | Pending: Retail Insurance
IBP: Services - Larger Modules | Core Infrastructure | Core Infra | IBP/iWork | Milestone 5 | Delivered - Deficit | Pending: Mobile responsive
IBP: Services - Larger Modules | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | IBP | Milestone 5 | Delivered - Deficit | Pending: Offer, Feature flagging (UI)
iWork: AI Components | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | iWork - CR | Milestone 6 | Yet to start | Need some information about the document rules that defines the idenity of it |  | 2026-06-24 |  | Jagadeesh
Framework: DPDP | Map PII tables |  | DPDP | Milestone 5 | QA - WIP |  |  | 2026-06-25
Framework: DPDP | Document Flows |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-06-24
Framework: DPDP | Perform security UAT |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-06-24
Framework: DPDP | Enforce business logic to restrict purpose |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-06-24
Framework: DPDP | Enable delete pipeline |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-06-26
Framework: DPDP | Allow user corrections |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-06-26
Framework: DPDP | Delete expired data |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-06-26
Framework: DPDP | Sign DPDP clauses |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-06-26
Framework: NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | NFR | Milestone 5 | Yet to start | Need clarity |  | 2026-06-26
Framework: DPDP | Define archival |  | DPDP | Milestone 5 | Yet to start |  |  | 2026-06-30
IBP: FRONTEND | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | IBP/iWork | Milestone 5 | Yet to start
IBP: FRONTEND | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | IBP | Milestone 5 | Yet to start |  |  |  |  | Manjusha
IBP: FRONTEND | Book Ambulance | Floater on the screen - Integrate to Ambulance Service | IBP | Milestone 5 | Yet to start
IBP: FRONTEND | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | IBP | Milestone 5 | Yet to start
IBP: FRONTEND | Wellness HR View | HR View of Wellness usage by Employees | IBP | Milestone 5 | Yet to start
IBP: FRONTEND | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | IBP/iWork | Milestone 5 | Yet to start
IBP: FRONTEND | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | IBP | Milestone 5 | Yet to start | Retail insurance(facility to load user insurance policies) |  | 2026-06-19 |  | Abhilash
IBP: FRONTEND | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | IBP | Milestone 5 | Yet to start
IBP: FRONTEND | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | IBP | Milestone 5 | Yet to start | Pending: Retail insurance |  |  |  | Abhilash
IBP: FRONTEND | Profile Migration | Request migration of Corporate Profile to Individual | IBP | Milestone 5 | Yet to start
IBP: FRONTEND | Profile Migration | Request migration of Individual Profile to Corporate | IBP | Milestone 5 | Yet to start
IBP: FRONTEND | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | IBP | Milestone 5 | Yet to start | Pending: Retail insurance |  |  |  | Manjusha
IBP: Services - AI Components | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | IBP | Milestone 5 | Yet to start | External chatbot integration?
IBP: SERVICES - Basic Modules | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | IBP | Milestone 5 | Yet to start
IBP: SERVICES - Basic Modules | Feedback Mgmt | User Feedback capture service | IBP | Milestone 5 | Yet to start | IBP support is already in place
IBP: Services - Larger Modules | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | IBP | Milestone 5 | Yet to start
IBP: Services - Larger Modules | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | IBP | Milestone 5 | Yet to start
IBP: Services - Larger Modules | Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | IBP | Milestone 5 | Yet to start
IBP: Services - Larger Modules | Evexia Club Integration | Integration to Evexia | IBP | Milestone 5 | Yet to start
IBP: Services - Larger Modules | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Yet to start
IBP: Services - Larger Modules | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | IBP | Milestone 5 | Yet to start
iWork: Services - Basic Modules | Cover Mgmt | Asset fields which are captured at Broking slip, few of the asset fields should not be printed at the time of Placement slip (example, no of members at inception, total lives, prev policy expiring year etc.) only for GMC | iWork - CR | Milestone 6 | Yet to start |  |  | 2026-06-24 |  | Karan
iWORK: Frontend | View Service Score | Servicing Stats Dashboard - Single Table (drillable) to calculate an overall score | iWork | Milestone 4 | Delivered - Deficit | Pending: Meeting, MIR calculation |  | 2026-06-26 |  | Pushyami
iWork: Services - Larger Modules | Teams Integration | MS Teams - Meetings & Tasks integration into iWork | iWork | Milestone 4 | Yet to start |  |  | 2026-06-30 |  | Rama
iWORK: Frontend | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | iWork | Milestone 5 | Delivered - Deficit
iWORK: Services - Basic Modules | HRMS Integration Mgmt | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? | iWork | Milestone 5 | Yet to start
iWork: Services - Basic Modules | Insurer Management | Enhance Insurer - Add, Edit, & Contacts | iWork - CR | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Pushyami
iWork: Services - Basic Modules | Endorsement Mgmt (Non-Group / Non-GMC / Non-EB) | Enhance the Non-GMC Process (Based on Kishore feedback) | iWork - CR | Milestone 6 | Delivered |  |  | 2026-05-28 |  | Pushyami
iWork: Services - Basic Modules | Endorsement Mgmt | PROD Bug: Data Discrepancy - Inception/Endorsement vs Send to Client/Insurer (Preview & Excel) | iWork | Milestone 6 | Delivered |  |  | 2026-05-27 |  | Prathiphala
iWork: Services - Basic Modules | Endorsement Mgmt | PROD Bug: When download the TPA file, dependents are Missing in the file | iWork | Milestone 6 | Delivered |  |  | 2026-05-27 |  | Sunil
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 |  | Karan
|  | Based on recent billing - Identifying the gaps in Redis data storage and gaps in implementation | IBP/iWork | Milestone 6 | Delivered |  |  | 2026-06-08 |  | Tharun
| VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | iWork | Milestone 6 | Delivered |  |  | 2026-06-12 |  | Prathiphala
| VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| One URL multiple companies | Flexibility to configure multiple companies on a single domain | IBP/iWork | Milestone 6 | Delivered |  |  | 2026-06-17
| VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| IIRM-10588 | Hide "Manage Policy" in "Manage Placements" link. | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Pushyami
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | iWork | Milestone 6 | Delivered |  |  | 2026-06-16
| IIRM-10591 | IBP - Enrolment Journey - Reset | IBP | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Abhilash
| VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Pushyami
| VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | iWork | Milestone 6 | Delivered
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 |  | Karan
| VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Pushyami
| VRK - PROD Feedback | Manage Insurer - Add Insurer Flow | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Pushyami
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 |  | Karan
| VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | iWork | Milestone 6 | Delivered |  |  | 2026-06-12 |  | Karan
| VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Karan
| VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | iWork | Milestone 6 | Delivered | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | iWork | Milestone 6 | Delivered |  |  | 2026-06-15
| VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | iWork | Milestone 6 | Delivered |  |  | 2026-06-10 |  | Prathiphala
| VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | iWork | Milestone 6 | Delivered |  |  | 2026-06-10
| Policy Config | New Policy constraints 1. Allow first child as Twin 2. Allow second child as Triplet 3. SI per Dependent 4. Parent Lock-in period | IBP/iWork | Milestone 6 | Delivered |  |  | 2026-06-16
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | iWork | Milestone 6 | Delivered |  |  | 2026-06-15 |  | Karan
| VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | iWork | Milestone 6 | Delivered |  |  | 2026-06-10 |  | Jagadeesh
| VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | iWork | Milestone 6 | Delivered |  |  | 2026-06-10 |  | Jagadeesh
| VRK - PROD Feedback | Opty. Flow - Add new Insurer Branch Details | iWork | Milestone 6 | Delivered |  |  | 2026-06-12 |  | Pushyami
| VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | iWork | Milestone 6 | Delivered |  |  | 2026-06-12
| VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Pushyami
| VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | iWork | Milestone 6 | Delivered |  |  | 2026-06-08
| VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | iWork | Milestone 6 | Delivered |  |  | 2026-06-09 |  | Pushyami
SSO - MS AD Account | VRK - PROD Feedback: 10-Jun-2026 | iWork - SSO with Microsoft AD (POC) | iWork | Milestone 6 | Dev - Done | Showed Demo to Venu |  | 2026-06-15 |  | Rama
IBP: Services - AI Components | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | IBP - CR | Milestone 6 | Dev - WIP |  |  | 2026-06-22 |  | Tharun
| Claims Corner | Claims Corner - Screen Re-design | IBP | Milestone 6 | Dev - WIP |  |  | 2026-06-22
| VRK - PROD Feedback: 8-Jun-2026 | TPA Integration for other TPA's - Approach/Prerequisites to initiate the process. | IBP/iWork | Milestone 6 | Dev - WIP |  |  |  |  | Tharun
iWork: Services - Basic Modules | Dashboard - FinOps Data | Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | iWork | Milestone 4 | Yet to start | Duplicate of reconcilation |  | 2026-06-22
iWORK: Services - Basic Modules | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | DPDP | Milestone 4 | Yet to start | Duplicate of Archival from NFR & DPDP |  | 2026-06-30
iWork: Services - Basic Modules | Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | iWork | Milestone 4 | Yet to start |  |  | 2026-06-24 |  | Karan
iWORK: Frontend | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) | iWork | Milestone 5 | Yet to start |  |  | 2026-06-26
iWORK: Frontend | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid | iWork | Milestone 5 | Yet to start |  |  | 2026-06-26
iWORK: Services - Basic Modules | Reconciliation Mgmt |  | iWork | Milestone 5 | Yet to start |  |  | 2026-06-26
iWORK: Services - Basic Modules | Insurer Integration Mgmt |  | iWork | Milestone 5 | Yet to start |  |  | 2026-06-26
| VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | iWork | Milestone 6 | Yet to start |  |  | 2026-06-12 | 2026-06-19 | Karan
| VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | iWork | Milestone 6 | Delivered |  |  | 2026-06-12 | 2026-06-19 | Rama
| VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | iWork | Milestone 6 | Yet to start |  |  | 2026-06-16
PROD-Bug | Export to Excel | Export to excel - iWork all the results table; Download is on Previlage | iWork | Milestone 6 | Yet to start
| VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | iWork | Milestone 6 | Yet to start
| VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | iWork | Milestone 6 | Yet to start |  |  | 2026-06-22
| VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | iWork | Milestone 6 | Yet to start
| VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | iWork | Milestone 6 | Yet to start |  |  | 2026-06-22 |  | Karan
| Rewards | Rewards - Specific & Generic Rewards - Start with a form and collect data | iWork | Milestone 6 | Yet to start
2026-06-19 | Discuss with Madhav | Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard)
Also, check if we are there are any data loads for 2025-26
Find a better way to get the details from Service team for Policy config
External API integration - Framework with utiliity transformation
Utility - Transformation - Make it Generic for Source to Destination columns
Sagar - Provide access after the call.
Dashboard - Hide the widgets where there is NO data in the cards
BizDone - Export feature is should be Previlage
BizDone - New Role or Previlage - Show org. full data
| Policy Component - Strapi | IBP Portal - Each card should have sepeare points & Policy feature documents | iWork | Milestone 5
| IIRM-10666 | IBP - Policy Component Card Re-design | IBP | Milestone 6 | Yet to start
| IIRM-10667 | iWork - Knowledge Central Re-Design | iWork | Milestone 6 | Yet to start
| IIRM-10668 | iLearn: Document Preview in-app | iWork | Milestone 6 | Yet to start

## ② Pending Roadmap
PENDING ROADMAP — Remaining Deliverables (live from SOW sheet)
🔎 Delivered & N/A items are filtered out by default. Click the filter arrow on the 'Delivery' column (F5) → tick 'Delivered' or 'Select All' to show them.
Milestone | Module | Feature | Functionality | Status | Delivery | ETA | Resource | Remarks
Milestone 1 | Framework | Project setup | Basic project / Development environment setup | Delivered | Delivered
Milestone 1 | Framework | UI Approach Design System | Building Design System | Delivered | Delivered
Milestone 1 | Framework | Core Infrastructure | Core Infra | Delivered | Delivered
Milestone 1 | Framework | Build UI components | This includes all the UI componnets to compose the application and module definitions: Form, Toast, Filter, Cards, Visualisation, Grid, Menu, Header, Footer, Maps Integration | Delivered | Delivered
Milestone 1 | Framework | UI Approach Style Establishment | UI Style Establishment | Delivered | Delivered
Milestone 1 | Framework | Service Workers Implementation | 0 | Delivered | Delivered
Milestone 1 | Framework | Core System | 0 | Delivered | Delivered
Milestone 1 | Framework | ACL & RBAC Control Framework | 0 | Delivered | Delivered
Milestone 1 | Framework | Micro Frontend Setup | 0 | Delivered | Delivered
Milestone 1 | Framework | Landing Page | 0 | Delivered | Delivered
Milestone 1 | Framework | Access Control Management | 0 | Delivered | Delivered
Milestone 1 | Framework | Auth Module (Simple Auth) | 0 | Delivered | Delivered
Milestone 1 | Framework | Micro Service Framework Setup | 0 | Delivered | Delivered
Milestone 1 | iWork | Common - Audit Trail Mgmt - Becomes critical in this phase iteself | 0 | Delivered | Delivered
Milestone 1 | iWork | Add/View/Edit Opportunity | Add Medium size form with 1->N list of Claims; Multiple drop downs Large View with several widgets, Simple Edit | Delivered | Delivered
Milestone 1 | iWork | Manage TPA/Insurer | Basic Add, View with edit of basic data, with lists of policies/companies | Delivered | Delivered
Milestone 1 | iWork | Core Infra | Infrastructure | Delivered | Delivered
Milestone 1 | iWork | Add/View/Edit Company | Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. Simple edit like Add; View is multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | Delivered | Delivered
Milestone 1 | iWork | Insurer/TPA Hub | List with Filter/Search | Delivered | Delivered
Milestone 1 | iWork | Add/View/Edit Contact | Simple edit like Add Contacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | Delivered | Delivered
Milestone 1 | iWork | Company (Prospect) Hub | Top 10/Latest companies, with search/filter, Table of basic attributes with GPS etc. | Delivered | Delivered
Milestone 1 | iWork | Contact Hub | Top 10/Latest Contacts, with search/filter, list with basic attributes | Delivered | Delivered
Milestone 1 | iWork | Opportunity Hub | Top Opportunities with search/filter, List of opportunities with high level summaries | Delivered | Delivered
Milestone 1 | iWork | Employee Mgmt | 0 | Delivered | Delivered | 2026-06-12 |  | User deletion need to be handled
Milestone 1 | iWork | Contact /Company/Insurer/TPA Mgmt | 0 | Delivered | Delivered
Milestone 1 | iWork | Task Mgmt | 0 | Delivered | Delivered
Milestone 1 | iWork | Meeting Mgmt | 0 | Delivered | Delivered
Milestone 1 | iWork | RBAC and ACL setup for Iwork Module | 0 | Delivered | Delivered
Milestone 1 | iWork | Opportunity Mgmt | 0 | Delivered | Delivered
Milestone 2 | Framework | Visualization framework | Charts and KPIs | Delivered | Delivered
Milestone 2 | Framework | Document Management | Create, Upload, Seach, Download | Delivered | Delivered
Milestone 2 | Framework | Master Data Management | 0 | Delivered | Delivered | 2026-05-27
Milestone 2 | Framework | Caching of API Data | 0 | Delivered | Delivered
Milestone 2 | Framework | Audit Data Capturing | 0 | Delivered | Delivered
Milestone 2 | Framework | CMS | 0 | Delivered | Delivered |  |  | Used in IBP
Milestone 2 | iWork | AI - (Non-OCR) Digital Document Processing for Content recognition (Company/Opportunity/Contact Creation from Previous Policy Document, Bizcard document) | 0 | Delivered | Delivered
Milestone 2 | iWork | AI - OCR for Content Collection | 0 | Delivered | Delivered
Milestone 2 | iWork | AI - Company Information by AI Search | 0 | Delivered | Delivered
Milestone 2 | iWork | Common, Contexual Upload Component | 0 | Delivered | Delivered
Milestone 2 | iWork | Common, Contexual Read and Spread Component (Utility) | 0 | Delivered | Delivered
Milestone 2 | iWork | Manage Stage Planning/Performance/Approval | Add iWork Stages (table) - Dates with each iWork Stage and who are the team members assigned to each Stage; Once all iWork stages are complete, ISG Team activities must be planned ISG Team can approve/reject each iWork Stage. Approving RFP Stage approves all iWork stages Completion of each iWork Stage (Activity) & ISG Stage - Comments, Attach Document, Date recorded, submit | Delivered | Delivered
Milestone 2 | iWork | Smart Add Component | Allow Upload of Document/Image, select what to create (Company/Contact/Opportunity) | Delivered | Delivered
Milestone 2 | iWork | Dashboard - Drilldowns | Drill down from the Tables (Targets vs. Actuals, Pending Activities, Followups, AR Report, Schedule) | Delivered | Delivered
Milestone 2 | iWork | Sales Team Hierarchy | Hierarchy / Org chart tied to Platform Users | Delivered | Delivered
Milestone 2 | iWork | View Policy | Long View, multiple widgets/entities, endorsements (each month), Claims, etc. | Delivered | Delivered
Milestone 2 | iWork | Common Data Mapping Component | Map input fields to output fields & Order | Delivered | Delivered | 2026-06-09 |  | Pending: Additional/Dynamic columns
Milestone 2 | iWork | Dashboard | Multiple KPI Cards: Business Performance, Svc Performance, Table of targets vs. actuals vs. lost, Sales Funnel, Renewal Funnel, Servce Funnel, AR from Insurers, Pending Activities(iWork Stages) Widget, Followups widget, Meetings widget Filters available (Geo, Branch, Team/Team Member, Dates), Approvals, iWork Stages, Tasks, Meetings | Delivered | Delivered
Milestone 2 | iWork | Dashboard - Pending tasks, approvals | Pending tasks/approvals, | Delivered | Delivered
Milestone 2 | iWork | Reports - Biz Done | Report View, Download, List of earlier snaps of the report, Search and Filter | Delivered | Delivered
Milestone 2 | iWork | Core Infrastructure | Core Infra | Delivered | Delivered
Milestone 2 | iWork | Organisation, Branch, Employee, & Hierarchy Mgmt | 0 | Delivered | Delivered
Milestone 2 | iWork | Dashboard (Place Holder) | 0 | Delivered | Delivered
Milestone 2 | iWork | Planning, Perform and Approval Mgmt | 0 | Delivered | Delivered
Milestone 2 | iWork | Policy Mgmt | 0 | Delivered | Delivered
Milestone 2 | iWork | Master Data Mgmt {Common, Contexual Master Data Mgmt} | 0 | Delivered | Delivered
Milestone 2 | Framework | User Management | 22-May: Other than iWork employee | Delivered | Delivered | 2026-06-12 |  | Pending: User deletion
Milestone 2 | Framework | User Management | 22-May: Other than iWork employee | Delivered | Delivered | 2026-06-12 |  | Pending: User deletion
Milestone 2 | Framework | Data Security Considerations | 0 | Delivered | Delivered | 2026-06-30 |  | Duplicate of Covers in DPDP items
Milestone 3 | IBP | 0 | Risk Watch: Showing policy feature documents at each policy | Pre-PROD | Pending | 2026-06-09 | Ravi
Milestone 4 | IBP | IBP - Portal Setup | Post policy creation, create default IBP Portal Config for all the company-policy(ies) | Pre-PROD | Pending | 2026-06-10 | Manjusha
Milestone 4 | iWork | Dashboard - FinOps Data | Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | Yet to start | Pending | 2026-06-22 |  | Duplicate of reconcilation
Milestone 3 | Framework | Document Generation | 0 | Delivered | Delivered
Milestone 3 | iWork | Manage Policy (Endorsements) | Add Endorsement - basic form with uploads of excel/document Validations of endorsement format - Map customer fields to internal fields Map internal fields to TPA fields (occasional per TPA) View/Update Endorsement, List View, Endorsement Performance | Delivered | Delivered
Milestone 3 | iWork | Cover Mgmt | 0 | Delivered | Delivered | 2026-06-10 | Karan
Milestone 3 | iWork | Stage Mgmt (Activity/Transaction/Quote) | 0 | Delivered | Delivered
Milestone 3 | iWork | Asset/Member Data Mgmt | 0 | Delivered | Delivered
Milestone 3 | iWork | Endorsement Mgmt | 0 | Delivered | Delivered
Milestone 5 | iWork | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid | Yet to start | Pending | 2026-06-26
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | Yet to start | Pending | 2026-06-12 | Karan
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | Delivered | Delivered | 2026-06-12 | Rama
Milestone 4 | IBP | NFR_Usability | NFR-USA-015: The system must show personalized welcome messages and profile information based on locale. | Delivered | Delivered
Milestone 4 | IBP | NFR_Usability | NFR-USA-016: Notification banners must be dismissible and configurable based on role. | Delivered | Delivered |  |  | No notifications in IBP
Milestone 4 | IBP | NFR_Usability | NFR-USA-018: The session management should be configurable from UI 23-May: Configure from UI & store in DB; When changed then restart server | Delivered | Delivered | 2026-06-15 | Manjusha
Milestone 4 | Framework | Notifications Management | 0 | Delivered | Delivered
Milestone 4 | Framework | Configuration Management | 0 | Delivered | Delivered |  |  | Considered Policy Config
Milestone 4 | Framework | Feature Flag Control Management | 0 | Delivered | Delivered
Milestone 4 | Framework | Localistation Management | 0 | Delivered | Delivered
Milestone 4 | Framework | Caching Implementation | 0 | Delivered | Delivered
Milestone 4 | IBP | Simple Auth | Username and Password based authentication and RBAC on simple-auth users. Auth rules needs configuration capability. IBP - HR User Management | Delivered | Delivered | 2026-06-12 | Abhilash
Milestone 4 | IBP | Whitelabelling Support | 0 | Delivered | Delivered
Milestone 4 | IBP | Company Plans | 6 Policies - GMC, GPA, GTL, Parental Plicy, Top-ups, OPD Policy (Summary view of policies) | Delivered | Delivered
Milestone 4 | IBP/iWork | Company Plan Configurator | Admin side of IBP should configure (per Corporate) how to define a Policy and determine how it breaks down the Premium and Coverage rules | Delivered | Delivered
Milestone 4 | IBP | IBP Landing Page - Basic | Basic Landing Page with only company plans and summart | Delivered | Delivered
Milestone 4 | IBP/iWork | Auth Config UI | Config for Auth Rules setup | Delivered | Delivered
Milestone 4 | IBP/iWork | Contact Matrix | Configure the Conact Info Matrix (IBP Admin) | Delivered | Delivered
Milestone 4 | IBP | Contact Matrix View | Contact Matrix View for end user | Delivered | Delivered
Milestone 4 | IBP | Core Infrastructure | Core Infra | Delivered | Delivered
Milestone 4 | IBP | My Documents | Document Hub - Covers Policies, Prescriptions, Reports | Delivered | Delivered | 2026-06-12 | Manjusha | Pending: Design
Milestone 4 | IBP | HR Portal View | Employee Search, Resend Email, Delete Employees, Extend Enrollment Windows, Reports, Bulk Email | Delivered | Delivered | 2026-06-11 | Abhilash
Milestone 4 | IBP | Per-policy Enrolment | Enrolment and addon policy selection | Delivered | Delivered
Milestone 4 | IBP | Policy Document | IBP-Risk Watch: Show the each policy document | Delivered | Delivered | 2026-06-19 | Tharun
Milestone 4 | IBP | My Insurance | Part-1: Hub of all plans I have as an employee - Company provided. Mostly a navigational page | Delivered | Delivered
Milestone 4 | IBP/iWork | Whitelabelling | Whitelabelling based on Org needs (IBP Admin) | Delivered | Delivered
Milestone 4 | IBP | Basic Landing Page Services | Company provided plans only | Delivered | Delivered
Milestone 4 | IBP | Document Mgmt for End User | Insurance, Health Reports and Prescriptions {No automatic pull from Partners} | Delivered | Delivered | 2026-06-12 | Manjusha | Pending: Design
Milestone 4 | IBP | Personal Profile Mgmt | Profile settings | Delivered | Delivered | 2026-06-10 | Manjusha | Pending:Add Dependents
Milestone 4 | IBP | Group Policy Mgmt - Enrollment | Enrollment (Adding Dependents, Choosing Options available). Submit the enrollment to Insurer or TPA 6 Types of Policies to be considered | Delivered | Delivered |  |  | Need Confirmation: If scope has, Insurer & TPA integrations, then they are pending
Milestone 4 | IBP | Group Policy Mgmt - Enrollment Configurator | Enrollment Configurator (Set of benefits and type of Dependent combinations allowed etc). This is more of an Iwork feature to configure the policy | Delivered | Delivered
Milestone 4 | IBP | End User onboarding | Generate Users, Send Emails, Password Rest | Delivered | Delivered
Milestone 4 | IBP | IBP - User Management | IBP: HR Portal - Company-Scoped Employee Access for Client HR (Ex. TeamLease's Customer) | Delivered | Delivered | 2026-05-26
Milestone 4 | IBP | Contact Matrix Configuration | Matrix of Contact Infomration | Delivered | Delivered
Milestone 4 | IBP | HR/Admin Portal View | Supporting services for Admin Portal | Delivered | Delivered
Milestone 4 | iWork | Knowledge Central | Grouped list of Documents/Resources, Add a Document, Remove a Document (Add/remove only for admins) | Delivered | Delivered
Milestone 4 | iWork | Endorsement Mgmt | Additional columns in file like Department, DOJ, Emp. Location, Vertical, Others | Delivered | Delivered | 2026-05-29 | Pushyami
Milestone 4 | iWork | Reports - Biz Done | Bizonde filter/table - Add "Income type" | Delivered | Delivered | 2026-05-26 | Karan
Milestone 4 | IBP/iWork | Client - Associated Location (IBP HR Module) | IBP - HR: Policy Location - Add Company Associated Locations, Flow to Opty., Policy & Policy Config | Delivered | Delivered | 2026-05-25 | Karan
Milestone 4 | iWork | Opportunity | Opportunity History details are unavailable for the end user to view. Show TAT section (Planned date, Performed/Completed date, Approved date) for planned acitivites | Delivered | Delivered | 2026-05-28 | Pushyami
Milestone 4 | iWork | Opportunity | RO Scheduler Enhancements | Delivered | Delivered | 2026-05-29 | Jagadeesh
Milestone 4 | iWork | Knowledge Central | 0 | Delivered | Delivered
Milestone 4 | iWork | TAT/SLA Mgmt (Including Service Score) | 0 | Delivered | Delivered
Milestone 4 | iWork | Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | Yet to start | Pending | 2026-06-24 | Karan
Milestone 4 | DPDP | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP | 0 | Yet to start | Pending | 2026-06-30 |  | Duplicate of Archival from NFR & DPDP
Milestone 5 | iWork | Insurer Integration Mgmt | 0 | Yet to start | Pending | 2026-06-26
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | Yet to start | Pending | 2026-06-16
Milestone 6 | iWork | IIRM-10587 | Add new fields - Business Month & Date of Business - Capture in Opty. & Flow to Policy and add filters in BizDone --> Refer to Madhav email "Business Month Requirement" | Delivered - Deficit | Pending | 2026-06-22 | Pushyami | Pending: Additional filters
Milestone 6 | iWork - CR | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | Yet to start | Pending | 2026-06-12
Milestone 6 | iWork | IIRM-10590 | Policy Config: Dependent Based Configurations - Per life depedent addition & increase SI - Apply Policy Parameters for dependents | Delivered | Delivered | 2026-06-15 | Jagadeesh
Milestone 4 | IBP | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | Pre-PROD | Pending | 2026-06-17 | Akhila
Milestone 5 | iWork | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) | Yet to start | Pending | 2026-06-26
Milestone 5 | iWork | Reconciliation Mgmt | 0 | Yet to start | Pending | 2026-06-26
Milestone 6 | iWork - CR | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | Yet to start | Pending | 2026-06-24 | Sunil
Milestone 3 | iWork | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | Yet to start | Pending | 2026-06-24 | Pushyami
Milestone 6 | iWork - CR | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | Yet to start | Pending | 2026-06-24 | Jagadeesh | Need some information about the document rules that defines the idenity of it
Milestone 5 | IBP | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | Yet to start | Pending | 2026-06-19 | Abhilash | Retail insurance(facility to load user insurance policies)
Milestone 4 | iWork | Teams Integration | MS Teams - Meetings & Tasks integration into iWork | Yet to start | Pending | 2026-06-30 | Rama
Milestone 4 | IBP/iWork | Security | InfoSec - IBP Portal (Security Issue) 19-Jun: Critical - 0 High - 3 Pending Medium - 24 pending Low - 2 pending | Dev - WIP | Pending | 2026-06-22
Milestone 6 | iWork - CR | Policy Configuration | Using AI - Extract the Policy document and perform Policy Configuration (Premium, Family, Parameters, & Others) | QA - WIP | Pending | 2026-06-16 | Jagadeesh
Milestone 5 | NFR | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure, which was broad symptom rather than a root cause. The renewed focus here is on failures related to cryptography which often leads to sensitive data exposure or system compromise. | 0 | Delivered | Delivered | 2026-06-05
Milestone 5 | NFR | NFR-COM-019: Terms and Conditions: The application must ensure require the customer to accept the Terms & Conditions at the first login to the application. This ensures compliance with PII regulations requiring Company group to inform the user of why Company is accessing/collecting personal data and why Company is using it. IIRM-4480 | 0 | Delivered | Delivered | 2026-06-05
Milestone 5 | IBP | 3rd Party SSO | Props based SSO links to 3rd Parties | Delivered | Delivered | 2026-06-01 | Abhilash | SSO Framework implemented fro TPA
Milestone 5 | IBP | Static Info Sections - Landing | Benefits Guide, FAQs, Help | Delivered | Delivered
Milestone 5 | IBP | Initiate Claim | Initiate claim for GMC (non-cashless), upload docs etc. | Delivered | Delivered |  |  | Pending: TPA & Insurer API integrations
Milestone 5 | IBP/iWork | IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | Delivered | Delivered
Milestone 5 | IBP | Claims Corner | View Claim Data for Individual Plans (if available), Track Status for Claims initiated from IBP for Group Plans, Track Status for Claims initiated with TPA directly, TAT reporting for Cashless (for Preauth and Discharge) | Delivered | Delivered |  |  | Pending: TPA & Insurer API integrations
Milestone 5 | IBP | Hospital Network Mgmt | Based on the Insurer and TPA, network of hospitals needs to be presented in a consolidated view | Delivered | Delivered | 2026-06-11
Milestone 5 | IBP | Claims Mgmt | Part-1: Company Provided Policy based claim mgmt, Tracking status, Document Mgmt related to claims | Delivered | Delivered
Milestone 5 | iWork | Claim Management (Add Claim, Import Claims & Claim Activities) | Basic Form with fields and upload for adding claim Bulk import to validate and map from TPA format to internal fields 3 stage workflow - each stage, update data on claim form | Delivered | Delivered
Milestone 5 | iWork | Report Hub | Landing Page and generic hub | Delivered | Delivered
Milestone 5 | iWork | CD Creation | Show current CD Balance against pooled/individual policies / Allow new CD creation, update CD balance and map policies to CD balances | Delivered | Delivered
Milestone 5 | IBP/iWork | TPA Integration Mgmt [GHPL] | Launch TPA - SSO Ecards API - Read & View Details Hospital Network Claims Status API - Read, Store & View Details Claim Intimation API Claim Live Status - Single Claim | Delivered | Delivered | 2026-06-12 | Ravi
Milestone 5 | iWork | CD Mgmt | 0 | Delivered | Delivered
Milestone 5 | iWork | Reports | 0 | Delivered | Delivered
Milestone 5 | iWork | Claim Mgmt | 0 | Delivered | Delivered
Milestone 5 | IBP | Wellness Banner & SSO | Add banner and SSO to Alyve Wellness (Only Banner) | Delivered | Delivered | 2026-06-10
Milestone 5 | DPDP | Integrate SSO / MFA | 0 | Dev - Done | Delivered | 2026-06-24 | Sunil
Milestone 5 | DPDP | Capture consent within app | 0 | Dev - Done | Delivered | 2026-06-24 | Sunil
Milestone 5 | DPDP | Allow easy consent withdrawal | 0 | Dev - Done | Delivered | 2026-06-24 | Sunil
Milestone 5 | DPDP | Remove unnecessary fields | 0 | Dev - Done | Delivered | 2026-06-25 | Sunil
Milestone 5 | DPDP | Approval workflow | 0 | Dev - Done | Delivered | 2026-06-24
Milestone 3 | iWork | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | Yet to start | Pending | 2026-06-24 | Pushyami
Milestone 6 | IBP - CR | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | Dev - WIP | Pending | 2026-06-22 | Tharun
Milestone 6 | IBP | Claims Corner | Claims Corner - Screen Re-design | Dev - WIP | Pending | 2026-06-22
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | Yet to start | Pending | 2026-06-22 | Karan
Milestone 4 | IBP | Admin Reports | Services for multiple reports | Yet to start | Pending | 2026-06-23 | Abhilash
Milestone 2 | Framework | Notification and Communication Management | 23-May: In-App, Emails, SMS, both or all. Template vs Channel | Delivered - Deficit | Pending | 2026-06-24 |  | Pending: Configuration UI
Milestone 4 | IBP | Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | Pre-PROD | Pending | 2026-06-24 | Tharun | Pending: HR Module - Endorsement
Milestone 4 | IBP/iWork | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | Delivered - Deficit | Pending | 2026-06-24 | Manjusha | Pending: Provide the document on how do we store and view it
Milestone 4 | Framework | Accessibility | 0 | Yet to start | Pending | 2026-06-24
Milestone 4 | IBP | NFR_Security | DPDP NFR | Yet to start | Pending | 2026-06-24 | Tharun
Milestone 4 | IBP/iWork | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | Yet to start | Pending | 2026-06-24 | Tharun | Check with Gopal
Milestone 2 | iWork | Cut Off Mgmt | 0 | Yet to start | Pending | 2026-06-26 |  | Need inputs related to the implementation
Milestone 5 | DPDP | Show privacy notice with purpose, retention, rights | 0 | Dev - WIP | Pending | 2026-06-24 | Sunil
Milestone 5 | DPDP | App vulnerability scans | 0 | Dev - WIP | Pending | 2026-06-24
Milestone 5 | IBP/iWork | TPA Integration Mgmt [Framework] | 1. Framework - KIT 2. WBS - with details -Medi Assist India Pvt. Ltd. -Family Health Plan Ltd. -Health India -MD India Healthcare Services (Pvt.) Ltd. -Vidal Health TPA Private Limited -Paramount Health Services Pvt. Ltd. | Dev - WIP | Pending | 2026-06-24 |  | 9-Jun: Shared errors to Neeraj
Milestone 5 | DPDP | Quarterly restore tests | 0 | Pre-PROD | Pending | 2026-06-24
Milestone 5 | DPDP | Document Flows | 0 | Yet to start | Pending | 2026-06-24
Milestone 5 | DPDP | Enforce business logic to restrict purpose | 0 | Yet to start | Pending | 2026-06-24
Milestone 5 | DPDP | Allow user corrections | 0 | Yet to start | Pending | 2026-06-26
Milestone 2 | Framework | Usage Tracking System (Reports) | 23-May: Handle as a part of Reports | Delivered - Deficit | Pending | 2026-06-25 |  | Pending: IBP usage
Milestone 4 | Framework | Localisation | 0 | Delivered - Deficit | Pending | 2026-06-25 | Karan | Pending: Service Flow & IBP
Milestone 4 | Framework | Workflow Management | 23-May: Integrate the 3'rd party libraries | Yet to start | Pending | 2026-06-26 | Nithin
Milestone 4 | Framework | Rule Definition Management | 23-May: Integrate the 3'rd party libraries | Yet to start | Pending | 2026-06-26 | Nithin
Milestone 5 | DPDP | Map PII tables | 0 | QA - WIP | Pending | 2026-06-25
Milestone 5 | DPDP | Perform security UAT | 0 | Yet to start | Pending | 2026-06-24
Milestone 5 | DPDP | Enable delete pipeline | 0 | Yet to start | Pending | 2026-06-26
Milestone 5 | DPDP | Delete expired data | 0 | Yet to start | Pending | 2026-06-26
Milestone 5 | NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. | 0 | Yet to start | Pending | 2026-06-26 |  | Need clarity
Milestone 5 | DPDP | Define archival | 0 | Yet to start | Pending | 2026-06-30
Milestone 6 | iWork - CR | Cover Mgmt | Asset fields which are captured at Broking slip, few of the asset fields should not be printed at the time of Placement slip (example, no of members at inception, total lives, prev policy expiring year etc.) only for GMC | Yet to start | Pending | 2026-06-24 | Karan
Milestone 4 | iWork | View Service Score | Servicing Stats Dashboard - Single Table (drillable) to calculate an overall score | Delivered - Deficit | Pending | 2026-06-26 | Pushyami | Pending: Meeting, MIR calculation
Milestone 5 | iWork | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | Delivered - Deficit | Pending
Milestone 5 | iWork | HRMS Integration Mgmt | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? | Yet to start | Pending
Milestone 5 | DPDP | Sign DPDP clauses | 0 | Yet to start | Pending | 2026-06-26
Milestone 5 | DPDP | Enable SAST | 0 | Dev - WIP | Pending
Milestone 5 | IBP | IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | Delivered - Deficit | Pending |  |  | Pending: Wellness Program related
Milestone 5 | IBP | Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | Delivered - Deficit | Pending |  | Manjusha | Pending: Offers & Discuounts
Milestone 5 | IBP | User Profile | Profile, Service Subscriptions, Feedback | Delivered - Deficit | Pending |  | Abhilash | Pending: Service Subscriptions, Feedback
Milestone 5 | IBP | Benefits Summary | End User's Summary View | Delivered - Deficit | Pending |  |  | Pending: Retail Insurance
Milestone 5 | IBP/iWork | Core Infrastructure | Core Infra | Delivered - Deficit | Pending |  |  | Pending: Mobile responsive
Milestone 5 | IBP | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | Delivered - Deficit | Pending |  |  | Pending: Offer, Feature flagging (UI)
Milestone 5 | IBP/iWork | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | Yet to start | Pending
Milestone 5 | IBP | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | Yet to start | Pending |  | Manjusha
Milestone 5 | IBP | Book Ambulance | Floater on the screen - Integrate to Ambulance Service | Yet to start | Pending
Milestone 5 | IBP | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | Yet to start | Pending
Milestone 5 | IBP | Wellness HR View | HR View of Wellness usage by Employees | Yet to start | Pending
Milestone 5 | IBP/iWork | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | Yet to start | Pending
Milestone 5 | IBP | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | Yet to start | Pending
Milestone 6 | iWork - CR | Insurer Management | Enhance Insurer - Add, Edit, & Contacts | Delivered | Delivered | 2026-06-09 | Pushyami
Milestone 6 | iWork - CR | Endorsement Mgmt (Non-Group / Non-GMC / Non-EB) | Enhance the Non-GMC Process (Based on Kishore feedback) | Delivered | Delivered | 2026-05-28 | Pushyami
Milestone 6 | iWork | Endorsement Mgmt | PROD Bug: Data Discrepancy - Inception/Endorsement vs Send to Client/Insurer (Preview & Excel) | Delivered | Delivered | 2026-05-27 | Prathiphala
Milestone 6 | iWork | Endorsement Mgmt | PROD Bug: When download the TPA file, dependents are Missing in the file | Delivered | Delivered | 2026-05-27 | Sunil
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | Delivered | Delivered | 2026-06-15 | Karan
Milestone 6 | IBP/iWork | 0 | Based on recent billing - Identifying the gaps in Redis data storage and gaps in implementation | Delivered | Delivered | 2026-06-08 | Tharun
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | Delivered | Delivered | 2026-06-12 | Prathiphala
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | Delivered | Delivered | 2026-06-08
Milestone 6 | IBP/iWork | One URL multiple companies | Flexibility to configure multiple companies on a single domain | Delivered | Delivered | 2026-06-17
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | IIRM-10588 | Hide "Manage Policy" in "Manage Placements" link. | Delivered | Delivered | 2026-06-09 | Pushyami
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | Delivered | Delivered | 2026-06-16
Milestone 6 | IBP | IIRM-10591 | IBP - Enrolment Journey - Reset | Delivered | Delivered | 2026-06-09 | Abhilash
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | Delivered | Delivered | 2026-06-09 | Pushyami
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | Delivered | Delivered
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | Delivered | Delivered | 2026-06-15 | Karan
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | Delivered | Delivered | 2026-06-09 | Pushyami
Milestone 6 | iWork | VRK - PROD Feedback | Manage Insurer - Add Insurer Flow | Delivered | Delivered | 2026-06-09 | Pushyami
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | Delivered | Delivered | 2026-06-15 | Karan
Milestone 6 | iWork | VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | Delivered | Delivered | 2026-06-12 | Karan
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | Delivered | Delivered | 2026-06-09 | Karan
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | Delivered | Delivered |  |  | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | Delivered | Delivered | 2026-06-15
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | Delivered | Delivered | 2026-06-10 | Prathiphala
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | Delivered | Delivered | 2026-06-10
Milestone 6 | IBP/iWork | Policy Config | New Policy constraints 1. Allow first child as Twin 2. Allow second child as Triplet 3. SI per Dependent 4. Parent Lock-in period | Delivered | Delivered | 2026-06-16
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | Delivered | Delivered | 2026-06-15 | Karan
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | Delivered | Delivered | 2026-06-10 | Jagadeesh
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | Delivered | Delivered | 2026-06-10 | Jagadeesh
Milestone 6 | iWork | VRK - PROD Feedback | Opty. Flow - Add new Insurer Branch Details | Delivered | Delivered | 2026-06-12 | Pushyami
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | Delivered | Delivered | 2026-06-12
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | Delivered | Delivered | 2026-06-09 | Pushyami
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | Delivered | Delivered | 2026-06-08
Milestone 6 | iWork | VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | Delivered | Delivered | 2026-06-09 | Pushyami
Milestone 6 | iWork | VRK - PROD Feedback: 10-Jun-2026 | iWork - SSO with Microsoft AD (POC) | Dev - Done | Delivered | 2026-06-15 | Rama | Showed Demo to Venu
Milestone 5 | IBP | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | Yet to start | Pending |  | Abhilash | Pending: Retail insurance
Milestone 5 | IBP | Profile Migration | Request migration of Corporate Profile to Individual | Yet to start | Pending
Milestone 5 | IBP | Profile Migration | Request migration of Individual Profile to Corporate | Yet to start | Pending
Milestone 5 | IBP | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | Yet to start | Pending |  | Manjusha | Pending: Retail insurance
Milestone 5 | IBP | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | Yet to start | Pending |  |  | External chatbot integration?
Milestone 5 | IBP | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | Yet to start | Pending
Milestone 5 | IBP | Feedback Mgmt | User Feedback capture service | Yet to start | Pending |  |  | IBP support is already in place
Milestone 5 | IBP | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | Yet to start | Pending
Milestone 5 | IBP | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | Yet to start | Pending
Milestone 5 | IBP | Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | Yet to start | Pending
Milestone 5 | IBP | Evexia Club Integration | Integration to Evexia | Yet to start | Pending
Milestone 5 | IBP | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | Yet to start | Pending
Milestone 5 | IBP | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | Yet to start | Pending
Milestone 6 | IBP/iWork | VRK - PROD Feedback: 8-Jun-2026 | TPA Integration for other TPA's - Approach/Prerequisites to initiate the process. | Dev - WIP | Pending |  | Tharun
Milestone 6 | iWork | Export to Excel | Export to excel - iWork all the results table; Download is on Previlage | Yet to start | Pending
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | Yet to start | Pending
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | Yet to start | Pending | 46195
Milestone 6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | Yet to start | Pending
Milestone 6 | iWork | Rewards | Rewards - Specific & Generic Rewards - Start with a form and collect data | Yet to start | Pending

## ③ Milestone Summary
MILESTONE SUMMARY — Pending Items by Milestone & Module
Counts show PENDING items only (Delivered & N/A excluded). Live from the SOW sheet.
Milestone | iWork (Backlog) | iWork (Change Requests) | IBP (Backlog) | IBP (Change Requests) | IBP / iWork (Shared) | Framework | DPDP | NFR | TOTAL PENDING
Milestone 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 2 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3
Milestone 3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3
Milestone 4 | 4 | 0 | 5 | 0 | 3 | 4 | 1 | 0 | 17
Milestone 5 | 6 | 0 | 24 | 0 | 4 | 0 | 13 | 1 | 48
Milestone 6 | 9 | 5 | 1 | 1 | 1 | 0 | 0 | 0 | 17
TOTAL | 22 | 5 | 31 | 1 | 8 | 6 | 14 | 1 | 88

## Helper (hidden)
Module | Phase | Status | Category | Bucket
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
iWork | Milestone 1 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
iWork | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered | Delivered | Delivered
Framework | Milestone 2 | Delivered - Deficit | Partial Delivery | Pending
Framework | Milestone 2 | Delivered - Deficit | Partial Delivery | Pending
iWork | Milestone 6 | Delivered - Deficit | Partial Delivery | Pending
Framework | Milestone 3 | Delivered | Delivered | Delivered
iWork | Milestone 3 | Delivered | Delivered | Delivered
iWork | Milestone 3 | Delivered | Delivered | Delivered
iWork | Milestone 3 | Delivered | Delivered | Delivered
iWork | Milestone 3 | Delivered | Delivered | Delivered
iWork | Milestone 3 | Delivered | Delivered | Delivered
IBP | Milestone 3 | Pre-PROD | Pre-PROD / UAT | Pending
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
Framework | Milestone 4 | Delivered | Delivered | Delivered
Framework | Milestone 4 | Delivered | Delivered | Delivered
Framework | Milestone 4 | Delivered | Delivered | Delivered
Framework | Milestone 4 | Delivered | Delivered | Delivered
Framework | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
IBP | Milestone 4 | Delivered | Delivered | Delivered
iWork | Milestone 4 | Delivered | Delivered | Delivered
iWork | Milestone 4 | Delivered | Delivered | Delivered
iWork | Milestone 4 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered
iWork | Milestone 4 | Delivered | Delivered | Delivered
iWork | Milestone 4 | Delivered | Delivered | Delivered
iWork | Milestone 4 | Delivered | Delivered | Delivered
iWork | Milestone 4 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 4 | Dev - WIP | In Development | Pending
iWork - CR | Milestone 6 | QA - WIP | In QA | Pending
IBP | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending
IBP | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending
IBP | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending
Framework | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending
IBP/iWork | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending
Framework | Milestone 4 | Yet to start | Not Started | Pending
Framework | Milestone 4 | Yet to start | Not Started | Pending
Framework | Milestone 4 | Yet to start | Not Started | Pending
IBP | Milestone 4 | Yet to start | Not Started | Pending
IBP | Milestone 4 | Yet to start | Not Started | Pending
IBP/iWork | Milestone 4 | Yet to start | Not Started | Pending
iWork | Milestone 2 | Yet to start | Not Started | Pending
iWork | Milestone 3 | Yet to start | Not Started | Pending
iWork | Milestone 3 | Yet to start | Not Started | Pending
NFR | Milestone 5 | Delivered | Delivered | Delivered
NFR | Milestone 5 | Delivered | Delivered | Delivered
IBP | Milestone 5 | Delivered | Delivered | Delivered
IBP | Milestone 5 | Delivered | Delivered | Delivered
IBP | Milestone 5 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered
IBP | Milestone 5 | Delivered | Delivered | Delivered
IBP | Milestone 5 | Delivered | Delivered | Delivered
IBP | Milestone 5 | Delivered | Delivered | Delivered
iWork | Milestone 5 | Delivered | Delivered | Delivered
iWork | Milestone 5 | Delivered | Delivered | Delivered
iWork | Milestone 5 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered
iWork | Milestone 5 | Delivered | Delivered | Delivered
iWork | Milestone 5 | Delivered | Delivered | Delivered
iWork | Milestone 5 | Delivered | Delivered | Delivered
IBP | Milestone 5 | Delivered | Delivered | Delivered
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered
DPDP | Milestone 5 | Dev - WIP | In Development | Pending
DPDP | Milestone 5 | Dev - WIP | In Development | Pending
DPDP | Milestone 5 | Dev - WIP | In Development | Pending
IBP/iWork | Milestone 5 | Dev - WIP | In Development | Pending
DPDP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending
IBP/iWork | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending
DPDP | Milestone 5 | QA - WIP | In QA | Pending
DPDP | Milestone 5 | Yet to start | Not Started | Pending
DPDP | Milestone 5 | Yet to start | Not Started | Pending
DPDP | Milestone 5 | Yet to start | Not Started | Pending
DPDP | Milestone 5 | Yet to start | Not Started | Pending
DPDP | Milestone 5 | Yet to start | Not Started | Pending
DPDP | Milestone 5 | Yet to start | Not Started | Pending
DPDP | Milestone 5 | Yet to start | Not Started | Pending
NFR | Milestone 5 | Yet to start | Not Started | Pending
DPDP | Milestone 5 | Yet to start | Not Started | Pending
IBP/iWork | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP/iWork | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
IBP | Milestone 5 | Yet to start | Not Started | Pending
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending
iWork | Milestone 4 | Yet to start | Not Started | Pending
iWork | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending
iWork | Milestone 5 | Yet to start | Not Started | Pending
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
IBP | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Dev - Done | Dev Complete | Delivered
IBP - CR | Milestone 6 | Dev - WIP | In Development | Pending
IBP | Milestone 6 | Dev - WIP | In Development | Pending
IBP/iWork | Milestone 6 | Dev - WIP | In Development | Pending
iWork | Milestone 4 | Yet to start | Not Started | Pending
DPDP | Milestone 4 | Yet to start | Not Started | Pending
iWork | Milestone 4 | Yet to start | Not Started | Pending
iWork | Milestone 5 | Yet to start | Not Started | Pending
iWork | Milestone 5 | Yet to start | Not Started | Pending
iWork | Milestone 5 | Yet to start | Not Started | Pending
iWork | Milestone 5 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Delivered | Delivered | Delivered
iWork | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Yet to start | Not Started | Pending
iWork | Milestone 6 | Yet to start | Not Started | Pending

## Config (hidden)
Status_Raw | Category | Bucket
Delivered | Delivered | Delivered
Dev - Done | Dev Complete | Delivered
Dev - WIP | In Development | Pending
QA - WIP | In QA | Pending
Pre-PROD | Pre-PROD / UAT | Pending
Yet to start | Not Started | Pending
Delivered - Deficit | Partial Delivery | Pending
Duplicate | N/A | N/A