## SOW, Feedbacks-Bug & CR_Items
Area | Feature | Functionality | Module | Phase | Status | Remarks | Requested Date | ETA | Resource
FRAMEWORK: Frontend | Project setup | Basic project / Development environment setup | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | UI Approach Design System | Building Design System | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Core Infrastructure | Core Infra | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Build UI components | This includes all the UI componnets to compose the application and module definitions: Form, Toast, Filter, Cards, Visualisation, Grid, Menu, Header, Footer, Maps Integration | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | UI Approach Style Establishment | UI Style Establishment | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Service Workers Implementation |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Core System |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | ACL & RBAC Control Framework |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Micro Frontend Setup |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Landing Page |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Services - Basic Modules | Access Control Management |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Services - Larger Modules | Auth Module (Simple Auth) |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Services - Larger Modules | Micro Service Framework Setup |  | Framework | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Employee Mgmt |  | iWork | Milestone 1 | Delivered | User deletion need to be handled | 2025-03-01 | 2026-06-12
iWORK: Common Components | Common - Audit Trail Mgmt - Becomes critical in this phase iteself |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Opportunity | Add Medium size form with 1->N list of Claims; Multiple drop downs Large View with several widgets, Simple Edit | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Manage TPA/Insurer | Basic Add, View with edit of basic data, with lists of policies/companies | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Core Infra | Infrastructure | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Company | Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. Simple edit like Add; View is multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Insurer/TPA Hub | List with Filter/Search | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Add/View/Edit Contact | Simple edit like Add Contacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Company (Prospect) Hub | Top 10/Latest companies, with search/filter, Table of basic attributes with GPS etc. | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Contact Hub | Top 10/Latest Contacts, with search/filter, list with basic attributes | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Frontend | Opportunity Hub | Top Opportunities with search/filter, List of opportunities with high level summaries | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Contact /Company/Insurer/TPA Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Task Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Meeting Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | RBAC and ACL setup for Iwork Module |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
iWORK: Services - Basic Modules | Opportunity Mgmt |  | iWork | Milestone 1 | Delivered |  | 2025-03-01
FRAMEWORK: Frontend | Master Data Management |  | Framework | Milestone 2 | Delivered |  | 2025-04-16 | 2026-05-27
FRAMEWORK: Frontend | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion | 2025-04-16 | 2026-06-12
FRAMEWORK: Services - Basic Modules | User Management | 22-May: Other than iWork employee | Framework | Milestone 2 | Delivered | Pending: User deletion | 2025-04-16 | 2026-06-12
FRAMEWORK: Services - Larger Modules | Data Security Considerations |  | Framework | Milestone 2 | Delivered | Duplicate of Covers in DPDP items | 2025-04-16 | 2026-06-30
FRAMEWORK: Frontend | Visualization framework | Charts and KPIs | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Frontend | Document Management | Create, Upload, Seach, Download | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Frontend | Caching of API Data |  | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Services - Basic Modules | Audit Data Capturing |  | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Services - Larger Modules | CMS |  | Framework | Milestone 2 | Delivered | Used in IBP | 2025-04-16
FRAMEWORK: Services - Basic Modules | Notification and Communication Management |  | Framework | Milestone 2 | Delivered |  | 2025-04-16
FRAMEWORK: Services - Basic Modules | Usage Tracking System (Reports) | 23-May: Handle as a part of Reports | Framework | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Common Data Mapping Component | Map input fields to output fields & Order | iWork | Milestone 2 | Delivered | Pending: Additional/Dynamic columns | 2025-04-16 | 2026-06-09
iWORK: AI Components | AI - (Non-OCR) Digital Document Processing for Content recognition (Company/Opportunity/Contact Creation from Previous Policy Document, Bizcard document) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: AI Components | AI - OCR for Content Collection |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: AI Components | AI - Company Information by AI Search |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Common Components | Common, Contexual Upload Component |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Common Components | Common, Contexual Read and Spread Component (Utility) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Manage Stage Planning/Performance/Approval | Add iWork Stages (table) - Dates with each iWork Stage and who are the team members assigned to each Stage; Once all iWork stages are complete, ISG Team activities must be planned ISG Team can approve/reject each iWork Stage. Approving RFP Stage approves all iWork stages Completion of each iWork Stage (Activity) & ISG Stage - Comments, Attach Document, Date recorded, submit | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Smart Add Component | Allow Upload of Document/Image, select what to create (Company/Contact/Opportunity) | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Dashboard - Drilldowns | Drill down from the Tables (Targets vs. Actuals, Pending Activities, Followups, AR Report, Schedule) | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Sales Team Hierarchy | Hierarchy / Org chart tied to Platform Users | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | View Policy | Long View, multiple widgets/entities, endorsements (each month), Claims, etc. | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Dashboard | Multiple KPI Cards: Business Performance, Svc Performance, Table of targets vs. actuals vs. lost, Sales Funnel, Renewal Funnel, Servce Funnel, AR from Insurers, Pending Activities(iWork Stages) Widget, Followups widget, Meetings widget Filters available (Geo, Branch, Team/Team Member, Dates), Approvals, iWork Stages, Tasks, Meetings | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Dashboard - Pending tasks, approvals | Pending tasks/approvals, | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Frontend | Reports - Biz Done | Report View, Download, List of earlier snaps of the report, Search and Filter | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Core Infrastructure | Core Infra | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Organisation, Branch, Employee, & Hierarchy Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Dashboard (Place Holder) |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Planning, Perform and Approval Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Policy Mgmt |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Master Data Mgmt {Common, Contexual Master Data Mgmt} |  | iWork | Milestone 2 | Delivered |  | 2025-04-16
iWORK: Services - Basic Modules | Cut Off Mgmt |  | iWork | Milestone 2 | QA - WIP |  | 2025-04-16 | 2026-07-30 | Karan
FRAMEWORK: Services - Larger Modules | Document Generation |  | Framework | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Cover Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16 | 2026-06-10 | Karan
iWORK: Frontend | Manage Policy (Endorsements) | Add Endorsement - basic form with uploads of excel/document Validations of endorsement format - Map customer fields to internal fields Map internal fields to TPA fields (occasional per TPA) View/Update Endorsement, List View, Endorsement Performance | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Stage Mgmt (Activity/Transaction/Quote) |  | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Asset/Member Data Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Services - Basic Modules | Endorsement Mgmt |  | iWork | Milestone 3 | Delivered |  | 2025-05-16
iWORK: Frontend | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | iWork | Milestone 3 | Delivered |  | 2025-05-16 | 2026-07-22 | Sunil
iWORK: Services - Basic Modules | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | iWork | Milestone 3 | Delivered |  | 2025-05-16 | 2026-07-22 | Sunil
iWORK: Services - Basic Modules | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | DPDP | Milestone 4 | Yet to start | Duplicate of Archival from NFR & DPDP | 2025-06-10 | 2026-07-31 | Rama
FRAMEWORK: Services - Basic Modules | Configuration Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Services - Basic Modules | Feature Flag Control Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Services - Larger Modules | Localistation Management |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Services - Larger Modules | Caching Implementation |  | Framework | Milestone 4 | Delivered |  | 2025-06-10
FRAMEWORK: Frontend | Notifications Management | Different email notification - Madhav excel. 1. Renewal Reminders - ASAP 2. Instalment Reminders 3. Others | Framework | Milestone 4 | Delivered - Deficit |  | 2025-06-10 | 2026-07-28 | Pushyami
FRAMEWORK: Services - Larger Modules | Workflow Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Not in scope | 23-Jul-2026: As per Gopal as this system custom and most of the data is driven from Master creating/plug any 3'rd Party will make complex. | 2025-06-10
FRAMEWORK: Frontend | Accessibility | 20-Jul: Jagadees --> Need More details | Framework | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-08-07
FRAMEWORK: Frontend | Localisation |  | Framework | Milestone 4 | Delivered - Deficit | Pending: Service Flow Pending: IBP | 2025-06-10 | 2026-07-31 | Tharun
FRAMEWORK: Services - Larger Modules | Rule Definition Management | 23-May: Integrate the 3'rd party libraries | Framework | Milestone 4 | Not in scope | 23-Jul-2026: As per Gopal as this system custom and most of the data is driven from Master creating/plug any 3'rd Party will make complex. | 2025-06-10
IBP: Services - Larger Modules | IBP - User Management | IBP: HR Portal - Company-Scoped Employee Access for Client HR (Ex. TeamLease's Customer) | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-05-26
IBP: Services - Larger Modules | IBP - Portal Setup | Post policy creation, create default IBP Portal Config for all the company-policy(ies) | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-19 | Manjusha
IBP: SERVICES - Basic Modules | Personal Profile Mgmt | Profile settings | IBP | Milestone 4 | Delivered | Pending:Add Dependents | 2025-06-10 | 2026-06-10 | Manjusha
IBP: FRONTEND | HR Portal View | Employee Search, Resend Email, Delete Employees, Extend Enrollment Windows, Reports, Bulk Email | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-11 | Abhilash
IBP: Common Components | Simple Auth | Username and Password based authentication and RBAC on simple-auth users. Auth rules needs configuration capability. IBP - HR User Management | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-12 | Abhilash
IBP: FRONTEND | My Documents | Document Hub - Covers Policies, Prescriptions, Reports | IBP | Milestone 4 | Delivered | Pending: Design | 2025-06-10 | 2026-06-12 | Manjusha
IBP: SERVICES - Basic Modules | Document Mgmt for End User | Insurance, Health Reports and Prescriptions {No automatic pull from Partners} | IBP | Milestone 4 | Delivered | Pending: Design | 2025-06-10 | 2026-06-12 | Manjusha
Framework: NFR | NFR_Usability | NFR-USA-018: The session management should be configurable from UI 23-May: Configure from UI & store in DB; When changed then restart server | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-15 | Manjusha
IBP: FRONTEND | Policy Document | IBP-Risk Watch: Show the each policy document | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-19 | Tharun
Framework: NFR | NFR_Usability | NFR-USA-015: The system must show personalized welcome messages and profile information based on locale. | IBP | Milestone 4 | Delivered |  | 2025-06-10
Framework: NFR | NFR_Usability | NFR-USA-016: Notification banners must be dismissible and configurable based on role. | IBP | Milestone 4 | Delivered | No notifications in IBP | 2025-06-10
IBP: Common Components | Whitelabelling Support |  | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Company Plans | 6 Policies - GMC, GPA, GTL, Parental Plicy, Top-ups, OPD Policy (Summary view of policies) | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | IBP Landing Page - Basic | Basic Landing Page with only company plans and summart | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Contact Matrix View | Contact Matrix View for end user | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Core Infrastructure | Core Infra | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Per-policy Enrolment | Enrolment and addon policy selection | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | My Insurance | Part-1: Hub of all plans I have as an employee - Company provided. Mostly a navigational page | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Basic Modules | Basic Landing Page Services | Company provided plans only | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment | Enrollment (Adding Dependents, Choosing Options available). Submit the enrollment to Insurer or TPA 6 Types of Policies to be considered | IBP | Milestone 4 | Delivered | Need Confirmation: If scope has, Insurer & TPA integrations, then they are pending | 2025-06-10
IBP: Services - Larger Modules | Group Policy Mgmt - Enrollment Configurator | Enrollment Configurator (Set of benefits and type of Dependent combinations allowed etc). This is more of an Iwork feature to configure the policy | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | End User onboarding | Generate Users, Send Emails, Password Rest | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | Contact Matrix Configuration | Matrix of Contact Infomration | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | HR/Admin Portal View | Supporting services for Admin Portal | IBP | Milestone 4 | Delivered |  | 2025-06-10
IBP: Services - Larger Modules | Admin Reports | Services for multiple reports | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-06-10 | Abhilash
Framework: NFR | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | IBP | Milestone 4 | Pre-PROD | Fine tuning the API's where there is a delay | 2025-06-10 | 2026-08-07 | Akhila
IBP: Services - Larger Modules | Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | IBP | Milestone 4 | Delivered |  | 2025-06-10 | 2026-07-02 | Ravi
iWork: Services - Basic Modules | Client - Associated Location (IBP HR Module) | IBP - HR: Policy Location - Add Company Associated Locations, Flow to Opty., Policy & Policy Config | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Karan
IBP: FRONTEND | Company Plan Configurator | Admin side of IBP should configure (per Corporate) how to define a Policy and determine how it breaks down the Premium and Coverage rules | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Auth Config UI | Config for Auth Rules setup | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Contact Matrix | Configure the Conact Info Matrix (IBP Admin) | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
IBP: FRONTEND | Whitelabelling | Whitelabelling based on Org needs (IBP Admin) | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10
iWORK: Common Components | Policy Component - Strapi | IBP Portal - Each card should have seperate points & Policy feature documents | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Manjusha
iWORK: Services - Basic Modules | TPA Integration Mgmt [Framework] | 1. Framework in iWork 2. Validate the integration for the existing 6 TPA's | IBP/iWork | Milestone 4 | Delivered |  | 2025-06-10 | 2026-07-24 | Ravi
iWORK: Services - Basic Modules | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | IBP/iWork | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-08-07 | Rama
iWORK: Frontend | View Service Score | My Client Portfolio: Service Score - Single Table (drillable) to calculate an overall score Dashboard - Service Score - Widget | iWork | Milestone 4 | Delivered |  | 2025-06-10 | 2026-07-29 | Sunil
iWork: Services - Basic Modules | Reports - Biz Done | Bizonde filter/table - Add "Income type" | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Karan
iWork: Services - Basic Modules | Opportunity | Opportunity History details are unavailable for the end user to view. Show TAT section (Planned date, Performed/Completed date, Approved date) for planned acitivites | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Pushyami
iWork: Services - Basic Modules | Endorsement Mgmt | Additional columns in file like Department, DOJ, Emp. Location, Vertical, Others | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Pushyami
iWork: Services - Basic Modules | Opportunity | RO Scheduler Enhancements | iWork | Milestone 4 | Delivered |  | 2025-06-10 |  | Jagadeesh
iWORK: Frontend | Knowledge Central | Grouped list of Documents/Resources, Add a Document, Remove a Document (Add/remove only for admins) | iWork | Milestone 4 | Delivered |  | 2025-06-10
iWORK: Services - Basic Modules | Knowledge Central |  | iWork | Milestone 4 | Delivered |  | 2025-06-10
iWORK: Services - Basic Modules | TAT/SLA Mgmt (Including Service Score) |  | iWork | Milestone 4 | Delivered |  | 2025-06-10
iWork: Services - Larger Modules | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | iWork | Milestone 4 | Yet to start |  | 2025-06-10 | 2026-08-07 | Rama
Framework: NFR | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | NFR | Milestone 4 | Delivered - Deficit | Pending: Provide the document on how do we store and view it | 2025-06-10 | 2026-07-31 | Rama
IBP: FRONTEND | Wellness Discount List Management | Add/Remove/update Discount program benefits | IBP/iWork | Milestone 4 | Dev - WIP |  | 2025-06-10 | 2026-07-31
IBP: FRONTEND | Upload from Partner of services bought on Partner site | Upload, listing, confirm & load into DB by an Iwork user. These are services purchased / discounts availed on partner sites by IBP corporate users | IBP/iWork | Milestone 4 | Dev - WIP |  | 2025-06-10 | 2026-07-31
Framework: DPDP | Enable SAST |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-15
Framework: DPDP | Integrate SSO / MFA |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-04-30
Framework: DPDP | Capture consent within app |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-05-30
Framework: DPDP | Allow easy consent withdrawal |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-05-30
Framework: DPDP | Approval workflow |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-05-30
Framework: DPDP | Show privacy notice with purpose, retention, rights |  | DPDP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-05-30
Framework: DPDP | App vulnerability scans |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Document Flows |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Perform security UAT |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Enforce business logic to restrict purpose |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Remove unnecessary fields |  | DPDP | Milestone 5 | Dev - Done |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Allow user corrections |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Delete expired data |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Sign DPDP clauses |  | DPDP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Map PII tables |  | DPDP | Milestone 5 | QA - WIP |  | 2025-07-31 | 2026-07-31 | Rama
Framework: DPDP | Enable delete pipeline |  | DPDP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Define archival |  | DPDP | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-07-31
Framework: DPDP | Quarterly restore tests |  | DPDP | Milestone 5 | Pre-PROD |  | 2025-07-31 | 2026-07-31 | Rama
IBP: SERVICES - Basic Modules | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | IBP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31 | Manjusha
IBP: Services - Larger Modules | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 | Ravi
IBP: Services - Larger Modules | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07
IBP: Services - Larger Modules | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07
IBP: Services - Larger Modules | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-07-31 | Ravi
IBP: Common Components | 3rd Party SSO | Props based SSO links to 3rd Parties | IBP | Milestone 5 | Delivered | SSO Framework implemented fro TPA | 2025-07-31 | 2026-06-01 | Abhilash
IBP: SERVICES - Basic Modules | Hospital Network Mgmt | Based on the Insurer and TPA, network of hospitals needs to be presented in a consolidated view | IBP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-11
IBP: FRONTEND | Static Info Sections - Landing | Benefits Guide, FAQs, Help | IBP | Milestone 5 | Delivered |  | 2025-07-31
IBP: FRONTEND | Initiate Claim | Initiate claim for GMC (non-cashless), upload docs etc. | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations | 2025-07-31
IBP: FRONTEND | Claims Corner | View Claim Data for Individual Plans (if available), Track Status for Claims initiated from IBP for Group Plans, Track Status for Claims initiated with TPA directly, TAT reporting for Cashless (for Preauth and Discharge) | IBP | Milestone 5 | Delivered | Pending: TPA & Insurer API integrations | 2025-07-31
IBP: Services - Larger Modules | Claims Mgmt | Part-1: Company Provided Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | Delivered |  | 2025-07-31
IBP: SERVICES - Basic Modules | Feedback Mgmt | User Feedback capture service | IBP | Milestone 5 | Delivered | IBP support is already in place | 2025-07-31
IBP: FRONTEND | IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | IBP | Milestone 5 | Delivered |  | 2025-07-31
IBP: FRONTEND | Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | IBP | Milestone 5 | Delivered | Pending: Offers & Discuounts | 2025-07-31 | 2026-04-10 | Manjusha
IBP: FRONTEND | User Profile | Profile, Service Subscriptions, Feedback | IBP | Milestone 5 | Dev - WIP | Pending: Service Subscriptions, Feedback | 2025-07-31 | 2026-07-31 | Ravi
IBP: Services - Larger Modules | Evexia Club Integration | Integration to Evexia | IBP | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31 | Abhilash
IBP: Services - Larger Modules | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | IBP/iWork | Milestone 5 | Dev - WIP | Pending: Offer, Feature flagging (UI) | 2025-07-31 | 2026-07-31 | Manjusha
IBP: SERVICES - Basic Modules | Benefits Summary | End User's Summary View | IBP | Milestone 5 | Delivered - Deficit |  | 2025-07-31 | 2026-07-31 | Ravi
IBP: FRONTEND | Book Ambulance | Floater on the screen - Integrate to Ambulance Service | IBP | Milestone 5 | Not in scope |  | 2025-07-31
IBP: FRONTEND | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | IBP | Milestone 5 | Delivered |  | 2025-07-31 | 2026-07-31
IBP: Services - Larger Modules | Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | IBP | Milestone 5 | Not in scope |  | 2025-07-31
IBP: FRONTEND | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 | Ravi
IBP: FRONTEND | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | IBP | Milestone 5 | Dev - WIP | Wellness | 2025-07-31 | 2026-07-31 | Manjusha
IBP: FRONTEND | Wellness HR View | HR View of Wellness usage by Employees | IBP | Milestone 5 | Yet to start | Wellness | 2025-07-31 | 2026-08-07 | Manjusha
IBP: FRONTEND | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | IBP | Milestone 5 | Dev - WIP | Wellness | 2025-07-31 | 2026-07-31 | Manjusha
IBP: FRONTEND | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 | Ravi
IBP: FRONTEND | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 | Ravi
IBP: Services - AI Components | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | IBP | Milestone 5 | Delivered | External chatbot integration? | 2025-07-31 | 2026-07-31 | Abhilash
IBP: FRONTEND | Profile Migration | Request migration of Corporate Profile to Individual | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 | Abhilash
IBP: FRONTEND | Profile Migration | Request migration of Individual Profile to Corporate | IBP | Milestone 5 | Yet to start | Retail Business | 2025-07-31 | 2026-08-07 | Abhilash
IBP: Services - Larger Modules | Core Infrastructure | Core Infra | IBP/iWork | Milestone 5 | Delivered | Pending: Mobile responsive | 2025-07-31 | 2026-07-31 | Velangini Raju
IBP: FRONTEND | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | IBP/iWork | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31 | Ravi
IBP: FRONTEND | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | IBP/iWork | Milestone 5 | Dev - WIP | Wellness HR View | 2025-07-31 | 2026-08-07 | Manjusha
iWORK: Services - Basic Modules | TPA Integration Mgmt [GHPL] | Launch TPA - SSO Ecards API - Read & View Details Hospital Network Claims Status API - Read, Store & View Details Claim Intimation API Claim Live Status - Single Claim | IBP/iWork | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-12 | Ravi
IBP: FRONTEND | IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | IBP/iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) Similar to TPA API Integration Framework for any 3'rd Party | iWork | Milestone 5 | Delivered |  | 2025-07-31 | 2026-07-24
iWORK: Services - Basic Modules | Insurer Integration Mgmt | Can be used as a part of External API Intergration | iWork | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-08-07
iWORK: Frontend | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | iWork | Milestone 5 | Delivered - Deficit | Linked with Reconciliation Management & Commission | 2025-07-31 | 2026-08-07
iWORK: Frontend | Claim Management (Add Claim, Import Claims & Claim Activities) | Basic Form with fields and upload for adding claim Bulk import to validate and map from TPA format to internal fields 3 stage workflow - each stage, update data on claim form | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | Report Hub | Landing Page and generic hub | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | CD Creation | Show current CD Balance against pooled/individual policies / Allow new CD creation, update CD balance and map policies to CD balances | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | CD Mgmt |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | Reports |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Services - Basic Modules | Claim Mgmt |  | iWork | Milestone 5 | Delivered |  | 2025-07-31
iWORK: Frontend | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | iWork | Milestone 5 | Yet to start | Need inputs from Kapil | 2025-07-31 | 2026-08-07
iWORK: Services - Basic Modules | Reconciliation Mgmt |  | iWork | Milestone 5 | Yet to start |  | 2025-07-31 | 2026-08-07
iWORK: Services - Basic Modules | HRMS Integration Mgmt Framework provided to link the HRMS portal in Risk Watch | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? HRMS - integrations with enrolment portal (POC - with Zoho People), client mentioned that they have already integrated MB360 for HCL IBP & HRMS Integration - HCL | iWork | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: NFR | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure, which was broad symptom rather than a root cause. The renewed focus here is on failures related to cryptography which often leads to sensitive data exposure or system compromise. |  | NFR | Milestone 5 | Dev - WIP |  | 2025-07-31 | 2026-07-31
Framework: NFR | NFR-COM-019: Terms and Conditions: The application must ensure require the customer to accept the Terms & Conditions at the first login to the application. This ensures compliance with PII regulations requiring Company group to inform the user of why Company is accessing/collecting personal data and why Company is using it. IIRM-4480 |  | NFR | Milestone 5 | Delivered |  | 2025-07-31 | 2026-06-05
Framework: NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | NFR | Milestone 5 | Yet to start | Discussed this with Surya sir last visit to Divami office | 2025-07-31 | 2026-07-31
Production - Feedback | Cover Mgmt | Asset fields which are captured at Broking slip, few of the asset fields should not be printed at the time of Placement slip (example, no of members at inception, total lives, prev policy expiring year etc.) only for GMC | iWork - CR | Milestone 6 | Delivered |  | 2026-02-17 | 2026-06-25 | Karan
Production - Feedback | Policy Configuration | DNV Group - Dependent based SI & Premium configuration | iWork - CR | Milestone 6 | Delivered |  | 2026-04-07 | 2026-07-16 | Jagadeesh
Production - Feedback | Policy Configuration | Premium Rater Table | iWork - CR | Milestone 6 | Yet to start |  | 2026-04-21 | 2026-08-07 | Jagadeesh
Production - Feedback | VRK - PROD Feedback | Manage Insurer - Add Insurer Flow | iWork | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-09 | Pushyami
Production - Feedback | VRK - PROD Feedback | Opty. Flow - Add new Insurer Branch Details | iWork | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-12 | Pushyami
Production - Feedback | Reports - Biz Done | BizDone - Finance Team to see the respective Org. data similar to VRK | iWork - CR | Milestone 6 | Delivered |  | 2026-05-01 | 2026-07-09 | Karan
Production - Feedback | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | iWork - CR | Milestone 6 | Yet to start |  | 2026-05-01 | 2026-08-07 | Sunil
Production - Feedback | Insurer Management | Enhance Insurer - Add, Edit, & Contacts | iWork - CR | Milestone 6 | Delivered |  | 2026-05-01 | 2026-06-09 | Pushyami
Production - Feedback | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | IBP - CR | Milestone 6 | Pre-PROD |  | 2026-05-08 | 2026-08-03 | Abhilash
Production - Feedback | Policy Configuration | Using AI - Extract the Policy document and perform Policy Configuration (Premium, Family, Parameters, & Others) | iWork - CR | Milestone 6 | Delivered |  | 2026-05-08 | 2026-07-01 | Jagadeesh
Production - Feedback | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | iWork - CR | Milestone 6 | Yet to start | Need some information about the document rules that defines the idenity of it | 2026-05-08 | 2026-08-07
Production - Feedback | Endorsement Mgmt (Non-Group / Non-GMC / Non-EB) | Enhance the Non-GMC Process (Based on Kishore feedback) | iWork - CR | Milestone 6 | Delivered |  | 2026-05-21 | 2026-05-28 | Pushyami
Production - Bug | Endorsement Mgmt | PROD Bug: Data Discrepancy - Inception/Endorsement vs Send to Client/Insurer (Preview & Excel) | iWork | Milestone 6 | Delivered |  | 2026-05-25 | 2026-05-27 | Prathiphala
Production - Bug | Endorsement Mgmt | PROD Bug: When download the TPA file, dependents are Missing in the file | iWork | Milestone 6 | Delivered |  | 2026-05-25 | 2026-05-27 | Sunil
Production - Feedback | IIRM-10587 | Add new fields - Business Month & Date of Business - Capture in Opty. & Flow to Policy and add filters in BizDone --> Refer to Madhav email "Business Month Requirement" | iWork | Milestone 6 | Delivered | Pending: Additional filters | 2026-05-28 | 2026-07-02 | Sunil
Production - Feedback | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-01 | 2026-07-17 | Abhilash
Production - Feedback | IIRM-10591 | IBP - Enrolment Journey - Reset | IBP | Milestone 6 | Delivered |  | 2026-06-03 | 2026-06-09 | Abhilash
Production - Feedback | VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | iWork | Milestone 6 | Delivered |  | 2026-06-05 | 2026-06-08
Production - Feedback | SSO - MS AD Account | iWork - SSO with Microsoft AD (POC) | iWork - CR | Milestone 6 | DEV - WIP | 10-Jun-2026: POC Demo to Venu completed | 2026-06-05 | 2026-07-31 | Rama
Production - Bug |  | Based on recent billing - Identifying the gaps in Redis data storage and gaps in implementation | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-06 | 2026-06-08 | Tharun
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-08
Production - Feedback | IIRM-10588 | Hide "Manage Policy" in "Manage Placements" link. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-09 | Pushyami
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-09 | Karan
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-10
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-12 | Karan
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-12
Production - Bug | VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-19 | Rama
Production - Bug | VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-24
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-09
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | iWork | Milestone 6 | Not a bug | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-06-30 | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | iWork | Milestone 6 | Delivered |  | 2026-06-08 | 2026-07-02
Production - Feedback | VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | iWork | Milestone 6 | Not a bug |  | 2026-06-08 | 2026-06-08
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | iWork | Milestone 6 | QA - WIP |  | 2026-06-09 | 2026-07-31 | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 | Pushyami
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 | Pushyami
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 | Pushyami
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-09 | Pushyami
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 | Prathiphala
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-10 | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-12 | Prathiphala
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 | Karan
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 | Karan
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 | Karan
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-15 | Karan
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-16
Production - Feedback | VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | iWork | Milestone 6 | Delivered |  | 2026-06-09 | 2026-06-19 | Karan
Production - Feedback | Risk Watch - Endorsement - Documents & Communication | Risk Watch - Endorsement - Documents & Communication | IBP | Milestone 6 | Delivered |  | 2026-06-10 | 2026-07-01 | Abhilash
Production - Feedback | Wellness Banner & SSO | Add banner and SSO to Alyve Wellness (Only Banner) | IBP | Milestone 6 | Delivered |  | 2026-06-10 | 2026-06-10
Production - Bug | Security | InfoSec - IBP Portal (Security Issue) | IBP/iWork | Milestone 6 | Delivered |  | 2026-06-11 |  | Manjusha
Production - Feedback | IIRM-10590 | Policy Config: Dependent Based Configurations - Per life depedent addition & increase SI - Apply Policy Parameters for dependents | IBP/iWork - CR | Milestone 6 | Delivered |  | 2026-06-11 | 2026-06-15 | Jagadeesh
Production - Feedback | Policy Config | New Policy constraints 1. Allow first child as Twin 2. Allow second child as Triplet 3. SI per Dependent 4. Parent Lock-in period | IBP/iWork - CR | Milestone 6 | Delivered |  | 2026-06-15 | 2026-06-16
Production - Bug | Export to Excel | Export to excel - iWork all the results table; Download is on Previlage | iWork | Milestone 6 | Yet to start |  | 2026-06-15 | 2026-08-07
Production - Feedback | IIRM-10667 | iWork - Knowledge Central Re-Design | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-06-15 | 2026-08-07
Production - Feedback | IIRM-10668 | iLearn: Document Preview in-app | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-06-15 | 2026-08-07
Production - Feedback | Discuss with Madhav | 19-Jun-2026: Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard) Also, check if we are there are any data loads for 2025-26 | iWork | Milestone 6 | Yet to start |  | 2026-06-15 | 2026-08-07
Production - Bug |  | Dashboard - Hide the widgets where there is NO data in the cards | iWork | Milestone 6 | Delivered |  | 2026-06-15 | 2026-07-10
Production - Feedback | Installment & Fee Requirements | Installments & Fee to BizDone | iWork | Milestone 6 | Yet to start |  | 2026-06-15 | 2026-08-07
Production - Feedback | Rewards | Rewards - Generic (Specific - Out of scope) | iWork | Milestone 6 | Delivered |  | 2026-06-18 | 2026-07-01 | Karan
Production - Feedback |  | Risk Watch: Showing policy feature documents at each policy | IBP | Milestone 6 | Delivered |  | 2026-06-19 | 2026-06-19 | Ravi
Production - Feedback | Wellness | IBP Portal Configure - Wellness - Buttons, CMS, & any other - Flag Driven | IBP | Milestone 6 | Delivered |  | 2026-06-19 | 2026-06-22 | Manjusha
Production - Feedback | Claims Corner | Claims Corner - Screen Re-design | IBP | Milestone 6 | Dev - WIP |  | 2026-06-21 | 2026-08-07 | Ravi
Production - Feedback | IIRM-10666 | IBP - Policy Component Card Re-design | IBP | Milestone 6 | Yet to start |  | 2026-06-21 | 2026-08-07 | Manjusha
Production - Bug | Risk Watch - Enrolment Drive | Risk Watch - List view to see the list of enrolment dritve | IBP | Milestone 6 | Delivered |  | 2026-06-22 | 2026-07-10 | Ravi
Production - Feedback | Claims Process | Process claims without TPA ID (GPA & GTL - flag based) | iWork - CR | Milestone 6 | Delivered |  | 2026-06-22 | 2026-07-01 | Jagadeesh
Production - Feedback | Teamlease - Request | Flexibility to configure multiple companies & policies on a single domain | IBP/iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 | Abhilash
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Additional section display: Placement Funnel, Schedule, Followup | iWork - CR | Milestone 6 | Dev - WIP |  | 2026-06-23 | 2026-07-30 | Karan
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-01 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-07 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-08 | Pushyami
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-14 | Karan
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - Filter & drill-down | iWork - CR | Milestone 6 | Delivered |  | 2026-06-23 | 2026-07-14 | Karan
Production - Feedback | VRK - PROD Feedback: 23-Jun-2026 | iWork and iTicket should be accessible via VPN | iWork - CR | Milestone 6 | Yet to start |  | 2026-06-23 | 2026-08-07 | Pushyami
Production - Feedback | InsureEasy | InsureEasy Integration - Retail Business | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07
Production - Feedback | AI | Wherever AI is implemented, there should be fallback if one day we turnoff AI then there shouldn’t be any impact in the working functionality | iWork | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07 | Rama
Production - Bug | AI | AI Nudges are NOT working. If there is NO AI, then DB scripts should run and show data | iWork | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07 | Rama
Production - Feedback | Inception/Endorsement | Endorsement data upload related * Track-1: TeamLease - 2024-2025 Year policies * All endorsement -> Headers, Member data, & endorsement Document * Track-2: Old Financial data * Track-3: Current Financial data * Track-4: Handle the data in IBP-Risk Watch | iWork | Milestone 6 | Dev - WIP |  | 2026-06-25 | 2026-08-07 | Rama
Production - Feedback | BizDone | Computed value & Reported values * Computed values - It’s the real-time values base on Policy inception/endorsement * Reported values - It’s validated by the mgmt. and share this number to update in the column. * Reported value MUST be used for the Dashboard & BizDone, which was declared by the company to public. * In the admin a feature to update the Reported values from the computed values * Legacy data - Premiums, Brokerage, CD Balance | iWork - CR | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07
Production - Feedback | IBP - Raise Ticket | Edit the ticket and update the status by the Lead CRM & System Admin | IBP/iWork | Milestone 6 | Delivered |  | 2026-07-01 | 2026-08-07 | Manjusha
Production - Feedback | One URL multiple companies | Flexibility to configure multiple companies on a single domain | IBP/iWork | Milestone 6 | Delivered |  | 2026-07-01 | 2026-07-07
Production - Bug | Service Flow - Upload Employee Details | Upsert logic - Tough there is an employee data historically, when user upload latest file we have to update the "Empolyee" or "Dependent" details with the latest information | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-07-01 | 2026-07-31 | Jagadeesh
Production - Feedback | Enrolment Journey | Add GPA note based on employee type (Leadership vs Employee) | IBP - CR | Milestone 6 | Delivered |  | 2026-07-03 | 2026-07-03 | Manjusha
Production - Feedback | No Policy Config - Enrolment Journey | Enrolment Journey - Collect Dependents Details ONLY | IBP/iWork - CR | Milestone 6 | Dev - WIP | 1. IBP - Enrolment - Completed 2. Service - WIP | 2026-07-04 | 2026-08-07 | Manjusha
Production - Feedback | Madhav & Veera | Data Load - Company, Policy, Broker & Insurer - 30 Files | iWork | Milestone 6 | Delivered |  | 2026-07-06 | 2026-07-12 | Rama
Production - Feedback | Neeraj Joshi | Policy - Inception/Endorsement - Data Load - 13 Files | iWork | Milestone 6 | Delivered |  | 2026-07-06 | 2026-07-12 | Rama
Production - Bug | Employee Details | Trim spaces in the dependent names | IBP | Milestone 6 | Delivered |  | 2026-07-07 | 2026-07-07 | Manjusha
Production - Bug | Employee Details | Show Insurer Policy Details | IBP | Milestone 6 | Delivered |  | 2026-07-07 | 2026-07-07 | Manjusha
Production - Bug | Employee Details | Hide DOJ as there is NO source for us. | IBP | Milestone 6 | Delivered |  | 2026-07-08 | 2026-07-08 | Manjusha
Production - Feedback | Toast Message - UI | Update the font & style for Toast message across application | IBP/iWork | Milestone 6 | Dev - WIP | Surya sir provided an idea via email to Me & Naveen | 2026-07-09 | 2026-08-07 | Tharun
Production - Feedback | IBP - Email Communication | Send employee emails - Either AWS or Send Grid - Company Config | IBP - CR | Milestone 6 | Delivered |  | 2026-07-10 | 2026-07-10 | Abhilash
Production - Bug | IBP - FAQ | Policy Level - FAQ | IBP | Milestone 6 | Delivered |  | 2026-07-11 | 2026-07-17 | Manjusha
Production - Feedback | Madhav & Veera | Data Load - Company, Policy, & Insurer - 38 Files | iWork | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-19 | Rama
Production - Feedback | Neeraj Joshi | Production Bugs - Via Emails/Tickets - 10 | iWork | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-19 | Rama
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Remove the Vertical section. Keep only Branch. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-13
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - Make the Funnel interactive so that clicking on each stage navigates to the corresponding enhanced screen. Also, when we click on "Numbers" also it has to move to respective screens | iWork - CR | Milestone 6 | Delivered | Pending: Becuase the enhanced screens are yet to Approve | 2026-07-13 | 2026-07-22 | Pushyami
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Organization-wise summary cards are not required. | iWork - CR | Milestone 6 | Not in scope | Madhav sir confirmed via Teams Chat | 2026-07-13
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Under PL, the bar chart should represent SO-level data instead of the currently displayed RO-level data. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-22 | Jagadeesh
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Remove the SO/RO labels from the bar charts. Display only the figures inside the bars, with the corresponding details available on mouse hover (tooltip). | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-14
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Review and correct the display of negative values for TeamLease under RO, particularly for Q3 bar-chart. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-14
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Brokerage Display - Display Brokerage information only. Hide Premium values in the enhanced screens. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | BizDone Enhanced Screen - Hide Premium. Display: RO Brokerage SO Brokerage | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Resolve the Premium value formatting issue. Values should be displayed consistently in Millions/Billions. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Display the Endorsement section above the section “Business Collection Summary”. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Move the Policy Type Distribution section above RO by SBU. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Rename/update the Policy Type names “Fire & Engineering”, “Speciality Lines - Liability” | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - The SO Activity Follow-up screen should not display ISG-related activities. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-15
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - When IIRM Holdings is selected, the Organization-level cards and graphs are not displayed. Verify and fix the issue. | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-17
Production - Feedback | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Display the data using an Accordion layout in the following order: Company → SBU → Branch → Executive → Client → Policy | iWork - CR | Milestone 6 | Delivered |  | 2026-07-13 | 2026-07-20
Production - Feedback | IBP - Welcome Emails | Dual approval/confirmation - Before sending to Employees. 1. 2 levels in iWork 2. CRM will submit & HR will approve in Risk Watch | IBP/iWork - CR | Milestone 6 | Yet to start |  | 2026-07-14 | 2026-08-07
Production - Feedback | Surya's feedback | Policy Details - Strip - Remove view more button and company is clickable | iWork | Milestone 6 | Delivered |  | 2026-07-14 | 2026-07-22 | Pushyami
Production - Bug | iWork - Report | When we generate 2025-2026 data for IIRM India then API request is a failure. Need to find a solution | iWork | Milestone 6 | Delivered |  | 2026-07-17 | 2026-07-18
Production - Feedback | Help Info - Field formulaes or field values | In any of the screen, we have to provide an info icon where it will help the users how critical fields in that screen are derieved or got populated | iWork - CR | Milestone 6 | Yet to start |  | 2026-07-17 | 2026-08-07
Production - Feedback | Application Access similar to SysAdmin | Need one more user like SYSADMIN. This user to be below SYSADMIN - and should be 100% read-only user - access etc all like SYSADMIN including Bizdone report download etc Also, inpersonate the user and see the data | iWork | Milestone 6 | Delivered | 1. Kapil sir sent it via Teams Chat. 2. Surya sir mentioned this in Call on Saturday | 2026-07-20 | 2026-07-24 | Pushyami
Production - Feedback | IBP - Send "Welcome Emails" or any email from IBP to include CC by HR or CRM User | IBP - Send "Welcome Emails" or any email from IBP to include CC by HR or CRM User | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-21 | Ravi
Production - Feedback | BizDone & Dashboard - Data Issue | Delete demo company, Demo company, Dummy company, Nokia Corporation (ref number 22337) | iWork | Milestone 6 | Delivered | Instead of delete, we maked the status NOT to show in the BizDone & Dashboard | 2026-07-20 | 2026-07-21 | Karan
Production - Feedback | BizDone | Update the associate CRM and Lead CRM as per enclosed sheet. This sheet has policy data. As per this, related SO, RO, Company also to be updated. Their are few records without any associate CRM assignment. So leave them blank. -- Refer to Data update.msg & CRM-Update.xlsx | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-21 | Jagadeesh
Production - Feedback | BizDone | Update Net Premium, Brokerage %, Brokerage Amount, & Income Month -- Refer to Data update - Set 2.msg & cl-updated.xlsx | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-21 | Jagadeesh
Production - Feedback | Madhav & Veera | Data Load - Company, Policy, & Insurer - 38 Files | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-24 | Rama
Production - Feedback | Neeraj Joshi | Production Bugs - Via Emails/Tickets - 10 | iWork | Milestone 6 | Delivered |  | 2026-07-20 | 2026-07-24 | Rama
Production - Feedback | BizDone | Update Lead CRM as Policy Owner for the selected Policies provided by Kapil | iWork | Milestone 6 | Delivered |  | 2026-07-21 | 2026-07-21 | Jagadeesh
Production - Feedback | BizDone | Update Opty. Owner value to Lead CRM of the Company | iWork | Milestone 6 | Delivered |  | 2026-07-21 | 2026-07-21 | Jagadeesh
Production - Bug | Access Issue | When a user above the hirerchary is accessing the data, application is throwing "unauthorized" message | iWork | Milestone 6 | Delivered |  | 2026-07-22 | 2026-07-22 | Pushyami
Production - Feedback | Kapil's feedback | Data change requests - Madhav's - Ass. CRM & Others - Refer to Jagadeesh email | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 | Jagadeesh
Production - Bug |  | Income month prefilling in endorsements | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 | Jagadeesh
Production - Feedback | UX issue | Display of complete amounts in KPI cards on hover | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 | Pushyami
Production - Bug |  | Dashboard and BizDone Brokerage mismatch | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 | Jagadeesh
Production - Feedback | Surya's feedback | Removal of + or - 5 days logic in the filters - Revert the logic | iWork | Milestone 6 | Delivered |  | 2026-07-23 | 2026-07-23 | Karan
Production - Feedback |  | In BizDone - Include Fee & Rewards in Total Brokerage | iWork | Milestone 6 | Delivered |  | 2026-07-24 |  | Pushyami
Production - Feedback |  | In Dashboard - Include Fee & Rewards in Achieved | iWork | Milestone 6 | Delivered | Rewards will be added in RO as per Surya's sir and mention a note. Later based on VRK's feedback we will update it. | 2026-07-24 |  | Pushyami
Production - Feedback | IBP - Email Communication | For an enrolled employee with Dependents using Service, instead of Welcome Email they should get Confirmation email | IBP/iWork | Milestone 6 | DEV - WIP | API is ready. Need to add into Notification framework | 2026-07-25 | 2026-08-04 | Abhilash
Production - Feedback | Personal Line Data Integrations | DSR and iWork Integration Enablement | iWork | Milestone 6 | Yet to start | Madhav sent in IIRM email | 2026-07-25 | 2026-08-07
Production - Feedback | ISG Flow Changes | Placement Slip flow - Terrorism premium in Insurer Sharing | iWork | Milestone 6 | Dev - WIP | Madhav sent in IIRM email | 2026-07-27 | 2026-07-31 | Karan
Production - Feedback | IBP - Email Communication | Enrollment reminders - Need another configuration "Every day" and send till last day of enrolment | IBP/iWork | Milestone 6 | Delivered |  | 2026-07-27 |  | Abhilash
Production - Bug | My Client Portfolio | My Client Portfolio: issues - company search and brokerage | iWork | Milestone 6 | Delivered |  | 2026-07-27 | 2026-07-27 | Pushyami
Production - Bug | Dashboard | Dashboard issue - ISG planning count mismatch | iWork | Milestone 6 | Delivered |  | 2026-07-28 | 2026-07-28 | Pushyami
Production - Bug | Dashboard | Business Performance-breakup - count mismatch | iWork | Milestone 6 | Delivered |  | 2026-07-28 | 2026-07-28 | Pushyami
Production - Bug | Enrolment Journey - EMI's | Based on Employee's enrolment period, the EMI months should be pro-ration month. Ex: Day-1 should show the all months EMI. If someone enrol after 2-months then EMI should be based on that. | IBP/iWork | Milestone 6 | Yet to start | Kriti raised | 2026-07-29 | 2026-08-04
Production - Bug | Enrolment Journey - Component - Notes | Policy Level - Component Notes from Stapi | IBP | Milestone 6 | Yet to start | Kriti raised | 2026-07-29 | 2026-08-04

## ① Executive Summary
PROJECT DELIVERY PLAN
iWork · IBP · Framework (IIRM SOW) ¦ Status Overview & Forward Roadmap · As of 25-Jul-2026
OVERALL COMPLETION | [6 empty] | REMAINING WORK
78.5% |  |  | 266 of 339 scope items delivered |  |  |  | 73 |  | items still to deliver across all modules — planned week by week in the weekly sheets
SOW SCOPE — ORIGINAL vs CURRENT ITEMS
Static comparison vs the 'SOW - Actual Items' reference sheet (original contracted scope). Matched by Module + Feature name. Recomputed on each re-run of the script.
Original SOW items | [5 empty] | 158
Currently tracked (all items) | [5 empty] | 340
— matched to original SOW | [5 empty] | 150
— new: DPDP / NFR / Change Requests | [5 empty] | 75
— new: organic growth (existing modules) | [5 empty] | 115
Net growth vs original SOW (158 → 340) | [5 empty] | +182
🔗 15 item(s) already mapped by hand to a renamed/restructured tracker row — see notes in 'SOW - Actual Items'.
WEEKLY INTAKE — items requested (by Requested Date)
Period | Added | Delivered | Pending | % Closed
Before 01-Jun-2026 | 209 | 157 | 52 | 75.12%
Week of 01 Jun 2026 | 5 | 4 | 1 | 80%
Week of 08 Jun 2026 | 43 | 42 | 1 | 97.67%
Week of 15 Jun 2026 | 12 | 5 | 7 | 41.67%
Week of 22 Jun 2026 | 21 | 14 | 7 | 66.67%
Week of 29 Jun 2026 | 5 | 3 | 2 | 60%
Week of 06 Jul 2026 | 8 | 7 | 1 | 87.5%
Week of 13 Jul 2026 — last week | 21 | 19 | 2 | 90.48%
Week of 20 Jul 2026 — this week | 15 | 15 | 0 | 100%
Requested ahead (after 26 Jul) | 0 | 0 | 0 | 0%
No Requested Date | 1 | 0 | 0 | 0%
TOTAL | 340 | 266 | 73 | 78.24%
STATUS BREAKDOWN (all items)
265 |  |  | 1 |  |  | 25 |  |  | 3
Delivered |  |  | Dev Complete |  |  | In Development |  |  | In QA
3 |  |  | 37 |  |  | 5 |  |  | 0
Pre-PROD / UAT |  |  | Not Started |  |  | Partial Delivery |  |  | N/A
PROGRESS BY MODULE
Module | Type | Total | Delivered | Pending | N/A | % Complete | Progress
iWork (Backlog) | Backlog | 139 | 125 | 14 | 0 | 89.93% | 89.93%
iWork (Change Requests) | Change Request | 41 | 33 | 8 | 0 | 80.49% | 80.49%
IBP (Backlog) | Backlog | 68 | 49 | 19 | 0 | 72.06% | 72.06%
IBP (Change Requests) | Change Request | 3 | 2 | 1 | 0 | 66.67% | 66.67%
IBP / iWork (Shared) | Backlog | 22 | 15 | 7 | 0 | 68.18% | 68.18%
IBP / iWork (Shared CRs) | Change Request | 9 | 3 | 6 | 0 | 33.33% | 33.33%
Framework | Backlog | 34 | 31 | 3 | 0 | 91.18% | 91.18%
DPDP | Backlog | 19 | 7 | 12 | 0 | 36.84% | 36.84%
NFR | Backlog | 4 | 1 | 3 | 0 | 25% | 25%
TOTAL | All | 340 | 266 | 73 | 1 | 78.47% | 78.47%
PENDING BY MILESTONE & MODULE
Milestone | iWork | iWork - CR | IBP | IBP - CR | IBP/iWork | IBP/iWork - CR | Framework | DPDP | NFR | TOTAL PENDING
Milestone 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Milestone 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 4 | 1 | 0 | 1 | 0 | 3 | 0 | 3 | 1 | 1 | 10
Milestone 5 | 5 | 0 | 16 | 0 | 3 | 0 | 0 | 11 | 2 | 37
Milestone 6 | 7 | 8 | 2 | 1 | 1 | 6 | 0 | 0 | 0 | 25
TOTAL | 14 | 8 | 19 | 1 | 7 | 6 | 3 | 12 | 3 | 73
ITEMS BY MILESTONE & STATUS
Milestone | Delivered | Dev Complete | In Development | In QA | Pre-PROD / UAT | Not Started | Partial Delivery | TOTAL
Milestone 1 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 29
Milestone 2 | 31 | 0 | 0 | 1 | 0 | 0 | 0 | 32
Milestone 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Milestone 4 | 47 | 0 | 2 | 0 | 1 | 4 | 3 | 57
Milestone 5 | 30 | 1 | 17 | 1 | 1 | 16 | 2 | 68
Milestone 6 | 120 | 0 | 6 | 1 | 1 | 17 | 0 | 145
TOTAL | 265 | 1 | 25 | 3 | 3 | 37 | 5 | 339
% Complete = Delivered ÷ (Delivered + Pending). N/A items (duplicates) are excluded from the calculation. All figures update live from the 'SOW, Feedbacks-Bug & CR_Items' sheet.

## 📅 13-Jul
WEEK OF 13 Jul 2026 → 19 Jul 2026 — 4 items · 4 delivered · 0 pending · LAST WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 3 items · 3 delivered · 0 pending
1 | iWork - CR | Policy Configuration | DNV Group - Dependent based SI & Premium configuration | Delivered | Milestone 6 | 07-Apr-2026 | 16-Jul-2026 | Jagadeesh
2 | iWork | Madhav & Veera | Data Load - Company, Policy, & Insurer - 38 Files | Delivered | Milestone 6 | 13-Jul-2026 | 19-Jul-2026 | Rama
3 | iWork | Neeraj Joshi | Production Bugs - Via Emails/Tickets - 10 | Delivered | Milestone 6 | 13-Jul-2026 | 19-Jul-2026 | Rama
IBP (Backlog & CRs) · 1 item · 1 delivered · 0 pending
4 | IBP - CR | IBP - FAQ | Policy Level - FAQ | Delivered | Milestone 6 | 11-Jul-2026 | 17-Jul-2026 | Manjusha

## 📍 20-Jul
WEEK OF 20 Jul 2026 → 26 Jul 2026 — 20 items · 20 delivered · 0 pending · CURRENT WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 20 items · 20 delivered · 0 pending
1 | iWork | IBP - Send "Welcome Emails" or any email from IBP to include CC by HR or CRM User | IBP - Send "Welcome Emails" or any email from IBP to include CC by HR or CRM User | Delivered | Milestone 6 | 20-Jul-2026 | 21-Jul-2026 | Ravi
2 | iWork | BizDone & Dashboard - Data Issue | Delete demo company, Demo company, Dummy company, Nokia Corporation (ref number 22337) | Delivered | Milestone 6 | 20-Jul-2026 | 21-Jul-2026 | Karan | Instead of delete, we maked the status NOT to show in the BizDone & Dashboard
3 | iWork | BizDone | Update the associate CRM and Lead CRM as per enclosed sheet. This sheet has policy data. As per this, related SO, RO, Company also to be updated. Their are few records without any associate CRM assignment. So leave them blank. -- Refer to Data update.msg & CRM-Update.xlsx | Delivered | Milestone 6 | 20-Jul-2026 | 21-Jul-2026 | Jagadeesh
4 | iWork | BizDone | Update Net Premium, Brokerage %, Brokerage Amount, & Income Month -- Refer to Data update - Set 2.msg & cl-updated.xlsx | Delivered | Milestone 6 | 20-Jul-2026 | 21-Jul-2026 | Jagadeesh
5 | iWork | BizDone | Update Lead CRM as Policy Owner for the selected Policies provided by Kapil | Delivered | Milestone 6 | 21-Jul-2026 | 21-Jul-2026 | Jagadeesh
6 | iWork | MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | Delivered | Milestone 3 | 16-May-2025 | 22-Jul-2026 | Sunil
7 | iWork | MIR Entry Mgmt | Module to manage MIR {Monthly Infomatiom Report} | Delivered | Milestone 3 | 16-May-2025 | 22-Jul-2026 | Sunil
8 | iWork | View Service Score | Servicing Stats Dashboard - Single Table (drillable) to calculate an overall score | Delivered | Milestone 4 | 10-Jun-2025 | 22-Jul-2026 | Sunil | Pending: Meeting, MIR calculation
9 | iWork | Surya's feedback | Policy Details - Strip - Remove view more button and company is clickable | Delivered | Milestone 6 | 14-Jul-2026 | 22-Jul-2026 | Pushyami
10 | iWork | Access Issue | When a user above the hirerchary is accessing the data, application is throwing "unauthorized" message | Delivered | Milestone 6 | 22-Jul-2026 | 22-Jul-2026 | Pushyami
11 | iWork | Kapil's feedback | Data change requests - Madhav's - Ass. CRM & Others - Refer to Jagadeesh email | Delivered | Milestone 6 | 23-Jul-2026 | 23-Jul-2026 | Jagadeesh
12 | iWork |  | Income month prefilling in endorsements | Delivered | Milestone 6 | 23-Jul-2026 | 23-Jul-2026 | Jagadeesh
13 | iWork | UX issue | Display of complete amounts in KPI cards on hover | Delivered | Milestone 6 | 23-Jul-2026 | 23-Jul-2026 | Pushyami
14 | iWork |  | Dashboard and BizDone Brokerage mismatch | Delivered | Milestone 6 | 23-Jul-2026 | 23-Jul-2026 | Jagadeesh
15 | iWork | Surya's feedback | Removal of + or - 5 days logic in the filters - Revert the logic | Delivered | Milestone 6 | 23-Jul-2026 | 23-Jul-2026 | Karan
16 | IBP/iWork | TPA Integration Mgmt [Framework] | 1. Framework in iWork 2. Validate the integration for the existing 6 TPA's | Delivered | Milestone 4 | 10-Jun-2025 | 24-Jul-2026 | Ravi
17 | iWork | Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) Similar to TPA API Integration Framework for any 3'rd Party | Delivered | Milestone 5 | 31-Jul-2025 | 24-Jul-2026
18 | iWork | Application Access similar to SysAdmin | Need one more user like SYSADMIN. This user to be below SYSADMIN - and should be 100% read-only user - access etc all like SYSADMIN including Bizdone report download etc Also, inpersonate the user and see the data | Delivered | Milestone 6 | 20-Jul-2026 | 24-Jul-2026 | Pushyami | 1. Kapil sir sent it via Teams Chat. 2. Surya sir mentioned this in Call on Saturday
19 | iWork | Madhav & Veera | Data Load - Company, Policy, & Insurer - 38 Files | Delivered | Milestone 6 | 20-Jul-2026 | 24-Jul-2026 | Rama
20 | iWork | Neeraj Joshi | Production Bugs - Via Emails/Tickets - 10 | Delivered | Milestone 6 | 20-Jul-2026 | 24-Jul-2026 | Rama

## 📅 27-Jul
WEEK OF 27 Jul 2026 → 02 Aug 2026 — 51 items · 1 delivered · 50 pending · NEXT WEEK
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 12 items · 0 delivered · 12 pending
1 | iWork | Cut Off Mgmt |  | QA - WIP | Milestone 2 | 16-Apr-2025 | 28-Jul-2026 | Karan
2 | IBP/iWork | Country Handling {Data Source Mgmt} | 23-May: Respective org. data should reside in the same country. | Yet to start | Milestone 4 | 10-Jun-2025 | 31-Jul-2026 | Rama
3 | IBP/iWork | Core Infrastructure | Core Infra | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Velangini Raju | Pending: Mobile responsive
4 | IBP/iWork | Wellness Admin Configurator | Admin side of IBP (in iWork) needs to customize/configure the offerings/page per Corporate. | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi
5 | IBP/iWork | Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi
6 | iWork | Insurer Integration Mgmt | Can be used as a part of External API Intergration | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
7 | iWork | Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
8 | iWork | Reconciliation Management Upload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid Premium vs Brokerage Invoice vs Brokerage Collected; Data from Finops | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 |  | Need inputs from Kapil
9 | iWork | Reconciliation Mgmt |  | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
10 | iWork | HRMS Integration Mgmt | Base framework needs to be built and actual integration should be on need - Need to create the API's for each service flow process (Endorsement - Add/Delete) - Endorsement process - What is the process for this? HRMS - integrations with enrolment portal (POC - with Zoho People), client mentioned that they have already integrated MB360 for HCL IBP & HRMS Integration - HCL | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
11 | IBP/iWork | End-2-End: Automation of IBP Go-live Setup | 1. Form based data collection 2. Default CMS details 3. Configure the sub-domain in AWS (any API) | Yet to start | Milestone 6 | 01-Jun-2026 | 31-Jul-2026 | Abhilash
12 | IBP/iWork - CR | No Policy Config - Enrolment Journey | Enrolment Journey - Collect Dependents Details ONLY | Dev - WIP | Milestone 6 | 04-Jul-2026 | 31-Jul-2026 | Manjusha | 1. IBP - Enrolment - Completed 2. Service - WIP
IBP (Backlog & CRs) · 21 items · 0 delivered · 21 pending
13 | IBP | Claims Corner | Claims Corner - Screen Re-design | Dev - WIP | Milestone 6 | 21-Jun-2026 | 28-Jul-2026 | Ravi
14 | IBP | NFR_Usability | NFR-USA-011: The system should support at least 100 concurrent users without performance degradation. | Pre-PROD | Milestone 4 | 10-Jun-2025 | 31-Jul-2026 | Akhila | Fine tuning the API's where there is a delay
15 | IBP | Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Manjusha
16 | IBP | Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi
17 | IBP | Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Abhilash
18 | IBP | Claims Mgmt | Part-2: Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Manjusha
19 | IBP | Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi
20 | IBP | User Profile | Profile, Service Subscriptions, Feedback | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi | Pending: Service Subscriptions, Feedback
21 | IBP | Evexia Club Integration | Integration to Evexia | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Abhilash
22 | IBP | End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Manjusha | Pending: Offer, Feature flagging (UI)
23 | IBP | Benefits Summary | End User's Summary View | Delivered - Deficit | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi | Pending: Retail Insurance
24 | IBP | Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
25 | IBP | My Insurance | Part-2: Hub of all plans I have as an employee - individually signed up. Mostly a navigational page | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi | Retail insurance(facility to load user insurance policies)
26 | IBP | Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Manjusha | wellness
27 | IBP | Wellness HR View | HR View of Wellness usage by Employees | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Manjusha | wellness
28 | IBP | Wellness Partner View | Partner/service provider view of the usage of their corresponding services | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Manjusha | wellness
29 | IBP | Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi | Pending: Retail insurance
30 | IBP | Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Ravi | Pending: Retail insurance
31 | IBP | Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Abhilash | External chatbot integration?
32 | IBP | Profile Migration | Request migration of Corporate Profile to Individual | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Abhilash
33 | IBP | Profile Migration | Request migration of Individual Profile to Corporate | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Abhilash
Framework (DPDP, NFR, Framework) · 18 items · 1 delivered · 17 pending
34 | Framework | Notifications Management | Different email notification - Madhav excel. 1. Renewal Reminders - ASAP 2. Instalment Reminders 3. Others......... | Delivered - Deficit | Milestone 4 | 10-Jun-2025 | 28-Jul-2026 | Pushyami
35 | DPDP | Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} - DPDP |  | Yet to start | Milestone 4 | 10-Jun-2025 | 31-Jul-2026 | Rama | Duplicate of Archival from NFR & DPDP
36 | Framework | Localisation |  | Delivered - Deficit | Milestone 4 | 10-Jun-2025 | 31-Jul-2026 | Tharun | Pending: Service Flow Pending: IBP
37 | NFR | NFR_Usability | NFR-USA-021: Guidelines for document management should be provided | Delivered - Deficit | Milestone 4 | 10-Jun-2025 | 31-Jul-2026 | Rama | Pending: Provide the document on how do we store and view it
38 | DPDP | App vulnerability scans |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
39 | DPDP | Document Flows |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
40 | DPDP | Perform security UAT |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
41 | DPDP | Enforce business logic to restrict purpose |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
42 | DPDP | Remove unnecessary fields |  | Dev - Done | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
43 | DPDP | Allow user corrections |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
44 | DPDP | Delete expired data |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
45 | DPDP | Sign DPDP clauses |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
46 | DPDP | Map PII tables |  | QA - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Rama
47 | DPDP | Enable delete pipeline |  | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
48 | DPDP | Define archival |  | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
49 | DPDP | Quarterly restore tests |  | Pre-PROD | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 | Rama
50 | NFR | NFR-OTH-015: The application must cryptographic Failures, previously known as Sensitive Data Exposure, which was broad symptom rather than a root cause. The renewed focus here is on failures related to cryptography which often leads to sensitive data exposure or system compromise. |  | Dev - WIP | Milestone 5 | 31-Jul-2025 | 31-Jul-2026
51 | NFR | NFR-OTH-022: A self-service report generator must be available for dynamic query/report creation. |  | Yet to start | Milestone 5 | 31-Jul-2025 | 31-Jul-2026 |  | Discussed this with Surya sir last visit to Divami office

## 📅 Upcoming
UPCOMING (ETA beyond 27 Jul week) — 4 items · 0 delivered · 4 pending
⚠️ Static snapshot. To update: edit STATUS/ETA in the source sheet, then re-run build_iirm_summary.py
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 3 items · 0 delivered · 3 pending
1 | iWork | Teams Integration | MS Teams - Meetings & Tasks integration into iWork Bi-Directional | Yet to start | Milestone 4 | 10-Jun-2025 | 07-Aug-2026 | Rama
2 | IBP/iWork - CR | InsureEasy | InsureEasy Integration - Retail Business | Yet to start | Milestone 6 | 25-Jun-2026 | 07-Aug-2026
3 | IBP/iWork | IBP - Raise Ticket | Edit the ticket and update the status by the Lead CRM & System Admin | Yet to start | Milestone 6 | 01-Jul-2026 | 07-Aug-2026 | Manjusha
IBP (Backlog & CRs) · 1 item · 0 delivered · 1 pending
4 | IBP | IIRM-10666 | IBP - Policy Component Card Re-design | Yet to start | Milestone 6 | 21-Jun-2026 | 07-Aug-2026 | Manjusha

## Unplanned (no ETA)
UNPLANNED — PENDING, NO ETA · 23 items
Pending items with no ETA yet. Assign an ETA in the source sheet to move an item into its week. Static snapshot — re-run to refresh.
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
iWork (Backlog & CRs) · 21 items
1 | IBP/iWork | Wellness Discount List Management | Add/Remove/update Discount program benefits | Yet to start | Milestone 4 | 10-Jun-2025
2 | IBP/iWork | Upload from Partner of services bought on Partner site | Upload, listing, confirm & load into DB by an Iwork user. These are services purchased / discounts availed on partner sites by IBP corporate users | Yet to start | Milestone 4 | 10-Jun-2025
3 | iWork - CR | Policy Configuration | Premium Rater Table | Yet to start | Milestone 6 | 21-Apr-2026 |  | Jagadeesh
4 | iWork - CR | Policy Configuration | Enable Parent-Child Policy Mapping for GMC and Sub-Plans (Parental, OPD, Dental, Others) - How to view config from Base to Child Policiy? - How to handle endorsement & Claims? (Entire Service Flow) | Yet to start | Milestone 6 | 01-May-2026 |  | Sunil
5 | iWork - CR | Opportunity - Validate uploaded documents | Using AI - Extract the documents, validate, populate the data in the Opty. flow (Ex. KDM Meeting, Policy Hard Copy, & Others) | Yet to start | Milestone 6 | 08-May-2026 |  |  | Need some information about the document rules that defines the idenity of it
6 | iWork | Export to Excel | Export to excel - iWork all the results table; Download is on Previlage | Yet to start | Milestone 6 | 15-Jun-2026
7 | iWork | IIRM-10667 | iWork - Knowledge Central Re-Design | Yet to start | Milestone 6 | 15-Jun-2026
8 | iWork | IIRM-10668 | iLearn: Document Preview in-app | Yet to start | Milestone 6 | 15-Jun-2026
9 | iWork | Discuss with Madhav | 19-Jun-2026: Financial Impact fields should be seperated from actual fields. These fields should NOT be populated on their own. (Mainly BizDone & Dashboard) Also, check if we are there are any data loads for 2025-26 | Yet to start | Milestone 6 | 15-Jun-2026
10 | iWork | Installment & Fee Requirements | Installments & Fee to BizDone | Yet to start | Milestone 6 | 15-Jun-2026
11 | iWork | AI | Wherever AI is implemented, there should be fallback if one day we turnoff AI then there shouldn’t be any impact in the working functionality | Yet to start | Milestone 6 | 25-Jun-2026 |  | Rama
12 | iWork | AI | AI Nudges are NOT working. If there is NO AI, then DB scripts should run and show data | Yet to start | Milestone 6 | 25-Jun-2026 |  | Rama
13 | iWork - CR | BizDone | Computed value & Reported values * Computed values - It’s the real-time values base on Policy inception/endorsement * Reported values - It’s validated by the mgmt. and share this number to update in the column. * Reported value MUST be used for the Dashboard & BizDone, which was declared by the company to public. * In the admin a feature to update the Reported values from the computed values * Legacy data - Premiums, Brokerage, CD Balance | Yet to start | Milestone 6 | 25-Jun-2026
14 | IBP/iWork - CR | Inception/Endorsement | Whenever we get Employee Details (Email, Phone & DOB) uploaded then update the existing record as this is the latest data | Yet to start | Milestone 6 | 01-Jul-2026 |  | Jagadeesh
15 | IBP/iWork - CR | IBP - Welcome Emails | Dual approval/confirmation - Before sending to Employees. 1. 2 levels in iWork 2. CRM will submit & HR will approve in Risk Watch | Yet to start | Milestone 6 | 14-Jul-2026
16 | iWork | iWork - Report | When we generate 2025-2026 data for IIRM India then API request is a failure. Need to find a solution | Yet to start | Milestone 6 | 17-Jul-2026
17 | iWork - CR | Help Info - Field formulaes or field values | In any of the screen, we have to provide an info icon where it will help the users how critical fields in that screen are derieved or got populated | Yet to start | Milestone 6 | 17-Jul-2026
18 | iWork | BizDone | Update Opty. Owner value to Lead CRM of the Company | Yet to start | Milestone 6 | 21-Jul-2026 |  | Jagadeesh
19 | iWork | Inception/Endorsement | Endorsement data upload related * Track-1: TeamLease - 2024-2025 Year policies * All endorsement -> Headers, Member data, & endorsement Document * Track-2: Old Financial data * Track-3: Current Financial data * Track-4: Handle the data in IBP-Risk Watch | Dev - WIP | Milestone 6 | 25-Jun-2026 |  | Rama
20 | iWork |  | In BizDone - Include Fee & Rewards in Total Brokerage | Dev - WIP | Milestone 6 | 24-Jul-2026 |  | Pushyami
21 | iWork |  | In Dashboard - Include Fee & Rewards in Achieved | Dev - WIP | Milestone 6 | 24-Jul-2026 |  | Pushyami | Rewards will be added in RO as per Surya's sir and mention a note. Later based on VRK's feedback we will update it.
IBP (Backlog & CRs) · 1 item
22 | IBP - CR | Claim Intimation & Submission | POC - Using AI(Amazon Textract) - Extract Claim documents and populate the data | Pre-PROD | Milestone 6 | 08-May-2026 |  | Abhilash
Framework (DPDP, NFR, Framework) · 1 item
23 | Framework | Accessibility | 20-Jul: Jagadees --> Need More details | Yet to start | Milestone 4 | 10-Jun-2025

## VRK Feedbacks
VRK — PROD FEEDBACK TRACKER · 67 items · 64 delivered · 3 pending
All 'VRK - PROD Feedback:' items, broken up by week (status then ETA within a week). Excluded from the other views. Static snapshot.
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
📅 WEEK OF 08 Jun → 14 Jun 2026 · PAST · 27 items
1 | iWork | VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | Delivered | Milestone 6 | 05-Jun-2026 | 08-Jun-2026
2 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
3 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
4 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
5 | iWork | VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
7 | iWork | VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
8 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
9 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
10 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
11 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
12 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | Delivered | Milestone 6 | 08-Jun-2026 | 09-Jun-2026 | Karan
13 | iWork | VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | Delivered | Milestone 6 | 08-Jun-2026 | 09-Jun-2026
14 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026
15 | iWork | VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
16 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
17 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
18 | iWork | VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
19 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | Delivered | Milestone 6 | 08-Jun-2026 | 10-Jun-2026
20 | iWork | VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Prathiphala
21 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Jagadeesh
22 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Jagadeesh
23 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | Delivered | Milestone 6 | 08-Jun-2026 | 12-Jun-2026 | Karan
24 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | Delivered | Milestone 6 | 08-Jun-2026 | 12-Jun-2026
25 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | Delivered | Milestone 6 | 09-Jun-2026 | 12-Jun-2026 | Prathiphala
26 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | Not a bug | Milestone 6 | 08-Jun-2026 | 08-Jun-2026 |  | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only
27 | iWork | VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | Not a bug | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
📅 WEEK OF 15 Jun → 21 Jun 2026 · PAST · 8 items
28 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
29 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
30 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
31 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026
32 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
33 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | Delivered | Milestone 6 | 09-Jun-2026 | 16-Jun-2026
34 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | Delivered | Milestone 6 | 08-Jun-2026 | 19-Jun-2026 | Rama
35 | iWork | VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | Delivered | Milestone 6 | 09-Jun-2026 | 19-Jun-2026 | Karan
📅 WEEK OF 22 Jun → 28 Jun 2026 · PAST · 1 item
36 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | Delivered | Milestone 6 | 08-Jun-2026 | 24-Jun-2026
📅 WEEK OF 29 Jun → 05 Jul 2026 · PAST · 8 items
37 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | Delivered | Milestone 6 | 08-Jun-2026 | 30-Jun-2026 | Jagadeesh
38 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
39 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
40 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
41 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
42 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
43 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
44 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | Delivered | Milestone 6 | 08-Jun-2026 | 02-Jul-2026
📅 WEEK OF 06 Jul → 12 Jul 2026 · PAST · 3 items
45 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 07-Jul-2026 | Pushyami
46 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Pushyami
47 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Pushyami
📅 WEEK OF 13 Jul → 19 Jul 2026 · LAST WEEK · 13 items
48 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Remove the Vertical section. Keep only Branch. | Delivered | Milestone 6 | 13-Jul-2026 | 13-Jul-2026
49 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 14-Jul-2026 | Karan
50 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - Filter & drill-down | Delivered | Milestone 6 | 23-Jun-2026 | 14-Jul-2026 | Karan
51 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Remove the SO/RO labels from the bar charts. Display only the figures inside the bars, with the corresponding details available on mouse hover (tooltip). | Delivered | Milestone 6 | 13-Jul-2026 | 14-Jul-2026
52 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Review and correct the display of negative values for TeamLease under RO, particularly for Q3 bar-chart. | Delivered | Milestone 6 | 13-Jul-2026 | 14-Jul-2026
53 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Brokerage Display - Display Brokerage information only. Hide Premium values in the enhanced screens. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
54 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | BizDone Enhanced Screen - Hide Premium. Display: RO Brokerage SO Brokerage | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
55 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Resolve the Premium value formatting issue. Values should be displayed consistently in Millions/Billions. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
56 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Display the Endorsement section above the section “Business Collection Summary”. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
57 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Move the Policy Type Distribution section above RO by SBU. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
58 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Rename/update the Policy Type names “Fire & Engineering”, “Speciality Lines - Liability” | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
59 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - The SO Activity Follow-up screen should not display ISG-related activities. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
60 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - When IIRM Holdings is selected, the Organization-level cards and graphs are not displayed. Verify and fix the issue. | Delivered | Milestone 6 | 13-Jul-2026 | 17-Jul-2026
📍 WEEK OF 20 Jul → 26 Jul 2026 · CURRENT WEEK · 3 items
61 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Display the data using an Accordion layout in the following order: Company → SBU → Branch → Executive → Client → Policy | Delivered | Milestone 6 | 13-Jul-2026 | 20-Jul-2026
62 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - Make the Funnel interactive so that clicking on each stage navigates to the corresponding enhanced screen. | Delivered | Milestone 6 | 13-Jul-2026 | 22-Jul-2026 |  | Pending: Becuase the enhanced screens are yet to Approve
63 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Under PL, the bar chart should represent SO-level data instead of the currently displayed RO-level data. | Delivered | Milestone 6 | 13-Jul-2026 | 22-Jul-2026
📅 WEEK OF 27 Jul → 02 Aug 2026 · NEXT WEEK · 2 items
64 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | Yet to start | Milestone 6 | 09-Jun-2026 | 28-Jul-2026 | Jagadeesh
65 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Additional section display: Placement Funnel, Schedule, Followup | Yet to start | Milestone 6 | 23-Jun-2026 | 31-Jul-2026 | Pushyami
🗓 No ETA assigned · 2 items
66 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | iWork and iTicket should be accessible via VPN | Yet to start | Milestone 6 | 23-Jun-2026 |  | Pushyami
67 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Organization-wise summary cards are not required. | Not in scope | Milestone 6 | 13-Jul-2026 |  |  | Madhav sir confirmed vie Teams Chat

## SOW - Actual Items
Module | Functionality | Module | Module | Match Status | Refer to "SOW, Feedbacks-Bug & CR_Items"
UI Approach Style Establishment | UI Style Establishment | Framework | Milestone 1 | ✓ Found in tracker
UI Approach Design System | Building Design System | Framework | Milestone 1 | ✓ Found in tracker
Project setup | Basic project / Development environment setup | Framework | Milestone 1 | ✓ Found in tracker
Build UI components | This includes all the UI componnets to compose the application and module definitions: Form, Toast, Filter, Cards, Visualisation, Grid, Menu, Header, Footer, Maps Integration | Framework | Milestone 1 | ✓ Found in tracker
Core System |  | Framework | Milestone 1 | ✓ Found in tracker
ACL & RBAC Control Framework |  | Framework | Milestone 1 | ✓ Found in tracker
Micro Frontend Setup |  | Framework | Milestone 1 | ✓ Found in tracker
Service Workers Implementation |  | Framework | Milestone 1 | ✓ Found in tracker
Landing Page |  | Framework | Milestone 1 | ✓ Found in tracker
Access Control Management |  | Framework | Milestone 1 | ✓ Found in tracker
Auth Module (Simple Auth) |  | Framework | Milestone 1 | ✓ Found in tracker
Micro Service Framework Setup |  | Framework | Milestone 1 | ✓ Found in tracker
Company (Prospect) Hub | Top 10/Latest companies, with search/filter, Table of basic attributes with GPS etc. | iWork | Milestone 1 | ✓ Found in tracker
Add/View/Edit Company | Large form with basic format based validations, some mandatory fields, multiple addresses, couple of Rich Text Editor fields; Some multi-line fields (e.g., GST), uploads; Duplicate detection on Company name, GST/PAN etc. Simple edit like Add; View is multiple widgets (Contacts, Opportunities, Policies, Claims, SLAs, Document list) | iWork | Milestone 1 | ✓ Found in tracker
Contact Hub | Top 10/Latest Contacts, with search/filter, list with basic attributes | iWork | Milestone 1 | ✓ Found in tracker
Add/View/Edit Contact | Simple edit like Add Contacts should maintain Company history although only 1 Company active with 1 contact; Medium size form with fields, linked in connect | iWork | Milestone 1 | ✓ Found in tracker
Opportunity Hub | Top Opportunities with search/filter, List of opportunities with high level summaries | iWork | Milestone 1 | ✓ Found in tracker
Add/View/Edit Opportunity | Add Medium size form with 1->N list of Claims; Multiple drop downs Large View with several widgets, Simple Edit | iWork | Milestone 1 | ✓ Found in tracker
Insurer/TPA Hub | List with Filter/Search | iWork | Milestone 1 | ✓ Found in tracker
Manage TPA/Insurer | Basic Add, View with edit of basic data, with lists of policies/companies | iWork | Milestone 1 | ✓ Found in tracker
Contact /Company/Insurer/TPA Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
Task Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
Meeting Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
Employee Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
RBAC and ACL setup for Iwork Module |  | iWork | Milestone 1 | ✓ Found in tracker
Opportunity Mgmt |  | iWork | Milestone 1 | ✓ Found in tracker
Common - Audit Trail Mgmt - Becomes critical in this phase iteself |  | iWork | Milestone 1 | ✓ Found in tracker
Visualization framework | Charts and KPIs | Framework | Milestone 2 | ✓ Found in tracker
Visualization framework (mobile) | Charts and KPIs | Framework | Milestone 2 | 🔗 Mapped (see note) | Map to line number 35 in Sheet-SOW, Feedbacks-Bug & CR_Items
User Management |  | Framework | Milestone 2 | ✓ Found in tracker
Notifications Management |  | Framework | Milestone 2 | ✓ Found in tracker
Document Management | Create, Upload, Seach, Download | Framework | Milestone 2 | ✓ Found in tracker
Document Management (Mobile) | Create, Upload, Seach, Download | Framework | Milestone 2 | 🔗 Mapped (see note) | Map to line number 36 in Sheet-SOW, Feedbacks-Bug & CR_Items
Caching of API Data |  | Framework | Milestone 2 | ✓ Found in tracker
Caching of API Data (Mobile) |  | Framework | Milestone 2 | 🔗 Mapped (see note) | Map to line number 37 in Sheet-SOW, Feedbacks-Bug & CR_Items
Master Data Management |  | Framework | Milestone 2 | ✓ Found in tracker
User Management |  | Framework | Milestone 2 | ✓ Found in tracker
Notification and Communication Management |  | Framework | Milestone 2 | ✓ Found in tracker
Audit Data Capturing |  | Framework | Milestone 2 | ✓ Found in tracker
Usage Tracking System |  | Framework | Milestone 2 | 🔗 Mapped (see note) | Map to line number 41 in Sheet-SOW, Feedbacks-Bug & CR_Items
CMS |  | Framework | Milestone 2 | ✓ Found in tracker
Data Security Considerations | Data ca n be accessed only through the APIs and in the same network Database can be accessed on through Jumphost Database access is based on privilages | Framework | Milestone 2 | ✓ Found in tracker
Dashboard | Multiple KPI Cards: Business Performance, Svc Performance, Table of targets vs. actuals vs. lost, Sales Funnel, Renewal Funnel, Servce Funnel, AR from Insurers, Pending Activities(iWork Stages) Widget, Followups widget, Meetings widget Filters available (Geo, Branch, Team/Team Member, Dates), Approvals, iWork Stages, Tasks, Meetings | iWork | Milestone 2 | ✓ Found in tracker
Dashboard - Drilldowns | Drill down from the Tables (Targets vs. Actuals, Pending Activities, Followups, AR Report, Schedule) | iWork | Milestone 2 | ✓ Found in tracker
Dashboard - Pending tasks, approvals | Pending tasks/approvals, | iWork | Milestone 2 | ✓ Found in tracker
Manage Stage Planning/Performance/Approval | Add iWork Stages (table) - Dates with each iWork Stage and who are the team members assigned to each Stage; Once all iWork stages are complete, ISG Team activities must be planned ISG Team can approve/reject each iWork Stage. Approving RFP Stage approves all iWork stages Completion of each iWork Stage (Activity) & ISG Stage - Comments, Attach Document, Date recorded, submit | iWork | Milestone 2 | ✓ Found in tracker
Sales Team Hierarchy | Hierarchy / Org chart tied to Platform Users | iWork | Milestone 2 | ✓ Found in tracker
View Policy | Long View, multiple widgets/entities, endorsements (each month), Claims, etc. | iWork | Milestone 2 | ✓ Found in tracker
Common Data Mapping Component | Map input fields to output fields & Order | iWork | Milestone 2 | ✓ Found in tracker
Reports - Biz Done | Report View, Download, List of earlier snaps of the report, Search and Filter | iWork | Milestone 2 | ✓ Found in tracker
Smart Add Component | Allow Upload of Document/Image, select what to create (Company/Contact/Opportunity) | iWork | Milestone 2 | ✓ Found in tracker
Organisation, Branch, Employee, & Hierarchy Mgmt |  | iWork | Milestone 2 | ✓ Found in tracker
Cut Off Mgmt |  | iWork | Milestone 2 | ✓ Found in tracker
Dashboard (Place Holder) |  | iWork | Milestone 2 | ✓ Found in tracker
Planning, Perform and Approval Mgmt |  | iWork | Milestone 2 | ✓ Found in tracker
Policy Mgmt |  | iWork | Milestone 2 | ✓ Found in tracker
AI - (Non-OCR) Digital Document Processing for Content recognition (Company/Opportunity/Contact Creation from Previous Policy Document, Bizcard document) |  | iWork | Milestone 2 | ✓ Found in tracker
AI - OCR for Content Collection |  | iWork | Milestone 2 | ✓ Found in tracker
AI - Company Information by AI Search |  | iWork | Milestone 2 | ✓ Found in tracker
Common, Contexual Upload Component |  | iWork | Milestone 2 | ✓ Found in tracker
Common, Contexual Read and Spread Component |  | iWork | Milestone 2 | 🔗 Mapped (see note) | Map to line number 47 in Sheet-SOW, Feedbacks-Bug & CR_Items
HR/Admin Portal View | Supporting services for Admin Portal | IBP | Milestone 2 | ✓ Found in tracker
Document Generation |  | Framework | Milestone 3 | ✓ Found in tracker
Manage Policy (Endorsements) | Add Endorsement - basic form with uploads of excel/document Validations of endorsement format - Map customer fields to internal fields Map internal fields to TPA fields (occasional per TPA) View/Update Endorsement, List View, Endorsement Performance | iWork | Milestone 3 | ✓ Found in tracker
MIR Entry Mgmt | Entry Form, Print to Document, List of Earlier MIRs, Search on MIRs | iWork | Milestone 3 | ✓ Found in tracker
Master Data Mgmt {Common, Contexual Master Data Mgmt} |  | iWork | Milestone 3 | ✓ Found in tracker
Stage Mgmt (Activity/Transaction/Quote) |  | iWork | Milestone 3 | ✓ Found in tracker
Asset/Member Data Mgmt |  | iWork | Milestone 3 | ✓ Found in tracker
Cover Mgmt |  | iWork | Milestone 3 | ✓ Found in tracker
Endorsement Mgmt |  | iWork | Milestone 3 | ✓ Found in tracker
MIR Entry Mgmt | Module to manage MIR {Monthly Information Report} | iWork | Milestone 3 | ✓ Found in tracker
Accessibility |  | Framework | Milestone 4 | ✓ Found in tracker
Localisation |  | Framework | Milestone 4 | ✓ Found in tracker
Configuration Management |  | Framework | Milestone 4 | ✓ Found in tracker
Feature Flag Control Management |  | Framework | Milestone 4 | ✓ Found in tracker
Workflow Management |  | Framework | Milestone 4 | ✓ Found in tracker
Rule Definition Management |  | Framework | Milestone 4 | ✓ Found in tracker
Caching Implementation |  | Framework | Milestone 4 | ✓ Found in tracker
Localistation Management |  | Framework | Milestone 4 | ✓ Found in tracker
Knowledge Central | Grouped list of Documents/Resources, Add a Document, Remove a Document (Add/remove only for admins) | iWork | Milestone 4 | ✓ Found in tracker
View Service Score | Servicing Stats Dashboard - Single Table (drillable) to calculate an overall score | iWork | Milestone 4 | ✓ Found in tracker
Knowledge Central |  | iWork | Milestone 4 | ✓ Found in tracker
TAT/SLA Mgmt (Including Service Score) |  | iWork | Milestone 4 | ✓ Found in tracker
Country Handling {Data Source Mgmt} | Physical data storage is limiited to a particular country and can't be combined with other country data | iWork | Milestone 4 | 🔗 Mapped (see note) | Map to line number 115 in Sheet-SOW, Feedbacks-Bug & CR_Items
Archived Oppurtunity, Policy Mgmt {Archived Biz Data and Retrieval on need} |  | iWork | Milestone 4 | 🔗 Mapped (see note) | Map to line number 71 in Sheet-SOW, Feedbacks-Bug & CR_Items
IBP Landing Page - Basic | Basic Landing Page with only company plans and summary | IBP | Milestone 4 | ✓ Found in tracker
My Insurance | Hub of all plans I have as an employee - both Company provided and individually signed up. Mostly a navigational page | IBP | Milestone 4 | ✓ Found in tracker
Company Plans | 6 Policies - GMC, GPA, GTL, Parental Plicy, Top-ups, OPD Policy (Summary view of policies | IBP | Milestone 4 | ✓ Found in tracker
Per-policy Enrolment | Enrolment and addon policy selection | IBP | Milestone 4 | ✓ Found in tracker
Company Plan Configurator | Admin side of IBP should configure (per Corporate) how to define a Policy and determine how it breaks down the Premium and Coverage rules | IBP/iWork | Milestone 4 | ✓ Found in tracker
My Documents | Document Hub - covers Policies, Prescriptions, Reports | IBP | Milestone 4 | ✓ Found in tracker
User Profile | Profile, Service Subscriptions, Feedback | IBP | Milestone 4 | ✓ Found in tracker
Whitelabelling | Whitelabelling based on Org needs (IBP Admin) | IBP/iWork | Milestone 4 | ✓ Found in tracker
Contact Matrix | Configure the Conact Info Matrix (IBP Admin) | IBP/iWork | Milestone 4 | ✓ Found in tracker
Contact Matrix View | Contact Matrix View for end user | IBP | Milestone 4 | ✓ Found in tracker
Auth Config UI | Config for Auth Rules setup | IBP/iWork | Milestone 4 | ✓ Found in tracker
Wellness Discount List Management | Add/Remove/update Discount program benefits | IBP/iWork | Milestone 4 | ✓ Found in tracker | Map to line number 126 in Sheet-SOW, Feedbacks-Bug & CR_Items
HR Portal View | Employee Search, Resend Email, Update Employee Info, Delete Employees, Extend Enrollment Windows, Reports, Bulk Email | IBP | Milestone 4 | ✓ Found in tracker
Basic Landing Page Services | Company provided plans only | IBP | Milestone 4 | ✓ Found in tracker
Document Mgmt for End User | Insurance, Health Reports and Prescriptions {No automatic pull from Partners} | IBP | Milestone 4 | ✓ Found in tracker
Personal Profile Mgmt | Profile settings | IBP | Milestone 4 | ✓ Found in tracker
Group Policy Mgmt - Enrollment | Enrollment (Adding Dependents, Choosing Options available). Submit the enrollment to Insurer or TPA 6 Types of Policies to be considered | IBP | Milestone 4 | ✓ Found in tracker
Group Policy Mgmt - Enrollment Configurator | Enrollment Configurator (Set of benefits and type of Dependent combinations allowed etc). This is more of an Iwork feature to configure the policy | IBP/iWork | Milestone 4 | 🔗 Mapped (see note) | Map to line number 100 in Sheet-SOW, Feedbacks-Bug & CR_Items
Group Policy Mgmt - Data Load | End User data load {Similar to inception data load only but this time it is from the policy definition stage and confiemd by HR of the Company}. Reuse of the inception data load | IBP | Milestone 4 | ✓ Found in tracker
Contact Matrix Configuration | Matrix of Contact Infomration | IBP | Milestone 4 | ✓ Found in tracker
Wellness Benefits Mgmt | Company Sponsered, Personal Discounted services | IBP | Milestone 4 | 🔗 Mapped (see note) | Map to line number 126 in Sheet-SOW, Feedbacks-Bug & CR_Items
End User onboarding | Generate Users, Send Emails, Password Rest | IBP | Milestone 4 | ✓ Found in tracker
Admin Reports | Services for multiple reports | IBP | Milestone 4 | ✓ Found in tracker
Simple Auth | Username and Password based authentication and RBAC on simple-auth users. Auth rules needs configuration capability | IBP | Milestone 4 | ✓ Found in tracker
Whitelabelling Support |  | IBP | Milestone 4 | ✓ Found in tracker
Reconciliation ManagementUpload Commission Statement | Upload commission statement, reconcile against issued policies; Upload invoice & reconcile against commission stmt; Upload invoice statuses and reconcile paid/unpaid | iWork | Milestone 5 | 🔗 Mapped (see note) | Map to line number 190 in Sheet-SOW, Feedbacks-Bug & CR_Items
Report Hub | Landing Page and generic hub | iWork | Milestone 5 | ✓ Found in tracker
Reports | Generic template for all the reports, Bizdone Report, Missing entries from commission statement against policies | iWork | Milestone 5 | ✓ Found in tracker
CD Creation | Show current CD Balance against pooled/individual policies / Allow new CD creation, update CD balance and map policies to CD balances | iWork | Milestone 5 | ✓ Found in tracker
Claim Management (Add Claim, Import Claims & Claim Activities) | Basic Form with fields and upload for adding claim Bulk import to validate and map from TPA format to internal fields 3 stage workflow - each stage, update data on claim form | iWork | Milestone 5 | ✓ Found in tracker
Integration UI Component | Integration UI Component (for TPA, HRMS, Insurer) | iWork | Milestone 5 | ✓ Found in tracker
CD Mgmt |  | iWork | Milestone 5 | ✓ Found in tracker
Reports |  | iWork | Milestone 5 | ✓ Found in tracker
Claim Mgmt |  | iWork | Milestone 5 | ✓ Found in tracker
Reconciliation Mgmt |  | iWork | Milestone 5 | ✓ Found in tracker
Insurer Integration Mgmt |  | iWork | Milestone 5 | ✓ Found in tracker
TPA Integration Mgmt |  | iWork | Milestone 5 | 🔗 Mapped (see note) | Map to line number 114 in Sheet-SOW, Feedbacks-Bug & CR_Items
HRMS Integration Mgmt | Base framework needs to be built and actual integration shoudl be on need | iWork | Milestone 5 | ✓ Found in tracker
IBP Landing Page - Advanced | Advanced Landing Page with individual plans & wellness programs introduced Quick Links, Promotional, high level dashboard, my plans, individual policies, company benefits, etc. Whitelabelling may be required (only Company Logo), but for future, theming may have to be supported | IBP | Milestone 5 | ✓ Found in tracker
IBP Landing Page - Customization | Landing Page customization in Admin side of IBP - available in iWork (per Corporate) | IBP/iWork | Milestone 5 | ✓ Found in tracker
Dynamic Info Sections - Landing | Hospital network, Offers and Discounts, Benfits at Glance, Quick Links | IBP | Milestone 5 | ✓ Found in tracker
Static Info Sections - Landing | Benefits Guide, FAQs, Help | IBP | Milestone 5 | ✓ Found in tracker
Individual Plan Summary | View of individual Plans currently owned with renewal dates, premiums etc. | IBP | Milestone 5 | ✓ Found in tracker
Individual Plans | Quotation flow of a new insurance - multple products; quotation ranges after basic data collection; cross-sells and finally an summary page that someone will get back to you. About 7 individual products - could be 4-5 screens in the flow of which 2 screens may be product-specific. | IBP | Milestone 5 | ✓ Found in tracker
Basic Wellness Hub | Basic wellness hub - Currently only 3 wellness programs (3rd parties) supported | IBP | Milestone 5 | ✓ Found in tracker
Upload from Partner of services bought on Partner site | Upload, listing, confirm & load into DB by an Iwork user. These are services purchased / discounts availed on partner sites by IBP corporate users | IBP/iWork | Milestone 5 | ✓ Found in tracker | Map to line number 127 in Sheet-SOW, Feedbacks-Bug & CR_Items
Wellness Admin Configurator | Admin side of IBM (in iWork) needs to customize/configure the offerings/page per Corporate. | IBP/iWork | Milestone 5 | ✓ Found in tracker
Wellness IIRM View | IIRM View of Wellness usage by Corporates/Employees (IBP Admin) | IBP/iWork | Milestone 5 | ✓ Found in tracker
Wellness HR View | HR View of Wellness usage by Employees | IBP | Milestone 5 | ✓ Found in tracker
Wellness Partner View | Partner/service provider view of the usage of their corresponding services | IBP | Milestone 5 | ✓ Found in tracker
Claims Corner | View Claim Data for Individual Plans (if available), Track Status for Claims initiated from IBP for Group Plans, Track Status for Claims initiated with TPA directly, TAT reporting for Cashless (for Preauth and Discharge) | IBP | Milestone 5 | ✓ Found in tracker
Initiate Claim | Initiate claim for GMC (non-cashless), upload docs etc. | IBP | Milestone 5 | ✓ Found in tracker
Profile Migration | Request migration of Corporate Profile to Individual | IBP | Milestone 5 | ✓ Found in tracker
Profile Migration | Request migration of Individual Profile to Corporate | IBP | Milestone 5 | ✓ Found in tracker
Book Ambulance | Floater on the screen - Integrate to Ambulance Service | IBP | Milestone 5 | ✓ Found in tracker
Chat Interface | Floater on the screen - Integrate with AI Component and IWork support channel | IBP | Milestone 5 | ✓ Found in tracker
OPD Claims Process Mgmt | Claim initiation - some metadata and upload of documents | IBP | Milestone 5 | 🔗 Mapped (see note) | Map to line number 149 in Sheet-SOW, Feedbacks-Bug & CR_Items
2nd Opinion Claims Process Mgmt | Managing 2nd opinion - initiate with data and upload documents | IBP | Milestone 5 | 🔗 Mapped (see note) | Map to line number 149 in Sheet-SOW, Feedbacks-Bug & CR_Items
OPD & 2nd Opinon Claims Processing | A report or generated file to be sent through manual processing | IBP/iWork | Milestone 5 | 🔗 Mapped (see note) | Map to line number 149 in Sheet-SOW, Feedbacks-Bug & CR_Items
Landing Page Services | Benefits Summary View, Upcoming welness appointment, Policy renewals, Individual Plans Summary views | IBP | Milestone 5 | ✓ Found in tracker
Benefits Summary | End User's Summary View | IBP | Milestone 5 | ✓ Found in tracker
Hospital Network Mgmt | Based on the Insurer and TPA, network of hospitals needs to be presented in a consolidated view | IBP | Milestone 5 | ✓ Found in tracker
My Services Mgmt | Summary view of the services subscribed (Wellness) | IBP | Milestone 5 | 🔗 Mapped (see note) | Map to line number 168 in Sheet-SOW, Feedbacks-Bug & CR_Items
Feedback Mgmt | User Feedback capture service | IBP | Milestone 5 | ✓ Found in tracker
Claims Mgmt | Company Provided and Personal Policy based claim mgmt, Tracking status, Document Mgmt related to claims | IBP | Milestone 5 | ✓ Found in tracker
Online Pharmacy Integration | External Pharmacy integration(s), more than one pharmacy capability. SSO to the pharmacy. | IBP | Milestone 5 | ✓ Found in tracker
Individual Insurance Plan Mgmt | Support for multiple categories of plans. Configuration Mgmt for Infomration capture, Flow and Summaries. Add on configuration, Insurer configuration, Offer configuration, Post the request to Sales Channel (Iwork) 7 Policy Types to be taken care of | IBP | Milestone 5 | ✓ Found in tracker
Premium Range Calculator | Calculate insurance premium range. Calculate the IDV of various assets | IBP | Milestone 5 | ✓ Found in tracker
End User Portal Configurator | What set of features to be enabled or disabled, Offers, Benefits etc. More or less how portal should contain and visible to end user needs to be configured (per Corporate Configuration) | IBP | Milestone 5 | ✓ Found in tracker
Multiple 3rd Party Service Mgmt | Elderly Services, Dental Services etc. 3rd Party integrations. Multiple providers 3 such services are in scope at this stage {Redhealth, MyDental, AkinCare} | IBP | Milestone 5 | ✓ Found in tracker
Evexia Club Integration | Integration to Evexia | IBP | Milestone 5 | ✓ Found in tracker
Chat for End Users | Chat Module to interact with Chat Bot and Customer Support Representative | IBP | Milestone 5 | ✓ Found in tracker
3rd Party SSO | Props based SSO links to 3rd Parties | IBP | Milestone 5 | ✓ Found in tracker

## Helper (hidden)
Module | Phase | Status | Category | Bucket | ReqDate
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
iWork | Milestone 1 | Delivered | Delivered | Delivered | 2025-03-01
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
Framework | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | Delivered | Delivered | Delivered | 2025-04-16
iWork | Milestone 2 | QA - WIP | In QA | Pending | 2025-04-16
Framework | Milestone 3 | Delivered | Delivered | Delivered | 2025-05-16
iWork | Milestone 3 | Delivered | Delivered | Delivered | 2025-05-16
iWork | Milestone 3 | Delivered | Delivered | Delivered | 2025-05-16
iWork | Milestone 3 | Delivered | Delivered | Delivered | 2025-05-16
iWork | Milestone 3 | Delivered | Delivered | Delivered | 2025-05-16
iWork | Milestone 3 | Delivered | Delivered | Delivered | 2025-05-16
iWork | Milestone 3 | Delivered | Delivered | Delivered | 2025-05-16
iWork | Milestone 3 | Delivered | Delivered | Delivered | 2025-05-16
DPDP | Milestone 4 | Yet to start | Not Started | Pending | 2025-06-10
Framework | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
Framework | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
Framework | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
Framework | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
Framework | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 2025-06-10
Framework | Milestone 4 | Not in scope | Delivered | Delivered | 2025-06-10
Framework | Milestone 4 | Yet to start | Not Started | Pending | 2025-06-10
Framework | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 2025-06-10
Framework | Milestone 4 | Not in scope | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP | Milestone 4 | Pre-PROD | Pre-PROD / UAT | Pending | 2025-06-10
IBP | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP/iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
IBP/iWork | Milestone 4 | Yet to start | Not Started | Pending | 2025-06-10
iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
iWork | Milestone 4 | Delivered | Delivered | Delivered | 2025-06-10
iWork | Milestone 4 | Yet to start | Not Started | Pending | 2025-06-10
NFR | Milestone 4 | Delivered - Deficit | Partial Delivery | Pending | 2025-06-10
IBP/iWork | Milestone 4 | Dev - WIP | In Development | Pending | 2025-06-10
IBP/iWork | Milestone 4 | Dev - WIP | In Development | Pending | 2025-06-10
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
DPDP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
DPDP | Milestone 5 | Dev - Done | Dev Complete | Delivered | 2025-07-31
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
DPDP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
DPDP | Milestone 5 | QA - WIP | In QA | Pending | 2025-07-31
DPDP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
DPDP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
DPDP | Milestone 5 | Pre-PROD | Pre-PROD / UAT | Pending | 2025-07-31
IBP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
IBP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
IBP/iWork | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
IBP | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 2025-07-31
IBP | Milestone 5 | Not in scope | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Not in scope | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP/iWork | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
IBP/iWork | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
IBP/iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
iWork | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
iWork | Milestone 5 | Delivered - Deficit | Partial Delivery | Pending | 2025-07-31
iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
iWork | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
iWork | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
iWork | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
iWork | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
NFR | Milestone 5 | Dev - WIP | In Development | Pending | 2025-07-31
NFR | Milestone 5 | Delivered | Delivered | Delivered | 2025-07-31
NFR | Milestone 5 | Yet to start | Not Started | Pending | 2025-07-31
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-02-17
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-04-07
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-04-21
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-01
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-01
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-01
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-05-01
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-01
IBP - CR | Milestone 6 | Pre-PROD | Pre-PROD / UAT | Pending | 2026-05-08
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-08
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-05-08
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-21
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-25
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-25
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-05-28
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-01
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-03
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-05
iWork - CR | Milestone 6 | DEV - WIP | In Development | Pending | 2026-06-05
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-06
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Not a bug | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | Not a bug | Delivered | Delivered | 2026-06-08
iWork | Milestone 6 | QA - WIP | In QA | Pending | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-09
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-10
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-10
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-11
IBP/iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-11
IBP/iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-15
iWork | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-15
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-15
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-15
iWork | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-15
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-15
iWork | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-15
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-18
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-19
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-19
IBP | Milestone 6 | Dev - WIP | In Development | Pending | 2026-06-21
IBP | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-21
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-22
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-22
IBP/iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Dev - WIP | In Development | Pending | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-06-23
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-23
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-25
iWork | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-25
iWork | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-25
iWork | Milestone 6 | Dev - WIP | In Development | Pending | 2026-06-25
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-06-25
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-01
IBP/iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-01
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-07-01
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
IBP - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-03
IBP/iWork - CR | Milestone 6 | Dev - WIP | In Development | Pending | 2026-07-04
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-06
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-06
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-07
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-07
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-08
IBP/iWork | Milestone 6 | Dev - WIP | In Development | Pending | 2026-07-09
IBP - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-10
IBP | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-11
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Not in scope | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-13
IBP/iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-07-14
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-14
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-17
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 2026-07-17
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-20
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-20
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-20
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-20
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-20
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-20
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-20
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-21
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-21
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-22
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-23
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-23
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-23
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-23
iWork | Milestone 6 | Delivered | Delivered | Delivered | 2026-07-23

## Config (hidden)
Status_Raw | Category | Bucket
Delivered | Delivered | Delivered
Dev - Done | Dev Complete | Delivered
Dev - WIP | In Development | Pending
QA - WIP | In QA | Pending
Pre-PROD | Pre-PROD / UAT | Pending
Yet to start | Not Started | Pending
Delivered - Deficit | Partial Delivery | Pending
Duplicate | N/A | N/A
Not a bug | Delivered | Delivered
Not in scope | Delivered | Delivered