## VRK Feedbacks
VRK — PROD FEEDBACK TRACKER · 67 items · 61 delivered · 6 pending
All 'VRK - PROD Feedback:' items, broken up by week (status then ETA within a week). Excluded from the other views. Static snapshot.
# | Module | Feature | Functionality | Status | Milestone | Requested | ETA | Resource | Remarks
📅 WEEK OF 08 Jun → 14 Jun 2026 · PAST · 27 items
1 | iWork | VRK - PROD Feedback: 5-Jun-2026 | Manage SO - Update the date filters to "SO Expiry Date" | Delivered | Milestone 6 | 05-Jun-2026 | 08-Jun-2026
2 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Critical: SO expiry logic and date validation should allow within 365 days at the time so creation. | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
3 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dashboard - Save View button to be moved to Run button --> Move the Save View button beside Reset | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
4 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Dont display CD management in menu link - move under Admin | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
5 | iWork | VRK - PROD Feedback: 8-Jun-2026 | filter out support services from the dashboard | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
6 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - hide Overall conversion values | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
7 | iWork | VRK - PROD Feedback: 8-Jun-2026 | In My RO, "BD planning" title should change to "Renewal Planning" for RO | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
8 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Manage TPA/BRoker/Insurer should be moved to Admin Module | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
9 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My Follow Up - hide "All" option - RO should be default | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
10 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - change to "Renewal Schedule by SBU" and move under renewal funnel | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
11 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Ribbon level reports link should be hidden --> Hide "Reports" on the header menu. And also move the "Utilization report" to Admin Module. | Delivered | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
12 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - Period (Company created) change to - Period (policies created) --- Show the same filters of Manage Policy | Delivered | Milestone 6 | 08-Jun-2026 | 09-Jun-2026 | Karan
13 | iWork | VRK - PROD Feedback: 8-Jun-2026 | isg roles: manage quotes screen should display the opportunities which are related to ISG only. | Delivered | Milestone 6 | 08-Jun-2026 | 09-Jun-2026
14 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BD/ISG planning dates should be empty and mandatory - should be mandatory to start the journey. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026
15 | iWork | VRK - PROD Feedback: 9-Jun-2026 | In "Manage Quotes"/"Manage SO" page, a link should be provided on the activity name, it should get redirected to respective activity stage. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
16 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Issue in Bizdone search results - Company name not visible | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
17 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10588 | Rename "My SO" to "Manage SO" in the sales portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
18 | iWork | VRK - PROD Feedback: 9-Jun-2026 | SO creation process: SO Expiry field title should be changed to "Opportunity/Existing Policy Expiry" - label to be changed. Nithin --> Also, change in SO details page as well | Delivered | Milestone 6 | 09-Jun-2026 | 09-Jun-2026 | Pushyami
19 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My RO clicked should not get highlighted to My SO menu link. | Delivered | Milestone 6 | 08-Jun-2026 | 10-Jun-2026
20 | iWork | VRK - PROD Feedback: 9-Jun-2026 | My followup section in the dashboard - should display default Activity names and show the values even there are zeros for each activity. | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Prathiphala
21 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if placement slip is not crossed, instantly mark the opportunity as "Lost" based on Opty. Expiry date | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Jagadeesh
22 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Opportunity lost logic:- if the activity crossed "Placement Slip", premium calculation and crossed 5 days, then mark the opportunity as "Lost" based on Opty. expiry date+5 days | Delivered | Milestone 6 | 09-Jun-2026 | 10-Jun-2026 | Jagadeesh
23 | iWork | VRK - PROD Feedback: 8-Jun-2026 IIRM-10589 | My client portfolio - list of all companies for Active policies only | Delivered | Milestone 6 | 08-Jun-2026 | 12-Jun-2026 | Karan
24 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Expiry Timeline by SBU - when clicked, redirect to RO screen with the counts. | Delivered | Milestone 6 | 08-Jun-2026 | 12-Jun-2026
25 | iWork | VRK - PROD Feedback: 9-Jun-2026 | BDR results list should display the link of policy ID and Opty ID. | Delivered | Milestone 6 | 09-Jun-2026 | 12-Jun-2026 | Prathiphala
26 | iWork | VRK - PROD Feedback: 8-Jun-2026 | My client portfolio: List of Companies should be displayed for which there are active RO's. The premium and brokerage should be displayed as per RO cards. --> Que: Yesterday it was asked to get the data related to Active Policies???? | Not a bug | Milestone 6 | 08-Jun-2026 | 08-Jun-2026 |  | 10-Jun: As per Surya/Kapil Sir. It's Active Policies only
27 | iWork | VRK - PROD Feedback: 8-Jun-2026 | my followup should be added into my actionalables with default display instead of "All" tab. | Not a bug | Milestone 6 | 08-Jun-2026 | 08-Jun-2026
📅 WEEK OF 15 Jun → 21 Jun 2026 · PAST · 8 items
28 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | All SO and RO items should be displayed order by Expiry Date (ascending) in the same page once "Manage Quotes" is clicked by the user. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
29 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | ISG users should be able to view ISG activities only and BD related activities should be collapsable and hidden; accordingly manage the breadcrums. Similarly, vice versa for BD users. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
30 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Manage Quote RO and Manager Quote SO should be clubbed to "Manage Quotes" link for ISG team only. --> 10-Jun: Surya -> Show the data only when opty. is in ISG Activity. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
31 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | My client portfolio: There must be a provision of "Past company" view in the Client Portfolio. | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026
32 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Nithin -> Add the filters required to handle both SO & RO in "Manage Quotes" | Delivered | Milestone 6 | 09-Jun-2026 | 15-Jun-2026 | Karan
33 | iWork | VRK - PROD Feedback: 9-Jun-2026 IIRM-10589 | Hide "My RO" from the Sales portfolio. Add in the "My Client Portfolio" | Delivered | Milestone 6 | 09-Jun-2026 | 16-Jun-2026
34 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Commercial lines 25-26 numbers should be rectified; it should be 24.99 | Delivered | Milestone 6 | 08-Jun-2026 | 19-Jun-2026 | Rama
35 | iWork | VRK - PROD Feedback: 9-Jun-2026 | All Stage/Activity-wise wherever Document upload option is there, should be a mandatory | Delivered | Milestone 6 | 09-Jun-2026 | 19-Jun-2026 | Karan
📅 WEEK OF 22 Jun → 28 Jun 2026 · PAST · 1 item
36 | iWork | VRK - PROD Feedback: 8-Jun-2026 | funnels - alignment graph issues with grid; | Delivered | Milestone 6 | 08-Jun-2026 | 24-Jun-2026
📅 WEEK OF 29 Jun → 05 Jul 2026 · PAST · 8 items
37 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Policy Hard copy receipt stage - When User uploads the Policy copy, system should capture the policy level elements like Ins Pol No., Dates, Premium amounts, etc and validate with the policy record saved. - Need discussion for more details to use the deviation and approval process to modify the values as per deviation from Policy Hard copy. | Delivered | Milestone 6 | 08-Jun-2026 | 30-Jun-2026 | Jagadeesh
38 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Ribbon level: Reports should include Poppins & Bizdone report | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
39 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Hide "Reports" from Left Menu | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
40 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Remove "±5 days of expiry" | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
41 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - SO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
42 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - RO - Add SBU schedule & My Follow-ups | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
43 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Business Performance - Update to stacked bar | Delivered | Milestone 6 | 23-Jun-2026 | 01-Jul-2026 | Pushyami
44 | iWork | VRK - PROD Feedback: 8-Jun-2026 | Filter stickyness is not working for Bizdone and check with all the other screens. (Filters Persistence in all the screens) | Delivered | Milestone 6 | 08-Jun-2026 | 02-Jul-2026
📅 WEEK OF 06 Jul → 12 Jul 2026 · PAST · 3 items
45 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | My RO - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 07-Jul-2026 | Pushyami
46 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Manage SO - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Pushyami
47 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | BizDone - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 08-Jul-2026 | Pushyami
📅 WEEK OF 13 Jul → 19 Jul 2026 · LAST WEEK · 13 items
48 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Remove the Vertical section. Keep only Branch. | Delivered | Milestone 6 | 13-Jul-2026 | 13-Jul-2026
49 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | My Client Portfolio - SBU, Vertical, Branch break-down with details | Delivered | Milestone 6 | 23-Jun-2026 | 14-Jul-2026 | Karan
50 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Dashboard - Filter & drill-down | Delivered | Milestone 6 | 23-Jun-2026 | 14-Jul-2026 | Karan
51 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Remove the SO/RO labels from the bar charts. Display only the figures inside the bars, with the corresponding details available on mouse hover (tooltip). | Delivered | Milestone 6 | 13-Jul-2026 | 14-Jul-2026
52 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Review and correct the display of negative values for TeamLease under RO, particularly for Q3 bar-chart. | Delivered | Milestone 6 | 13-Jul-2026 | 14-Jul-2026
53 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Brokerage Display - Display Brokerage information only. Hide Premium values in the enhanced screens. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
54 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | BizDone Enhanced Screen - Hide Premium. Display: RO Brokerage SO Brokerage | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
55 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Resolve the Premium value formatting issue. Values should be displayed consistently in Millions/Billions. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
56 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Display the Endorsement section above the section “Business Collection Summary”. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
57 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Move the Policy Type Distribution section above RO by SBU. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
58 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard UI & Visualization - Rename/update the Policy Type names “Fire & Engineering”, “Speciality Lines - Liability” | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
59 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - The SO Activity Follow-up screen should not display ISG-related activities. | Delivered | Milestone 6 | 13-Jul-2026 | 15-Jul-2026
60 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - When IIRM Holdings is selected, the Organization-level cards and graphs are not displayed. Verify and fix the issue. | Delivered | Milestone 6 | 13-Jul-2026 | 17-Jul-2026
📍 WEEK OF 20 Jul → 26 Jul 2026 · CURRENT WEEK · 6 items
61 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Functional Changes - Make the Funnel interactive so that clicking on each stage navigates to the corresponding enhanced screen. | Yet to start | Milestone 6 | 13-Jul-2026 | 24-Jul-2026 |  | Pending: Becuase the enhanced screens are yet to Approve
62 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Organization-wise summary cards are not required. | Yet to start | Milestone 6 | 13-Jul-2026 | 24-Jul-2026
63 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Dashboard Issues - Under PL, the bar chart should represent SO-level data instead of the currently displayed RO-level data. Update in the data to make SO | Yet to start | Milestone 6 | 13-Jul-2026 | 24-Jul-2026
64 | iWork | VRK - PROD Feedback: 9-Jun-2026 | Dual approval mechanism - current logic and recommendation to enable as per the current CRM hierarchy | Yet to start | Milestone 6 | 09-Jun-2026 | 24-Jul-2026 | Jagadeesh
65 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | Additional section display: Placement Funnel, Schedule, Followup (ISG Funnel) | Yet to start | Milestone 6 | 23-Jun-2026 | 24-Jul-2026 | Pushyami
66 | iWork - CR | VRK - PROD Feedback: 13-Jul-2026 | Enhanced Screens: Layout Changes - Display the data using an Accordion layout in the following order: Company → SBU → Branch → Executive → Client → Policy | Delivered | Milestone 6 | 13-Jul-2026 | 20-Jul-2026 |  | Nithin to check the Manager+Team logic and get abck
🗓 No ETA assigned · 1 item
67 | iWork - CR | VRK - PROD Feedback: 23-Jun-2026 | iWork and iTicket should be accessible via VPN | Yet to start | Milestone 6 | 23-Jun-2026 |  | Pushyami

## Helper (hidden)
Module | Phase | Status | Category | Bucket | ReqDate
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!
#REF! | #REF! | #REF! | Unknown | N/A | #REF!

## Config (hidden)
Status_Raw | Category | Bucket
Delivered | Delivered | Delivered
Dev - Done | Dev Complete | Delivered
Dev - WIP | In Development | Pending
QA - WIP | In QA | Pending
Pre-PROD | Pre-PROD / UAT | Pending
Yet to start | Not Started | Pending
Delivered - Deficit | Partial Delivery | Pending
Duplicate | N/A | N/A
Not a bug | Delivered | Delivered