## Stabilization - Items
Area | Feature | Functionality | Module | Phase | Status | Remarks | Requested Date | ETA | Priority | Start Date | End Date | Resource | Jira ID
Stablization | Business Critical | PROD Bug: Dashboard vs RO page - When login user applied the same filters in Dashboard and the same in RO then counts are NO matching - Example Milind in email | iWork | Milestone 6 | DEV - WIP |  | 2026-08-06 | 2026-08-06 | High |  |  | Karan
Stablization | Orphan Records | Orphan - Companies - Identifying the records, Validate & Delete | iWork | Milestone 6 | Yet to start |  | 2026-08-06 | 2026-08-11 | High | 2026-08-07 | 2026-08-11 | Gopal / Rama
Stablization | Orphan Records | Orphan - Oppotunities - Identifying the records, Validate & Delete | iWork | Milestone 6 | Yet to start |  | 2026-08-06 | 2026-08-11 | High | 2026-08-07 | 2026-08-11 | Gopal / Rama
Stablization | Orphan Records | Orphan - Policies - Identifying the records, Validate & Delete | iWork | Milestone 6 | Yet to start |  | 2026-08-06 | 2026-08-11 | High | 2026-08-07 | 2026-08-11 | Gopal / Rama
Stablization | Business Critical | Migration Data load should be always complete only after manual Performances Job Execution - Continous acitivity | iWork | Milestone 6 | DEV - WIP | Anytime, manual load or adjustments are done, performance job needs to be executed for entire period | 2026-08-01 | 2026-08-03 | High | 2026-08-03 | 2026-08-03 | Rama
Stablization | Business Critical | Dashboard: Having individual component loaders on the landing page for each component and web-socket framework to avoid long-loading blank page issue. | iWork | Milestone 6 | Dev - Done |  | 2026-08-01 | 2026-08-04 | High | 2026-08-03 | 2026-08-04 | Manjusha
Stablization | Business Critical | BizDone & Dashboard: Filters Persistance | iWork | Milestone 6 | Delivered |  | 2026-08-01 | 2026-08-04 | High | 2026-08-04 | 2026-08-04 | Sunil
Stablization | Business Critical | BizDone - Download - User select the desired sheet | iWork - CR | Milestone 6 | Delivered |  | 2026-08-01 | 2026-08-04 | High | 2026-08-04 | 2026-08-04 | Karan
Stablization | Business Critical | BizDone - Download - Indian template along with Localization fields | iWork | Milestone 6 | UAT - WIP |  | 2026-08-01 | 2026-08-04 | High | 2026-08-04 | 2026-08-04 | Leela
Stablization | Business Critical | BizDone - Download - Performance (Offload Excel Generation) - API, Queue, Store in S3 & Download | iWork | Milestone 6 | Delivered |  | 2026-08-01 | 2026-08-05 | High | 2026-08-03 | 2026-08-05 | Karan
Stablization | Business Critical | BizDone - Applied filters in the Downloaded file in Sheet-1 | iWork | Milestone 6 | Delivered |  | 2026-08-01 | 2026-08-05 | High | 2026-08-04 | 2026-08-05 | Sunil
Stablization | Business Critical | IBP - Risk Watch - Report Issues - Enrolment Drive - Validate, enhance, and document | IBP | Milestone 6 | Dev - Done |  | 2026-08-01 | 2026-08-05 | High | 2026-08-04 | 2026-08-05 | Ravikiran |  | PR is ready, Waiting for nithin to verify
Stablization | Business Critical | The owner selection process remains highly user-unfriendly, with a very small expand ('>') button, incomplete visibility of names, and insufficient hierarchy indentation. | iWork | Milestone 6 | DEV - WIP |  | 2026-07-18 | 2026-08-06 | High | 2026-08-04 | 2026-08-06 | Raju
Stablization | Business Critical | BizDone - Old & Enhance Screens - For now both will be live(Metrics) | iWork | Milestone 6 | Dev - WIP |  | 2026-08-01 | 2026-08-06 | High | 2026-08-05 | 2026-08-06 | Karan | Leela
Stablization | Business Critical | Dashboard & BizDone: Centralised code or utility to fetch the KPIs data for re-usability | iWork | Milestone 6 | Dev - WIP |  | 2026-08-01 | 2026-08-06 | High | 2026-08-05 | 2026-08-06 | Sunil
Stablization | Business Critical | Dashboard: Implementation of the dynamic fetching of widgets data without depending on performance output cron job | iWork | Milestone 6 | UAT - WIP |  | 2026-08-01 | 2026-08-03 | High | 2026-08-06 | 2026-08-06 | Jagadeesh
Stablization | Business Critical | BizDone & Dashboard - Consider Fee & Rewards as "Brokerage" | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-07 | High | 2026-08-06 | 2026-08-07 | Sunil
Stablization | Business Critical | BizDone - Screen & Download data is not consistent | iWork | Milestone 6 | Dev - WIP |  | 2026-07-18 | 2026-08-07 | High | 2026-08-06 | 2026-08-07 | Karan | leela
Stablization | Business Critical | IBP - Risk Watch - Company & Policy Levels are not matching (CD, Endorsement, Claims) | IBP | Milestone 6 | Dev - Done |  | 2026-08-01 | 2026-08-07 | High | 2026-08-06 | 2026-08-07 | Ravikiran
Stablization | Business Critical | BizDone - Performance - Query Fine Tuning | iWork | Milestone 6 | Dev - WIP |  | 2026-08-01 | 2026-08-10 | High | 2026-08-10 | 2026-08-10 | Karan
Stablization | Business Critical | BizDone & other filters - Multi-select for Vertical & Branch | iWork | Milestone 6 | Dev - WIP |  | 2026-07-18 | 2026-08-11 | High | 2026-08-10 | 2026-08-11 | Sunil
Stablization | Business Critical | Dashboard - Performance - Query Fine Tuning | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-12 | High | 2026-08-12 | 2026-08-12 | Sunil
Stablization | Business Critical | BizDone - Download - Reduce the file size (Ex. Excel binary or others) | iWork - CR | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-12 | High | 2026-08-12 | 2026-08-12 | Karan
Stablization | Business Critical | IBP - Email Notification - Company specific email templates for all types (Welcome, Confirmation, Reminder, Raise Ticket, & Others) | iWork/IBP | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Business Critical | Computed value & Reported values * Computed values - It’s the real-time values base on Policy inception/endorsement * Reported values - It’s validated by the mgmt. and share this number to update in the column. * Reported value MUST be used for the Dashboard & BizDone, which was declared by the company to public. * In the admin a feature to update the Reported values from the computed values * Legacy data - Premiums, Brokerage, CD Balance | iWork - CR | Milestone 6 | Yet to start |  | 2026-06-25 | 2026-08-07 | Medium
Stablization | Maintenance | Convert Policy from Active to Generated | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Maintenance | Delete - Policy Configuration | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium
Stablization | Maintenance | iWork - Reports - View Dump for each download for comparision | iWork | Milestone 6 | Yet to start |  | 2026-04-20 |  | Medium |  |  | Gopal
Stablization | Maintenance | PROD: Health Check of the Application, Alert notification & Triage the situation | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Maintenance | Delete - Inception/Endorsement Data | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Maintenance | Employee Mgmt - Create, Update, Delete - Validate and document | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Maintenance | Hierarchy Mgmt - View & Update - Report & Visual Chart | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Maintenance | In any of the screen, we have to provide an info icon where it will help the users how critical fields in that screen are derieved or got populated | iWork | Milestone 6 | Yet to start |  | 2026-07-17 |  | Low
Stablization | Maintenance | IBP - Go-Live: Check-list document & SOP | iWork/IBP | Milestone 6 | Yet to start |  | 2026-04-20 |  | Low |  |  | Nithin
Stablization | Maintenance | iWork - Reports - Use BizDone framework | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Job - Dashboard - Review, Enhance and document | iWork | Milestone 6 | Delivered | Flag based development / remove job post approval | 2026-08-01 | 2026-08-06 | High | 2026-08-04 | 2026-08-05 | Sunil
Stablization | Operational | Personal Lines Data Integration (DSR and iWork) | iWork | Milestone 6 | Dev - Done |  | 2026-07-25 | 2026-08-05 | High | 2026-08-04 | 2026-08-05 | Junaid
Stablization | Operational | Demo Env. - Stop all the Job; Make sure emails & SMS are working as expected | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-06 | High | 2026-08-05 | 2026-08-06 | Tharun
Stablization | Operational | PROD & Other env.: Database Vaccum - Schedule a periodic acitvity in all the env. | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-07 | High | 2026-08-06 | 2026-08-07 | Abhilash
Stablization | Operational | Demo Env. - Record the application/Infrastruction/DevOps situation when application is in Zero state | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-11 | High | 2026-08-10 | 2026-08-11 | Tharun / Jagadeesh
Stablization | Operational | PROD & Demo Env.: Database - Partitioning | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-11 | High | 2026-08-10 | 2026-08-11 | Abhilash
Stablization | Operational | Notification Mgmt - Turn on, Turn off, History, Approval, template changes | iWork/IBP | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-11 | High | 2026-08-11 | 2026-08-11 | Karan
Stablization | Operational | Job - Expiry Opportunity - Review, Enhance and document | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-12 | High | 2026-08-12 | 2026-08-12 | Karan
Stablization | Operational | PROD & Demo Env.: Database - Indexing | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-13 | High | 2026-08-12 | 2026-08-13 | Abhilash
Stablization | Operational | Job - RO Creation - Review, Enhance and document | iWork | Milestone 6 | Yet to start | 6-Aug: Surya sir want to discuss thing | 2026-08-01 | 2026-08-13 | High | 2026-08-13 | 2026-08-13 | Karan
Stablization | Operational | PROD & Demo Env.: Database - SQL Functions for all the reports | iWork | Milestone 6 | Yet to start |  | 2026-08-01 | 2026-08-14 | High | 2026-08-14 | 2026-08-14 | Abhilash
Stablization | Operational | PROD Bug: SES - Notifications - Check what is the configuration. (Scenario: For the very first time Email or SMS is taking time then rest are instant) | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Infra - Season based bumping (Example: When policies are expiring, need to bump the infra/DB because load will be more). Identify the data and plan this acitivity. | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Optimal allocate the memory/infra size based on the service operational usage rather than generic size for all | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Split Service - Risk Watch because it should run on it own and NOT impact other iWork or IBP services | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Split Service - Identify service areas because either iWork or IBP utilization should not impact other services | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Reports - iWork - Validate, enhance, and document | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Policy Config - Premium Rater Table | iWork - CR | Milestone 6 | Yet to start |  | 2026-04-21 |  | Low |  |  | Jagadeesh
Stablization | Operational | CMS - Policy Level - Component Notes from Strapi | iWork | Milestone 6 | Yet to start | Ex. TL - Parental 2-years Lock-in; SI may vary | 2026-07-31 |  | Low
Stablization | Operational | Automation process for Data Load (Gopal & Rama's Task) | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Medium |  |  | Rama
Stablization | Operational | Export to excel - iWork all the results table; Download is on Previlage | iWork | Milestone 6 | Yet to start |  | 2026-06-15 |  | High
Stablization | Operational | Export - IBP-Risk Watch - All the results/Widget must be downloadable based onn Previlage | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Email Notifications - Policy Renewals - CRM users & Insurer Contact | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | High
Stablization | Operational | Email Notifications - Opty. Lost/ Policy Renewals/ Instalments - CRM users | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low
Stablization | Operational | Add/Update - Address & Contact - Across Application | iWork | Milestone 6 | Yet to start |  | 2026-08-01 |  | Low

## Stabilization - Summary
STABILIZATION — STATUS OVERVIEW
Stabilization Area ¦ Break-up by Feature · As of 07-Aug-2026
OVERALL COMPLETION | [6 empty] | REMAINING WORK
15% |  |  | 9 of 60 Stabilization items delivered |  |  |  | 51 |  | Stabilization items still to deliver, broken up by Feature below
STATUS BREAKDOWN (Stabilization items)
5 |  |  | 4 |  |  | 8 |  |  | 0
Delivered |  |  | Dev Complete |  |  | In Development |  |  | In QA
2 |  |  | 41 |  |  | 0 |  |  | 0
Pre-PROD / UAT |  |  | Not Started |  |  | Partial Delivery |  |  | N/A
BREAKDOWN BY FEATURE
Feature | Total | Delivered | Pending | N/A | % Complete | Progress
Business Critical | 22 | 7 | 15 | 0 | 31.82% | 31.82%
Maintenance | 10 | 0 | 10 | 0 | 0% | 0%
Operational | 25 | 2 | 23 | 0 | 8% | 8%
Orphan Records | 3 | 0 | 3 | 0 | 0% | 0%
TOTAL | 60 | 9 | 51 | 0 | 15% | 15%
Scope: rows where Area = 'Stablization' in the source sheet. % Complete = Delivered ÷ (Delivered + Pending). N/A items excluded. Counts update live from the source sheet; re-run the script only if a new Feature value is added under this Area (to add its row here).
PRIORITY vs STATUS
Priority | Delivered | Dev Complete | In Development | In QA | Pre-PROD / UAT | Not Started | Partial Delivery | N/A | Unknown | TOTAL
High | 5 | 4 | 8 | 0 | 2 | 17 | 0 | 0 | 0 | 36
Medium | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6
Low | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 18
TOTAL | 5 | 4 | 8 | 0 | 2 | 41 | 0 | 0 | 0 | 60
Scope: rows where Area = 'Stablization', grouped by the 'Priority' column. Counts update live from the source sheet; re-run the script only if a new Priority value is used (to add its row here).
DAILY PROGRESS — toward the 14-Aug-2026 deadline
Date | Total | Planned Delivered | Delivered | Planned Pending | Pending | Delivered Today | % Complete | Ahead/Behind Plan | Days Left | Req. Pace/day
2026-08-07 | 35 | 21 | 9 | 14 | 26 | — | 25.71% | -12 | 7 | 3.7
2026-08-08 | — | 21 | — | 14 | — | — | — | — | 6 | —
2026-08-09 | — | 21 | — | 14 | — | — | — | — | 5 | —
2026-08-10 | — | 22 | — | 13 | — | — | — | — | 4 | —
2026-08-11 | — | 29 | — | 6 | — | — | — | — | 3 | —
2026-08-12 | — | 32 | — | 3 | — | — | — | — | 2 | —
2026-08-13 | — | 34 | — | 1 | — | — | — | — | 1 | —
2026-08-14 | — | 35 | — | 0 | — | — | — | — | 0 | —
Unplanned (no ETA / ETA beyond 14-Aug) |  | 25
Scope: only the 35 Stablization items with an ETA on or before 14-Aug-2026 — that's the actual plan for this deadline. Planned Delivered/Pending = cumulative count of those items due on or before that day, from their real ETA dates (not a smoothed ramp); recomputed every run, so it shifts if ETAs or the item set change. Ahead/Behind Plan = Delivered − Planned Delivered for that day. The 25 item(s) with no ETA (or an ETA after 14-Aug) are listed above, not counted toward this deadline.

## Helper (hidden)
Module | Phase | Status | Category | Bucket | ReqDate
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46240
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46240
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46240
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46240
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46235
iWork | Milestone 6 | Dev - Done | Dev Complete | Delivered | 46235
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46235
iWork - CR | Milestone 6 | Delivered | Delivered | Delivered | 46235
iWork | Milestone 6 | UAT - WIP | Pre-PROD / UAT | Pending | 46235
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46235
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46235
IBP | Milestone 6 | Dev - Done | Dev Complete | Delivered | 46235
iWork | Milestone 6 | DEV - WIP | In Development | Pending | 46221
iWork | Milestone 6 | Dev - WIP | In Development | Pending | 46235
iWork | Milestone 6 | Dev - WIP | In Development | Pending | 46235
iWork | Milestone 6 | UAT - WIP | Pre-PROD / UAT | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Dev - WIP | In Development | Pending | 46221
IBP | Milestone 6 | Dev - Done | Dev Complete | Delivered | 46235
iWork | Milestone 6 | Dev - WIP | In Development | Pending | 46235
iWork | Milestone 6 | Dev - WIP | In Development | Pending | 46221
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork/IBP | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46198
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46132
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46220
iWork/IBP | Milestone 6 | Yet to start | Not Started | Pending | 46132
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Delivered | Delivered | Delivered | 46235
iWork | Milestone 6 | Dev - Done | Dev Complete | Delivered | 46228
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork/IBP | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork - CR | Milestone 6 | Yet to start | Not Started | Pending | 46133
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46234
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46188
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235
iWork | Milestone 6 | Yet to start | Not Started | Pending | 46235

## Config (hidden)
Status_Raw | Category | Bucket
Delivered | Delivered | Delivered
Dev - Done | Dev Complete | Delivered
DEV - Done | Dev Complete | Delivered
Dev - WIP | In Development | Pending
DEV - WIP | In Development | Pending
QA - WIP | In QA | Pending
Pre-PROD | Pre-PROD / UAT | Pending
UAT - WIP | Pre-PROD / UAT | Pending
Yet to start | Not Started | Pending
Delivered - Deficit | Partial Delivery | Pending
Duplicate | N/A | N/A
Not a bug | Delivered | Delivered
Not in scope | Delivered | Delivered