## DPDP_Rule_Summary
Rule Ref | Rule Title | Applicable? | Applicability Notes
Section 1 | Short title, extent, commencement | YES | Applies by default to all organizations operating in India. No action required but legally binding.
Section 2 | Definitions | YES | Defines terms like Data Principal, Data Fiduciary, processing, consent etc. Applies automatically.
Section 3 | Obligations of Data Fiduciary | YES | Core obligations such as notice, consent, purpose limitation, accuracy, minimization—mandatory for all companies.
Section 4 | Consent Managers | NO | Not applicable as the company is not a registered Consent Manager under MeitY.
Section 5 | Govt benefit processing | NO | Not applicable because the company does not provide government subsidies, welfare, or public services.
Section 6 | Security safeguards | YES | Mandatory security safeguards including encryption, access control, logging, DR, and vendor security.
Section 7 | Data breach notification | YES | Mandatory 72‑hour breach notification requirement for all organizations.
Section 8 | Data retention & erasure | YES | Mandatory rule requiring deletion of personal data once purpose ends; retention justification required.
Section 9 | Grievance redressal / DPO contact | YES | Must publish grievance redressal contact / DPO contact for Data Principals.
Section 10 | Children’s data processing | NO | Not applicable—company does not process personal data of children under 18.
Section 11 | Guardian consent (disability) | NO | Not applicable—company does not process data of persons requiring guardian consent.
Section 12 | Child data exemptions | NO | Not applicable—company not engaged in child education/health/transport services.
Section 13 | Significant Data Fiduciary obligations | CONDITIONAL | Applicable only if designated as Significant Data Fiduciary (SDF) by Government.
Section 14 | Data Principal Rights | YES | Must allow access, correction, erasure, grievance redressal—mandatory.
Section 15 | Cross-border data transfer | YES | Mandatory transparency for any cross‑border data transfer (AWS/Azure foreign regions used).
Section 16 | Exemptions | NO | Not applicable—company does not fall under research or government exemptions.
Section 17 | DPB establishment | NO | DPB administrative section—no action required.
Section 18 | DPB inquiry powers | NO | DPB inquiry powers—no action required unless under investigation.
Section 19 | Penalties | NO | Penalty structure—applies only if non‑compliant.
Section 20 | Appeal to TDSAT | NO | Appeal process—applies only in case of penalty dispute.
Section 21 | Voluntary undertaking | NO | Voluntary undertaking—applicable only if company makes a legal commitment to DPB.
Section 22 | Rule-making powers | NO | Government rule‑making powers—informational only.
Section 23 | Notification of Rules | NO | Government notification powers—informational only.
Rule 3 | Privacy Notice Requirements | YES | Mandatory privacy notice requirements—must specify data collected, purpose, grievance, retention.
Rule 4 | Consent Manager rules | NO | Not applicable—company is not a Consent Manager.
Rule 5 | Govt welfare processing | NO | Not applicable—company does not provide government welfare services.
Rule 6(a) | Encryption at rest | YES | Mandatory encryption at rest—servers, endpoints, backups must be encrypted.
Rule 6(b) | Access control | YES | Mandatory access control—least privilege, MFA, RBAC required.
Rule 6(c) | Logging | YES | Mandatory logging of access, errors, and security events.
Rule 6(d) | Backup/DR | YES | Mandatory backup and disaster recovery controls with restore testing.
Rule 6(e) | Log retention (1 year) | YES | Mandatory 1‑year log retention for accountability.
Rule 6(f) | Vendor/processor controls | YES | Vendor contractual obligations—must include DPDP clauses.
Rule 6(g) | Additional security safeguards | YES | Catch‑all rule—any additional technical/organizational security controls needed.
Rule 7 | Breach notification | YES | Must report breaches to Data Protection Board & affected users within 72 hours.
Rule 8 | Retention & deletion | YES | Mandates deletion, retention justification, and data lifecycle management.
Rule 9 | Publish contact / grievance | YES | Requires publishing valid contact/DPO information for Data Principals.
Rule 10 | Child data processing | NO | Not applicable—no children’s data processed.
Rule 11 | Guardian consent | NO | Not applicable—no guardian‑based consent scenarios.
Rule 12 | Child data exemption rules | NO | Not applicable—company not in child‑related services.
Rule 13(1) | SDF DPIA Requirement | CONDITIONAL | Applies only if designated SDF—annual DPIA required.
Rule 13(2) | SDF Annual Audit | CONDITIONAL | Applies only if SDF—annual independent data audit required.
Rule 13(3) | Algorithmic risk assessment | NO | Not applicable—no automated or algorithmic decision‑making systems.
Rule 13(4) | SDF cross-border restrictions | CONDITIONAL | Applies only if SDF—special cross‑border restrictions.
Rule 13(5) | DPO reporting to Board | CONDITIONAL | Applies only if SDF—DPO must report to Board.
Rule 14 | Rights Handling | YES | Mandatory handling of user rights (access, correction, deletion).
Rule 15 | Cross-border transfer compliance | YES | Mandatory international data transfer documentation and compliance.
Rules 16–23 | DPB administrative procedures | NO | DPB internal procedures—no implementation required unless under investigation.

## Infrastructure
Compliance Status | DPDP Requirement | Rule Ref | Infra Controls Needed / Existing | Where | Priority | Responsible | Comments | Final Deadline | Impacted services /device list | Business impact | Effort estimate (man-days) | Cost Estimate (On-time) | Cost Estimate (Annual) | Notes
| Encryption missing on endpoints | Rule 6(a) | Enable BitLocker/FileVault | Endpoints | High | IT Infra | Endpoints must be encrypted |  |  |  | 60-90 | 0 | 0 | BitLocker deployment + recovery key mgmt
| Server encryption missing | Rule 6(a) | Enable disk encryption | On-prem Servers | High | Infra/Server Team | Servers host PII |  |  |  | 30-60 | 0 | 0 | Enable Windows/Linux disk encryption - Also impact analysis on apps and backups
| VPN without MFA | Rule 6(b) | Enable MFA for VPN | Firewall/VPN | High | Network | Mandatory MFA |  |  |  | 8–10 | 0 | 150000 | FortiToken Mobile for 200 users
| RDP/SSH no MFA | Rule 6(b) | MFA on RDP/SSH | Servers | High | Infra | Critical access |  |  |  | 15-20 | 150000 | 0 | Jump server + MFA integration
| Legacy OS | Rule 6(g) | Upgrade OS | Servers | High | Infra | EOL OS |  |  |  | 30-60 | 900000 | 0 | Upgrade 15 windows servers
| Firewall logs <12 months | Rule 6(e) | Increase retention | Firewalls | High | Network | Need 12 months |  |  |  | 5–7 | 0 | 30000 | Expand retention on forti analyzer
| SIEM retention <12 months | Rule 6(e) | Expand storage | SIEM | High | Security | Need 1yr logs |  |  |  | 60-90 | 8,00,000 | 1050000 | 3-node OpenSearch + Wazuh cluster + Experienced SIEM Engineer
| Old RV042 routers | Rule 6(g) | Replace routers | Branches | High | Network | Outdated |  |  |  | 30-60 | 0 | 390000 | Rental 40E routers for 13 branches
| Zimbra no MFA | Rule 6(b) | Add MFA / Migrate | Email | High | IT/Security | No MFA |  |  |  | 20–30 | 0 | 310000 | Migrate 200 users to M365
| Redmail outdated | Rule 6(b) | Upgrade/replace | Email | High | IT | Legacy email |  |  |  | 20-30 | 0 | 0 | Internal mail migration to Zimbra
| No DR runbook | Rule 6(d) | Create DR runbook | Infra/DR | High | Infra | Required |  |  |  | 12–15 | 0 | 0 | Documentation only
| No DR environment | Rule 6(d) | Create DR infra | Infra | High | Leadership | Backup≠DR |  |  |  | - | 0 | 0 | Not in business scope (NA)
| No vendor DPDP agreements | Rule 6(f) | Sign contracts | Vendors | High | Legal/IT | Processor obligations |  |  |  | 10–12 | 0 | 0 | Vendor qualification + DPA
| No 72hr breach workflow | Rule 7 | Create SOP | Security | High | Security | Mandatory |  |  |  | 4–5 | 0 | 0 | Create breach handling SOP (Enhance incident management SOP)
| No endpoint baseline | Rule 6(g) | Implement CIS baseline | Endpoints | Medium | IT | Hardening needed |  |  |  | 120-180 | 0 | 0 | CIS Lite baseline scripting and bring all endpoints to same baseline
| Privileged access periodic only | Rule 6(c) | Continuous monitoring | Servers | Medium | Security | Admin logs missing |  |  |  | 8–10 | 0 | 0 | Enable sudo/admin logs in Wazuh
| Restore tests yearly only | Rule 6(d) | Quarterly tests | Backups | Medium | Infra | Increase frequency |  |  |  | 10 | 0 | 0 | Quarterly restore evidence
| No Conditional Access | Rule 6(b) | Implement CA | Azure AD | Medium | Identity | Stronger MFA |  |  |  | - | 0 | 0 | DPDP impact low; MFA sufficient
| No PAM | Rule 6(b) | Deploy PAM | Infra | Medium | Security | Privileged control |  |  |  | 12–18 | 150000 | 0 | Need to explore options
| Network segmentation | Rule 6(g) | VLAN segmentation | Network | Low | Network | Segregation active, DMZ to be implemeted | Achieved (Partial) |  |  | - | 0 | 0
| SIEM implemented | Rule 6(c) | Wazuh SIEM active | Logs | Medium | Security | Needs 12-month retention | Achieved (Partial) |  |  | - | 0 | 0
| Restore tests yearly | Rule 6(d) | Annual restore test | Backups | Medium | Infra | Needs quarterly | Achieved (Partial) |  |  | - | 0 | 0
| Endpoint MFA enabled | Rule 6(b) | Windows Hello MFA | Endpoints | Low | IT | MFA already enforced | Achieved |  |  |  | 0 | 0
| USB / Device Control implemented | Rule 6(g) | Device Control Active | Endpoints | Low | IT/Security | USB blocked | Achieved
| Local admin rights removed | Rule 6(b) | Privilege restrictions | Endpoints | Low | IT | Least privilege | Achieved
| SSL Inspection enabled | Rule 6(g) | Fortigate SSL inspection | Firewall | Low | Network | Traffic inspected | Achieved
| IPS/IDS enabled | Rule 6(g) | Fortigate IPS/IDS | Firewall | Low | Network | Threat detection | Achieved
| DKIM/DMARC/SPF configured | Rule 6(g) | Email security configured | Email | Low | IT/Security | Domain protection | Achieved
| Microsoft 365 MFA enabled | Rule 6(b) | MFA on cloud accounts | Identity | Low | IT | Compliant | Achieved
| Legacy Authentication blocked | Rule 6(b) | Legacy auth disabled | Identity | Low | IT | Enhanced protection | Achieved
| Admin roles reviewed | Rule 6(c) | Privileged logging | Identity | Low | Security | Meets requirement | Achieved
| Server room access control | Rule 6(g) | Controlled entry | Physical | Low | Admin/IT | Secure access | Achieved
| CCTV coverage | Rule 6(g) | CCTV active | Physical | Low | Admin | Compliant | Achieved
| UPS/Power backup | Rule 6(d) | UPS maintained | Physical | Low | Admin/IT | Redundancy | Achieved
| Secure hardware disposal | Rule 6(g) | Secure wipe/shredding | Physical | Low | IT | Compliant | Achieved
| Daily backups enabled | Rule 6(d) | Automated backups | Backups | Low | Infra | Backup successful | Achieved
| Backup encryption | Rule 6(a) | Encrypted backup sets | Backups | Low | Infra | Compliant | Achieved
| Offsite backups | Rule 6(d) | Cloud/offsite backup | Backups | Low | Infra | Redundancy | Achieved

## Application
Compliance Status | DPDP Requirement | Rule Ref | Infra Controls Needed / Existing | Where | Priority | Timeline (days) | Responsible | Notes | Final Deadline | Impacted services /device list | Business impact | Effort estimate | Cost Estimate
| Privacy Notice Display | Rule 3(b), Rule 3(c) | Show privacy notice with purpose, retention, rights | App Frontend | High |  | App Team | Mandatory before data collection
| Consent Capture | Rule 3(b) | Capture consent within app | App Frontend | High |  | App Team | Must record explicit consent
| Consent Withdrawal | Rule 14 | Allow easy consent withdrawal | App UI | High |  | App/Backend | Required under DPDP
| Purpose Limitation | Rule 3(b) | Enforce business logic to restrict purpose | Backend | High |  | Dev/Backend | Use only declared purpose
| Data Minimization | Rule 3(b) | Remove unnecessary fields | Backend | High |  | App/Backend | Mandatory
| Strong Authentication | Rule 6(b) | Integrate SSO/MFA | Auth Module | High |  | App/Identity | Strong auth required
| RBAC | Rule 6(b) | Implement role-based access | App Auth | High |  | App Team | Restrict PII by role
| Remove Shared Accounts | Rule 6(b) | Unique IDs only | App IAM | High |  | App/IT | Shared logins forbidden
| Session Timeout | Rule 6(b) | Implement auto logout | App Auth | Medium |  | App Team | Security control
| Input Validation | Rule 6(g) | SQLi/XSS protection | API/App | High |  | Dev Team | Critical requirement
| API Authentication | Rule 6(g) | OAuth2/Token-based protection | API Layer | High |  | API Team | Required
| Rate Limiting | Rule 6(g) | Enable rate limits | API Gateway | Medium |  | API Team | Prevents automated abuse
| App Activity Logging | Rule 6(c) | Enable CRUD logs | App Logs | High |  | App Team | Audit trail required
| Failed Login Logging | Rule 6(c) | Track failed attempts | App Logs | High |  | App Team | Security requirement
| Log Retention 1 Year | Rule 6(e) | Retain logs for 12 months | Log Storage | High |  | Security/IT | Mandatory
| SIEM Integration | Rule 6(c) | Forward logs to SIEM | App Logs | Medium |  | Security | Monitoring requirement
| Data Deletion Workflow | Rule 8 | Enable delete pipeline | Backend | High |  | App/Backend | User right
| Data Correction | Rule 14 | Allow user corrections | App UI | Medium |  | App Team | DPDP right
| Data Export | Rule 14 | Provide downloadable data | Backend | Medium |  | App Team | Mandatory under DPDP
| Grievance/DPO Display | Rule 9 | Show DPO details | Frontend | High |  | App Team | Mandatory display
| Secure Dev Practices | Rule 6(g) | Secure SDLC | DevOps | Medium |  | DevSecOps | T&O control
| Static Code Scanning | Rule 6(g) | Enable SAST | DevSecOps | Medium |  | Security/Dev | Required
| Vulnerability Scanning | Rule 6(g) | App vulnerability scans | DevSecOps | Medium |  | Security | Required
| Pre-release Security Test | Rule 6(g) | Perform security UAT | QA | Medium |  | QA/Sec | Required
| HTTPS/TLS | Rule 6(a) | Enforce TLS 1.2+ | App | High |  | App/Network | Encryption
| Secrets in Vault | Rule 6(a) | Store secrets securely | DevOps | High |  | DevOps | Avoid hardcoding
| Application Data Flow Map | Rule 6(g) | Document flows | Architecture | Medium |  | App Team | Mandatory mapping
| No Prod Data in UAT | Rule 6(g) | Mask PII | Testing | High |  | QA/Dev | Mandatory
| CAPTCHA | Rule 6(g) | Add CAPTCHA | App UI | Low |  | App Team | Prevents bot attacks

## Database
Compliance Status | DPDP Requirement | Rule Ref | Infra Controls Needed / Existing | Where | Priority | Timeline (days) | Responsible | Notes | Final Deadline | Impacted services /device list | Business impact | Effort estimate | Cost Estimate
| DB Encryption at Rest (TDE) | Rule 6(a) | Enable TDE | Oracle/SQL | High |  | DBA | Mandatory encryption | 2027-05-01
| Encrypted DB Backups | Rule 6(a) | Encrypt backups | Backup | High |  | DBA/Infra | Required | 2027-05-01
| Least Privilege DB Access | Rule 6(b) | Restrict roles | DB Users | High |  | DBA | Minimum access | 2027-05-01
| Unique DBA Accounts | Rule 6(b) | Remove shared accounts | DBA Team | High |  | DBA | Mandatory | 2027-05-01
| DB MFA | Rule 6(b) | MFA via jump/PAM | DBA | High |  | Security | Required | 2027-05-01
| Privilege Review Quarterly | Rule 6(b) | Access review | DB Users | Medium |  | Security/DBA | Required | 2027-05-01
| DB Audit Logging | Rule 6(c) | Enable audit logs | DB | High |  | DBA | Record all DB actions | 2027-05-01
| DB Log Retention 1 Year | Rule 6(e) | Store logs | Log Storage | High |  | Security/IT | Must retain 12 months | 2027-05-01
| Forward DB Logs to SIEM | Rule 6(c) | Send DB logs to SIEM | Logging | Medium |  | Security/DBA | Required | 2027-05-01
| PII Masking in Non-Prod | Rule 6(g) | Implement masking | Test/UAT | High |  | DBA/QA | Protect PII | 2027-05-01
| DB-Level Data Minimization | Rule 3(b) | Remove unnecessary columns | DB Schema | Medium |  | DBA | Mandatory | 2027-05-01
| Data Deletion Workflow | Rule 8 | Delete expired data | DB Ops | High |  | DBA | DPDP right | 2027-05-01
| Archival Policy | Rule 8 | Define archival | DB Ops | Medium |  | DBA | Retention compliance | 2027-05-01
| DB Restore Testing | Rule 6(d) | Quarterly restore tests | DB Backup | Medium |  | Infra/DBA | Ensure recoverability | 2027-05-01
| Backup Retention Policy | Rule 6(d) | Define DB retention | Backup | Medium |  | Infra | Mandatory | 2027-05-01
| DB Patch Compliance | Rule 6(g) | Patch Oracle/Linux | DB | High |  | DBA | Must patch regularly | 2027-05-01
| DB Hardening | Rule 6(g) | Apply CIS baseline | DB | Medium |  | DBA | Recommended | 2027-05-01
| DB VLAN Segregation | Rule 6(g) | Isolate DB network | Network | High |  | Network | Mandatory | 2027-05-01
| No Internet Exposure | Rule 6(g) | Block public access | Network | High |  | Network | Critical | 2027-05-01
| TLS for DB Connections | Rule 6(a) | Enable SSL/TLS | DB Network | High |  | DBA | Encrypt DB traffic | 2027-05-01
| DB Data Flow Map | Rule 6(g) | Map PII tables | DBA | Medium |  | DB Team | Mandatory | 2027-05-01
| Legacy DB Cleanup | Rule 6(g) | Upgrade DB versions | DB | Medium |  | DBA | Remove outdated DBs | 2027-05-01
| Vendor DPDP Clauses | Rule 6(f) | Sign DPDP clauses | Vendor DB | High |  | Legal/IT | Required | 2027-05-01
| Schema Change Control | Rule 6(g) | Approval workflow | DevOps/DBA | Medium |  | DBA/DevOps | Mandatory | 2027-05-01
| DB DR Plan | Rule 6(d) | Enable DR replication | DB Infra | High |  | Infra/DBA | Mandatory | 2027-05-01
| DB Credentials in Vault | Rule 6(a) | Use vault | DevOps | High |  | DevOps | Secure credentials | 2027-05-01
| DB Performance Logging | Rule 6(c) | Capture slow queries | DBA | Medium |  | DBA | Recommended | 2027-05-01
| No Prod PII in Test | Rule 6(g) | Mask PII | QA/Dev | High |  | QA/DBA | Mandatory | 2027-05-01

## Governance
Document | Purpose / Required By | Priority | Owner | Target Timeline (days) | Notes | Final Deadline
Privacy Notice (DPDP format) | Rule 3 - public notice & consent | High | Legal/Compliance | 14 | Publish on website and apps | May 2027
Data Retention Policy | Rule 8 - retention & erasure | High | IT/Compliance | 21 | Define retention by data class | May 2027
Information Security Policy (DPDP aligned) | Rule 6 - org controls | High | Security | 30 | Include encryption, access, logs | May 2027
Incident Response Plan (72-hour) | Rule 7 - breach reporting | High | Security/IT | 14 | Templates + escalation matrix | May 2027
Access Control Policy | Rule 6(b) | High | IT/Security | 21 | RBAC, periodic reviews | May 2027
Vendor / Processor Agreement Template | Rule 6(f) | High | Procurement/Legal | 21 | Include breach + logs clauses | May 2027
Breach Notification Templates | Rule 7 | High | Security/Legal | 7 | Templates for DP and Board | May 2027
Backup & DR Policy | Rule 6(d) | High | IT/Operations | 21 | Restore testing schedule | May 2027
Log Management Policy | Rule 6(c),(e) | High | Security/IT | 21 | Retention and tamper-evidence | May 2027
DPDP Data Principal Rights SOP | Rule 14 | High | Compliance/Support | 14 | Request handling within 90 days | May 2027

## DPIA_Template
DPIA ID | System/Application | Description of Processing | Data Categories | Purpose | Risk Score (1-5) | Identified Risks | Likelihood | Impact | Mitigations | Residual Risk | DPO Sign-off | Review Date
DPIA1 | Customer Portal | Stores customer PII for service | Name,Email,Phone | Service Delivery | 4 | Unauthorized access to PII | 3 | 4 | MFA, Encryption, WAF | 2

## Breach_Register
Breach ID | Date Detected | Detected By | Affected Data Categories | Estimated No. of Data Principals | Scope (systems) | Immediate Actions Taken | Notified DP (Y/N) | Notified Board (Y/N) | Reported to DPB (Y/N) | 72-hour Report Filed (Y/N) | Root Cause | Remediation | Closure Date | Notes
BR1 | 2025-11-20 | SIEM Alert | Emails, Names | 50 | Email Server | Blocked account, rotated keys | Y | Y | N | N | Credential compromise | Reset creds, MFA enforced | 2025-11-22 | Sample entry

## DP_Request_Register
Request ID | Date Received | Data Principal Name | Request Type (Access/Erasure/Rectify/Withdraw Consent) | Identity Verified (Y/N) | Assigned To | Date Resolved | Resolution Summary | SLA Days | Notes
REQ1 | 2025-11-18 | A. Kumar | Access | Y | Support Team | 2025-11-20 | Provided export of data | 2 | Sample

## Vendor_Risk_Assessment
Vendor ID | Vendor Name | Service | Data Access Level | DPDP Contract Signed (Y/N) | ISO Certified (Y/N) | Breach SLA (hrs) | Log Retention (days) | Risk Rating | Review Date | Notes
V1 | PayrollCo | Payroll Processing | Full payroll PII access | Y | Y | 24 | 365 | High | 2025-11-01

## Evidence_Checklist
Control ID | Control Description | Evidence Type | Stored Location | Owner | Last Updated | Notes
C-LOG-1 | Firewall logs retention | Exported log archive | Secure Share/Logs | Network Team | 2025-11-15 | Logs for 1 year available

## DPDP_ISO_SEBI_Map
DPDP Rule/Control | ISO27001 Control | SEBI Requirement | Existing Control | Gap | Action Required | Owner | Target Timeline (days)
Rule6 - Logging | A.12.4 - Logging | SEBI - Audit logs | Firewall + SIEM | No centralized SIEM | Deploy SIEM | Security | 60

## Training_Register
Employee ID | Name | Department | Training Module | Date Completed | Score | Next Due | Notes
E001 | R. Sharma | IT | DPDP Awareness | 2025-11-10 | 85 | 2026-11-10

## Key_Management
Key ID | Key Purpose | KMS (Yes/No) | Location | Access List | Rotation Frequency (days) | Last Rotated | Notes
K-DB-1 | Oracle TDE Master Key | Yes | AWS KMS | Security Admins | 365 | 2025-02-01